## NMH Project Template
Type | Name | Values | Prompting Name
checklist | QA 8_Below Ground Pipework Checklist - Water - NMH |  | Below Ground Pipework Checklist - Water
checkpoint | LendLease Permits Issued
checkpoint | Set out pits depths and trench runs.
note | As per DRG#
textbox | Drawing No.:
checkpoint | Pipes and fittings comply with relevant Authority and Specification.
note | Spec#: AS3500
checkpoint | Bedding placement and compaction and material meets specification.
note | Spec#: AS3500 and Hydraulic Specification
checkpoint | Jointing of pipes
button | Jointing type | Electrofusion, Butt Welding, Both
note | Refer to 'QA16 EF Welding' and/or 'QA 25 Butt Welding' ITP
checkpoint | Connections to pits and existing services as per spec and Australian Standards
checkpoint | Hydrostatic tests are carried out as required.
button | GPL QA6 form completed | Yes,No
textbox | Water system tested to (kPa)
checkpoint | Placement and compaction of backfill and material meets spec.
button | Compacted backfill as per the Specification | Yes,No
note | Detectable marker tape
checkpoint | Temporary cover provided to open drain.
checkpoint | PVC/ Plastic caps to open ends
checkpoint | As built information updated onto drawings
note | Ongoing
note | To be provided
checkpoint | Sign Off
button | Geschke Group Signature added below | Yes,No,N/A
button | LendLease Signature added below | Yes,No,N/A
button | ARUP Group Signature added below | Yes,No,N/A