## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Fit Off Checklist - Miscellaneous Item |  |  |  |  | Yes | Fit Off Checklist - Miscellaneous Item | 0b51344d-dff7-4edc-838a-4b3131c10e70
checkpoint-status |  |  | checkpoint | Confirm the structure is in accordance with the details supplied by PBI
label | 31d45639-4a4a-4893-9d3e-5407e3a8b1f5 |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Photos taken of installed item
checkpoint-status |  |  | checkpoint | Installed as per PBI drawings supplied and manufacturer's requirements
checklist-flat |  |  | checklist | Rail Checklist |  |  |  |  | Yes | Rail Checklist | 385dd248-1112-4939-97b5-065436b9e474
checkpoint-status |  |  | checkpoint | Confirm the structure is in accordance with the details supplied by PBI
label | e8290b74-d9f4-4fff-8ae6-12b9cea20415 |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Photo taken of Engraved Line Plate / ID Tag
checkpoint-status |  |  | checkpoint | Video taken of system
checkpoint-status |  |  | checkpoint | Description input of location / person Rail systems shuttle left with
text | ca58e151-497c-4575-8066-88012502f631 |  | textbox | Location / Person:
checkpoint-status |  |  | checkpoint | Installed as per PBI drawings supplied and manufacturer's requirements
checklist-flat |  |  | checklist | Fit Off Checklist - Line |  |  |  |  | Yes | Fit Off Checklist - Line | 3b158c74-e6c6-4aba-8dbf-8ad45aa17144
checkpoint-status |  |  | checkpoint | Confirm the structure is in accordance with the details supplied by PBI
label | 6242ec89-db8b-4c92-ac8b-40331fb90cc3 |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Photo taken of line pull test and swages
checkpoint-status |  |  | checkpoint | Photo taken of Engraved Line Plate / ID Tag
checkpoint-status |  |  | checkpoint | Video taken of system
checkpoint-status |  |  | checkpoint | Installed as per PBI drawings supplied and manufacturer's requirements
checklist-flat |  |  | checklist | Pre-Fit Off Checklist |  |  |  |  | Yes | Pre-Fit Off Checklist | 421b4f28-8232-420d-ba77-6e54d73a3cb5
checkpoint-status |  |  | checkpoint | Confirm structure is in accordance to the details provided
label | f33b5857-8198-41c5-971a-8ab0ef42c8f7 |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Plinths/ bases/post installed in accordance with details provided
checkpoint-status |  |  | checkpoint | Photos taken
checklist-flat |  |  | checklist | Re-Certification - Anchor Point |  |  |  |  | Yes | Re-Certification - Anchor Point Checklist | 47d3da23-709e-4969-8e27-045dd660804f
checkpoint-no-status |  |  | checkpoint | Re-Certification - Anchor Point
text | f3a8e793-07db-5a07-9d3c-9ba9f7651392 |  | textbox | Anchor no's:
text | d36fd9c6-1a59-5371-b369-dfc1df0cf5aa |  | textbox | Location:
text | 87a11285-a288-582c-b353-21209ae2b653 |  | textbox | Type | Fall Arrest, Abseil, Both
checkpoint-status |  |  | checkpoint | Ensure anchors are secure
checkpoint-status |  |  | checkpoint | Roof seal/leaks around anchors - seal as req'd
checkpoint-status |  |  | checkpoint | General wear & tear, rust damage etc
checkpoint-status |  |  | checkpoint | Damaged supporting structure
checkpoint-status |  |  | checkpoint | Chemset / friction style anchor - load test 7.5Kn & hold for 3 minutes
checkpoint-status |  |  | checkpoint | Re-tag / engraved all anchors
checkpoint-no-status |  |  | checkpoint | Note any defects/issues/concerns
checklist-flat |  |  | checklist | Practical Completion |  |  |  |  | Yes | Practical Completion | 541c4066-32d8-4fb5-b578-d019cfb37c36
checkpoint-no-status |  |  | checkpoint | System installed and ready for review from Project Manager.
holdpoint |  |  | signoff | Request Review from PM
checkpoint-status |  |  | checkpoint | Project Manager has reviewed, checked and approved system.
checkpoint-status |  |  | checkpoint | PM to send to PBI admin to close out and archive
checklist-flat |  |  | checklist | Re-Certification - Cable Safety Line |  |  |  |  | Yes | Re-Certification - Cable Safety Line Checklist | 68fdea52-7c26-4412-bbe5-59da6f591940
checkpoint-no-status |  |  | checkpoint | Re-Certification - Cable Safety Line
text | 0e55d3c6-6ca2-5a98-9931-44e9208f7ac8 |  | textbox | Line i.D:
text | ec6ec9c1-d753-537d-87fc-bf0031ac51b0 |  | textbox | Length:
text | a8fd90c7-ac20-56b0-98cb-e42e4ce75c6c |  | textbox | Mounting:
checkpoint-status |  |  | checkpoint | End posts & fixings/caps
checkpoint-status |  |  | checkpoint | Intermediate post/s & fixings/caps
checkpoint-status |  |  | checkpoint | Roof seal/leaks around posts - seal as req'd
checkpoint-status |  |  | checkpoint | Ensure cable passes through brackets correctly
checkpoint-status |  |  | checkpoint | Ensure cable is free from damage etc
checkpoint-status |  |  | checkpoint | Ensure correct cable tension (tension to 0.8Kn)
checkpoint-status |  |  | checkpoint | Ensure absorber/s have not been activated
checkpoint-status |  |  | checkpoint | Tighten all fixings as appropriate
checkpoint-status |  |  | checkpoint | Correct no. Of swages / all swages between 10.7Mm - 11.3Mm
checkpoint-status |  |  | checkpoint | General wear & tear, rust damage etc
checkpoint-status |  |  | checkpoint | Line systems shuttle
checkpoint-status |  |  | checkpoint | Engraved each line plate/sign
checkpoint-no-status |  |  | checkpoint | Note any defects/issues/concerns
checklist-flat |  |  | checklist | Fit Off Checklist - Anchor |  |  |  |  | Yes | Fit Off Checklist - Anchor | 76fabc8e-974d-4f95-a3d3-8caa5e7131ac
checkpoint-status |  |  | checkpoint | Confirm the structure is in accordance with the details supplied by PBI
label | 10b13284-475d-4dd5-8ace-bbc47a64d07b |  | note | If FAILED add brief explanation in comments and click below to email PM
holdpoint |  |  | signoff | EMAIL PM
checkpoint-status |  |  | checkpoint | Required number of photo(s) taken of installed anchor(s)
select | 075e8ef5-42fb-423c-9690-730db3d03787 |  | dropdown | Anchor Type | FROG 1 photo req,L4543 2 photos req,L4544 3 photos req,L4550 2 photos req,L4551 2 photos req,L4552 2 photos req,M16 Chemset 2 photos req,M16 Through BOLT 2 photos req,SAFETOR 3 photos req,Spiratech 1 photo req
checkpoint-status |  |  | checkpoint | Installed as per PBI drawings supplied and manufacturer's requirements
checklist-flat |  |  | checklist | Re-Certification - Rail / Track |  |  |  |  | Yes | Re-Certification - Rail / Track Checklist | 958727fc-4b66-4476-9321-c3c40d802e0b
checkpoint-no-status |  |  | checkpoint | Re-Certification - Rail / Track
text | 0d963ea0-9e2f-5459-b629-7e9035935112 |  | textbox | Rail i.D:
text | 5df4e6e1-1fb6-5f6e-9110-f3ecd0d0fe06 |  | textbox | Length:
text | f17f052b-4932-54ff-a404-c081aa0da283 |  | textbox | Mounting:
checkpoint-status |  |  | checkpoint | Dents / holes / cracks in system
checkpoint-status |  |  | checkpoint | General wear & tear, rust damage etc
checkpoint-status |  |  | checkpoint | Roof seal/leaks - seal as req'd
checkpoint-status |  |  | checkpoint | Tighten all fixings as appropriate
checkpoint-status |  |  | checkpoint | System shuttle operates smoothly throughout the system
checkpoint-status |  |  | checkpoint | System rated for fall arrest only
checkpoint-status |  |  | checkpoint | System rated for abseil & fall arrest
checkpoint-status |  |  | checkpoint | Engraved each rail plate/sign
checkpoint-no-status |  |  | checkpoint | Note any defects/issues/concerns
checklist-flat |  |  | checklist | Fit Off Checklist - Ladder System |  |  |  |  | Yes | Fit Off Checklist - Ladder System | a20d4f56-828c-46dd-95d7-8692c9d97297
checkpoint-status |  |  | checkpoint | Installed to manufacturer or PBI Installation instructions
checkpoint-status |  |  | checkpoint | Installed as per AS1657:2018
checkpoint-status |  |  | checkpoint | All fixings secure
checkpoint-status |  |  | checkpoint | Top step of ladder flush with either walk-off kit or building edge
checkpoint-status |  |  | checkpoint | No unsealed penetrations to the roof
select | 7f188f6e-a2a0-5b14-88f8-9a89729b92bf | DataPoint is missing 'select' values | dropdown | If caged, cage start between 2m and 2.2m from ground level?
select | eddab9a9-8714-5765-96cc-c2305bd95466 | DataPoint is missing 'select' values | dropdown | If ladder is above 3.5m, does it contain a cage?
select | bed0619c-85c7-52bc-aae9-988b0e6eaf7b | DataPoint is missing 'select' values | dropdown | If ladder is above 6m, does it have a mid-way platform?
checkpoint-status |  |  | checkpoint | Photo uploaded of clean work area
label | 27ba80a5-f8a7-5ce5-b040-e8cca6d0b78e |  | note | 1 photo required
checkpoint-status |  |  | checkpoint | Video taken
label | 09a44681-2c5a-5db4-86ad-fbfd13f5e542 |  | note | 1 photo required
checklist-flat |  |  | checklist | Data Plate, Access Point & Carriages/Travellers |  |  |  |  | Yes | Data Plate, Access Point & Carriages/Travellers | e0941abc-4181-48bc-b94d-5b0c7b28ce9d
checkpoint-no-status |  |  | checkpoint | Details of Data Plate
select | 63469906-f15a-5496-8221-9448894bafda |  | dropdown | Has the Data Plate been installed on site? | Yes,No
label | d20042fa-7b7b-59f5-810f-ad0743858b6a |  | note | Comment why not if 'no' selected
checkpoint-status |  |  | checkpoint | 1 photo required of Data Plate
checkpoint-no-status |  |  | checkpoint | Details of Access Point
select | 0e6a920d-bef6-5104-bb3f-af69c22c9a99 |  | dropdown | Has the Access Point been confirmed? | Yes, No
label | d0ddc701-4f77-5d80-a6ea-7cf06d1fbdaf |  | note | Comment why not if 'no' selected
checkpoint-status |  |  | checkpoint | 1 photo required of Access Area
checkpoint-no-status |  |  | checkpoint | Details of Rail Carriages/Cable Travellers
select | e64fb688-5f88-58ac-a761-ee142bdb13e1 |  | dropdown | Has the Rail Carriages/Cable Travellers been left on site | Yes, No
label | 09d4b280-ffd0-5382-8504-c7adb1ec24a9 |  | note | Comment why not if 'no' selected
checkpoint-status |  |  | checkpoint | 1 photo required of carriages/travellers
checklist-sectioned |  |  | checklist | PPE Inspection Service Records |  |  |  |  | Yes | PPE Inspection Service Records Checklist | e994515a-038e-417a-80da-9b66d2c41e02
checkpoint-group |  |  | section | PPE Inspection Service Records:
checkpoint-no-status |  |  | checkpoint | PPE Inspection Service Records:
text | dc34fbeb-823a-5b23-aed6-886fc9e5a511 |  | textbox | Client:
text | b4f88217-6191-5c6c-a5c5-3f2cecbc7a58 |  | textbox | Contact name:
text | f7f2c0c5-6a89-513e-a5eb-6f1624fea1f5 |  | textbox | Phone no.:
text | f24927d0-dee5-5c71-bf56-39d9267dd1a2 |  | textbox | Order number:
checkpoint-group |  |  | section | Product details
checkpoint-status |  |  | checkpoint | Product details captured below:
text | bafc7b22-83b4-5147-ba4b-0114c5385fd0 |  | textbox | Serial number:
text | dad4fe23-c698-5c43-83e4-51537235fbdf |  | textbox | Manufacture:
text | 35ea0d6b-1e3b-595e-9d37-d55c6c1838ef |  | textbox | Model or part no.
text | 60bfe02e-491b-564e-bffd-ace99fb33fd6 |  | textbox | Other (lot no., Etc.)
text | a66c24a9-72bf-58bb-b2df-c31897f05da6 |  | textbox | Item description:
text | d2cd8564-3a7f-57c1-b676-a9145c7b070d |  | textbox | Date of manufacture:
text | 3eb0c131-04fc-5d80-844c-cbf356bec82b |  | textbox | Date of expiry:
checkpoint-group |  |  | section | Inspection checklist
checkpoint-status |  |  | checkpoint | Webbing
checkpoint-status |  |  | checkpoint | Rope
checkpoint-status |  |  | checkpoint | Stitching
checkpoint-status |  |  | checkpoint | Energy absorber
checkpoint-status |  |  | checkpoint | Impact indicator
checkpoint-status |  |  | checkpoint | Dorsal plate
checkpoint-status |  |  | checkpoint | Connecting buckles
checkpoint-status |  |  | checkpoint | Snap hooks
checkpoint-status |  |  | checkpoint | Karabiners
checkpoint-status |  |  | checkpoint | Retractable mechanism
checkpoint-status |  |  | checkpoint | Hardware / casing
checkpoint-status |  |  | checkpoint | Other (name)
checkpoint-status |  |  | checkpoint | PPE Unit Information Label/Serial Number
label | ce4153ed-eb75-4978-9cd2-51c788bb31a6 |  | note | Attach photo of PPE unit clearly showing the information label and the serial number