## Groundbeam & Guardrail
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | C1603A - Waikare Underslip Retaining Wall |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Groundbeam & Guardrail Installation |  | Izzy Atchley | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: C1603A - Wakhare Retaining Wall |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location: S.H.02 R.S 577 RP 13.922
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Preliminary
1.1 | Alternative Detailed Construction/ Installation Methodology | H | Documentation from the supplier that proves the safety complies with Section 5 of the project Specification | Prior to commencement | Submission | Section 5 of the Project Specification | Email | Site Engineer | CPS Engineer
1.2 | Earthworks and Pavement Works | H | Earthworks and pavement construction shall be completed prior to Ground beam and Barrier installation. | Prior to commencement | Review | Previous ITP's approved | Previous ITP's | Site Engineer | CPS Engineer
2 | Material Compliance
2.1 | Reinforcement Steel Compliance | W | All reinforcing steel to comply with AS/NZS 4671 Grade 500E | Prior to commencement | Submission | DH16, DH12, RH12 reinforcing steel delivered and dockets collected | Delivery dockets, packing slips, invoices | Site Engineer
2.2 | Concrete Mix Compliance | W | Concrete mix to meet required strength | Three weeks prior to placement of concrete | Submission | Minimum concrete compressive strength to be 30 MPa at 28 days | Mix design, delivery dockets | Site Engineer
2.3 | Geogrid Compliance | W | All rolls bar codes are to be collected and attached to the rest of the QA Documentation | Prior to commencement | Document Review | Compliant with Tensar Triax TX160 or equivalent | Delivery dockets, packing slips, invoices | Site Engineer
2.4 | Safety Barrier Compliance | H | Documentation from the supplier that proves the safety complies with Section 5 of the project Specification | Prior to commencement | Submission | Section 5 of the Project Specification | Email | Site Engineer | CPS Engineer
3 | Ground Beam Construction
3.2 | Install Reinforcement Steel | H | Reinforcing steel to have minimum 50mm cover | During construction | Visual Inspection | Reinforcing steel placed as per design. No concrete to be poured until formwork and reinforcement approved by CPS Engineer | CS-4040 Concrete Inspection Record, Photos | Site Engineer | CPS Engineer
3.3 | Concrete Pouring | H | Cast-in bracket as per NZTA B5 | During construction | Visual Inspection | As per design Concrete dispatch dockets | CS-4040. Concrete Inspection Record, Photos | Site Engineer | CPS Engineer
3.4 | Concrete Testing | H | Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores Concrete slump and spread test reports | After Construction | Visual Inspection |  | Test results | Site Engineer | CPS Engineer
3.5 | Geogrid | W | 1.9m wide strip laid evenly across beam and adjacent ground | During construction | Visual Inspection | Geogrid at minimum 65mm above top of ground beam | Photos | Site Engineer | CPS Engineer
4 | Barrier Construction
4.1 | Guardrail Installation | W | Install guardrail as per contractors methodology | During installation | Visual inspection | Nominally max 3 days, once concrete is hard enough. TBC with the guardrail contractor. | Photos | Site Engineer
4.2 | RSHDS Inspection | H | Inspection of constructed safety barrier to confirm compliance with NZTA M23 and the IFC Drawings | At completion of Safety Barrier Installation | Visual Inspection |  | RSHDS Audit Form | Site Engineer | CPS Engineer
5 | Post-Construction Closeout
5.1 | Final Walkover (Snags) | H | The final walkover must be scheduled at least one week before the site's completion or demobilisation. | At the completion of the Lot of work | Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out) | Completed report with Snag List | Snag List signed by attendees | Quality Manager
5.2 | Survey As-builts | H | Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided | At the completion of the Lot of work | Drawings Survey as-built | All RFI, NCRs and site changes must be recorded. Signed and dated | As-built Drawings. Redline Markups | Site Engineer | CPS Engineer
5.3 | Quality Assurance Deliverables | W | Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | At the completion of the Lot of work | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Quality Manager
5.4 | Final Approvals | H | Signoffs by Project Manager, Quality Manager, CPS Manager | At the completion of the Lot of work | Document Review | Ensure all parties have signed and approved ITP | Signatures | Project Manager, Quality Manager, CPS Manager