## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - C1603A - Waikare Gorge Descent - Groundbeam & Guardrail | itp |  |  |  | Yes | ITP - C1603A - Waikare Gorge Descent - Groundbeam & Guardrail | 8873c421-178e-4696-a70a-6d584cec4636
checkpoint-group |  |  | section | 1 - Preliminary
checkpoint-status |  |  | checkpoint | Project Site reps.
text | d1329917-ab2d-59ff-91e7-ce3c8ad49bb9 |  | textbox | CPS Eng.
text | 2670618f-526b-5da5-94ae-f3ab577f4289 |  | textbox | Site Engineer
text | c04a7f37-6065-55ff-818e-29a520fe4865 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Alternative Detailed Construction/ Installation Methodology
label | 0556865c-a122-512d-a0ab-56f31b5f415d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 87caa383-9358-5b9a-a85b-e05c95edf470 |  | note | Detail - Documentation from the supplier that proves the safety complies with Section 5 of the project Specification
label | dea3660a-d95a-5001-9c72-f2b3bb799de9 |  | note | Frequency - Prior to commencement
label | 9b09f885-6972-580e-b28e-bd4c6a06b6f8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 4a8670ca-c8fb-5d80-b517-81dfd7de5c51 |  | note | Conformance Criteria - Section 5 of the Project Specification
label | b88c5555-b56e-5eba-baa3-81dfe05fdd63 |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Earthworks and Pavement Works
label | 36a595b8-803b-5998-a86d-8f5ebf6a6e75 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 817ec378-3b06-57c2-b5b9-a750295c2b60 |  | note | Detail - Earthworks and pavement construction shall be completed prior to Ground beam and Barrier installation.
label | 46c27f3c-5156-562c-8abe-b0bdd7a80b8a |  | note | Frequency - Prior to commencement
label | 4334b27a-17ae-5167-b998-3b8cdb5d39a0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 31a83ee3-c034-54b9-8b52-16747d7e1277 |  | note | Conformance Criteria - Previous ITP's approved
label | 6e73de46-4268-5d90-abe5-e32d42e6ee1e |  | note | Records - Previous ITP's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Reinforcement Steel Compliance
label | 67b71111-e73c-5d04-8df3-894d9d637c23 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b1d73887-9aa1-5eb6-a2cf-e0130b34262e |  | note | Detail - All reinforcing steel to comply with AS/NZS 4671 Grade 500E
label | 63f87062-6b37-5c92-a81f-38a140405b1b |  | note | Frequency - Prior to commencement
label | b7269fe4-1926-54a7-a1d9-cfdce5fe21b8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | df86bad9-75fc-548e-b544-768c8cb2a451 |  | note | Conformance Criteria - DH16, DH12, RH12 reinforcing steel delivered and dockets collected
label | 19bbbc36-6d57-5388-a979-2f3c58b046bc |  | note | Records - Delivery dockets, packing slips, invoices
checkpoint-status |  |  | checkpoint | 2.2 - Concrete Mix Compliance
label | c64d16ac-de84-5563-a76b-44938bb61fdd |  | note | ACTION (Hold, Monitor, Witness) - W
label | e0c997c9-95e4-52a7-92e9-dcb7d49192c2 |  | note | Detail - Concrete mix to meet required strength
label | bf1db101-9820-54ac-9882-d0c64df731a7 |  | note | Frequency - Three weeks prior to placement of concrete
label | fd953b46-711d-5c0b-b63a-5c14c88b4c3d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | c0b5885e-61ae-57cd-b36c-8cfb33222347 |  | note | Conformance Criteria - Minimum concrete compressive strength to be 30 MPa at 28 days
label | 154fa6e0-1027-56c4-9a7a-9c2c6f874718 |  | note | Records - Mix design, delivery dockets
checkpoint-status |  |  | checkpoint | 2.3 - Geogrid Compliance
label | 1f9a9807-72e0-5d38-910c-e3f957473776 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a80489bd-7df2-52cf-b710-daf00b71be35 |  | note | Detail - All rolls bar codes are to be collected and attached to the rest of the QA Documentation
label | 153b607c-87c2-5e2d-bfd7-047a9d825fc4 |  | note | Frequency - Prior to commencement
label | c7fdf94d-664c-5d95-8e9f-6f5e4db8f8f1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 1bb75949-941a-59b3-b860-ce5f289d56cd |  | note | Conformance Criteria - Compliant with Tensar Triax TX160 or equivalent
label | 97fadf55-4ddc-5b35-a13e-9432ac59e1c8 |  | note | Records - Delivery dockets, packing slips, invoices
checkpoint-status |  |  | checkpoint | 2.4 - Safety Barrier Compliance
label | 9be1937f-b06d-5492-8526-16250101bda7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 54ec98e2-8f46-5b51-b19f-d45e18f59f8d |  | note | Detail - Documentation from the supplier that proves the safety complies with Section 5 of the project Specification
label | 13e76bbf-9684-5541-95d7-7cf0b9951f89 |  | note | Frequency - Prior to commencement
label | e31e7012-4b6b-598c-9f91-03a08d55d258 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 393e36b0-0d58-536e-8211-d09130df4b6d |  | note | Conformance Criteria - Section 5 of the Project Specification
label | 3101145c-8d44-5d3a-bb97-a8f5224126be |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Ground Beam Construction
checkpoint-status |  |  | checkpoint | 3.2 - Install Reinforcement Steel
label | 87797773-7e11-5d6d-b132-a25a9468018b |  | note | ACTION (Hold, Monitor, Witness) - H
label | e96b45dc-256d-579b-939c-929a2cd77ba6 |  | note | Detail - Reinforcing steel to have minimum 50mm cover
label | 8f1a7f4d-cff1-5c6d-bae8-7d275c7711d2 |  | note | Frequency - During construction
label | 6dc782f0-1569-5072-96b9-7c39d5b170bf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 977163e1-197b-5fb7-a0d3-2c728e454b0a |  | note | Conformance Criteria - Reinforcing steel placed as per design. No concrete to be poured until formwork and reinforcement approved by CPS Engineer
label | b9c461c6-277e-5fb9-9dcb-94060e5ece0f |  | note | Records - CS-4040 Concrete Inspection Record, Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Concrete Pouring
label | 9d7363ac-7404-5b0e-99a6-ab253471b2a4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b9509732-9e15-5873-a157-481ab183f200 |  | note | Detail - Cast-in bracket as per NZTA B5
label | fb6a2a4f-a308-5fe4-a229-8d8414387aa2 |  | note | Frequency - During construction
label | ed42170e-b7dd-509c-b508-6162502e420c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 75df6793-2a86-5b9c-9add-b4468aa9c28b |  | note | Conformance Criteria - As per design, Concrete dispatch dockets
label | 0f6501d1-ba97-554c-ab3e-4268bce85c76 |  | note | Records - CS-4040. Concrete Inspection Record, Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Concrete Testing
label | d477f10f-d033-5536-9af9-b0cf4ec2bbd9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e7f6f563-d05b-531d-ab25-810d922c2537 |  | note | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores. Concrete slump and spread test reports.
label | 1ffb37c6-b41f-5587-8537-cbb28eee41cf |  | note | Frequency - After Construction
label | e73ced51-e40d-5de2-b1a7-7db264938cf0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | ee857aac-f524-5ec2-bbff-b63fb6ead987 |  | note | Conformance Criteria -
label | 89ff1823-35a4-5519-878a-fa185dce591d |  | note | Records - Test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Geogrid
label | b973aeb9-682e-5b10-80d6-d407ed1f2d1e |  | note | ACTION (Hold, Monitor, Witness) - W
label | 442103e1-5e57-52f9-a72b-38d40409b693 |  | note | Detail - 1.9m wide strip laid evenly across beam and adjacent ground
label | 8e9bb300-c345-5425-b162-fb052f5a48a2 |  | note | Frequency - During construction
label | 88d5c86d-d55b-5566-9a0e-8b759f4ca267 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 51a66eab-3c4d-5d95-b2d9-0b6c853effb3 |  | note | Conformance Criteria - Geogrid at minimum 65mm above top of ground beam
label | 6adc35ec-0d4f-5ba3-be6a-23a6d27fa786 |  | note | Records - Photos
checkpoint-group |  |  | section | 4 - Barrier Construction
checkpoint-status |  |  | checkpoint | 4.1 - Guardrail Installation
label | e10197ea-2b06-5095-add8-bc85ebc7e63b |  | note | ACTION (Hold, Monitor, Witness) - W
label | df60fd46-10d7-532c-954d-5b7e282640cc |  | note | Detail - Install guardrail as per contractors methodology
label | a59a5396-88fd-54d9-9a4f-722566ea7534 |  | note | Frequency - During installation
label | b340d40d-b0a4-5347-aceb-a89ea0e4f583 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 76e28e13-4b50-55b3-ab7e-0d21a5c5ccbe |  | note | Conformance Criteria - Nominally max 3 days, once concrete is hard enough. TBC with the guardrail contractor.
label | b68949ab-c64c-5329-b06c-0c3e290c172d |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 4.2 - RSHDS Inspection
label | 8c8b30d0-a886-5582-872d-f4a78fbd374d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2a5bc6c0-4b85-5dd2-a40a-065f230d8d85 |  | note | Detail - Inspection of constructed safety barrier to confirm compliance with NZTA M23 and the IFC Drawings
label | 426e4140-4bc6-58ca-9132-9d6b8857f62d |  | note | Frequency - At completion of Safety Barrier Installation
label | d1bd57f0-650e-5072-9342-1640a19cbbd8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 87808cfb-b95f-5c41-9ce1-d7edd6ebfb9b |  | note | Conformance Criteria -
label | fcb7aa1d-7bd0-588d-9642-5fa56f1b181d |  | note | Records - RSHDS Audit Form
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 - Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 5.1 - Final Walkover (Snags)
label | 1ec01b00-f506-5d7b-9a46-6e8106b4749a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1583b1b1-5afc-5be2-be31-342bb4a25f4c |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | ec9d3ee8-adf0-5cf5-8faf-cc055de75af2 |  | note | Frequency - At the completion of the Lot of work
label | acbb8d84-893c-550d-91a1-a5abfdd49e0d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | 8925842e-f0cc-5a3d-ad99-54a8a72ca936 |  | note | Conformance Criteria - Completed report with Snag List
label | 8fce97f2-50d3-5a16-87c7-8fb3a6a7a4d4 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Survey As-builts
label | 805417a1-c248-5d7e-bfe9-1d34d5cc49be |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5ddefbe6-b388-5a15-b654-c1b6f656b058 |  | note | Detail - Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided.
label | 8471dba5-9a59-516c-bfa9-d54f95cdd854 |  | note | Frequency - At the completion of the Lot of work
label | 6fb89fe4-7c5e-525b-bd73-426306a69dfc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 9d1f7821-674f-563b-8c07-e3ee1d5a9ec9 |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | 65d9eabe-4f76-58f9-aaee-de534e04fe69 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Quality Assurance Deliverables
label | cc827e45-5de3-5f90-9358-46b72efc8c99 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 17a266d8-48f4-51e0-94b9-e67bd0cfa444 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file.
label | 4f5ad46a-f4e9-5e06-b47a-061baef6ecde |  | note | Frequency - At the completion of the Lot of work
label | c0a38b7b-ecd0-5610-961c-a4497f7773f4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 1c8a90ad-da53-50d0-b67e-5b0184bccc9a |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 765d1ab1-b61d-51e2-986f-3e412df62c1c |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 5.4 - Final Approvals
label | 73a122dd-dfd0-56a2-b641-d4deefe9940f |  | note | ACTION (Hold, Monitor, Witness) - H
label | bc858959-1e65-564c-b4d0-786ffe1654d5 |  | note | Detail - Signoffs by Project Manager, Quality Manager, CPS Manager
label | dd9ac091-4419-523a-86b3-f21ef6d2c24e |  | note | Frequency - At the completion of the Lot of work
label | 20128416-f935-56b1-b42f-9a06a929fbff |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 14bf7d46-06c0-5fb5-aa55-b7fa86580df5 |  | note | Conformance Criteria - Ensure all parties have signed and approved ITP
label | 552b9390-306e-5593-ba47-e4082b05059e |  | note | Records - Signatures
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT