## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - C1603A - Waikare Gorge Descent - Groundbeam & Guardrail | itp |  |  |  |  | ITP - C1603A - Waikare Gorge Descent - Groundbeam & Guardrail
section | 1 - Preliminary
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Alternative Detailed Construction/ Installation Methodology
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Documentation from the supplier that proves the safety complies with Section 5 of the project Specification
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Section 5 of the Project Specification
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Earthworks and Pavement Works
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Earthworks and pavement construction shall be completed prior to Ground beam and Barrier installation.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Conformance Criteria - Previous ITP's approved
label | Records - Previous ITP's
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Material Compliance
checkpoint | 2.1 - Reinforcement Steel Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All reinforcing steel to comply with AS/NZS 4671 Grade 500E
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - DH16, DH12, RH12 reinforcing steel delivered and dockets collected
label | Records - Delivery dockets, packing slips, invoices
checkpoint | 2.2 - Concrete Mix Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Concrete mix to meet required strength
label | Frequency - Three weeks prior to placement of concrete
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Minimum concrete compressive strength to be 30 MPa at 28 days
label | Records - Mix design, delivery dockets
checkpoint | 2.3 - Geogrid Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All rolls bar codes are to be collected and attached to the rest of the QA Documentation
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Compliant with Tensar Triax TX160 or equivalent
label | Records - Delivery dockets, packing slips, invoices
checkpoint | 2.4 - Safety Barrier Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Documentation from the supplier that proves the safety complies with Section 5 of the project Specification
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Section 5 of the Project Specification
label | Records - Email
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Ground Beam Construction
checkpoint | 3.2 - Install Reinforcement Steel
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Reinforcing steel to have minimum 50mm cover
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Reinforcing steel placed as per design. No concrete to be poured until formwork and reinforcement approved by CPS Engineer
label | Records - CS-4040 Concrete Inspection Record, Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Concrete Pouring
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Cast-in bracket as per NZTA B5
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - As per design, Concrete dispatch dockets
label | Records - CS-4040. Concrete Inspection Record, Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Concrete Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores. Concrete slump and spread test reports.
label | Frequency - After Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria -
label | Records - Test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Geogrid
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - 1.9m wide strip laid evenly across beam and adjacent ground
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Geogrid at minimum 65mm above top of ground beam
label | Records - Photos
section | 4 - Barrier Construction
checkpoint | 4.1 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install guardrail as per contractors methodology
label | Frequency - During installation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Nominally max 3 days, once concrete is hard enough. TBC with the guardrail contractor.
label | Records - Photos
checkpoint | 4.2 - RSHDS Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspection of constructed safety barrier to confirm compliance with NZTA M23 and the IFC Drawings
label | Frequency - At completion of Safety Barrier Installation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria -
label | Records - RSHDS Audit Form
holdpoint | AUTHORITY HOLDPOINT
section | 5 - Post-Construction Closeout
checkpoint | 5.1 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Conformance Criteria - Completed report with Snag List
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 5.4 - Final Approvals
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Signoffs by Project Manager, Quality Manager, CPS Manager
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all parties have signed and approved ITP
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT