## Sheet1
1.1 | Alternative Detailed Construction/ Installation Methodology | H | Documentation from the supplier that proves the safety complies with Section 5 of the project Specification | Prior to commencement | Submission | Section 5 of the Project Specification | Email | 1.1 - Alternative Detailed Construction/ Installation Methodology | ACTION (Hold, Monitor, Witness) - H | Detail - Documentation from the supplier that proves the safety complies with Section 5 of the project Specification | Frequency - Prior to commencement | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission | Conformance Criteria - Section 5 of the Project Specification | Records - Email | 1.1 - Alternative Detailed Construction/ Installation Methodology
1.2 | Earthworks and Pavement Works | H | Earthworks and pavement construction shall be completed prior to Ground beam and Barrier installation. | Prior to commencement | Review | Previous ITP's approved | Previous ITP's | 1.2 - Earthworks and Pavement Works | ACTION (Hold, Monitor, Witness) - H | Detail - Earthworks and pavement construction shall be completed prior to Ground beam and Barrier installation. | Frequency - Prior to commencement | Inspection / Test Method submission, visual inspection, testing, measure, review - Review | Conformance Criteria - Previous ITP's approved | Records - Previous ITP's | ACTION (Hold, Monitor, Witness) - H
2.1 | Reinforcement Steel Compliance | W | All reinforcing steel to comply with AS/NZS 4671 Grade 500E | Prior to commencement | Submission | DH16, DH12, RH12 reinforcing steel delivered and dockets collected | Delivery dockets, packing slips, invoices | 2.1 - Reinforcement Steel Compliance | ACTION (Hold, Monitor, Witness) - W | Detail - All reinforcing steel to comply with AS/NZS 4671 Grade 500E | Frequency - Prior to commencement | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission | Conformance Criteria - DH16, DH12, RH12 reinforcing steel delivered and dockets collected | Records - Delivery dockets, packing slips, invoices | Detail - Documentation from the supplier that proves the safety complies with Section 5 of the project Specification
2.2 | Concrete Mix Compliance | W | Concrete mix to meet required strength | Three weeks prior to placement of concrete | Submission | Minimum concrete compressive strength to be 30 MPa at 28 days | Mix design, delivery dockets | 2.2 - Concrete Mix Compliance | ACTION (Hold, Monitor, Witness) - W | Detail - Concrete mix to meet required strength | Frequency - Three weeks prior to placement of concrete | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission | Conformance Criteria - Minimum concrete compressive strength to be 30 MPa at 28 days | Records - Mix design, delivery dockets | Frequency - Prior to commencement
2.3 | Geogrid Compliance | W | All rolls bar codes are to be collected and attached to the rest of the QA Documentation | Prior to commencement | Document Review | Compliant with Tensar Triax TX160 or equivalent | Delivery dockets, packing slips, invoices | 2.3 - Geogrid Compliance | ACTION (Hold, Monitor, Witness) - W | Detail - All rolls bar codes are to be collected and attached to the rest of the QA Documentation | Frequency - Prior to commencement | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review | Conformance Criteria - Compliant with Tensar Triax TX160 or equivalent | Records - Delivery dockets, packing slips, invoices | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
2.4 | Safety Barrier Compliance | H | Documentation from the supplier that proves the safety complies with Section 5 of the project Specification | Prior to commencement | Submission | Section 5 of the Project Specification | Email | 2.4 - Safety Barrier Compliance | ACTION (Hold, Monitor, Witness) - H | Detail - Documentation from the supplier that proves the safety complies with Section 5 of the project Specification | Frequency - Prior to commencement | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission | Conformance Criteria - Section 5 of the Project Specification | Records - Email | Conformance Criteria - Section 5 of the Project Specification
3.2 | Install Reinforcement Steel | H | Reinforcing steel to have minimum 50mm cover | During construction | Visual Inspection | Reinforcing steel placed as per design. No concrete to be poured until formwork and reinforcement approved by CPS Engineer | CS-4040 Concrete Inspection Record, Photos | 3.2 - Install Reinforcement Steel | ACTION (Hold, Monitor, Witness) - H | Detail - Reinforcing steel to have minimum 50mm cover | Frequency - During construction | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection | Conformance Criteria - Reinforcing steel placed as per design. No concrete to be poured until formwork and reinforcement approved by CPS Engineer | Records - CS-4040 Concrete Inspection Record, Photos | Records - Email
3.3 | Concrete Pouring | H | Cast-in bracket as per NZTA B5 | During construction | Visual Inspection | As per design Concrete dispatch dockets | CS-4040. Concrete Inspection Record, Photos | 3.3 - Concrete Pouring | ACTION (Hold, Monitor, Witness) - H | Detail - Cast-in bracket as per NZTA B5 | Frequency - During construction | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection | Conformance Criteria - As per design Concrete dispatch dockets | Records - CS-4040. Concrete Inspection Record, Photos | 1.2 - Earthworks and Pavement Works
3.4 | Concrete Testing | H | Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores Concrete slump and spread test reports | After Construction | Visual Inspection |  | Test results | 3.4 - Concrete Testing | ACTION (Hold, Monitor, Witness) - H | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores Concrete slump and spread test reports | Frequency - After Construction | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection | Conformance Criteria - | Records - Test results | ACTION (Hold, Monitor, Witness) - H
3.5 | Geogrid | W | 1.9m wide strip laid evenly across beam and adjacent ground | During construction | Visual Inspection | Geogrid at minimum 65mm above top of ground beam | Photos | 3.5 - Geogrid | ACTION (Hold, Monitor, Witness) - W | Detail - 1.9m wide strip laid evenly across beam and adjacent ground | Frequency - During construction | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection | Conformance Criteria - Geogrid at minimum 65mm above top of ground beam | Records - Photos | Detail - Earthworks and pavement construction shall be completed prior to Ground beam and Barrier installation.
4.1 | Guardrail Installation | W | Install guardrail as per contractors methodology | During installation | Visual inspection | Nominally max 3 days, once concrete is hard enough. TBC with the guardrail contractor. | Photos | 4.1 - Guardrail Installation | ACTION (Hold, Monitor, Witness) - W | Detail - Install guardrail as per contractors methodology | Frequency - During installation | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection | Conformance Criteria - Nominally max 3 days, once concrete is hard enough. TBC with the guardrail contractor. | Records - Photos | Frequency - Prior to commencement
4.2 | RSHDS Inspection | H | Inspection of constructed safety barrier to confirm compliance with NZTA M23 and the IFC Drawings | At completion of Safety Barrier Installation | Visual Inspection |  | RSHDS Audit Form | 4.2 - RSHDS Inspection | ACTION (Hold, Monitor, Witness) - H | Detail - Inspection of constructed safety barrier to confirm compliance with NZTA M23 and the IFC Drawings | Frequency - At completion of Safety Barrier Installation | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection | Conformance Criteria - | Records - RSHDS Audit Form | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
5.1 | Final Walkover (Snags) | H | The final walkover must be scheduled at least one week before the site's completion or demobilisation. | At the completion of the Lot of work | Walkover must be attended by Handover, Quality, CPS CHAR(AMP) Construction (other parties might be invited e.g. Resource consent close out) | Completed report with Snag List | Snag List signed by attendees | 5.1 - Final Walkover (Snags) | ACTION (Hold, Monitor, Witness) - H | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation. | Frequency - At the completion of the Lot of work | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS CHAR(AMP) Construction (other parties might be invited e.g. Resource consent close out) | Conformance Criteria - Completed report with Snag List | Records - Snag List signed by attendees | Conformance Criteria - Previous ITP's approved
5.2 | Survey As-builts | H | Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided | At the completion of the Lot of work | Drawings Survey as-built | All RFI, NCRs and site changes must be recorded. Signed and dated | As-built Drawings. Redline Markups | 5.2 - Survey As-builts | ACTION (Hold, Monitor, Witness) - H | Detail - Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided | Frequency - At the completion of the Lot of work | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings Survey as-built | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated | Records - As-built Drawings. Redline Markups | Records - Previous ITP's
5.3 | Quality Assurance Deliverables | W | Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | At the completion of the Lot of work | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | 5.3 - Quality Assurance Deliverables | ACTION (Hold, Monitor, Witness) - W | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | Frequency - At the completion of the Lot of work | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore | Records - As-builts, NCR's and RFI's | 2.1 - Reinforcement Steel Compliance
5.4 | Final Approvals | H | Signoffs by Project Manager, Quality Manager, CPS Manager | At the completion of the Lot of work | Document Review | Ensure all parties have signed and approved ITP | Signatures | 5.4 - Final Approvals | ACTION (Hold, Monitor, Witness) - H | Detail - Signoffs by Project Manager, Quality Manager, CPS Manager | Frequency - At the completion of the Lot of work | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review | Conformance Criteria - Ensure all parties have signed and approved ITP | Records - Signatures | ACTION (Hold, Monitor, Witness) - W
Detail - All reinforcing steel to comply with AS/NZS 4671 Grade 500E
Frequency - Prior to commencement
Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
Conformance Criteria - DH16, DH12, RH12 reinforcing steel delivered and dockets collected
Records - Delivery dockets, packing slips, invoices
2.2 - Concrete Mix Compliance
ACTION (Hold, Monitor, Witness) - W
Detail - Concrete mix to meet required strength
Frequency - Three weeks prior to placement of concrete
Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
Conformance Criteria - Minimum concrete compressive strength to be 30 MPa at 28 days
Records - Mix design, delivery dockets
2.3 - Geogrid Compliance
ACTION (Hold, Monitor, Witness) - W
Detail - All rolls bar codes are to be collected and attached to the rest of the QA Documentation
Frequency - Prior to commencement
Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
Conformance Criteria - Compliant with Tensar Triax TX160 or equivalent
Records - Delivery dockets, packing slips, invoices
2.4 - Safety Barrier Compliance
ACTION (Hold, Monitor, Witness) - H
Detail - Documentation from the supplier that proves the safety complies with Section 5 of the project Specification
Frequency - Prior to commencement
Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
Conformance Criteria - Section 5 of the Project Specification
Records - Email
3.2 - Install Reinforcement Steel
ACTION (Hold, Monitor, Witness) - H
Detail - Reinforcing steel to have minimum 50mm cover
Frequency - During construction
Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
Conformance Criteria - Reinforcing steel placed as per design. No concrete to be poured until formwork and reinforcement approved by CPS Engineer
Records - CS-4040 Concrete Inspection Record, Photos
3.3 - Concrete Pouring
ACTION (Hold, Monitor, Witness) - H
Detail - Cast-in bracket as per NZTA B5
Frequency - During construction
Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
Conformance Criteria - As per design Concrete dispatch dockets
Records - CS-4040. Concrete Inspection Record, Photos
3.4 - Concrete Testing
ACTION (Hold, Monitor, Witness) - H
Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores Concrete slump and spread test reports
Frequency - After Construction
Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
Conformance Criteria -
Records - Test results
3.5 - Geogrid
ACTION (Hold, Monitor, Witness) - W
Detail - 1.9m wide strip laid evenly across beam and adjacent ground
Frequency - During construction
Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
Conformance Criteria - Geogrid at minimum 65mm above top of ground beam
Records - Photos
4.1 - Guardrail Installation
ACTION (Hold, Monitor, Witness) - W
Detail - Install guardrail as per contractors methodology
Frequency - During installation
Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
Conformance Criteria - Nominally max 3 days, once concrete is hard enough. TBC with the guardrail contractor.
Records - Photos
4.2 - RSHDS Inspection
ACTION (Hold, Monitor, Witness) - H
Detail - Inspection of constructed safety barrier to confirm compliance with NZTA M23 and the IFC Drawings
Frequency - At completion of Safety Barrier Installation
Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
Conformance Criteria -
Records - RSHDS Audit Form
5.1 - Final Walkover (Snags)
ACTION (Hold, Monitor, Witness) - H
Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
Frequency - At the completion of the Lot of work
Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS CHAR(AMP) Construction (other parties might be invited e.g. Resource consent close out)
Conformance Criteria - Completed report with Snag List
Records - Snag List signed by attendees
5.2 - Survey As-builts
ACTION (Hold, Monitor, Witness) - H
Detail - Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided
Frequency - At the completion of the Lot of work
Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings Survey as-built
Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated
Records - As-built Drawings. Redline Markups
5.3 - Quality Assurance Deliverables
ACTION (Hold, Monitor, Witness) - W
Detail - Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file.
Frequency - At the completion of the Lot of work
Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
Records - As-builts, NCR's and RFI's
5.4 - Final Approvals
ACTION (Hold, Monitor, Witness) - H
Detail - Signoffs by Project Manager, Quality Manager, CPS Manager
Frequency - At the completion of the Lot of work
Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
Conformance Criteria - Ensure all parties have signed and approved ITP
Records - Signatures