## Sheet3
Inspection and Test Plan Te Ara o Te Ata Fill 14 Bored Piles ITP # MMA-QA-ITP-Z07-EW-GE006
Rev Number | This ITP has been prepared by |  |  | Reviewed by (QA representative) |  |  | Reviewed by (DSR Representative) |  |  | Approved by [Construction Manager]
| Name | Signature | Date | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date
Rev 01 | William McCracken | WM | 2024-02-14 | Ramy Faragalla | R Faragalla | 2024-03-06 | Dani Thompson Hayden Bowen | DANT / HJB | 2024-03-04 | Hardus Pieters |  |  |  | 2024-03-20
Rev 02
Rev 03
Rev 04
ITP NO: MMA-QA-ITP-Z07-EW-GE006 |  | Project: Te Ara o Te Ata | [8 empty] | Rev.01
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. | [7 empty] | Responsibilities PE = MTM Alliance Construction TWD = Temporary Design Team
Activity/Specification: Concrete Culvert | [7 empty] | Area Location / Work Breakdown: Length of Mt Messenger Bypass
Item | Construction Step or Material |  | Specifications and Standards |  | Acceptance criteria and testing |  |  |  | Method (H,I,W,R) |  |  |  | Verifying Records Checklists, Test and Supplier Certificates
Responsible [tick]
[5 empty] | Method/Description | Test frequency |  | Conformance Criteria | Contractor | Designer | Client | Lab
1.0 Pre-Construction
1.1.0 Pre-construction approvals
1.1.1 | Construction Environmental Management Plan |  | MMA-ENV-RMP-RPT-15631 |  | Document Review | Prior to work starting |  | Ensure all crew members are briefed on the CEMP | H |  |  |  | Signed CEMP
1.1.2 | Construction Work Plan |  | CWP |  | Document Review | Prior to work starting |  | Ensure all crew members are briefed on the CWP | H |  |  |  | Signed off CWP
1.1.3 | IANZ accredited testing organisation |  | Details of proposed testing organisation |  | Document Review | Once prior to works commencing |  | Designer review and approval required on all test equipment calibration certificates and frequency on testing | H | H |  |  | Test and supplier certificates
1.1.4 | IFC drawings |  | Obtain IFC drawings |  | Document Review | Once prior to works commencing |  | Ensure all drawings are approved and of the latest revision, or written approval from PAB | H | H |  |  | IFC drawings or Written approval from PAB
1.1.5 | Survey Set Out |  | MMA-DES-GEO-E1-DRG-2022 |  | Survey Set Out | Prior to work starting |  | Surveyor to confirm set out is as per latest IFC Drawings | H | W
1.1.6 | Piling Platform |  | MMA-CON-DRW-Z07-TW-CV112 |  | Temporary Works Design Engineer to sign off permit to load prior to loading | Prior to works commencing |  | Piling platform construction to conform to approved temporary works design | H |  |  |  | Permit to Load
1.1.7 | Method statement and piling programme |  | NZGS Piling Specification |  | Document Review | At least 1 week prior to work starting |  | Provision of information to the Designer | H | H
1.1.8 | Piling supervision |  | NZGS Piling Specification |  | Nomination | Before construction and as necessary until the end of works. |  | The Piling Supervisor shall be responsible for ensuring that all piling operations comply with the requirements of this Specification. The Piling Supervisor shall also ensure that all monitoring and pile records are maintained up to date and are available for inspection by the Engineer. The Piling Supervisor shall not be removed from the works without the Engineer being notified one week in advance. The Contractor shall nominate a suitable replacement before the Piling Supervisor is removed from the works. | H | W
1.1.9 | Observation |  | NZGS Piling Specification |  | Contractor to provide adequate notice to enable DSR inspections | Daily during works |  | The Contractor shall keep the Engineer informed daily or as agreed with the Engineer as to the work anticipated to be carried out on the next working day. | W | W
1.1.10 | Tremie check |  | NZGS Piling Specification |  | Confirmation of tremie sizing as outlined in section 2.1.5.2 of the specification. | Once prior to works commencing |  | Accepted by DSR | H | W |  |  | Record
1.1.11 | Design of temporary casing |  | NZGS Piling Specification |  | Contractor to complete detailed design of temporary casings | Once prior to works commencing |  | Review | H | W |  |  | Record
1.2.0 Material compliance
1.2.1 | Concrete Mix Design |  | MMA-DES-STR-E1-SPC-8699 Cluase 7 NZS 3104:2003 CL 2.13.3.3 |  | Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 1 week prior to placing concrete and approved before placing concrete | Prior to commencement |  | Concrete shall typically be NORMAL concrete (N) as defined in NZS 3104 Clause 2.10.1 supplied from an approved Ready Mix plant. The Concrete Mix design should comply with NZS 3104 Clause 2.13.3.3 & 2.14 requirements. The minimum Concrete strength at 28 days should be 40MPa. Accepted by DSR | H | H |  |  | Mix Design Certificate
1.2.2 | Steel Reinforcement |  | MMA-DES-STR-E1-SPC-8729 Clause 6.1.1 AS/NZS 4671 & NZS 3109 |  | Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings | Prior to ordering steel |  | Steel reinforcement shall be either Grade 300E or Grade 500E, complying with AS/NZS 4671 unless specified otherwise in the drawings or by the designer. Reinforcing bars shall be manufactured using the microalloy process. | H | W? |  |  | Mill Certificates Detail Sheets
1.2.3 | Welding of Reinforcement |  | AS/NZS 1554.5 Table 6.2, NZS3404 |  | Any welding or mechanical splicing to be approved in writing by the Design Engineer | Prior to welding or splicing |  | Approved by DSR | H | H |  |  | As-Built
1.2.4 | Welding of Reinforcement |  | AS/NZS 1554.5 Table 6.2, All Welds to be 10mm FWSP lengths as per AS/NZS 1554.3. |  | 100% Visual Scanning of all welds 100% Visual Inspection 10% magnetic particle or liquid penetrant 10% radiography or ultrasonics | Each Weld |  | No defects identifed in any welds | H | W |  | I | Weld Inspection Report
1.2.5 | On-Site Bending of Reinforcement |  |  |  | Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer | Prior to cutting or bending onsite |  | Accepted by DSR | H | H |  |  | Approved RFI
1.2.6 | Storage of pile casings |  | NZGS Piling Specification |  | Pile casings shall be stacked on suitable supports on firm ground | Prior to commencement |  | Accepted by DSR | H | H |  |  | Approved RFI
1.2.7 | Concreting placement methodology |  | NZGS Piling Specification |  | The concreting methodology shall be reviewed in advance by the Engineer, who will require to be satisfied that the method of placing and the concrete mix design will result in concrete fully compacted in place, possessing the specified strength and having the necessary density, integrity and durability. | Prior to commencement |  | Accepted by DSR | H | H |  |  | Approved RFI
2.0 Construction
2.1.0 Drilling
2.1.0 | Installation/Removal of Temporary Casing |  |  |  | Vibe temporary casing to rock level, Extract Casing immediately following concrete pour. Suffiecient quanitity of concrete to be mainted with in the casing during removal to ensure external pressures are exceeded | Each Pile |  | A short length of temporary casing shall be provided for all piles to maintain an upstand of at least 0.9 m above the adjacent ground surface level. Casing to be removed as soon as practically possible unless approved otherwise by the DSR. | H |  |  |  | Bored Pile Record
2.1.1 | Drill Rig Set Up |  | NZGS Piling Specification |  | Check drilling performance, verticality and position. Drilling equipment must be capable of drilling into inclined rock surface | Each Pile |  | Confirm pile tolerances. Pile tolerance is to be: - 75mm horizontally of the location as shown in the drawings - Vertical location of the pile top at plus 40mm or minus 75mm of the position shown in the drawings - Pile verticality of 1H:75V or straighter If tolerances on site are not achieved remedial work shall not be carried out without the written permission of the designer. | W | W |  |  | Bored Pile Record
2.1.2 | Pile Bore and Condition Log |  | NZGS Piling Specification |  | Inspect pile bore condition, pile depth, rock socket length, toe level and ground water level. No Pile shall be left open for greater then 24 hrs; pile borehole to be checked and cleaned if open more than 12 hrs; Concreting shall be done on the same day | Each Pile |  | Accepted by DSR | H | W |  |  | Bored Pile Record
2.1.3 | Rock Socket |  | IFC Drawings |  | Each bored pile excavation shall be inspected by a Geotechnical Site Representative to ensure that the material at the base of the pile complies with the design requirements (i.e. founded in Mt Messenger Formation rock). The pile construction record shall be signed by the Geotechnical Site Representative to say the inspection has taken place and that the founding stratum meets the design requirements. | Each Pile |  | Min 1m rock socket required | H | W |  |  | Bored Pile Record
2.1.4 | Cleaness of Pile Base |  | NZGS Piling Specification Appendix A |  | All loose material to be removed from the bore using appropriate methods. Details of cleaning equipment to be submitted to the DSR at least 7 days prior to use onsite | Each Pile |  | Accepted by DSR | H | H |  |  | Approved RFI Bored Pile Record
2.1.5 | Base Hardness |  | NZGS Piling Specification Appendix A, Section 3.3, Table 1.1 |  | Base Hardness Test to be undertaken immediately prior to placement of reinforecemnt cage. | Each Pile |  | Testing to be carried out by DSR. Base hardness value to be between Grades 1 - 3 | H | H |  |  | Bored Pile Record
2.1.6 | Pile bore |  | NZGS Piling Specification - section 3.8 |  | Observation of geotechnical conditions encountered and confirmation of key design assumptions. Contractor to inform designer at least 1 day in advance where pile observations will be required. | Each Pile |  | Confirmation with DSR. | H | H |  |  | Bored Pile Record
2.2.0 Construction of Pile
2.2.1 | Reinforcement Cage |  | IFC Drawings |  | Visual Inspection to check supply and installation of reinforcement cage. Confirm cages have been supplied as per detail sheets. Confirm Grade, Size, spacing, lap lengths and weld postions are as per IFC drawings | Each Pile |  | Approved by DSR Pre-Pour Signed off by DSR | H | H |  |  | Detail Sheets Bored Pile Record
2.2.2 | Pre Pour Inspection |  | IFC Drawings |  | DSR to inspect and sign off each pile prior to concreting Visual check of socket cleanliness inf dry | Each Pile |  | Pre-Pour Signed by DSR Min 75mm cover to be mainted to all surfaces and top of pile | H | H |  |  | Bored Pile Record
2.2.3 | Concrete Supply |  | NZS 3104 Apporved Mix Design |  | All concrete delivered to site shall be produced strictly in accordance with the approved mix design Concrete dockets checked for correct mix and concrete site testing undertaken. One set of 3 cylinders to be taken for each set of poured piles Onsite Slump Test | Each Delivery |  | Confirm cocnrete dockets match mix design Tagret Slump 180mm, Min Compressive Strength of 40MPa @ 28 Days | H | W |  | I | Concrete Dockets Bored Pile Record Concrete Test Results
2.2.4 | Concrete Placement - Placing concrete under water |  | NZGS Piling Specification |  | Should either: • the depth of water at the base of the pile at the commencement of concrete placement exceed 75 mm; or • the inflow of water exceeds 200 mm of bore depth per hour; or • the use of drilling fluid prove necessary to maintain excavation stability,then concrete shall be placed using a tremie and a methodology that meets the appropriate requirements which are stipulated in this specification and the recommendations that are described in the publication “Recommended Practice Tremie Concrete for Deep Foundations (CIA, 2012) and/or Guide to Tremie Concrete for Deep Foundations (EFFC/DFI, 2018)”. | Each Pile |  | Confirmation with DSR. | H | H
2.2.5 | Concrete Placement - Dry Pour |  | NZGS Piling Specification |  | Concrete height to be no greater than 10m. Concreting of piles shall be carried out continuously so no segregation occurs. No concrete shall be placed when there is any danger of adverse weather causing damage to plastic or partially set concrete due to movement of pile casings. | Each Pile |  | Confirmation with DSR. | H | H
2.2.6 | Post Pour Inspection |  | IFC Drawings and NZGS Piling Specification |  | Complete Survey of Wet concrete level to ensure pile is poured to correct height Confirm finish is as per IFC Drawings Record of pile length | Each Pile |  | Accepted by DSR | H | W |  |  | Bored Pile Record
2.2.7 | Reinforcement cage support during installation |  | NZGS Piling Specification |  | Reinforcement cage to be adequately supported at all times during construction | Each Pile |  | Accepted by DSR | H | W |  |  | Bored Pile Record
3.0 Post Construction
3.1 | Survey/as-builts |  | IFC Drawings |  | Survey final position and top R.L. of each pile, produce As-Built drawings including stated measurements of pile lengths; record bedrock level | Each Pile |  | Pile tolerance is to be: - 75mm horizontally of the location as shown in the drawings - Vertical location of the pile top at plus 40mm or minus 75mm of the position shown in the drawings - Pile verticality of 1H:75V or straighter | H | R |  |  | As-Built
3.2 | Red-Line As-built |  | . |  | Draewings updated to reflect any changes during construction Any RFI's and NCR's noted on drawings and closed out prior to drawing re-issue | On Completion of Works |  | Accepted by CPS Manager & Quality Manger | H | R |  |  | Red-Line As-Built