## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Fill 14 Bored Piles | itp |  |  |  |  | ITP - Fill 14 Bored Piles
section | 1.1.0 Pre-construction approvals
checkpoint | 1.1.1 - Construction Environmental Management Plan
label | Method/Description - Document Review
label | Test frequency - Prior to work starting
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed CEMP
checkpoint | 1.1.2 - Construction Work Plan
label | Method/Description - Document Review
label | Test frequency - Prior to work starting
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
checkpoint | 1.1.3 - IANZ accredited testing organisation
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Test and supplier certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.4 - IFC drawings
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or Written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.5 - Survey Set Out
label | Method/Description - Survey Set Out
label | Test frequency - Prior to work starting
label | Contractor - H
label | Designer - W
checkpoint | 1.1.6 - Piling Platform
label | Method/Description - Temporary Works Design Engineer to sign off permit to load prior to loading
label | Test frequency - Prior to works commencing
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Permit to Load
checkpoint | 1.1.7 - Method statement and piling programme
label | Method/Description - Document Review
label | Test frequency - At least 1 week prior to work starting
label | Contractor - H
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.8 - Piling supervision
label | Method/Description - Nomination
label | Test frequency - Before construction and as necessary until the end of works.
label | Contractor - H
label | Designer - W
checkpoint | 1.1.9 - Observation
label | Method/Description - Contractor to provide adequate notice to enable DSR inspections
label | Test frequency - Daily during works
label | Contractor - W
label | Designer - W
checkpoint | 1.1.10 - Tremie check
label | Method/Description - Confirmation of tremie sizing as outlined in section 2.1.5.2 of the specification.
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Record
checkpoint | 1.1.11 - Design of temporary casing
label | Method/Description - Contractor to complete detailed design of temporary casings
label | Test frequency - Once prior to works commencing
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Record
section | 1.2.0 Material compliance
checkpoint | 1.2.1 - Concrete Mix Design
label | Method/Description - Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 1 week prior to placing concrete and approved before placing concrete
label | Test frequency - Prior to commencement
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Mix Design Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.2 - Steel Reinforcement
label | Method/Description - Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings
label | Test frequency - Prior to ordering steel
label | Contractor - H
label | Designer - W?
label | Verifying Records Checklists, Test and Supplier Certificates - Mill Certificates, Detail Sheets
checkpoint | 1.2.3 - Welding of Reinforcement
label | Method/Description - Any welding or mechanical splicing to be approved in writing by the Design Engineer
label | Test frequency - Prior to welding or splicing
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - As-Built
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.4 - Welding of Reinforcement
label | Method/Description - 100% Visual Scanning of all welds
label | ○ 100% Visual Inspection
label | ○ 10% magnetic particle or liquid penetrant
label | ○ 10% radiography or ultrasonics
label | Test frequency - Each Weld
label | Contractor - H
label | Designer - W
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Weld Inspection Report
checkpoint | 1.2.5 - On-Site Bending of Reinforcement
label | Method/Description - Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer
label | Test frequency - Prior to cutting or bending onsite
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Approved RFI
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.6 - Storage of pile casings
label | Method/Description - Pile casings shall be stacked on suitable supports on firm ground
label | Test frequency - Prior to commencement
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Approved RFI
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.7 - Concreting placement methodology
label | Method/Description - The concreting methodology shall be reviewed in advance by the Engineer, who will require to be satisfied that the method of placing and the concrete mix design will result in concrete fully compacted in place, possessing the specified strength and having the necessary density, integrity and durability.
label | Test frequency - Prior to commencement
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Approved RFI
holdpoint | AUTHORITY HOLDPOINT
section | 2.1.0 Drilling
checkpoint | 2.1.0 - Installation/Removal of Temporary Casing
label | Method/Description - Vibe temporary casing to rock level, Extract Casing immediately following concrete pour.
label | ○ Sufficient quanitity of concrete to be mainted with in the casing during removal to ensure external pressures are exceeded
label | Test frequency - Each Pile
label | Contractor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
checkpoint | 2.1.1 - Drill Rig Set Up
label | Method/Description - Check drilling performance, verticality and position. Drilling equipment must be capable of drilling into inclined rock surface
label | Test frequency - Each Pile
label | Contractor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
checkpoint | 2.1.2 - Pile Bore and Condition Log
label | Method/Description - Inspect pile bore condition, pile depth, rock socket length, toe level and ground water level.
label | ○ No Pile shall be left open for greater then 24 hrs; pile borehole to be checked and cleaned if open more than 12 hrs; Concreting shall be done on the same day
label | Test frequency - Each Pile
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
checkpoint | 2.1.3 - Rock Socket
label | Method/Description - Each bored pile excavation shall be inspected by a Geotechnical Site Representative to ensure that the material at the base of the pile complies with the design requirements (i.e. founded in Mt Messenger Formation rock). The pile construction record shall be signed by the Geotechnical Site Representative to say the inspection has taken place and that the founding stratum meets the design requirements.
label | Test frequency - Each Pile
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
checkpoint | 2.1.4 - Cleaness of Pile Base
label | Method/Description - All loose material to be removed from the bore using appropriate methods. Details of cleaning equipment to be submitted to the DSR at least 7 days prior to use onsite
label | Test frequency - Each Pile
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Approved RFI Bored Pile Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.5 - Base Hardness
label | Method/Description - Base Hardness Test to be undertaken immediately prior to placement of reinforecemnt cage.
label | Test frequency - Each Pile
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.6 - Pile bore
label | Method/Description - Observation of geotechnical conditions encountered and confirmation of key design assumptions. Contractor to inform designer at least 1 day in advance where pile observations will be required.
label | Test frequency - Each Pile
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
holdpoint | AUTHORITY HOLDPOINT
section | 2.2.0 Construction of Pile
checkpoint | 2.2.1 - Reinforcement Cage
label | Method/Description - Visual Inspection to check supply and installation of reinforcement cage.
label | ○ Confirm cages have been supplied as per detail sheets.
label | ○ Confirm Grade, Size, spacing, lap lengths and weld postions are as per IFC drawings
label | Test frequency - Each Pile
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Detail Sheets, Bored Pile Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.2 - Pre Pour Inspection
label | Method/Description - DSR to inspect and sign off each pile prior to concreting
label | ○ Visual check of socket cleanliness inf dry
label | Test frequency - Each Pile
label | Contractor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.3 - Concrete Supply
label | Method/Description - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
label | ○ Concrete dockets checked for correct mix and concrete site testing undertaken.
label | ○ One set of 3 cylinders to be taken for each set of poured piles
label | ○ Onsite Slump Test
label | Test frequency - Each Delivery
label | Contractor - H
label | Designer - W
label | Lab - I
label | Verifying Records Checklists, Test and Supplier Certificates - Concrete Dockets, Bored Pile Record, Concrete Test Results
checkpoint | 2.2.4 - Concrete Placement - Placing concrete under water
label | Method/Description - Should either:
label | ○ the depth of water at the base of the pile at the commencement of concrete placement exceed 75 mm; or
label | ○ the inflow of water exceeds 200 mm of bore depth per hour; or
label | ○ the use of drilling fluid prove necessary to maintain excavation stability,then concrete shall be placed using a tremie and a methodology that meets the appropriate requirements which are stipulated in this specification and the recommendations that are described in the publication “Recommended Practice Tremie Concrete for Deep Foundations (CIA, 2012) and/or Guide to Tremie Concrete for Deep Foundations (EFFC/DFI, 2018)”.
label | Test frequency - Each Pile
label | Contractor - H
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.5 - Concrete Placement - Dry Pour
label | Method/Description - Concrete height to be no greater than 10m.
label | ○ Concreting of piles shall be carried out continuously so no segregation occurs.
label | ○ No concrete shall be placed when there is any danger of adverse weather causing damage to plastic or partially set concrete due to movement of pile casings.
label | Test frequency - Each Pile
label | Contractor - H
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2.6 - Post Pour Inspection
label | Method/Description - Complete Survey of Wet concrete level to ensure pile is poured to correct height
label | ○ Confirm finish is as per IFC Drawings
label | ○ Record of pile length
label | Test frequency - Each Pile
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
checkpoint | 2.2.7 - Reinforcement cage support during installation
label | Method/Description - Reinforcement cage to be adequately supported at all times during construction
label | Test frequency - Each Pile
label | Contractor - H
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Bored Pile Record
section | 3.0 Post Construction
checkpoint | 3.1 - Survey/as-builts
label | Method/Description - Survey final position and top R.L. of each pile, produce As-Built drawings including stated measurements of pile lengths; record bedrock level
label | Test frequency - Each Pile
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - As-Built
checkpoint | 3.2 - Red-Line As-built
label | Method/Description - Draewings updated to reflect any changes during construction
label | ○ Any RFI's and NCR's noted on drawings and closed out prior to drawing re-issue
label | Test frequency - On Completion of Works
label | Contractor - H
label | Designer - R
label | Verifying Records Checklists, Test and Supplier Certificates - Red-Line As-Built