## Pavement Construction
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | SH5 SIP Generic |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Pavement Construction incl Culvert Extn |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Setout & Saw Cutting
1.1 | Survey Setout | M | Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction | Prior to commencement | Survey |  | Survey receipt | Site Engineer
1.2 | Saw cutting | H | Proposed Sawcut line to be inspected by the engineer | During construction | Visual Inspection | Project Specification 6.6 | Photos | Site Engineer | CPS Engineer
2 | Material Compliance
2.1 | Sub Base Material Compliance | H | Aggregate material compliance for Sub Base stockpiles | Prior to commencement | Lab Testing | Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC | Notice to Supplier and Lab Test results for the stockpiles used during construction | Site Engineer | CPS Engineer
2.2 | Base Course Material Compliance | H | Aggregate material compliance for Base Course stockpiles | Prior to commencement | Lab Testing | Aggregate shall comply with TNZ M/4 | Notice to Supplier and Lab Test results for the stockpiles used during construction | Site Engineer | CPS Engineer
2.3 | Base Course Mat Sample Testing | H | Mat sampling of Basecourse Material | 1 mat sample for the job. Pavement CPS Engineer for further instruction | Lab testing | Grading to comply with specification | Mat sample lab test result | Site Engineer | CPS Engineer
2.4 | Concrete Pipes | W | Specification Compliance | Each delivery to site | Certification | All concrete pipes shall comply with the requirements of NZS 3107 "Precast Concrete Drainage and Pressure Pipes". | Delivery Dockets | Site Engineer
2.5 | Pipe Bedding Material Compliance | H | Material to meet specifications dependant on material type selected | Each material used | Document Review | Compliance with requirements from Specifications | Lab Test Report | Site Engineer | CPS Engineer
2.6 | Pipe Backfill Compliance | H | Material to meet specifications dependant on material type selected | Each material used | Document Review | Comply with grading specification |  | Site Engineer | CPS Engineer
2.7 | Chip Seal design | H | Seal design to be reviewed prior to sealing. Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer. | Prior to Sealing | Review | The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995. | Emails/NTE | Site Engineer | CPS Engineer
3 | Sub Grade Construction
3.1 | Sub Grade Strength | H | Determine Bearing strength of Sub Grade | After Dig out, every 5m | Testing | Min. 2 blows /100mm 2 blows = 4 CBR | QA measurement Sheet CS-4000 1m Scala | Site Engineer | CPS Engineer
3.2 | Proof Roll of subgrade | H | Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement | Prior to Sub Base Construction | Visual Inspection | Engineers Acceptance | Emails | Site Engineer | CPS Engineer
4 | Sub Base Construction
4.1 | Sub Base Aggregate Delivery Checks | M | All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number | During construction | Measurement and recording | Comply with TNZ M/3 Specification. NZTA B/2 Specification | Delivery Dockets, Aggregate Deliveries Register | Site Engineer
4.2 | Sub Base Material Contamination Checks | M | Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant | During construction | Visual Inspection |  | Photos | Site Engineer
4.3 | Sub Base Trimmed Level Checks | M | Carry out a Level Check on the trimmed Sub base | 1/100m if machine control is used or 1/20m if no machine control | Measurement | TNZ B/2 Tolerance = -25mm/+5mm | QA measurement Sheet CS-4100a Subbase Approval | Site Engineer
4.4 | Sub Base Compaction Lower | H | Degree of Compaction. The subbase shall be constructed in two layers. Lower subbase results must be approved before construction of upper layer. | Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area. | NDM Testing | Avg. >= 95% MDD and Min. >= 92% MDD | Pavement Lab Testing Spreadsheet | Site Engineer | CPS Engineer
4.5 | Sub Base Compaction Upper | H | Degree of Compaction. The subbase shall be constructed in two layers. Upper subbase results must be approved before construction of basecourse. | Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area. | NDM Testing | Avg. >= 95% MDD and Min. >= 92% MDD | Pavement Lab Testing Spreadsheet | Site Engineer | CPS Engineer
5 | Base Course Construction
5.1 | Base Course Aggregate Delivery Checks | M | All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number | During construction | Measurement and recording | Comply with TNZ M/4 Specification. Traceability of all materials delivered to site | Delivery Dockets, Aggregate Deliveries Register | Site Engineer
5.2 | Base Course Material Contamination Checks | M | Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant | During construction | Visual Inspection |  | Photos | Site Engineer
5.3 | Base Course Trimmed Level Checks | M | Carry out a Level Check on the trimmed Basecourse | 1/100m if machine control is used or 1/20m if no machine control | Measurement | Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm | QA measurement Sheet CS-4100b Basecourse Approval | Site Engineer
5.4 | Base Course Compaction | H | Degree of Compaction | 5 per Lot | NDM Lab Testing | Avg. >= 98% MDD and Min. >= 95% MDD | Pavement Lab Testing Spreadsheet | Site Engineer | CPS Engineer
5.5 | Base Course Surface shape check | H | Surface shape check | Prior to sealing | Measurement | No point of the surface shall vary more than 10mm over a 3m long straight edge | QA measurement Sheet CS-4100b Basecourse Approval | Site Engineer | CPS Engineer
5.6 | Base Course Surface finish check | H | Surface finish check | Prior to sealing | Visual inspection by CPS Engineer after site sweeping | The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping | Site photos, Emails | Site Engineer | CPS Engineer
6 | Extension of Culvert
6.1 | Foundation Compliance | H | Test formation level on completion of excavation to check if undercut required | One test per 5 linear metres | Scala Penetrometer | Min. 2 blows /100mm 2 blows = 4 CBR | Lab Test Report | Site Engineer | CPS Engineer
6.2 | Levels Compliance | H | Test formation level on completion of excavation to check if undercut required | As stated | Visual | Designer to inspect formation level at outfalls / inlets. | Photos, Visual | Site Engineer | CPS Engineer
7 | Sealing
7.1 | Location/Size Confirmation | W | Mark up extent of Chipseal | Prior to Sealing | Mark out |  | Photos | Site Engineer
7.2 | Surface Cleanliness | W | To confirm that all loose material is removed from the surface and surrounding area. | Prior to application of binder | Visual inspection |  | Photos | Site Engineer
7.3 | Binder Application | W | Ensure the Binder application is according to the seal design | During sealing | Measure | According to seal design | Sealing sheet | Site Engineer
7.4 | Chip Application | W | Ensure the Chip application is according to the seal design | During sealing | Measure | According to seal design | Sealing sheet | Site Engineer |  |  | `
7.5 | Compaction | W | At completion of rolling | During sealing | Visual | Ensure sufficient passes with roller to embed chip (typically 4-5 passes) | Photos, QA measurement Sheet | Site Engineer
7.6 | Removal of excess chip | M | Removal of excess chip | Within 48 Hours of Sealing | Visual | Ensure all excess chip removed from site. No chip windrows left on site in Shoulders. | Photos, Site logs | Site Engineer
7.7 | Surface finish check | H | Surface finish check | After sealing | Visual | Engineers Acceptance | Photos Email | Site Engineer | CPS Engineer
8 | Road Marking
8.1 | Road Marking | H | The engineer is to be given the opportunity to inspect the proposed location & type of markings | Prior to the final line marking | Visual | Engineers Acceptance | Photos Email | Site Engineer | CPS Engineer
9 | Hydroseeding
9.1 | Hydroseeding | H | Engineer to inspect and confirm satisfactory cover achieved | At the completion of the Lot of work | Visual | Engineers Acceptance | Photos Email | Site Engineer | CPS Engineer
10 | Post-Construction Closeout
10.1 | Final Walkover (Snags) | H | The final walkover must be scheduled at least one week before the site's completion or demobilisation. | At the completion of the Lot of work | Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out) | Completed report | Snag List signed by attendees | Quality
10.2 | Survey As-builts | H | Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided | At the completion of the CWP of work | Drawings Survey as-built | All RFI, NCRs and site changes must be recorded. Signed and dated | As-built Drawings. Redline Markups | Site Engineer
10.3 | Quality Assurance Deliverables | W | Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file. | At the completion of the CWP | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer