## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - E3001 - SH05 SIP Generic - Pavement Construction | itp |  |  |  | Yes | ITP - E3001 - SH05 SIP Generic - Pavement Construction | 3a1d22fe-c551-4a3f-ae0f-be3fdd2243c4
checkpoint-group |  |  | section | 1. Setout & Saw Cutting
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 6ea2e9b0-3e99-515b-8af7-0ff1cc351d4d |  | textbox | CPS Eng.
text | a1ccf71d-377d-59ec-a75e-937d152a07fc |  | textbox | Site Engineer
text | 24b53b5e-8359-54ba-90f2-0bf1919c2e02 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Survey Setout
label | 0ee1be7d-466b-5bb0-bda2-fb13d54353a7 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 30a17514-b305-5d91-95b4-1c6d1d56b912 |  | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | 252d7dc2-2808-547a-84ab-e2a8fde743bd |  | note | Frequency - Prior to commencement
label | ca1c2cd4-99d7-5431-a2a4-bec2573cf7f1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 8e8dc048-fefc-5e77-a938-15b5f5fea317 |  | note | Conformance Criteria -
label | 72a7b585-b5ca-5d22-aa57-24497eee6a17 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 1.2 - Saw cutting
label | 895c7822-c09b-5446-bf04-565f7b21b767 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 18983e90-1ada-5aa0-b14d-d3e6023a6578 |  | note | Detail - Proposed Sawcut line to be inspected by the engineer
label | 8e05daa0-c3c9-5855-a441-ededb80ba7ea |  | note | Frequency - During construction
label | c923999d-0696-5e2f-b60e-cdea5b012567 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 215687a8-f104-504d-84df-0947cfe76e7a |  | note | Conformance Criteria - Project Specification 6.6
label | 9d626d29-a8b2-5f2d-8174-015bf2fc6ed5 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2. Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Sub Base Material Compliance
label | b6018eea-16a5-574e-8472-911419491cd2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 682ce5b7-8519-5217-a57d-aee6c4127020 |  | note | Detail - Aggregate material compliance for Sub Base stockpiles
label | 9b14de80-269d-5959-9d8c-2195501696d4 |  | note | Frequency - Prior to commencement
label | 1c688bb0-7482-59e9-8369-16d1f71cb5e2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 3dd00bb4-298f-5653-96ca-d468c67cadd3 |  | note | Conformance Criteria - Comply with TNZ M/3 Specification.
label | 93887794-75b2-58c6-bc4b-e3596c7d5ac8 |  | note | ○ NZTA B/2 Specification Lab test for MDD at OWC
label | 81b800f1-6a6c-5813-ba2e-4b8de6e9fd41 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Base Course Material Compliance
label | b51447ed-eb37-51b4-a6af-2f8c5e8484dd |  | note | ACTION (Hold, Monitor, Witness) - H
label | 063e5cf1-bddb-583e-99f4-4b2617b4a1ee |  | note | Detail - Aggregate material compliance for Base Course stockpiles
label | 94526e72-d168-5bfb-ac84-77a4686b82b9 |  | note | Frequency - Prior to commencement
label | b36ecc74-8ff8-5f1c-91fc-e494307d2ad5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 2b71edbc-3376-55b3-9e5d-c2911961c706 |  | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
label | 0e9e8491-caf6-51e4-a636-af6f3e4d9bf6 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Base Course Mat Sample Testing
label | 99f9ff7b-4ed2-553b-b6d2-fcd8ebc1537a |  | note | ACTION (Hold, Monitor, Witness) - H
label | ff0679ab-f699-54e1-8909-833171f8d034 |  | note | Detail - Mat sampling of Basecourse Material
label | 72b25cb6-8795-5ab8-9ed7-900f72514fc1 |  | note | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
label | 7cde541c-7ea7-576f-808a-9d0f142c3668 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab testing
label | 6fd03ea9-009d-5679-847a-3fa7e4fdbd74 |  | note | Conformance Criteria - Grading to comply with specification
label | b6021767-392d-53aa-ad87-25ef4de60c2e |  | note | Records - Mat sample lab test result
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Chip Seal design
label | 6cb76005-ed6a-5b71-9b4e-a401467f532c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 18a64b26-47b9-5b09-831d-ab9204f52645 |  | note | Detail - Seal design to be reviewed prior to sealing.
label | 37eeb198-4f90-5ef3-b157-014f36c8bf17 |  | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
label | 78eaa47c-f9e0-58da-8115-9f85a223f672 |  | note | Frequency - Prior to Sealing
label | 96fcfd5e-5c5b-5d59-b37e-662741d7538a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | f7dafc8d-a89e-5413-b156-695121c19b3d |  | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
label | 51776416-837c-5e3c-92c0-81751a00c3f6 |  | note | Records - Emails/NTE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Sub Grade Construction
checkpoint-status |  |  | checkpoint | 3.1 - Sub Grade Strength
label | ae64bb17-e97d-5506-9b11-2f58eaee14a1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | cc7399ba-26fe-56b8-a4ef-994e4ca4abf6 |  | note | Detail - Determine Bearing strength of Sub Grade
label | a351a4a3-1fda-52b5-a489-f4a0fd20e655 |  | note | Frequency - After Dig out, every 5m
label | da115f0f-fa99-52b2-910c-408e78f5c754 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 7898c6e9-a567-5a75-baff-fba901c57fc5 |  | note | Conformance Criteria - Min. 2 blows /100mm
label | 68b7e438-a634-5b5c-abd6-638ded287e59 |  | note | ○ 2 blows = 4 CBR
label | 27a2b633-bcae-5404-bb27-86ff5c7600ce |  | note | Records - QA measurement Sheet, CS-4000 1m Scala
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Proof Roll of subgrade
label | b8946c21-8e0f-57ff-8b66-049307f9ef4f |  | note | ACTION (Hold, Monitor, Witness) - H
label | e5a44703-1ef6-5e00-bb0a-6ac84c81f4a4 |  | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | ca054a18-e63b-54ca-b637-4de0b2b8765c |  | note | Frequency - Prior to Sub Base Construction
label | ad86e5c6-fab0-59ab-a466-93da00a6aeac |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d88e0662-448a-57b7-a3c3-d25958f5a551 |  | note | Conformance Criteria - Engineers Acceptance
label | d5783548-4fd3-5b62-9958-3ec294c8cd87 |  | note | Records - Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Sub Base Construction
checkpoint-status |  |  | checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
label | 90a61496-bb5d-5408-8fff-882fc7731f67 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 02a946bb-66a3-546d-b95a-4746ffa5ce7e |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | d83812b1-5250-5635-b968-b73a5b22b190 |  | note | Frequency - During construction
label | 7aeb445e-3f00-5999-8968-399aec327010 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | 5e7eb728-afdb-539e-b59e-b76394498146 |  | note | Conformance Criteria - Comply with TNZ M/3 Specification.
label | 26ab1f2d-ffa7-5968-9b3c-a8a9c3995f83 |  | note | ○ NZTA B/2 Specification
label | 54836ac7-06f3-5157-9abb-3f7627977f71 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 4.2 - Sub Base Material Contamination Checks
label | bb08d263-81f2-5548-9161-fa2e6c82e9ed |  | note | ACTION (Hold, Monitor, Witness) - M
label | fad86ded-c37e-5764-9c17-877f72d7c361 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | d9f8382a-af29-5f95-b49b-ed792fd77995 |  | note | Frequency - During construction
label | 165c3b73-5b09-5250-83c2-752bc08110e6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | f1652b3e-e7f0-5098-b957-98417ef27f82 |  | note | Conformance Criteria -
label | 50eec905-5274-50f9-8c16-6e1014ac2412 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 4.3 - Sub Base Trimmed Level Checks
label | 05a03da3-4468-50ea-9058-85092c9b892b |  | note | ACTION (Hold, Monitor, Witness) - M
label | 64acba90-39ec-5ec7-89c7-96cea54bf112 |  | note | Detail - Carry out a Level Check on the trimmed Sub base
label | 72aac000-e52a-5329-97e4-96f71d84bff7 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 86f9dd8a-9f23-5cae-ad8d-70c5e22b7973 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 0725ca40-7792-52fc-af1b-c11a6e146afe |  | note | Conformance Criteria - TNZ B/2
label | fe9c2327-8ad1-5fc0-9ce1-fd447a3f8c3a |  | note | ○ Tolerance = -25mm/+5mm
label | 6914bc45-8ab6-5b59-b08e-861cf1540a89 |  | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
checkpoint-status |  |  | checkpoint | 4.4 - Sub Base Compaction Lower
label | 9f376486-aacf-584d-a65b-025ee3d382a6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6dbb00e2-e26f-5d32-9e48-8138b0855984 |  | note | Detail - Degree of Compaction.
label | e19580b3-71d5-5b1a-9640-ab3b0ee2864f |  | note | ○ The subbase shall be constructed in two layers.
label | 067055a3-8a5d-54bd-8d1b-daaf2c051bbd |  | note | ○ Lower subbase results must be approved before construction of upper layer.
label | 6cbc8cf1-67d0-5a57-93b9-0e85774b836c |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | b9911019-0976-5c3e-884c-7eb3bd659ae4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | dcd1e9cd-e4e4-5714-b7cc-68e879489eac |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | 910139be-b2b4-5b17-ac06-956749fe91dd |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Sub Base Compaction Upper
label | 698c8699-81a1-55f5-82d8-95567c907031 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 50a54336-831f-5867-9752-2faade92565c |  | note | Detail - Degree of Compaction.
label | 0eee789c-4be8-55e6-8b06-537c1367a6f5 |  | note | ○ The subbase shall be constructed in two layers.
label | a27921f1-caeb-563c-a303-343ca7c24b87 |  | note | ○ Upper subbase results must be approved before construction of basecourse.
label | a4358bd3-a241-56ad-a2f6-7ccc7641e744 |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | 432e36fe-def3-5e02-b8d3-17e838591c57 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 8e67e332-e320-5880-9346-876b04a9f5b3 |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | 5fbb47ca-306c-529d-8ea0-b936ed89fcdf |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5. Base Course Construction
checkpoint-status |  |  | checkpoint | 5.1 - Base Course Aggregate Delivery Checks
label | 0e655c31-5121-59a4-9ad8-ab8d33bad0b5 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 0efe8526-ca6d-5232-9388-2769f1d8a0c3 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 92a11ca4-adc6-597e-8684-47a9b485c8e4 |  | note | Frequency - During construction
label | 0611c7f9-c68a-52b3-8091-98b5c7edf8d1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | 4063ac84-5e5a-5ecd-8ef9-8e8791b13f62 |  | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | 14350f2a-c720-5f6c-9d5a-d784641fe57e |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 5.2 - Base Course Material Contamination Checks
label | 646c831a-ebaa-5764-8452-0531550227ef |  | note | ACTION (Hold, Monitor, Witness) - M
label | 03057e0c-35a6-5eb6-a374-1ef8fd237751 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 9575eb34-3e23-535b-9cc1-06f7acbb58ad |  | note | Frequency - During construction
label | cb588cbc-5c2c-5c62-84f6-1e609b0ef0e3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | fb2c983b-cdaa-5713-8d9e-a9783647cef8 |  | note | Conformance Criteria -
label | 0849127a-5d25-5273-abda-b01fa3e1b165 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 5.3 - Base Course Trimmed Level Checks
label | 0ea7d093-7aa3-5ee6-a394-085f362883b2 |  | note | ACTION (Hold, Monitor, Witness) - M
label | dd53081e-7111-5338-829a-04f1fbbf9b34 |  | note | Detail - Carry out a Level Check on the trimmed Basecourse
label | 69b5cc46-cdde-5c5b-b1e9-5d885d5d2f59 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | dee576d0-61fb-542a-9287-4f8ffec5c634 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 27107afd-68d8-5606-97b6-d27b3c127408 |  | note | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
label | 2c4c703b-7aac-5183-97d9-03aa4acaeeee |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
checkpoint-status |  |  | checkpoint | 5.4 - Base Course Compaction
label | 9cc77dd4-2d79-543f-a0f7-cb53f9158c4d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1bf4d2b7-d308-5fa2-8659-a6d3182da809 |  | note | Detail - Degree of Compaction
label | d1ddf990-4365-5740-9066-a50160d0a047 |  | note | Frequency - 5 per Lot
label | 14a2bcaf-022f-53da-b97a-b3f1532626a3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | 32fea6b3-8a4d-54f2-ae30-1da69957f536 |  | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | 59aba317-3e2f-545d-8239-f2e8e36dc133 |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Base Course Surface shape check
label | 4fa7dd78-583b-5e96-8b47-78377ef45724 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0a95c74d-92ab-5fea-afd1-82f3c91f003b |  | note | Detail - Surface shape check
label | a1d5ab5d-0506-5bb3-af25-d5abc6548db5 |  | note | Frequency - Prior to sealing
label | 0ea633e9-0b81-555d-aa0a-b53ea929e7cc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 9ff8d790-2783-5d38-812a-657cd28c169e |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | 163d5a1a-3908-55d2-afd3-86cf85a52d4f |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Base Course Surface finish check
label | ff9cd5ee-eff3-564a-aeb6-7500757b6981 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d6bc956d-c1ee-50d7-8e03-f286b32fc7b8 |  | note | Detail - Surface finish check
label | e8924a93-4ae0-51eb-98fd-86a5b683f095 |  | note | Frequency - Prior to sealing
label | f9baefac-7955-56ed-a83d-9d8f27fe2040 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | 8a2c9c49-661e-50de-a385-6c97fdbd6be5 |  | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | b095856c-23e0-57ab-9870-0d89374998b7 |  | note | Records - Site photos, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6. Sealing
checkpoint-status |  |  | checkpoint | 6.1 - Location/Size Confirmation
label | c399061b-2739-525a-9154-ed0adb2802fc |  | note | ACTION (Hold, Monitor, Witness) - W
label | 18f05878-56aa-5ff3-8bf6-af9d43a29a41 |  | note | Detail - Mark up extent of Chipseal
label | 7f4ee690-8323-5e62-80b7-d014e9c7d21e |  | note | Frequency - Prior to Sealing
label | 13abd30c-5421-5926-935c-f9369708816a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | 3f1fe611-0081-536d-9d1a-ab13935d173c |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 6.2 - Surface Cleanliness
label | c7e6eb72-009a-5b1a-9441-e5b50e0841a6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 32487b15-225f-5de7-8e8f-ca1bbe87f9e9 |  | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | 20e1c398-29a1-5b67-87a0-52a437fa1207 |  | note | Frequency - Prior to application of binder
label | ad033c84-bd93-532d-bd1f-85462f63dff8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 4c3aa560-6110-59a2-9f26-d05dc954c43c |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 6.3 - Binder Application
label | ba5de36b-c8b0-527a-ab9e-77f5fbe848a3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d4a15de7-53d4-5f9d-8c9a-bfda00411c3b |  | note | Detail - Ensure the Binder application is according to the seal design
label | 92867935-84aa-5dec-8092-7af1c0231117 |  | note | Frequency - During sealing
label | ddb8af94-5f39-53ca-a413-c29d73a77963 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | af9398ae-369d-5d37-82f9-aa685db9b5cd |  | note | Conformance Criteria - According to seal design
label | 74498145-30e2-5af1-9d47-d94ba22e7ce6 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 6.4 - Chip Application
label | e389d6bb-6f45-5ab1-b10f-9b74eb95b389 |  | note | ACTION (Hold, Monitor, Witness) - W
label | df676853-d375-5069-adc0-9aab01f082b0 |  | note | Detail - Ensure the Chip application is according to the seal design
label | 2db41e56-7a32-5923-8c49-3aaaa776beb7 |  | note | Frequency - During sealing
label | ab130ae3-bf29-5f20-9f70-bb2b99a6fd76 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | a7a06eb8-8d26-5f77-b001-5c5e7d2e5d9b |  | note | Conformance Criteria - According to seal design
label | d538e32e-104d-542a-a853-230a96f89d5f |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 6.5 - Compaction
label | a73973bc-15af-5c94-ac57-baa4806f9a40 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 16f961dd-135e-5d2a-bbc6-900d6fc52ddc |  | note | Detail - At completion of rolling
label | 9d8dcae7-0637-5dbd-aa49-767aa03bcaec |  | note | Frequency - During sealing
label | d12c285e-8a28-53cd-a1be-23211a9a8c65 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 2ea7a3bb-bdd2-5d62-8baa-764574daa9e4 |  | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 202ab1f6-88ef-58ed-9f12-1405b5d316f3 |  | note | Records - Photos, QA measurement Sheet
checkpoint-status |  |  | checkpoint | 6.6 - Removal of excess chip
label | 4baef4f6-2e6e-5846-9e5c-22e9572c410c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 8923bc8a-a675-57e9-b94d-0a78da9be64f |  | note | Detail - Removal of excess chip
label | 09e9dcba-cab0-55cd-80d3-f9ab06d72fba |  | note | Frequency - Within 48 Hours of Sealing
label | 1e3803da-43b7-5763-8e70-313c74d5f3e6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | ecacffd0-9af1-5265-aa01-a859daac1df4 |  | note | Conformance Criteria - Ensure all excess chip removed from site.
label | 9e25d188-06dc-5bcc-9f7a-f6b841c8399b |  | note | ○ No chip windrows left on site in Shoulders.
label | fbdef7e5-ba58-536d-8af9-01c239eb3d7a |  | note | Records - Photos, Site logs
checkpoint-status |  |  | checkpoint | 6.7 - Surface finish check
label | b0496b9c-76d6-5210-8d12-915ee13d3f10 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 35208f78-017b-52f6-959f-832f45df06dc |  | note | Detail - Surface finish check
label | 4a0cc324-9233-57bf-a277-3fdf34638cda |  | note | Frequency - After sealing
label | 3bea6c29-258e-566e-82c1-9cbc1900c868 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 94127224-b7d4-52cd-8081-af9e0a751039 |  | note | Conformance Criteria - Engineers Acceptance
label | 80d571f0-ecd3-5460-aacb-ac07c61dfcc7 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7. Road Marking
checkpoint-status |  |  | checkpoint | 7.1 - Road Marking
label | 14835991-4d51-5cd5-983f-5ce9a0abe4d7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2ce389ee-838f-5d0e-81bd-3dd906952987 |  | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | 62c6603e-32bd-51a4-a1f6-78d8d0859f0b |  | note | Frequency - Prior to the final line marking
label | 06b45db0-725d-5912-bbc5-4b00e54980e7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | aa0b4278-0aeb-56b6-83ce-13f52ea9496e |  | note | Conformance Criteria - Engineers Acceptance
label | 151ac3d7-05ee-5089-af42-baac5fcabc40 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 8. Hydroseeding
checkpoint-status |  |  | checkpoint | 8.1 - Hydroseeding
label | 5bd91a3e-afc5-55ed-a12b-0e6685153b02 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 05661e4e-e6a3-5c9b-a97d-6225b8578a34 |  | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | d6ba0565-ef35-5377-818d-265bd88824bb |  | note | Frequency - At the completion of the Lot of work
label | 885746cf-5489-5756-86ba-bbffc9a52886 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 78a1ca4d-1450-5092-9304-2d5c8c9c2586 |  | note | Conformance Criteria - Engineers Acceptance
label | fac8b7a1-91a5-5b08-8d96-124fdc400221 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 9. Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 9.1 - Final Walkover (Snags)
label | 19f6be86-a5df-55d5-8d44-45379cb22fa2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4459d765-aa11-5154-9b2a-ce8c8b37e36e |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | f80a2e4c-2146-51c4-90c7-069bccabf285 |  | note | Frequency - At the completion of the Lot of work
label | 55081097-a8e2-5643-9257-66ae49121a0d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | e16298eb-558d-58ac-99c5-5aa33e9987e8 |  | note | Conformance Criteria - Completed report
label | 2d47c780-4fd5-592d-ad75-b29f07898122 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.2 - Survey As-builts
label | 0479ea7c-c60d-5ca1-aa71-b98bcb83f6ff |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7a5e63e2-34e9-5f2d-b779-6dbec2cff15f |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | bed34a48-c741-5dea-be95-5caa7ba7c19a |  | note | ○ A survey as-built of completed work must be provided
label | b008360a-1c88-51ad-b6aa-75493199ebce |  | note | Frequency - At the completion of the CWP of work
label | 025066a4-a42a-5dbb-a615-bd560df255d1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 154040db-ee46-580d-8578-7e417c84c30b |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded.
label | 0e0b2de3-628b-50d6-8a65-6de45aa86556 |  | note | ○ Signed and dated
label | d3ea43a5-2412-5ddf-aa49-f2bf843227f1 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.3 - Quality Assurance Deliverables
label | 5c053464-d4e4-5d01-ae42-eb8067d66dfe |  | note | ACTION (Hold, Monitor, Witness) - W
label | f8c5ce4e-42a2-524b-963d-a21ff1ad31d9 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | f570f929-5577-5146-b86d-3d0735c05d26 |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | 9ada14f6-7ee5-5a89-95c9-6bc5ffc8accb |  | note | Frequency - At the completion of the CWP
label | 24ab9273-ec73-594f-a256-90210192c868 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 0a719fa8-fc36-5ee7-9c7b-d4fb8fc96860 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 5ca0768e-978a-5e2c-9eae-c81080a75bad |  | note | Records - As-builts, NCR's and RFI's
checklist-sectioned |  |  | checklist | ITP - E3001 - SH05 SIP Generic - Pavement Construction incl Culvert Extn | itp |  |  |  | Yes | ITP - E3001 - SH05 SIP Generic - Pavement Construction incl Culvert Extn | e9b02e05-4a8b-4ec3-8f68-9fc7efbfc9ce
checkpoint-group |  |  | section | 1. Setout & Saw Cutting
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 9ce1f35e-76a7-5b3c-aa9a-fc1df0c0f5d6 |  | textbox | CPS Eng.
text | 2c8a9808-6c01-57c1-86e2-47990d510f5f |  | textbox | Site Engineer
text | bf9f9142-454e-5d51-b1e7-820f48a4f833 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Survey Setout
label | 7ae96138-2bde-5db0-98e9-86903f764f7e |  | note | ACTION (Hold, Monitor, Witness) - M
label | 3149dec2-142e-5574-9558-ebd0d2054dfc |  | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | 0929aa0b-4ffa-501d-876f-ebfa101dbce9 |  | note | Frequency - Prior to commencement
label | 54b47c6f-6bdb-5122-8b07-1cbafe785304 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 273d53ec-98b5-5fcd-bac1-58b80ab1ba08 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 1.2 - Saw cutting
label | 1a3e5c4a-15c8-53cb-9e41-8933c41c25a1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 018fdcee-a87f-5b3f-9834-2c40339f1918 |  | note | Detail - Proposed Sawcut line to be inspected by the engineer
label | dbc2cf99-fecd-5a12-8958-503e3394de6f |  | note | Frequency - During construction
label | 463bdaa6-f8e7-5263-894b-c40166c6d949 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 558e0bbf-7f12-510a-a6cb-d95cabb7127f |  | note | Conformance Criteria - Project Specification 6.6
label | c97ac814-ee34-55c2-8d0a-04ec024669f8 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2. Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Sub Base Material Compliance
label | 7ac2b99f-54f4-5d43-8f20-118c413297b0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5a0ce795-39d5-588e-b14b-66cb3284d482 |  | note | Detail - Aggregate material compliance for Sub Base stockpiles
label | 00a8935a-729a-5bab-9d82-a2e4439c4457 |  | note | Frequency - Prior to commencement
label | e65cac31-644a-51fb-94b3-f9d2b39a24bf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 7c08b8da-d6be-57a0-b52a-0aae34ee3178 |  | note | Conformance Criteria - Comply with TNZ M/3 Specification.
label | 2ade152a-4211-5591-bdc4-e2203e08a656 |  | note | ○ NZTA B/2 Specification Lab test for MDD at OWC.
label | 1443824a-5374-5d59-b9ab-cb8178316a5d |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Base Course Material Compliance
label | 6c5c5a07-4d3f-5547-bfd9-6ce0fbaa7897 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5ddf5f74-7c1f-5e71-a926-80b877f370b2 |  | note | Detail - Aggregate material compliance for Base Course stockpiles
label | 3b560496-63bc-5fbe-bdf9-040cba51c859 |  | note | Frequency - Prior to commencement
label | 47dd98e9-3514-5dc5-8995-47f58f792b24 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | a0671090-cede-55d6-89b1-816d9dcbe83a |  | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
label | 0acd8990-8b54-5a75-9b93-f1a2ec1c84db |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Base Course Mat Sample Testing
label | 2fbc43ab-1bb9-5883-a701-83325110de10 |  | note | ACTION (Hold, Monitor, Witness) - H
label | bef1127a-c8a4-5ddc-a0d5-f1d0d327e68a |  | note | Detail - Mat sampling of Basecourse Material
label | 4c731d45-cb3a-52d2-b51f-6b07e8723cd4 |  | note | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
label | d6de8b2c-bea9-5edb-9d2c-cecb7ff2e5b7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab testing
label | daea67b6-d86c-5aab-ab18-923513e05a5e |  | note | Conformance Criteria - Grading to comply with specification
label | f7439385-b22b-578f-a741-4fc74921e776 |  | note | Records - Mat sample lab test result
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Concrete Pipes
label | 87314527-dbd1-509d-915e-9b569e7cb185 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e7a27303-17ca-53d1-81e9-6290b952a968 |  | note | Detail - Specification Compliance
label | 20687415-62aa-5be4-aa46-665cb1131b4b |  | note | Frequency - Each delivery to site
label | e6e586fb-d9a3-5822-a73c-ff33cf38f5b4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
label | fd3bcc6d-0db6-5678-9970-dd5943bc7e61 |  | note | Conformance Criteria - All concrete pipes shall comply with the requirements of NZS 3107 "Precast Concrete Drainage and Pressure Pipes".
label | 76c1a483-b959-5144-b95b-5af03d72e2bc |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 2.5 - Pipe Bedding Material Compliance
label | 4d8f8f37-8fab-59f1-8b9f-f618ec0f9f2b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 440b398b-5de6-5a4d-bce8-de50a5cf67ed |  | note | Detail - Material to meet specifications dependant on material type selected
label | ba3e5641-445e-5ea5-adca-92b125824f7b |  | note | Frequency - Each material used
label | 8a2bbef4-da7a-563d-8aa2-f1180cbbcd5a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 48af8dff-b831-5610-a47d-d2a363082cfd |  | note | Conformance Criteria - Compliance with requirements from Specifications
label | f0c2eaff-b884-5e78-8844-c56c7b27731d |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Pipe Backfill Compliance
label | 762d2c41-f39b-5c7e-8496-2071e341d1c9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4961cd62-56ef-5a6f-8fa1-93d94c1c7276 |  | note | Detail - Material to meet specifications dependant on material type selected
label | 659e0b65-f1b8-56b1-95a7-18d7f885022a |  | note | Frequency - Each material used
label | 4722293d-6139-5345-8313-6eb4f3090d9e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | a932c686-c766-5ab7-a363-80889c364842 |  | note | Conformance Criteria - Comply with grading specification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Chip Seal design
label | cfe837e3-5f4d-5555-bc8b-ce44ac847e57 |  | note | ACTION (Hold, Monitor, Witness) - H
label | abc3a8d4-b7b2-54db-a8c0-6af326661e9f |  | note | Detail - Seal design to be reviewed prior to sealing.
label | 63ffc584-6c48-5010-813b-47091e3e5932 |  | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
label | ea27dac5-e63e-5da0-9853-58263ea709d7 |  | note | Frequency - Prior to Sealing
label | 703382c7-24f9-5f6e-84eb-89ffd5486cd3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 8df544c3-a3e8-556e-aef6-7053cd09631f |  | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
label | d24acce0-8bf9-5b66-a9ff-e5a0d15b6ee4 |  | note | Records - Emails/NTE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Sub Grade Construction
checkpoint-status |  |  | checkpoint | 3.1 - Sub Grade Strength
label | a863b3d0-161b-5434-a9fc-31038b113ab1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b4cd07f6-b8d8-5a27-9503-27af5853c622 |  | note | Detail - Determine Bearing strength of Sub Grade
label | 816cbf19-00c0-50f1-98e4-8f9577685ee9 |  | note | Frequency - After Dig out, every 5m
label | a252a2d1-a13c-5e97-869e-592547972c9c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | fbbb8b09-b4bd-56f3-8f34-727633cc0695 |  | note | Conformance Criteria - Min. 2 blows /100mm, 2 blows = 4 CBR
label | fea47037-19a5-56da-aef8-049ca4f77f34 |  | note | Records - QA measurement Sheet, CS-4000 1m Scala
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Proof Roll of subgrade
label | cebf5dc1-3f52-51a3-9cb9-c691bd285146 |  | note | ACTION (Hold, Monitor, Witness) - H
label | fdf3506f-1119-5453-9b12-41d3444b941f |  | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | e0724539-3029-564b-82dc-183caf047a3c |  | note | Frequency - Prior to Sub Base Construction
label | 255594cf-14be-55d6-8f31-d6eed92106a2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | efa8800f-47ac-5e7a-bc55-6476280e937f |  | note | Conformance Criteria - Engineers Acceptance
label | 7f785f2a-9e27-5740-a8ae-bf3a40d457d8 |  | note | Records - Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Sub Base Construction
checkpoint-status |  |  | checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
label | b4364af1-0076-5bb9-8477-e6cdf8367d53 |  | note | ACTION (Hold, Monitor, Witness) - M
label | d2b2edcf-94cb-50c8-8c67-a7a4ae0d5f3e |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 2e29359d-1e74-5b60-8e22-4409361d4ed0 |  | note | Frequency - During construction
label | b57e3707-d9bb-5004-aa66-6acb13586e20 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | f9a0b613-4da9-5a93-a402-ed6b8c89465a |  | note | Conformance Criteria - Comply with TNZ M/3 Specification.
label | 34ce98f0-d165-53a4-8445-034f5ba6b130 |  | note | ○ NZTA B/2 Specification.
label | ec3e09a5-3df4-5d67-98e4-00565e19cb38 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 4.2 - Sub Base Material Contamination Checks
label | 2b3ef890-d249-5a26-b5b9-41020ebb90cf |  | note | ACTION (Hold, Monitor, Witness) - M
label | 20b90db6-b628-5075-827c-a533b08b7771 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 810beec6-525f-5cc2-bce2-e7c2cd34ab43 |  | note | Frequency - During construction
label | c7ebec40-40c6-5f43-baa1-13dfcd43eab0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 9f99e5d3-06ea-501a-a300-c60229241bfb |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 4.3 - Sub Base Trimmed Level Checks
label | 55298ce3-3d8a-5ea8-8f30-c70907cbccf2 |  | note | ACTION (Hold, Monitor, Witness) - M
label | fb1f9f6d-5f7e-5b7b-a14e-158ffa13d2b2 |  | note | Detail - Carry out a Level Check on the trimmed Sub base
label | a8b3b83e-422f-5111-855d-1fd9ad5d693e |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 1b9de626-57ab-52df-818f-6ea43bd55f4a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 61f12aaa-4659-5ce0-b3ff-15876d44a660 |  | note | Conformance Criteria - TNZ B/2
label | 765304c5-b343-5c54-aff0-b61374f1a180 |  | note | ○ Tolerance = -25mm/+5mm
label | 043cbbe0-a382-5be3-8e0a-709c40708100 |  | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
checkpoint-status |  |  | checkpoint | 4.4 - Sub Base Compaction Lower
label | 9240d5e8-058d-58df-8e41-56d5753b414f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 51a429e5-812a-5dc9-a09d-d20a069a127d |  | note | Detail - Degree of Compaction.
label | 7cfd3ac8-b279-5735-a571-ea3573829e8a |  | note | ○ The subbase shall be constructed in two layers.
label | 863ff24f-da28-50f4-9e42-0b59864fe73a |  | note | ○ Lower subbase results must be approved before construction of upper layer.
label | 1b38f1d9-01b0-559e-ae65-04ae3937b5f6 |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | a61430f9-7862-5868-a6b4-6b89bc0a6562 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 5dac9e67-70dc-51a4-b36c-53e8241c6bf9 |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | 869295c9-93d4-5b81-bf01-7ad2ab2d73fd |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Sub Base Compaction Upper
label | dfb65156-7da8-580a-a0fb-3212d845895c |  | note | ACTION (Hold, Monitor, Witness) - H
label | e4f42a23-2779-5483-9492-bfbcbb01fa7a |  | note | Detail - Degree of Compaction.
label | d826c4b7-02b7-55c0-94ba-d8512d70ab9b |  | note | ○ The subbase shall be constructed in two layers.
label | 00d72ab9-d80a-547a-b9dc-512d21118e60 |  | note | ○ Upper subbase results must be approved before construction of basecourse.
label | c67894f7-3671-575e-a5ce-98b94fbb1fda |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | c4895cfe-eb9c-5810-93da-003197349279 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | a02d2c91-e8c3-5de5-951c-49ebd7c43a22 |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | 77891d4c-2c21-5992-b3ea-ae84aa78446b |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5. Base Course Construction
checkpoint-status |  |  | checkpoint | 5.1 - Base Course Aggregate Delivery Checks
label | d4c78109-34a3-5b73-a7b2-0f93f34fa78c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 0a112c96-a607-571a-9497-06d4fca3dc5d |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 29efe8de-6493-5c47-af74-3a8ff5baa834 |  | note | Frequency - During construction
label | 8cb6be14-829f-5f4a-8865-e64a7dd1abae |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | 61afba88-1b1a-5769-bc3d-cf099b62c59c |  | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | 477f6cb3-84a6-511f-87c8-5cae4ba2bd5f |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 5.2 - Base Course Material Contamination Checks
label | b03b4fd4-693e-5d31-98d1-5c4a5e0d65ba |  | note | ACTION (Hold, Monitor, Witness) - M
label | 61da3a9b-7e56-5b37-ab77-38256c0a1518 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 625932cd-2942-541e-988c-d4a36709f87e |  | note | Frequency - During construction
label | c787a0d5-993a-5165-8d18-5096bf99c2ff |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3dc89d11-e3ee-5097-9c73-037e4e9d7e9d |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 5.3 - Base Course Trimmed Level Checks
label | cd2584b1-504c-582a-8b34-5352fc333c63 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 41abc580-20c0-5c1a-adec-e7b5b3c7b51b |  | note | Detail - Carry out a Level Check on the trimmed Basecourse
label | d71a8625-551b-5ec6-821c-d8b909c7b0d7 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | d8668638-7d69-5437-b232-9369941442a0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 99149bf0-b529-5ce4-bfad-46626380f421 |  | note | Conformance Criteria - Tolerance = -5mm/+15mm
label | 4c685373-b6ac-585d-88cf-b4d01b51633c |  | note | ○ if constrained (kerb) Tolerance = -5mm/+5mm
label | 504ccab6-21c5-520b-99c6-313e4450b5db |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
checkpoint-status |  |  | checkpoint | 5.4 - Base Course Compaction
label | 8c4b8e61-9c58-5142-833d-2a383d998e77 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f46a1184-0d38-5fb4-8a93-0efc79b6be71 |  | note | Detail - Degree of Compaction
label | e4c6919f-5621-5e43-94bf-ae5cc8a8292e |  | note | Frequency - 5 per Lot
label | 1aae71af-5d32-5633-a6fb-f240cad7e9e7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | 831df6a8-3210-59d0-b483-ac0eeb3edb6a |  | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | e01e0f79-7dee-5736-b2c4-436777b91786 |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Base Course Surface shape check
label | 91c53700-df46-5077-9683-57750b487068 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a99319c9-723a-5920-a501-2cb5365f7f69 |  | note | Detail - Surface shape check
label | 62716a5f-12f8-5a62-ba65-331ae54d086a |  | note | Frequency - Prior to sealing
label | 60097ab6-6f2f-5d79-b89b-e1cc8ca71e01 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 9ca60351-2997-5d5c-adbb-7b0783edb75b |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | 1564206e-39f9-59ae-b3c5-8d1625f84755 |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Base Course Surface finish check
label | ab0793cf-9c5a-59ef-8a69-69e91a182787 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f43da890-92bd-5018-b4b2-9725a7a281c5 |  | note | Detail - Surface finish check
label | 1422edc3-96af-56ea-9512-0d5c8fc9a48e |  | note | Frequency - Prior to sealing
label | 60d94cde-8839-510c-8b4d-0bc40f734006 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | f28573d7-41bb-5f80-8f8d-3e09c026b1bd |  | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | 263f1acb-a5ba-5056-b144-1c0c9e690eb4 |  | note | Records - Site photos, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6. Extension of Culvert
checkpoint-status |  |  | checkpoint | 6.1 - Foundation Compliance
label | 1b3f5216-3428-5662-a510-32239bb67f92 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7c0714ff-1227-52e7-909f-a859b10653fa |  | note | Detail - Test formation level on completion of excavation to check if undercut required
label | ab13df29-0a3f-5316-8897-29d3be2ce1c2 |  | note | Frequency - One test per 5 linear metres
label | 02d56bea-8350-5799-85e4-a21032538c78 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | 372212f1-c350-5835-8a32-9f70fe99bf27 |  | note | Conformance Criteria - Min. 2 blows /100mm
label | 9d285fca-d44b-5568-b6f7-3871de00b547 |  | note | ○ 2 blows = 4 CBR
label | 0108a17d-ea92-573b-a725-d676d4f5fc03 |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - Levels Compliance
label | 45c3e8f7-d899-557e-bf10-23ca4f5b2a88 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 27778dfe-fef7-54a1-bf7d-9b4b060e32e7 |  | note | Detail - Test formation level on completion of excavation to check if undercut required
label | 642edcad-c648-516a-8f3d-1fd6f39a0774 |  | note | Frequency - As stated
label | 54890746-774a-55bd-a528-fc578379fb9e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | a8cd8454-22c4-5813-8137-461ee98cbe11 |  | note | Conformance Criteria - Designer to inspect formation level at outfalls / inlets.
label | 33e9021e-8b77-53d0-a689-720143bf11c9 |  | note | Records - Photos, Visual
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7. Sealing
checkpoint-status |  |  | checkpoint | 7.1 - Location/Size Confirmation
label | 0b3abbbe-61c2-5deb-9410-3239b458ce3d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 889a6e99-7292-5a03-baf8-c4e8205232f6 |  | note | Detail - Mark up extent of Chipseal
label | 5a1b5bf3-736e-5c18-9ad5-3605efb07b40 |  | note | Frequency - Prior to Sealing
label | 1d228bfa-7520-50ee-84b3-ad5b6920b822 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | dd2b1ee3-9645-5503-ba98-4ecd17714dec |  | note | Conformance Criteria -
label | 250138ae-4472-576e-a097-d1b669b7d464 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 7.2 - Surface Cleanliness
label | 6fd44084-ca2a-50ea-9ae8-c9cde660bdbe |  | note | ACTION (Hold, Monitor, Witness) - W
label | 69367b26-3272-5c25-bf9e-769822ac1959 |  | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | 8f7916b6-4a2b-5b48-9f1d-4eb492dddae5 |  | note | Frequency - Prior to application of binder
label | 3e339253-537e-5a8e-9141-9e157f02cbf6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 24a023a8-5f74-51e4-b2ae-88574f27b0b3 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 7.3 - Binder Application
label | 890ca594-f9ea-5616-9a25-deb604ea5e43 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b2687fbf-ad33-582a-a613-fe32e21798a8 |  | note | Detail - Ensure the Binder application is according to the seal design
label | 4c0a9797-43bc-5994-9bd0-8d6681f094ea |  | note | Frequency - During sealing
label | e17d31ef-dd19-5c75-b7ab-e012ce07694a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 1b2d9547-3a45-55e4-a46a-efab039af768 |  | note | Conformance Criteria - According to seal design
label | af43d413-bd2a-5f0b-8aed-36c37b5ecb63 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 7.4 - Chip Application
label | 5a2ebc7e-1fed-54bd-bad5-b81208e4dcd0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a2bf96b2-7f02-502b-b82a-3ae3e5d71c40 |  | note | Detail - Ensure the Chip application is according to the seal design
label | f6dc59dd-348d-5862-a9c6-c62ab75d65fc |  | note | Frequency - During sealing
label | c5252c26-5cec-5141-989f-ba419b8595b8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | d45e4c50-cdf1-5b89-96a3-b6b7248ae5d3 |  | note | Conformance Criteria - According to seal design
label | a6f825e1-6cf7-5663-99aa-83477e0391b5 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 7.5 - Compaction
label | 9dd05e4f-ad2a-5794-8771-32f5c9470d84 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 18832216-c261-5271-acae-a4227d7532bf |  | note | Detail - At completion of rolling
label | efc81bde-e9c9-5c64-91ef-42638232d46f |  | note | Frequency - During sealing
label | d799f111-d74a-5f7c-afa4-766ddc20dbe3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | ea6650da-5d6d-5b40-9076-ca20c98f12a8 |  | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | d7b24350-f433-57bd-b97d-3d0a6b613567 |  | note | Records - Photos, QA measurement Sheet
checkpoint-status |  |  | checkpoint | 7.6 - Removal of excess chip
label | 13005bc4-804c-53ed-a1ed-6d289fcb2224 |  | note | ACTION (Hold, Monitor, Witness) - M
label | dbeb6b00-35dd-57de-9141-992ec1033593 |  | note | Detail - Removal of excess chip
label | e78207ec-60be-503a-9d27-a995f5670a67 |  | note | Frequency - Within 48 Hours of Sealing
label | 007dcf16-629b-5d68-a13c-8115d1b7f4a9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | fcbd0f76-3a5b-59a3-81ba-9f0c2eddc9d2 |  | note | Conformance Criteria - Ensure all excess chip removed from site.
label | 79473162-10d4-5de4-8bf8-092d903115ac |  | note | ○ No chip windrows left on site in Shoulders.
label | a10b2fc2-4cd8-5028-bfa9-9f92062505a8 |  | note | Records - Photos, Site logs
checkpoint-status |  |  | checkpoint | 7.7 - Surface finish check
label | 0d8add72-8214-51b9-8944-3dec0f2c3b7c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1c0d802e-8633-5fa7-9eae-53fa77d937bc |  | note | Detail - Surface finish check
label | a1ea5924-f7e8-5499-b586-d65f631962ca |  | note | Frequency - After sealing
label | d186cc22-6f94-5ebc-a7af-596c3449e0b9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 8e8b4d46-3cbd-5014-8cef-ed7d31b1e23a |  | note | Conformance Criteria - Engineers Acceptance
label | 9c77c6a8-de48-509f-912b-6a9cd891bab1 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 8. Road Marking
checkpoint-status |  |  | checkpoint | 8.1 - Road Marking
label | 85189b8a-220c-5649-bb53-5fd852cd7067 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8c1238ba-7c3c-5601-bd79-8b96449fbae3 |  | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | 81f6d7b7-548b-54d8-9d63-97beeafd7084 |  | note | Frequency - Prior to the final line marking
label | bec53a2c-92e1-527d-bcea-a1b089fd9c35 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 97d210df-4dfd-599f-b7f1-1dc4a2956715 |  | note | Conformance Criteria - Engineers Acceptance
label | b5a23775-828d-563f-9151-c9bcf26792ee |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 9. Hydroseeding
checkpoint-status |  |  | checkpoint | 9.1 - Hydroseeding
label | 24d16e96-c7a1-5341-8799-5cbfccd931a3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 283e78f0-a8ee-52d5-85ae-18912a42a915 |  | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | caed83b7-df0b-53a6-a057-4feca423fe0c |  | note | Frequency - At the completion of the Lot of work
label | 6c07c63a-a10a-5004-abdd-5fbed3538814 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | e602bb73-fb78-5635-a4ad-70fe46f3b7c8 |  | note | Conformance Criteria - Engineers Acceptance
label | 5490f4f7-7e5d-5c41-914f-f16aa20e9f89 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10. Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 10.1 - Final Walkover (Snags)
label | 263515ad-4454-5eb1-96fe-65456f96d0d2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8cd81723-329e-5d40-a9e9-96d91a72abdf |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | bf751700-4f4e-57ad-bb13-9f4e7a7afb1f |  | note | Frequency - At the completion of the Lot of work
label | de116035-741d-5f0e-a69c-6bb35db60a51 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | b972551d-4d0b-56a6-968f-4c3533cb629f |  | note | Conformance Criteria - Completed report
label | d10daeaf-8ec9-53d0-905f-ba857372075c |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.2 - Survey As-builts
label | afb36436-7fa4-5891-add7-be4534a7a400 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f2601dbc-319e-517f-9d8e-507835da97d5 |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ce2daadf-4d83-5492-bd71-0a7f0d636ca0 |  | note | ○ A survey as-built of completed work must be provided
label | ccda0400-3db7-5547-8971-f44ac254256c |  | note | Frequency - At the completion of the CWP of work
label | 641eebb3-a697-5ebd-a38d-335e35d45cc8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 4ad4db0d-b4cf-56e6-bbe1-9471fac6e8c3 |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | 6ba3039d-7126-571c-9b67-e9786f11aef8 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.3 - Quality Assurance Deliverables
label | 0de96a70-f838-58e1-b37f-1ac078da2344 |  | note | ACTION (Hold, Monitor, Witness) - W
label | fb6d43f0-a347-5ed6-b420-1582b68833d0 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | cd2a1882-6eaf-58bc-8e3c-27e4554ea43e |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | ec63282f-fe5c-5a90-8b1f-e55d9d935535 |  | note | Frequency - At the completion of the CWP
label | 7d37fd43-f24f-5546-9467-102be1b8d659 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 14632523-b5d6-5b8a-826b-06ad5c17f0e3 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | b08e92bd-15f0-5f78-89f3-911152dbe7d8 |  | note | Records - As-builts, NCR's and RFI's