## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Enviro HP1200 + 700X |  |  |  |  | Yes | Enviro HP1200 + 700X | 052ea11e-75d5-4fd6-a291-e10449f6842b
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 2871326c-edf9-504c-874e-2eb2cbd5bff4 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate. The surface must be clean, dry and free from all loose particles including dust, laitance, grease, coatings, curing compounds and any other foreign matter. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns)
label | b7697ec3-82f4-595d-ab4c-c5328b7de70d |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Substrate Preparation and Caulking. Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris. Remove all sharp edges including screws, nails and concrete/mortar projections. Apply a suitable and approved joint sealant such as Enviro Flex Pro or Enviro Flex FC to all joints and connecting building parts prior to the application of Enviro 700X
label | 14069379-bddb-5d3c-8070-1fb82ded4ee8 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Priming. Apply primer (Enviro Epoxy B-LV / Enviro Prime P2 / Enviro Shield) using a brush or roller. Allow primer to fully cure before proceeding with the application of Enviro 700X
label | fe5e5ae8-003a-5a75-8062-e5121e8487a0 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. HP1200 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Apply Enviro 700X using brush/roller achieving 1.6mm WFT / 1.5mm DFT. (2 coats)
label | 6c4e733b-882a-55d5-ac2d-e555385af2a9 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Curing. Allow product to cure for 12 hours before recoating. Care should be taken when walking over newly installed Enviro 700X to ensure the membrane is not damaged
checkpoint-status |  |  | checkpoint | Top Coat. Enviro 700X should be thoroughly mixed using a mechanical mixer at low speed prior to application.Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application. Allow to react for 15 minutes when thinning with Enviro Thinner No.8 before application. Do not apply in damp or wet conditions. Allow each coat to sufficiently dry before proceeding to the next coat
label | 98598ec0-7e8d-5759-8886-970951d278e5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test
label | 051f686e-60c5-55c4-b6b9-7c93add2f20a |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200+900 |  |  |  |  | Yes | Enviro HP1200+900 | 05f8b844-1547-4be8-9c1c-dde35468f2a0
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 6b5eb2f6-91e9-56bd-8c95-f04273726dd7 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | 2d72828d-4b23-5c5f-84a5-e9b68b2d04ce |  | note | Attach Photo of substrate
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | 8e9d687c-a14c-5b8f-b879-fafcb4a2307b |  | note | Attach Photo.
checkpoint-status |  |  | checkpoint | Moisture Content Test.
label | af42b830-ba35-512e-9d68-44e6c4de09dd |  | note | Attach Photo of moiture reading or enter moisture reading in comment section
checkpoint-status |  |  | checkpoint | Check label on drum to ensure correct material is being used
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 6788bafd-76fc-5d62-a641-dab638f306ff |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | fe700356-abb5-5dab-bf9e-47a63cc9fe51 |  | note | Visual inspection, ensure adequately cured.
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
checkpoint-status |  |  | checkpoint | Mixing. Mix HP 1200. Mixing by way of 1:1 mix ratio (by volume) in heated plural component spray equipment such as Graco E-10 or EXP-2. Both low and high pressure spray equipment can be used for the application of Enviro HP1200.
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun. Achieve 1.5mm DFT.
label | 41ee08d6-d2c8-5740-ae4a-e231a91dec0f |  | note | Attach photo.
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test.
label | 5420e3bf-b4e2-5fbd-a666-02c2127daa3f |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Wear Coat - Mix and Apply Enviro 900 with brush or new roller (spray application optional) Broadcast aggregate uniformly to the wet Enviro 900 within the timeframes specified
label | c966b1f5-1f74-5b19-9e70-f554be09dd6d |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Top Coat Mix and Apply Enviro 850 with brush or new roller (second coat optional pending specification)
label | c172ec2f-90a8-5712-bc4e-e9a81d2ec716 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | DFT Testing
label | e4379f1f-0317-59e7-943e-70d6b9d0bfb5 |  | note | Attach Photo. Enter DFT reading on comment section.
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro Hydrostatic 1 |  |  |  |  | Yes | Enviro Hydrostatic 1 | 05fd2664-3a06-4ffa-a417-0af906a1cdd0
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 65e80158-d78e-5585-8f79-ddca997a9eeb |  | note | Specification / Standard: AS4654.2-2012, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | d6ec6816-0de2-5ad6-b434-6947c190e576 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 79296616-3f2b-5f76-b020-39c7ebbc7f69 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Primer application - Lightly Spray areas to receive Hydrostatic 1
label | f68d6d0f-f97d-54d7-a08d-2e063e83eaa4 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Membrane Application (1st coat) - Mix Enviro Hydrostatic 1 thoroughly using a mechanical mixer. Apply first coat of Enviro Hydrostatic 1 by brush or roller Use Enviro Joint Band in floor-wall junctions and general movement joints
checkpoint-status |  |  | checkpoint | Membrane Application (2nd coat) - Mix Enviro Hydrostatic 1 thoroughly using a mechanical mixer. Apply second coat of Enviro Hydrostatic 1 by brush or roller
checkpoint-status |  |  | checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro CSH |  |  |  |  | Yes | Enviro CSH | 0cf62547-ce4f-41d3-a19d-a8d63675b2e8
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | c65f9847-726a-5279-9b2b-46906dd7d44d |  | note | Specification / Standard: Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate. (moisture test if oncrete not fully cured) and prepare surface using a scraper or grinder and vacuum or sweep residual debris.
checkpoint-status |  |  | checkpoint | Check for cracks/defect in concrete.
label | a8d94ea5-cc06-5af4-a5ec-203123c2afae |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Perform mechanical profiling / shot blasting to concrete
label | 102e6a5f-de6c-58ea-a80f-5fdc0a9c2695 |  | note | Visual
checkpoint-status |  |  | checkpoint | Spray Enviro CSH concrete surface hardener and moisture barrier, first application
label | 89dcda3a-b815-5b14-b2b1-56da91ec88d0 |  | note | Visual
checkpoint-status |  |  | checkpoint | Spray Enviro CSH concrete surface hardener and moisture barrier, second application
label | 4c711032-d173-52f1-821d-5244d21bff66 |  | note | Visual
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
label | d14a4dec-8b3e-5df4-a9e8-61f2f9567ed8 |  | note | Attach Photo.
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro 700X |  |  |  |  | Yes | Enviro 700X | 14eb502d-3f68-4f61-a6ce-55640a8f055f
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 7bdc50ee-b259-5398-bbeb-b677f969059c |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
label | f91010de-c16b-5675-a006-2dfdf4a0de50 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | da701615-12b7-5301-b1ce-0ebb50786c1b |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | a704aba9-1ccf-568a-ac76-49ab7f41d82e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 5e2cddf8-7d7b-5874-b825-32fdccd665b0 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | ec2b20b8-0c05-585a-a7e7-c9baa93de3d1 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Membrane Application (1st coat) - Apply Enviro 700X using a brush or roller
checkpoint-status |  |  | checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint-status |  |  | checkpoint | Membrane Application (2nd coat) - Apply Enviro 700X using a brush or roller
checkpoint-status |  |  | checkpoint | Flood Testing (if required)
label | 45d3dd69-11fa-5c07-944b-800324240702 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro Clad |  |  |  |  | Yes | Enviro Clad | 164a11a9-4781-417c-99ef-775199a17e9a
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | ad681c03-bc9b-5911-bf70-277854e03177 |  | note | Specification / Standard: AS4654.2-2012, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | 528cecf2-8445-5997-bb72-2f0a15f50c7a |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Primer Application - Pending Substrate Condition, Apply Enviro Prime WB using a brush or roller
label | 734dbe5d-114b-5145-85ad-098ac9092bad |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 6b994924-23a2-5604-8e03-fd88a7a03ab6 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Membrane Application (1st coat) - Mix and Apply Enviro Clad as a first coat to the thicknesses prescribed by the specifications
checkpoint-status |  |  | checkpoint | Membrane Application (2nd coat) - Mix and Apply Enviro Clad as a second coat to the thicknesses prescribed by the specifications
checkpoint-status |  |  | checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-sectioned |  |  | checklist | B-LV+HP1200+900PUR+800TC |  |  |  |  | Yes | B-LV+HP1200+900PUR+800TC | 26a00ce7-7f73-46f1-b5a3-e013127725fa
checkpoint-group |  |  | section | Batch Detail Number of Products
checkpoint-status |  |  | checkpoint | Enviro B-LV
checkpoint-status |  |  | checkpoint | Enviro Flex FC/compatible sealant
checkpoint-status |  |  | checkpoint | Enviro HP1200
checkpoint-status |  |  | checkpoint | Enviro 900 PUR
checkpoint-status |  |  | checkpoint | Enviro 800TC
checkpoint-group |  |  | section | Pre Commencement
checkpoint-status |  |  | checkpoint | Material Management & Storage
label | 7737a6ce-f9f2-556f-9a4a-dfea827896c8 |  | note | Material to be stored in a dry, clean place and directly out of sunlight.
checkpoint-status |  |  | checkpoint | Acceptance of Substrate
label | 4e6826a8-e7a6-514a-ba31-4b9150ea6bd4 |  | note | Obtain Clearance for work to commence. The Substrate shall be smooth, without protrusions, voids or formwork distortions. There should be no blow holes/ bug holes in the substrate. All patching products must be properly cured in accordance to the PDS before membrane application
checkpoint-status |  |  | checkpoint | Acceptance of Puddle Flanges
label | daae963b-3a15-531d-8d34-5a6991a209cf |  | note | All Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
checkpoint-status |  |  | checkpoint | Falls in Substrate
label | 7330023f-932c-5b35-881a-2f97eda3cc3a |  | note | Check for falls prior to application of membrane. Builder to confirm compliant falls. Achieve Minimum 1-100 falls
holdpoint |  |  | signoff | Foreman to confirm falls - Signature
checkpoint-status |  |  | checkpoint | Cracks in Substrate
label | 32459877-3308-541a-999f-7cf43295fd73 |  | note | Cracks in substrate wider than 1.0mm( but not more than 1.6mm) must be V-grooved and filled with Epoxy B-LV. Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks to be referred to engineers for treatment methodology.
checkpoint-group |  |  | section | Substrate Preparation: AS 4654.2-2012
checkpoint-status |  |  | checkpoint | Ensure Surface is prepared to receive primer application.
checkpoint-status |  |  | checkpoint | Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
checkpoint-status |  |  | checkpoint | Remove all sharp edges including screws,nails and concrete/mortar projection.
checkpoint-status |  |  | checkpoint | Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary.
checkpoint-group |  |  | section | BL-V Coating - First Coat
checkpoint-status |  |  | checkpoint | Moisture Content
label | 227a7465-c37d-56e1-b973-7b450902fb83 |  | note | Check Moisture content of substrate, not to exceed 6% ( Min.1 test per 10m2)
checkpoint-status |  |  | checkpoint | Weather/RH
label | 98ef6cad-60dc-57a8-98e1-ab04708c6ce3 |  | note | Product to be applied at temperatures no less than 10C or no more than 35C. RH must be greater than 50%
checkpoint-status |  |  | checkpoint | Product Mixing
label | 85167801-69b5-5fd4-8187-9c10306d6989 |  | note | Mix Part A (12L) and Part B (6L) separately. Add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached. Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | Primer Application
label | a468f164-8694-55fb-bb38-09463b6715a2 |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied. Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface. Apply one coat of Enviro Epoxy B to achieve a minimum Dry Film Thickness (DFT) of 75 microns. Ensure Primer is dry and tack free ( within 24 hours) prior to next coat.
checkpoint-group |  |  | section | BL-V Coating - Second Coat
checkpoint-status |  |  | checkpoint | Weather/RH
label | d743138c-34ac-5767-b980-ca6d61144f82 |  | note | Product to be applied at temperatures no less than 10C or no more than 35C. RH must be greater than 50%
checkpoint-status |  |  | checkpoint | Product Mixing
label | 44a806a5-5965-53f2-ace0-c44439a0a542 |  | note | Mix Part A (12L) and Part B (6L) separately. Add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached. Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | Filler Application
label | 0095c4a4-3943-526f-9924-77c1e85af142 |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied. Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface. Apply one coat of Enviro Epoxy B to achieve a minimum Dry Film Thickness (DFT) of 75 microns. Ensure Primer is dry and tack free ( within 24 hours) prior to next coat.
checkpoint-group |  |  | section | BL-V Coating - Third Coat
checkpoint-status |  |  | checkpoint | Weather/RH
label | 808c015a-53a5-5bd1-9183-441bb4fc335f |  | note | Product to be applied at temperatures no less than 10C or no more than 35C. RH must be greater than 50%
checkpoint-status |  |  | checkpoint | Product Mixing
label | ee3098e1-4498-5da6-9f42-baa6c30eaaa8 |  | note | Mix Part A (12L) and Part B (6L) separately. Add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached. Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | Filler Application
label | 3aaa1a79-bd7e-52da-b498-72aa1e16f84c |  | note | Apply primer using a brush or roller and casting aggregate for every 5 m2 applied. Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface. Apply one coat of Enviro Epoxy B to achieve a minimum Dry Film Thickness (DFT) of 75 microns. Ensure Primer is dry and tack free ( within 24 hours) prior to next coat.
checkpoint-group |  |  | section | HP1200 Coating
checkpoint-status |  |  | checkpoint | Weather/RH
label | d71ffead-e5f5-514b-8a33-30b945405089 |  | note | Product to be applied at temperatures no less than 10C or no more than 35C. RH must be greater than 50%
checkpoint-status |  |  | checkpoint | Bond Breaker
label | 0933bb6f-8127-541b-9005-90a5a6451edd |  | note | Apply Enviro Flex FC/compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints. This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas. Allow to cure prior to over coating with membrane coats.
checkpoint-status |  |  | checkpoint | HP1200 Application
label | 2fe526d9-12a5-59fa-8548-b9ff4af978e2 |  | note | Mixing by way of 1:1 mix ratio (by volume) in heated plural component spray equipment such as Graco E-10 or EXP-2. Both low- and high-pressure spray equipment can be used for the application of Enviro HP1200. Enviro HP1200 is to be applied a rate of 1.6 kg/m² to the prepared and primed substrate to a minimum dry film thickness (DFT) of 1.5 mm. Visually check product is cured before proceeding to the next step.
checkpoint-status |  |  | checkpoint | QA TESTING
label | 65235948-5b1b-5990-a86d-b0f0a67263ba |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions.( 1 test per 10m2) Conduct Electronic Leak Testing ( ELT) to entire area.
checkpoint-group |  |  | section | ENVIRO 900 Coating
checkpoint-status |  |  | checkpoint | Weather/RH
label | 2ecb01b6-8092-5968-a4a1-71c5fcc9f3e0 |  | note | Product to be applied at temperatures no less than 10C or no more than 35C. RH must be greater than 50%
checkpoint-status |  |  | checkpoint | Mixing of Product
label | aee8cd73-4c17-5cfb-84f4-9926647f8ce1 |  | note | Enviro 900 has a mix ratio of 2.2:1 (A:B). Mix Part A and Part B separately, before combining. Enviro 900 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for a minimum of thirty seconds prior to application.
checkpoint-status |  |  | checkpoint | 900 Application
label | 9b70de5c-a96b-52c4-b9a2-858a9444779d |  | note | Enviro 900 to be applied by squeegee, roller or brush to finished membrane. Aggregate should be uniformly broadcasted to the wet Enviro 900 within 10 minutes.
checkpoint-group |  |  | section | Enviro 800TC Coating - Second Coat
checkpoint-status |  |  | checkpoint | Weather/RH
label | 7880f716-7984-581c-afc5-ca73635db7b7 |  | note | Product to be applied at temperatures no less than 10C or no more than 35C. RH must be or greater than 50%
checkpoint-status |  |  | checkpoint | Product mixing
label | 463c0d88-fefe-58fa-a613-5cf6d3fe878a |  | note | Mixing by way of 4:1 mix ratio (A:B) by volume. Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application.
checkpoint-status |  |  | checkpoint | 800 TC Application
label | ca944261-7b8c-52dd-9bdd-31b71d1ac86e |  | note | Enviro 800TC to be applied by roller or brush to finished membrane. Allow each coat to sufficiently dry before proceeding to the next coat
checkpoint-group |  |  | section | Enviro 800TC Coating - First Coat
checkpoint-status |  |  | checkpoint | Weather/RH
label | a8fc6e67-7f97-59c4-943f-d94d9b762c7e |  | note | Product to be applied at temperatures no less than 10C or no more than 35C. RH must be or greater than 50%
checkpoint-status |  |  | checkpoint | Product mixing
label | 00584479-5807-5ab3-a873-402c13baf2a3 |  | note | Mixing by way of 4:1 mix ratio (A:B) by volume. Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application.
checkpoint-status |  |  | checkpoint | 800 TC Application
label | a03905cf-5640-5336-9368-e653edb03d5e |  | note | Enviro 800TC to be applied by roller or brush to finished membrane. Allow each coat to sufficiently dry before proceeding to the next coat
checkpoint-group |  |  | section | Detailing
checkpoint-status |  |  | checkpoint | Vertical termination detailing
label | a8a1661d-dccb-5d6f-a72f-e4d7564b1b39 |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
checkpoint-group |  |  | section | Final Builders Sign Off
checkpoint-status |  |  | checkpoint | Signed off by Builder
holdpoint |  |  | signoff | Final Sign off
checklist-sectioned |  |  | checklist | EnviroShield+ 250NS |  |  |  |  | Yes | EnviroShield+ 250NS | 272fd83b-7953-4053-bbbd-c1de7e72efe8
checkpoint-group |  |  | section | BATCH DETAIL NUMBER OF PRODUCTS
checkpoint-status |  |  | checkpoint | Enviro Shield
checkpoint-status |  |  | checkpoint | Enviro Flex FC
checkpoint-status |  |  | checkpoint | Enviro 250NS
checkpoint-status |  |  | checkpoint | Enviro 700X
checkpoint-group |  |  | section | PRE COMMENCEMENT
checkpoint-status |  |  | checkpoint | Material Management & Storage
label | 17c73df5-6f80-567a-967b-90a662e44329 |  | note | •Material to be stored in a dry, clean place and directly out of sunlight.
checkpoint-status |  |  | checkpoint | Subfloor Preparation
label | 0e195416-b0e3-59fb-93cc-0dce8127d0df |  | note | •Properly prepare the identified areas by mechanically abrading to remove surface •Contamination and any delaminating material. Surface should be prepared by abrasive grind and high-pressure wash or vacuum to allow for optimal bonding.
checkpoint-group |  |  | section | PRIMING APPLICATION - ENVIROSHIELD
checkpoint-status |  |  | checkpoint | Weather/RH
label | c17d20db-12ed-58c7-b7a1-e2a8ddad4c09 |  | note | •Product to be applied at temperatures no less than 10C or no more than 35C. •RH must be greater than 50%
checkpoint-status |  |  | checkpoint | Product Mixing
label | 52d62039-7a58-5d7a-8301-4f38ef131fcd |  | note | •Mix Part A and Part B separately. Add Part B, liquid hardener, to the Enviro Shield Part A base. •Enviro Shield should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached. •Mix for 3 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | Primer Application
label | 505a7a0c-cfbd-5a04-b900-d36dc26dbd91 |  | note | • Apply a prime coat of Enviro Shield with a brush and roller at the application rate of 5m2/litre and allow to dry for at least 4 hours. • Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface. • When Priming, broadcast Aggregate into wet primer to enhance holdup of the subsequent applied topping.
checkpoint-group |  |  | section | DETAILING
checkpoint-status |  |  | checkpoint | Bond Breaker
label | 4dd6b10e-3d88-56c9-92c0-ee8d65082a7b |  | note | • To the clean, dry surface apply Enviro Flex FC sealant as a minimum 15mm angle fillet to the turn-up, turn-down or internal corner. • Tool Sealant to a smooth concave finish. Allow to cure for a minimum 12 hours.
checkpoint-group |  |  | section | Primer Application
checkpoint-status |  |  | checkpoint | Weather/RH
label | dba9c6c8-671f-59ec-8cbe-feb39463d26f |  | note | •Product to be applied at temperatures no less than 10C or no more than 35C. •RH must be or greater than 50%
checkpoint-status |  |  | checkpoint | Product mixing
label | d2d14352-ffa3-51a7-88ae-4ac51d1e3201 |  | note | •Enviro 250-NS should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. •Mix to a uniform colour and consistency for a minimum of 3 minutes.
checkpoint-status |  |  | checkpoint | 250-NS Application
label | cbcd27e8-5333-5058-a52a-b772a8bf106a |  | note | •Enviro 250-NS to be applied by roller or brush to Primed membrane. •Allow each coat to sufficiently dry before proceeding to the next coat •Applications where the coating is to be applied over joints where excessive movement is anticipated, apply an additional Bandage strip of Enviro 250-NS coating and Enviro Joint Band re-enforcing over the joint area prior to application of Enviro 250-NS Second coat.
checkpoint-group |  |  | section | Enviro 250-NS COATING - SECOND COAT
checkpoint-status |  |  | checkpoint | Weather/RH
label | 6ef00d67-7935-547e-ac57-a7a948f89461 |  | note | •Product to be applied at temperatures no less than 10C or no more than 35C. •RH must be or greater than 50%
checkpoint-status |  |  | checkpoint | Product mixing
label | 191a29ee-3180-5bf5-84ed-8af0a6254698 |  | note | •Enviro 250-NS should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. •Mix to a uniform colour and consistency for a minimum of 3 minutes.
checkpoint-status |  |  | checkpoint | 250-NS Application
label | 4bcd1d4c-89ce-570d-8f43-b81c108937f4 |  | note | •Enviro 250-NS to be applied by roller or brush to Primed membrane. •Allow each coat to sufficiently dry before proceeding to the next coat
checkpoint-group |  |  | section | QA/TESTING
checkpoint-status |  |  | checkpoint | Inspection
label | 621b0b0f-3a04-5222-b843-636b84c885ac |  | note | •Visually examine the coating. Note and record the following properties: Overall evenness of coating appearance. •Presence of entrapped contaminants in the coating such as dirt, concrete and construction waste, leaves, or other contaminants. Presence of pinholes or out-gassing, indicated by 1mm or larger diameter bubbles in the coating surface. •Presence of uncured coating, indicated by soft, sticky, or liquid patches in the coating. A summary of on-site,in-situ tests and test results required. Results: - Evenness of Coating Finish. - Leaves, Concrete Waste etc. Trapped in Coating not allowed. - Minor Excessive Aeration of Coating Surface allowed. . - Presence of Pinholes or Out-Gassing not allowed. - Presence of Soft, Tacky or Uncured Coating not allowed.
checkpoint-group |  |  | section | FINAL BUILDERS SIGN OFF
checkpoint-no-status |  |  | checkpoint | signoff
holdpoint |  |  | signoff | Final Sign off.
checklist-flat |  |  | checklist | Enviro Shield / Prime P2 / Epoxy B-LV |  |  |  |  | Yes | Enviro Shield / Prime P2 / Epoxy B-LV | 28518ab3-07ba-4aa8-b0ca-1bb4d9d31945
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 0c7176f7-ed83-57fd-a604-1de1ae1e3b4f |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Screed (moisture test if required, Enviro Shield is moisture tolerant.)
label | d907aa7f-af59-51b7-bb4d-3d9112598cf5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply first coat of Enviro Shield with a brush or roller.
label | e4fe0f9a-27ad-58ae-9eac-6697f20c9e01 |  | note | Visual
checkpoint-status |  |  | checkpoint | Apply second coat of Enviro Shield with a brush or roller.
label | 22d45fa1-9239-5c54-8ac5-6a63da74a25a |  | note | Attach photo
checkpoint-status |  |  | checkpoint | Protection board. Install Elmich Versidrain 8 Geo. Applicable to planters only
label | 98863976-7159-5ebb-8f18-e3e1ff0a117b |  | note | Attach photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-sectioned |  |  | checklist | B-LV +HP1200+900PUR+800TC |  |  |  |  | Yes | B-LV +HP1200+900PUR+800TC | 30fbc69f-b829-4615-8822-feb5208bc503
checkpoint-group |  |  | section | Batch Detail Number of Products
checkpoint-status |  |  | checkpoint | Enviro B-LV
checkpoint-status |  |  | checkpoint | Enviro Flex FC/compatible sealant
checkpoint-status |  |  | checkpoint | Enviro HP1200
checkpoint-status |  |  | checkpoint | Enviro 900 PUR/P2
checkpoint-status |  |  | checkpoint | Enviro 800TC
checkpoint-group |  |  | section | Pre Commencement Checklist
checkpoint-status |  |  | checkpoint | Material Management & Storage
label | 051a11f5-faf6-55e5-940b-79b5a8172fbe |  | note | Material to be stored in a dry, clean place and directly out of sunlight.
checkpoint-status |  |  | checkpoint | Acceptance of Substrate
label | b5ac1b78-be0e-58a7-910c-8cda61fc65d3 |  | note | Obtain Clearance for work to commence. The Substrate shall be smooth, without protrusions, voids or formwork distortions. Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
checkpoint-status |  |  | checkpoint | Substrate Preparation :AS 4654.2-2012
label | 35c33d66-87af-59eb-92ce-3276463c4e06 |  | note | Ensure Surface is prepared to receive primer application. The Substrate shall be smooth, without protrusions, voids or formwork distortions. There should be no blow holes/ bug holes in the substrate. All patching products must be properly cured (3 days) before membrane application. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary. Concrete finish:CSP 2-3
checkpoint-status |  |  | checkpoint | Puddle Flanges
label | 46f3e3fc-ca69-5da3-be09-b88ca741c52c |  | note | PVC Puddle flanges to be recessed into substrate to finish flush ready for waterproofing.
checkpoint-status |  |  | checkpoint | Wall acceptance
label | 8bc900e1-6af9-5b86-8887-10e3477e58a8 |  | note | FC sheeting to have max 6mm gap at floor/wall junction. Sheets to be set with manufacturers base coat. Mortar in block work needs to be a flush joint, smooth and level with the blocks, no blow outs of mortar.
checkpoint-status |  |  | checkpoint | Falls in Substrate
label | 40d59015-da1b-5c2c-80e9-e2d0ebf43541 |  | note | Builder to confirm falls of substrate to drains to prevent ponding water -1:100 min and 1:80 Max
holdpoint |  |  | signoff | Foreman to confirm falls - Signature
checkpoint-status |  |  | checkpoint | Cracks in Substrate
label | 1e50a627-31c2-561d-8e4c-9d368362079a |  | note | Fill all cracks in substrate wider than 1.0mm( but not more than 1.6mm) with filler compatible with the membrane system. Cracks of 1.6mm and over, movement structural joints, cold joints and Live cracks to be referred to engineers for treatment methodology.
checkpoint-group |  |  | section | Primer Application
checkpoint-status |  |  | checkpoint | Moisture Content
label | 3957c605-26f2-5ec1-8ba7-a9b46d381c1b |  | note | Check Moisture content of substrate, not to exceed 5% ( Min.3 tests per 15m2)
checkpoint-status |  |  | checkpoint | Weather/ RH
label | 6d68b70d-5f96-5a33-a392-3a059f19e797 |  | note | Product to be applied at temperatures no less than 0C or no more than 35C. RH must be greater than 50%
checkpoint-status |  |  | checkpoint | Mixing of product
label | 7f70f954-89dc-5cc6-bcce-a97fd47f41ac |  | note | Mix Part A (12L) and Part B (6L) separately. Add Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Enviro Epoxy B-LV should be thoroughly mixed with a mechanical mixer at low speed with a suitable mixing paddle attached. Mix for 5 minutes or until uniform with a mechanical mixer at low speed (less than 400 RPM) prior to application.
checkpoint-status |  |  | checkpoint | Application of B-LV
label | 716f1d91-a5cd-5229-a9a6-d35466ff660d |  | note | Apply primer using a brush or roller. Applications of excessive build should be avoided, and material must not be allowed to pool on the substrate surface. Apply one coat of Enviro Epoxy B to achieve a minimum Dry Film Thickness (DFT) of 75 microns. Ensure Primer is dry prior to next step
checkpoint-group |  |  | section | Membrane Application of System
checkpoint-status |  |  | checkpoint | Weather/RH
label | f7eeed9f-254d-5ea5-aaad-95605beb03ee |  | note | Product to be applied at temperatures no less than 0C or no more than 35C. RH must be greater than 50%
checkpoint-status |  |  | checkpoint | Bond Breaker
label | f42782ec-15d6-5c97-833c-4e12d44b01c3 |  | note | Apply Enviro Flex FC/compatible sealant to form smooth flexible cove to all internal corners, penetrations and joints. This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal areas and 15mm x 15mm coved fillet as per AS4654.1 class III membrane requirements for external areas. Allow to cure prior to over coating with membrane coats.
checkpoint-status |  |  | checkpoint | Mixing and application of HP 1200
label | aeec96d8-f0a8-53e2-bca0-764aff3d82ab |  | note | Mixing by way of 1:1 mix ratio (by volume) in heated plural component spray equipment such as Graco E-10 or EXP-2. Both low- and high-pressure spray equipment can be used for the application of Enviro HP1200. Enviro HP1200 is to be applied a rate of 1.6 kg/m² to the prepared and primed substrate to a minimum dry film thickness (DFT) of 1.5 mm. Visually check product is cured before proceeding to the next step.
checkpoint-status |  |  | checkpoint | QA Testing
label | 884471d1-86c0-55e0-baa3-748c7bb12ee5 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions. Conduct Electronic Leak Testing ( ELT) to entire area.
checkpoint-group |  |  | section | Wearcoat Application of System
checkpoint-status |  |  | checkpoint | Weather/RH
label | ab224e68-5c24-5876-a358-a7c4da2ae4f0 |  | note | Product to be applied at temperatures no less than 0C or no more than 35 C.RH must be greater than 50%
checkpoint-status |  |  | checkpoint | Mixing of product
label | dc1cbf00-5ce5-525a-b66b-5592799f2829 |  | note | Enviro 900 has a mix ratio of 2.2:1 (A:B). It is critical to mix Part A and Part B separately. It is supplied in pre-weighed packages, and it is essential that all of the hardener (Part B) is added to the entire resin component (Part A). Enviro 900 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) for a minimum of thirty seconds prior to application.
checkpoint-status |  |  | checkpoint | Application of HP 1200
label | 78e7722b-5ae7-5695-a125-c5d7aca284dc |  | note | Enviro 900 to be applied by squeegee, roller or brush to finished membrane. Aggregate should be uniformly broadcasted to the wet Enviro 900 within 10 minutes.
checkpoint-group |  |  | section | Topcoat Application of System
checkpoint-status |  |  | checkpoint | Weather/RH- First Coat
label | d29b85da-2ab7-5f35-8384-887c19f5157c |  | note | Product to be applied at temperatures no less than 0C or no more than 35C. RH must be or greater than 50%
checkpoint-status |  |  | checkpoint | Mixing - First Coat
label | 01d4356d-9eba-5f5d-a4fd-73be2fd28424 |  | note | Mixing by way of 4:1 mix ratio (A:B) by volume. Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application.
checkpoint-status |  |  | checkpoint | Application- First Coat
label | d258166c-e692-5138-9237-13fe800f98a0 |  | note | Enviro 800TC to be applied by roller or brush to finished membrane. Allow each coat to sufficiently dry before proceeding to the next coat
checkpoint-status |  |  | checkpoint | Weather/RH- Second Coat
label | 01d6b2ab-23ee-5c35-8449-995645716aed |  | note | Product to be applied at temperatures no less than 0C or no more than 35C. RH must be or greater than 50%
checkpoint-status |  |  | checkpoint | Mixing - Second Coat
label | 2bccb6f0-41b8-5436-b775-95314cc8a414 |  | note | Mixing by way of 4:1 mix ratio (A:B) by volume. Enviro 800 TC should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application.
checkpoint-status |  |  | checkpoint | Application - Second Coat
label | 930d48ac-bfe7-59e7-b904-713714c068ca |  | note | Enviro 800 TC can be recoated after 16-24 hours depending on temperature conditions. Preferably, apply at 90° to the direction of the previous coat. If there is uncertainty about the conditions, allow longer drying time.
checkpoint-group |  |  | section | Detailing
checkpoint-status |  |  | checkpoint | Vertical Termination
label | 7e9ccb99-75db-5ac5-bc4c-0ea1f4630251 |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | 322da84a-cb55-5b3e-9407-98149d92228b |  | note | Final Builders Sign off.
holdpoint |  |  | signoff | Builders final sign off.
checklist-flat |  |  | checklist | Combiflex |  |  |  |  | Yes | Combiflex | 3bc30f8b-d0c5-43d2-a105-14ad8dcc7d99
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 905d3aa5-66b2-51ec-9afc-a3bc5f2b75c6 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | 8b128c1b-5cca-555e-8cb4-fc467b86d02f |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare Substrate. (moisture test if required) prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | 7af628f1-a68f-51c0-be3c-bc51a505e6d4 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Measure and Temporarily fix ElastoFlex or Combiflex
label | d5e59cd4-d177-55af-9f56-dbb56661777a |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Install ElastoFlex or Combiflex to Movement Joint locations
label | 07e507ca-115e-526d-ba46-0001b7999bfc |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Remove Push Pins and Patch holes
label | 3b95553f-f654-5a58-9295-2bf9a1d9ca61 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Inspect Length of Combiflex material
label | 50fe05b1-ab65-55e2-9d07-e6a3ba1247dc |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Inspect Length of epoxy anchor
label | 080a27b3-6f96-540f-952d-596ee57f194d |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Carry ouf sprinkler testing
label | 09356ce2-cac0-577f-9491-99058eea02ac |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Check Substrate & Repair defects
label | 8271e8ad-89b6-557f-b529-96269bfb6a0d |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff. Visually inspect and ensure adequately cured. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200+900+800TC |  |  |  |  | Yes | Enviro HP1200+900+800TC | 4179ea1e-d976-4dd9-a1f9-0ca3e2904dc7
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | ab59039b-900a-5906-9fbf-ea421d675171 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
label | c5a81eca-c69c-54d8-b2da-939ebf0cd19f |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | d0843839-b647-5546-8af2-59db278efbf6 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | a0e9411f-0870-53de-8fca-d2a2bfe56326 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 865475f7-c8ce-512b-af9e-dd0cc371cabb |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | f33c0074-bc41-54a8-ad70-52c4aab3bd5c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | f57428eb-c573-5a17-8dcc-bb4397c4fdfe |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Wear Coat - Mix and Apply Enviro 900 with brush or new roller (spray application optional) Broadcast aggregate uniformly to the wet Enviro 900 within the timeframes specified
label | a091d505-a7ee-554c-9881-e5b0cff77422 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Top Coat Mix and Apply Enviro 850 with brush or new roller (second coat optional pending specification)
label | 79b7eff1-7e22-597a-8324-d0a2459e7f3a |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro BLV + HP1200 |  |  |  |  | Yes | Enviro BLV + HP1200 | 5622150f-6e58-4eeb-8b47-3d12e8b9cb02
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | d744a9ed-06b0-513d-a0a7-2ff7837f5b43 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate. The surface must be clean, dry and free from all loose particles including dust, laitance, grease, coatings, curing compounds and any other foreign matter. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns)
label | 44081f8d-7c85-532c-9d9a-9b038172b087 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Substrate Preparation and Caulking. Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris. Remove all sharp edges including screws, nails and concrete/mortar projections. Apply a suitable and approved joint sealant such as Enviro Flex Pro or Enviro Flex FC to all joints and connecting building parts prior to the application of Enviro 700X
label | d7e09f4b-50f5-50bc-9688-6e5fa3545232 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Priming. Apply BLV using a brush or roller. Allow primer to fully cure before proceeding with the application of HP1200
label | 13735d25-a5d5-5051-99b4-80ac36ec8e00 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. HP1200 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application
label | 40d93835-c926-5cca-a9aa-1f487cff7583 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Curing. Allow product to cure for 12 hours before recoating. Care should be taken when walking over newly installed waterproofing system to ensure the membrane is not damaged
checkpoint-status |  |  | checkpoint | Top Coat. should be thoroughly mixed using a mechanical mixer at low speed prior to application.Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application. Allow to react for 15 minutes when thinning with Enviro Thinner No.8 before application. Do not apply in damp or wet conditions. Allow each coat to sufficiently dry before proceeding to the next coat
label | a06e5b33-407b-577f-b354-02ddab1e3383 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test
label | 2ab308b1-daf6-5b80-a95a-9b7e7eecddf4 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro P2 + HP1200 |  |  |  |  | Yes | Enviro P2 + HP1200 | 57c13594-b408-4591-bcd5-e153797b1e4f
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | f59aabe4-7a92-5903-aedd-436e0d818bd7 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate. The surface must be clean, dry and free from all loose particles including dust, laitance, grease, coatings, curing compounds and any other foreign matter. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns)
label | 1b96263c-2d16-5e63-86ee-2be4788a9c22 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Substrate Preparation and Caulking. Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris. Remove all sharp edges including screws, nails and concrete/mortar projections. Apply a suitable and approved joint sealant such as Enviro Flex Pro or Enviro Flex FC to all joints and connecting building parts prior to the application of Enviro 700X
label | 736a3974-c403-5d17-83bf-247d26ca8e65 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Priming. Apply P2 using a brush or roller. Allow primer to fully cure before proceeding with the application of Enviro 700X
label | 13925042-f8a2-5c8c-8181-90b5497a4916 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. HP1200 should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application
label | 8d6e0bc4-a56b-5dc5-a179-ec80eddfcbc6 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Curing. Allow product to cure for 12 hours before recoating. Care should be taken when walking over newly installed waterproofing system to ensure the membrane is not damaged
checkpoint-status |  |  | checkpoint | Top Coat. should be thoroughly mixed using a mechanical mixer at low speed prior to application.Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application. Allow to react for 15 minutes when thinning with Enviro Thinner No.8 before application. Do not apply in damp or wet conditions. Allow each coat to sufficiently dry before proceeding to the next coat
label | 222e7a59-5ee2-57ab-928a-47160bcd8a3e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test
label | c077af6a-41c0-596a-8f90-5507a947ade6 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro Flex 2 Part |  |  |  |  | Yes | Enviro Flex 2 Part | 5a565494-eb25-495c-98cb-565f60296f8b
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 792f2930-d976-5189-a74c-c180959bb7e0 |  | note | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | fc8305db-804f-50c1-b05a-e14340875776 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 692d70c5-9d94-5adc-93c0-5fd00a532a3a |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 5ccd1c2b-9407-50cd-b33f-4a7c223fbf5c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | 280f16cc-19f7-5893-8ff9-44fc62891ab4 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Membrane Application (1st coat) - Apply Enviro Flex 2 Part using a brush or roller
checkpoint-status |  |  | checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint-status |  |  | checkpoint | Membrane Application (2nd coat) - Apply Enviro Flex 2 Part using a brush or roller
checkpoint-status |  |  | checkpoint | Flood Testing (if required)
label | 226c6369-a91c-53a5-a724-ceab5402c52e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Envirosystems 200P - Internal Wet Areas |  |  |  |  | Yes | Envirosystems 200P - Internal Wet Areas | 5a705ca7-3877-4e48-b0bb-34a9503bc1c8
checkpoint-status |  |  | checkpoint | Batch Number
label | e77d7eae-f40c-51e8-93e4-306214a1380a |  | note | Record batch number Min 1 photo
checkpoint-status |  |  | checkpoint | Floor Substrate
label | 8452af2c-97e0-5862-b046-c5cd6513d219 |  | note | Surfaces must be clean, dry and free from all loose particles including dust, laitance, grease, or any foreign matter. All loose particles including dust, laitance, grease and other contaminants such as spray paint, coatings and curing compounds and the like should be removed by grinding or similar. Steel surfaces should be treated with appropriate degreasers, then grit blasted and/or wire brushed where necessary. Cracks bigger than 1mm to be reffered to engineers for treatment methodolgy. Min 2 photos
checkpoint-status |  |  | checkpoint | Puddle Flanges
label | 4090e097-18a9-5e66-b030-2b17e5bfd3bd |  | note | PVC Puddle flanges to be recessed into substrate so that they finish flush with the substrate. Min 2 photos
checkpoint-status |  |  | checkpoint | Wall Substrate
label | 5c63ab75-3a98-521e-b640-49f792e80c20 |  | note | FC sheeting to be installed to manufacturers specifications (i.e. maximum 6mm gap at floor / wall junctions) FC sheet and nails to be set with manufacturers base coat. Masonry substrates must be rendered /skimmed. Min 2 photos
checkpoint-status |  |  | checkpoint | SFL
label | 57602664-204e-50ea-bb84-ac2a9c7c43d7 |  | note | Falls in the substrate to drains to prevent ponding water outside of shower (1:100). Falls in the substrate to drains to prevent ponding water inside of shower (1:80). Falls in the substrate to drains to prevent ponding water in a bathroom designed as an unenclosed shower (1:80).
checkpoint-status |  |  | checkpoint | Holdpoint
label | 34e12e9f-68b6-5bc8-b96f-e99a1bf03db7 |  | note | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Moisture Content-Tramex Moisture Reader
label | a0630c07-8d98-579a-9681-07931d527ea4 |  | note | Enviro Shield -Max 6.9% Enviro Prime WB - Max 4.5% Record and mark reading on tested area ( min 3 tests ) 3 photo of Markings on tested area and Tramex reading.
checkpoint-status |  |  | checkpoint | Primer Application
label | 3d43261a-453c-57d2-8086-12be2505977c |  | note | Add Enviro Shield Part B (grey liquid hardener) to the Enviro Shield Part A (base). Mix using slow speed (max 400 rpm) mechanical mixing equipment with a suitable paste type mixing paddle attached. Mix for 5 minutes or until uniform. Allow to stand 5 minutes after mixing and then mix again for a minute. Apply 1 coat of Enviro Shield between temperatures of 5-35C with a brush and roller. Visually check product is cured before proceeding to the next step. Same applies for Enviro Prime WB above. Min 2 photos of primer applied. Min 1 photo of temperature reading prior to application.
checkpoint-status |  |  | checkpoint | Fillet and Bondbreaker
label | 6cd7c3aa-9196-592f-857e-1132e73860a5 |  | note | Surfaces must be clean and dry. Apply the sealant firmly into the internal corner or joint and tool to the required cove size as per the relevant Australian Standard. This is to be a 12mm x 12mm coved fillet as per AS3740 class III membrane requirements for internal. Allow to be track free before proceeding with membrane application. Visually check product is cured before proceeding to the next step. Min 2 photos. Min 1 photo with coving testing tool.
checkpoint-status |  |  | checkpoint | Wall Membrane Application
label | 724a5753-0b14-5bfc-abb2-5c56e27ad155 |  | note | Enviro 200P Ultra can be applied using a brush or roller in temperatures of 5-35C. Apply Enviro 200P Ultra to achieve the minimum Dry Film Thickness (DFT) of 0.6mm. Prefabricated waterproof collars to be installed and incorporated into waterproofing membrane around all plumbing penetrations. Visually check product is cured before proceeding to the next step. Min 2 Photos Min 1 photo of temperature reading
checkpoint-status |  |  | checkpoint | Floor Membrane 1st Coat
label | e6b76cdf-bf57-5a63-831f-536f05ea86a3 |  | note | Mix using slow speed (max 400 rpm) mechanical mixing equipment with a suitable paste type mixing paddle attached. Enviro 200P Ultra can be applied using a brush or roller in temperatures of 5-35C. Apply Enviro 200P Ultra to achieve the minimum Dry Film Thickness (DFT) of 0.5mm. Visually check product is cured before proceeding to the next step. Min 2 photos Min 1 photo of temperature reading
checkpoint-status |  |  | checkpoint | Floor Membrane 2nd Coat
label | 450e6667-b192-5058-b907-fa6391f1c1c9 |  | note | Mix using slow speed (max 400 rpm) mechanical mixing equipment with a suitable paste type mixing paddle attached. Enviro 200P Ultra can be applied using a brush (Min 150mm upturns) or roller in temperatures between 5-35C. Apply Enviro 200P Ultra to achieve the minimum Dry Film Thickness (DFT) of 0.5mm. Visually check product is cured before proceeding to the next step. Min 2 photos Min 1 photo of temperature reading
checkpoint-status |  |  | checkpoint | QA Testing
label | d73dab86-57b7-5a09-91e2-e091a719fa07 |  | note | Thickness testing of application to the recommended DFT to manufacturers instructions( 0.6mm walls 1.0mm floors 3 tests on floor/ 3 tests on walls.) 24 hour Flood testing. 6 photo of markings of testing on susbtrate and Positector reading Min 1 photo of Flood testing
checkpoint-status |  |  | checkpoint | Holdpoint
label | 7f302730-4a36-520b-bb7d-016833df65fb |  | note | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | Enviro HP1200+800TC |  |  |  |  | Yes | Enviro HP1200+800TC | 5ef7c5ad-1dde-4c02-97f4-1d9f1f76d994
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 0279143c-f58b-5db6-9f83-46813f493721 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | d9a825a4-3bc5-5f39-a02c-ef018d3adc95 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 5697c8e8-fc0b-5f4d-aab9-1d62e07fac18 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 6c6d69b5-1666-5010-b0aa-eafe1f63cba6 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | deeb8b47-60b0-55b5-8444-45473043958c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | c36162e3-60b6-58a9-91c5-89a69a9cfc53 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Top Coat - Mix and Apply Enviro 800TC with brush or new roller (spray application optional) Re-apply as required or determined by the Specification
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | 3688fe16-d4c7-5a23-a59f-e7e63cd90a8e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200+850TC |  |  |  |  | Yes | Enviro HP1200+850TC | 5f154536-6585-4b51-a006-9ef599ebb8b7
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 129bd9b1-35fd-5418-8cfb-d6d7924e3599 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
label | b149bc61-f419-576f-bfcd-f3b3c3d17edb |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | 5eaea391-dc11-51bb-b2d3-3d83eed4db42 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | c48dbf8d-2097-554e-9b36-6116ca2a4e9f |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | c461715d-6a46-5038-b181-8217f4557a12 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | 9f5d9517-9642-5212-b1d4-a5bfc7d58add |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Top Coat - Mix and Apply Enviro 850TC with brush or new roller (spray application optional) Re-apply as required or determined by the Specification
label | ce8f41c4-6c30-57a8-8b33-320824ee9c22 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | 4c86cf19-69c1-58a5-9331-90b5024c53ef |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro 700X + 200P |  |  |  |  | Yes | Enviro 700X + 200P | 5f7083b7-a416-41fc-9912-8c0ef4cc4f74
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 4f9be934-5055-52bb-85a3-eb4da88c8e02 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | 56e864dc-b804-5a13-978e-1b36e86e993e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare Substrate. (moisture test if required) prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | 079fa901-15c6-502f-b521-a64ec9f71246 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer (Enviro Shield/Enviro prime P2 or Enviro Epoxy B-LV) by brush/roller
label | 7579cb93-4827-549a-a0d9-ab712f915ad3 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking. Apply Enviro Flex FC junction fillets (where applicable)
label | 0e8ef5ce-6ce0-53fd-ac9a-052c92f49f84 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. Mix Enviro 700X thoroughtly using mechanical mixer. Apply Enviro 700X using brush/roller achieving 1.6mm WFT / 1.5mm DFT.
label | cde1e2e5-770a-5d33-aae2-b64a809fba2a |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Flood test when applicable.
label | 4cebb6c1-6736-50c6-aab0-7ba9b6b043c4 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | First signoff. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder.
checkpoint-status |  |  | checkpoint | Check Screed (moisture test if required).
checkpoint-status |  |  | checkpoint | Apply primer (Enviro Shield/Enviro Shield or Prime WB by brush/roller
label | 511a89eb-00d3-5e3f-b4ad-9ff3d7f09391 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply first coat of Enviro 200P Ultra with a brush or roller.
label | e574018b-6b71-503d-8dd6-8ce756fb6e53 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply second coat of Enviro 200P Ultra with a brush or roller. Achieve 0.8mm WFT and 1.0mm DFT.
label | 324c3826-3751-5b65-ab09-5e984831ab6b |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff. Visually inspect and ensure adequately cured. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200+900+850TC |  |  |  |  | Yes | Enviro HP1200+900+850TC | 6caa28cd-c1c3-4abc-bf2c-23a77b87aa41
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 35c4a1a4-5bb1-51ef-a97c-8262809f8ffe |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
label | 12317d83-514c-5673-a947-9767570b1866 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | 0515c406-0f07-55a1-8ac0-bd913df23fa5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 8fdcac01-cb26-5b6b-889f-5fd44d756dce |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 07af8172-8cdb-5dd8-ba78-0274c0e31ad3 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | aa87345f-85ab-5219-a8a8-7b6f3dbb7fe4 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | c938d943-e77e-5c1d-8548-5f4e36158430 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Wear Coat - Mix and Apply Enviro 900 with brush or new roller (spray application optional) Broadcast aggregate uniformly to the wet Enviro 900 within the timeframes specified
label | 8de3d95d-0673-5fca-8190-75baa5ddb50c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Top Coat Mix and Apply Enviro 850 with brush or new roller (second coat optional pending specification)
label | 1031dee8-da81-5c3a-8b2a-3e7a1f670f99 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro 200P Secondary |  |  |  |  | Yes | Enviro 200P Secondary | 731d1b1f-e7c1-4122-969f-95b4a4ede24b
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 915833b8-dc85-5d09-9669-e7d9b4166ccb |  | note | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Screed (moisture test if required).
label | 0c134d58-9796-5719-a395-f1f9f3596269 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply Primer. Enviro Shield or Enviro Prime WB.
label | d2893762-6b1c-57b0-a0f5-175dfb3195f0 |  | note | Visual
checkpoint-status |  |  | checkpoint | Apply first coat of Enviro 200P with a brush or roller.
label | a5594d70-398b-57ce-8f5e-03ccd5d45186 |  | note | Visual
checkpoint-status |  |  | checkpoint | Apply first coat of Enviro 200P with a brush or roller. Achieve 0.8mm WFT and 1.0mm DFT.
label | f4c861ef-cf86-560d-ad11-e7b6622801f7 |  | note | Attach Photo of WFT reading. Enter WFT reading on comment section.
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1600 |  |  |  |  | Yes | Enviro HP1600 | 76a09be9-1a3a-47e4-9a88-0a4a419df60e
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 12fdd208-4cdf-589a-a2e5-1c6e0d2a77f5 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | 72d1ebb4-4110-5ede-aa60-9c98bf7a8e66 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | d1013089-ca93-5aa8-b007-3a22dd4257e6 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 38d7d8fe-78b2-58cf-a981-87f4ce7565c1 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | 5a9970ec-1e35-5beb-aca9-a41b95dfca65 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1600 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | be5228a8-a7ef-53cf-b3d0-3f890a334cc0 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro Epoxy RC / Ultra Tuff |  |  |  |  | Yes | Enviro Epoxy RC / Ultra Tuff | 792cba99-95b2-4b90-b026-a2f9250607c0
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 35b97312-e4f4-5082-8059-13059533a4c9 |  | note | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | 23685a5e-8a35-557c-abed-d9aadee1a116 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 672369ab-6ca1-5ac2-b904-5daf29863a9a |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Cutting - Make sure that adjoining ends of intersecting waterstop segments are cut extremely straight
label | 18471631-a44b-5cc3-bc33-3538f99225d2 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | 4a35be57-7621-541d-85cf-a8b1abe6c438 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Epoxy Application (1st coat) - Apply Enviro Epoxy RC / Enviro Ultra Tuff with a brush, roller or spray
label | 91661c90-d451-5d7e-bcea-675e9cb433d4 |  | note | (If no aggregate is required, 1st coat of epoxy can be diluted with 10% xylene
label | cad402ab-e075-57a9-897b-4e54ab59232c |  | note | If aggregate is required, broadcast at correct coverage while 1st coat has been applied and is in it's wet state prior to curing
checkpoint-status |  |  | checkpoint | Epoxy Application (2nd Coat) - Apply Enviro Epoxy RC / Enviro Ultra Tuff with a brush, roller or spray
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured.
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | SikaRoof® MTC-12 UV (SIKA Sikalastic 100 EP + 488 +622) |  |  |  |  | Yes | SikaRoof® MTC-12 UV (SIKA Sikalastic 100 EP + 488 +622) | 8155760d-0c62-413c-8b3c-21334a7577c5
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | e099b1fa-27bd-5f3e-af5b-ede691815822 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | c33be733-c831-5d5b-b0f6-d399e535e00c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare Substrate. (moisture test if required) prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | 537c8854-00a9-54b0-8fbe-c7ed7e9d734e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | PRIMER: 2:1 mix ratio (Part A: Part B) mixed for a minimum of 2 minutes - Prior the application of SikaRoof® MTC-12 UV the priming coat if used must have cured tack-free.. For the Waiting Time / Overcoating please refer to the PDS of the appropriate primer. Damageable areas (handrails etc.) have to be protected with tape or plastic wrapping. Please note, always begin with details prior to the installation of the horizontal surface
label | 7e9917a7-e105-538c-9c65-bbd3f95de184 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | 1. Apply first coat of Sikalastic®-488. Please refer to the Sikalastic®-488 product data sheet for application rates and drying times; 2 coats will be required to achieve the DFT of 1.2mm
label | a6ba5bea-7c69-5d56-ad15-7f695b4426a2 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | 2. Apply the top coat of Sikalastic®-622 Excel Top PLUS. If a non-slip finish is required, two coats will need be installed with the non-slip finish being broadcast into the first coat of Sikalastic®-622 Excel Top PLUS. Once first coat is cured, the coating should be broomed/vacuumed of excess material and the subsequent top coat applied within 24 hours.
label | b025c475-f6e8-5539-8eba-b56b9c7a9f7c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | First signoff. Visually inspect and ensure adequately cured. Check for any potential defects. Sign-off from builder.
checkpoint-status |  |  | checkpoint | Inspection of welds. All Elements to be inspected. Corner terminations, overlaps, lifts, burns, joins, and pressure seal
checkpoint-status |  |  | checkpoint | Test Welds. All Elements to be reinspected. Corner terminations, overlaps, pile heads. ensure all action items from previous inspection have been resolved.
label | 9e04e7c1-2d4e-5f28-aedf-23e1316ce1ce |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff. Visually inspect and ensure adequately cured. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200 |  |  |  |  | Yes | Enviro HP1200 | 86f31228-a2bb-4b25-b1ba-b0ce562b638c
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | d852f775-c71b-5622-9083-80d917325749 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections
label | 56be3291-15c4-5d9f-b463-036d0b498af5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | c145ffc6-43b2-5791-82ca-659a6dd41be0 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 792ee52e-a630-5811-a5e3-a1866fd84e0a |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | bc4752c0-b771-5132-88ac-ba39ac8194ce |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing
checkpoint-status |  |  | checkpoint | Apply Enviro HP1200 using a spray gun
checkpoint-status |  |  | checkpoint | Curing
checkpoint-status |  |  | checkpoint | Pin Hole Detection Test of area with holiday tester Pull Off Adhesion Testing shall not be less than 1MPa. Thickness shall not be less than 1.5mm
label | 985b4f04-f870-5ad8-a921-365f9a702884 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro 700X + 800TC |  |  |  |  | Yes | Enviro 700X + 800TC | 8de6b158-f6c7-487d-8687-62fbd6d5cec3
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 3d91cd10-c394-5739-ad89-c11390b58141 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate. The surface must be clean, dry and free from all loose particles including dust, laitance, grease, coatings, curing compounds and any other foreign matter. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns)
label | 3886f6ef-7fc8-5476-9eb7-df8f4ef10d38 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Substrate Preparation and Caulking. Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris. Remove all sharp edges including screws, nails and concrete/mortar projections. Apply a suitable and approved joint sealant such as Enviro Flex Pro or Enviro Flex FC to all joints and connecting building parts prior to the application of Enviro 700X.
label | 193319c9-9f33-5612-b0e0-4883bcc95756 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Priming. Apply primer (Enviro Epoxy B-LV / Enviro Prime P2 / Enviro Shield) using a brush or roller. Allow primer to fully cure before proceeding with the application of Enviro 700X.
label | ac97f24c-08fc-5842-9b46-e556f71c2d10 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. Enviro 700X should be thoroughly mixed with a mechanical mixer at low speed (less than 400 RPM) prior to application. Apply Enviro 700X using brush/roller achieving 1.6mm WFT / 1.5mm DFT. (2 coats).
label | 4851f8b8-66bb-5d3e-9635-820bc02888af |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Curing. Allow product to cure for 12 hours before recoating. Care should be taken when walking over newly installed Enviro 700X to ensure the membrane is not damaged.
checkpoint-status |  |  | checkpoint | Top Coat. Enviro 800 TC should be thoroughly mixed using a mechanical mixer at low speed prior to application.Add Part B to Part A and mix to a uniform colour and consistency for a minimum of 3 minutes. Allow to react for 10 minutes before application. Allow to react for 15 minutes when thinning with Enviro Thinner No.8 before application. Do not apply in damp or wet conditions. Allow each coat to sufficiently dry before proceeding to the next coat.
label | ed9eb374-bcad-5da3-9a55-24579df12000 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test.
label | e4a60b00-ec57-53bf-b1dc-d2ebec1758b9 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-sectioned |  |  | checklist | Polyseal SWMS - Roller & Spray Application |  |  |  |  | Yes | Polyseal SWMS - Roller & Spray Application | 8f945403-eaea-4310-aa57-34b15815fe5a
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | e350832d-ba91-5b17-893d-dccbaba3eca1 |  | note | Occupational Health and Safety Act 1984
label | fac492df-841f-583f-8421-d622fd115c00 |  | note | Occupational Health and Safety Regulation 1996
label | 3bf81f94-2325-519a-8265-005b128b816d |  | note | NOHS Standard-Manual Handling
label | 421d29d7-0473-5b14-9a7b-6e2d296614ac |  | note | NOHS Standard-Hazardous Substances
label | 60489275-08ce-5e5d-b8f1-04cf6438e0ac |  | note | AS/NZS 4654.1:2009, AS/NZS 4654.2:2009, AS1337 Eye Protection
checkpoint-status |  |  | checkpoint | This SWMS was prepared and approved and details are entered correctly below
text | 165aebe6-d6c7-5754-81f4-311c7faebb1a |  | textbox | Name:
text | 1d577e52-1e03-5a76-8368-60ffce09c8a4 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | The names and positions of personnel assigned the responsibility for supervising this work and their qualifications entered correctly below
text | ca5748a6-c049-5fe4-b7a6-08931d1343ad |  | textbox | Name:
text | 76b05281-1925-54ac-9dd8-4cc040c53df1 |  | textbox | Position
text | 2279cb0d-8f05-591d-bca6-7be52146fa0c |  | textbox | Qualification
text | 7f747cf5-27fc-5f08-b179-9b97bba01b68 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | The names of workers or their nominated safety representatives who were consulted and involved in the development of this SWMS are as follows:
text | 9c552645-308b-578a-b00d-7bb49a4cdb23 |  | textbox | Workers / safety reps names
checkpoint-group |  |  | section | Item no. 1 Material delivery & unloading
checkpoint-status |  |  | checkpoint | Hazard and Risk : Manual handling injuries, Spills, Moving plant
label | 32bdedd3-5836-55cc-a55b-a5e8914d8406 |  | note | Use of lift for vertical delivery of materials & equipment
label | c95c93d1-ab88-5bce-b520-cebc62c93c47 |  | note | Use proper lifting techniques. Code of practice for manual handling
label | 1e4319b5-f23d-5c0e-ba5d-1ccf8b78af0c |  | note | Use of trolleys for horizontal delivery of materials.
label | 3898e910-ad59-5383-ac4d-07a6b6588dca |  | note | Drums to be secured.
label | 455be5e3-f36d-51b7-ba13-78e7cad78e43 |  | note | Use absorbent (soil sand, vermiculite or other inert material) to collect and seal in properly labelled containers for disposal
label | 0bdaa210-3b61-5479-aadc-4de00c39496d |  | note | Make sure pathways are clear and free of loose materials
label | 4a922cf5-d610-551b-aa71-d8cad1bfffa3 |  | note | Be aware of surroundings and moving plants.
label | 41ea00be-05b6-5b8d-9c03-4464f3f5847b |  | note | High visibility vest, safety boots, long sleeve shirts and pants to be worn at all times.
label | eb542cce-c531-5edb-b44d-00578443d378 |  | note | Be aware of other workers.
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checkpoint-group |  |  | section | Item no. 2 Transport/Carry materials to workface or storage
checkpoint-status |  |  | checkpoint | Hazard and Risk : Manual handling injuries, Slips, Roof Access, Working at Height
label | be78632e-f1ba-5dc2-9100-c607374be899 |  | note | Limit manual lifting weight to 20kgs.
label | 6ef4769e-e851-56d6-9f5c-ae544961f321 |  | note | Use of lift for vertical delivery of materials & equipment
label | deaee3c4-632e-55fc-b189-213789a6633d |  | note | Use proper lifting techniques. Code of practice for manual handling.
label | 6af7c80e-490d-551a-bbf2-46b7511d7263 |  | note | Use of trolleys for horizontal delivery of materials
label | bf6f7b33-50b3-5826-bc73-bd85688aab76 |  | note | Drums to be secured.
label | dfaa89c7-4702-53ba-8355-6726c15a894d |  | note | Make sure pathways are clear and free of loose materials
label | f068a491-445a-5de9-9468-a7d1619a6c25 |  | note | Be aware of surroundings and moving plants.
label | d9063ac7-05cd-5c23-9493-54206aa239f6 |  | note | All personnel provided with appropriate PPE : masks, hard hats, safety boots, high vis vest, safety glasses, gloves, long sleeve shirts and pants
label | 84d340c6-502f-53a5-b912-cfe4e418043a |  | note | Be aware of other workers.
label | 0942f468-e978-599d-ac22-ee59fc3c0398 |  | note | Roof access permit required prior to accessing roof, working at heights certificate and harness/fall restraint to be worn if working within 3m of a live edge.
label | 73032f19-6f32-5a97-a174-806202bfbd03 |  | note | Roof access hatch to be closed and locked when operatives no longer working on the roof (end of day or during breaks)
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checkpoint-group |  |  | section | Item no. 3 Safe storage of chemicals in agreed designated area approved by the builder
checkpoint-status |  |  | checkpoint | Hazard and Risk : Spillage, Exposure
label | 4f6f6429-04b1-57a2-899c-5d82e65798e6 |  | note | Drums to be secured. Use absorbent soil sand, vermiculite or other inert material to collect and seal in properly labeled containers for disposal.
label | 04a26bad-9b52-52ea-98c9-f2b1150cb0de |  | note | All personnel provided with appropriate PPE : masks, hard hats, safety boots, high vis vest, safety glasses, gloves, long sleeve shirts and pants
label | 95671092-6d55-5dd9-ae28-23f23cf8086e |  | note | All employees in house and supplier trained in MSDS requirements (refer to MSDS for appropriate handling of product). All storage to be in line with SDS attached
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checkpoint-group |  |  | section | Item no. 4 Floor grinding to prepare surface to be membraned / coated
checkpoint-status |  |  | checkpoint | Hazard and Risk : Manual handling injuries. Contact with faulty electrical equipment. Running over obstacles and debris.
label | d9949492-877f-5f90-a59f-161c4c8b6fcd |  | note | Prior to using tools, ensure Polyseal risk assessment is completed with FM for the use of electrical leads and non battery tools. Ensure that person operating the machinery is suitably qualified.
label | d2f42a0e-c072-5981-b9b9-07294cb893a6 |  | note | Ensure permits for floor grinding are obtained and current for duration of the work.
label | 3f00dbbf-d641-52ec-a340-509d301016e2 |  | note | Ensure a p2 filter mask is worn during the grinding works to prevent inhalation of silica dust
label | 12400c84-2a11-5182-9a3c-bb16e10a7c6d |  | note | Ensure vacuum extraction with HEPA filter is in use and all fittings are adequate
label | 922685b2-7df7-5da5-a697-2643bc278486 |  | note | Check leads and connections daily.
label | 1a0b66bc-2735-5947-8f5b-4d57780cfe13 |  | note | Set up exclusion zones where work is to be undertaken.
label | 4e7b7a32-a6b1-5672-bba6-816abe042f08 |  | note | Ensure Polyseal provides provisions (e.g. tape off area) to prevent access from any other trades.
label | 42ba89e5-8e21-5750-80d2-db6c7aca1fe5 |  | note | All personnel provided with appropriate PPE: masks, hard hats, safety boots, high vis vest, safety glasses, gloves, long sleeve shirts, pants and ear protection.
label | 8f9512b0-79df-5672-8167-e7c8c72054a6 |  | note | Ensure hand grinder is currently tagged and frequently inspected & service monthly / serviced by licensed electrician. Check leads and connections daily.
label | 8b2cb14c-9e67-5117-a1b6-0dcf0e7904f3 |  | note | Ensure experienced operators use the machines as per personnel competency & training.
label | 6614deb6-bf06-5396-8ef8-602b8ad02e71 |  | note | Dust to be placed in plastic bags and secured and placed in bins provided.
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checkpoint-group |  |  | section | Item no. 5 Barricade work areas and clean work area and apply primer with brush or roller
checkpoint-status |  |  | checkpoint | Hazard and Risk : Dust, Inhalation/Health Risk
label | 9e4362e2-7b81-5ed6-abf9-1d4accb3816d |  | note | All personnel provided with appropriate PPE: Respirators, hard hats, safety boots, high vis vest, safety glasses, gloves, long sleeve shirts, pants and ear protection.
label | 6aeb55a2-57aa-5586-bf75-ce79863df667 |  | note | Provide fire extinguisher - refer MSDS for spillage etc.
label | 16abbc43-0048-536a-993c-46bd4d5c89b0 |  | note | Make sure pathways are clear and free of loose materials.
label | f03ea0e7-7564-5c4c-b2a2-71a7a84db4d2 |  | note | Set-up barricades and/or signage where and if required.
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checkpoint-group |  |  | section | Item no. 6 Apply membranes:
checkpoint-status |  |  | checkpoint | Hazard and Risk : Contact with chemicals- exposure, skin contact, eye contact, dust and burns Manual handling injuries with lifting pails Using hazardous substances and flammable chemicals e.g. (xylene, toluene). Ignition of chemicals and fire come into contact with body. Using faulty electrical equipment. Protection of existing surface finishes Working around peno’s , slab edges, voids. Risk of fall
label | 571661e9-c2f1-5f4c-8955-7555ccf53fe4 |  | note | All personnel provided with appropriate PPE : respirators, hard hats, safety boots, high vis vest, safety glasses, gloves, long sleeve shirts, pants and ear protection.
label | d9611be8-df26-59af-aa77-0cb04dc612e7 |  | note | All employees in house and supplier trained in MSDS requirements (Refer to product MSDS for appropriate handling of product).
label | 0388c8b5-ac6d-5ca0-a17e-d601f183f222 |  | note | All leads to be suspended off the ground.
label | abdeaf27-eb5f-5412-ae86-13d6805e1ece |  | note | Tools and leads inspected and tagged by licensed electrician on a monthly basis.Trained and qualified personnel use machine refer skills and competencies register.
label | 9001c939-9ff8-5bb2-869c-e221a3c3a438 |  | note | Proper lifting and handling techniques to be adopted.
label | 32ce679c-9ecc-5a05-b3d6-7ead68b2bd5e |  | note | Barricade & exclusion zone to work areas including signage.
label | f558c47e-c488-5d02-94a6-01c7c92a48d5 |  | note | Ensure work area is clear & safe to work in.
label | 7715b35f-4a1b-5181-9b5a-454ced0565c7 |  | note | Ensure all staff have been inducted & read, signed SWMS, MSDS, and Hazards Register for new products to be used. Follow recommended controls stated in SDS attached
label | 00421002-4153-5dfc-b618-7585f6df90fd |  | note | Spill kits to be used on site at all times.
label | 2f339f25-7264-5ddf-aa4d-ae0a8e33cb2c |  | note | No smoking in work area. Ensuring that any sources of ignition are kept away from area.
label | 670dbbc1-e4ba-54f0-ac91-aa980b32d8fa |  | note | Appropriate warning signs displayed around perimeter of work.
label | cff7cd7b-d110-5f19-8cbb-83acd65d0cf8 |  | note | Ensure that person operating the machinery is suitably qualified.
label | 3df31dac-3a43-58ff-acf1-0367d96c68ad |  | note | Ensure electrical equipment is inspected/tagged and checked regularly.
label | 1126a6a3-7757-57dc-b65b-ff4f196df5c5 |  | note | Advise builder should anything not be barricaded or closed up.
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checkpoint-group |  |  | section | Item no. 7 Rubbish disposal
checkpoint-status |  |  | checkpoint | Hazard and Risk : Environmental problem, Contamination
label | 364d8e03-a2c2-5b2f-894f-9dfdbd45961e |  | note | Daily clean of work site and storage areas
label | 37590c09-c378-512c-b304-020e744d7ad3 |  | note | Removal of debris to designated areas/bins etc.
label | ad5644f7-6247-5450-b8de-b441faabef85 |  | note | Polyseal to remove empty drums from the workplace and place in bins provided by builder
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checkpoint-group |  |  | section | SWMS Induction Statement
checkpoint-status |  |  | checkpoint | SWMS Induction Statement - The following persons have been inducted into the work activities described in this SWMS.
text | 07cf93f4-e7af-5bd5-9249-8c00304e3633 |  | textbox | Persons
checkpoint-status |  |  | checkpoint | I have read and understood the content of this SWMS.
checkpoint-status |  |  | checkpoint | I will work in accordance with this SWMS.
checkpoint-status |  |  | checkpoint | If deemed necessary to amend this SWMS I will consult with my immediate supervisor and assist where required in reviewing this SWMS.
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST POLYSEAL EMPLOYEE SIGN OFF
checklist-flat |  |  | checklist | Enviro Shield + 700X |  |  |  |  | Yes | Enviro Shield + 700X | 91facc92-05f7-4118-9f9d-1f807ccc7796
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | ce5b9be0-8117-5f9e-80a9-5e78db2231d7 |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate/Work Area, Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | 43a1fa63-7c20-5378-ba9a-06449f29a245 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare Substrate. (moisture test if required) Prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | 4466fe27-cf6a-5164-94ee-1e1a55097e85 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer (Enviro Shield/Enviro prime P2 or Enviro Epoxy B-LV) by brush/roller
label | a5b7774f-1363-5c53-b493-9c4bc6666dcf |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking. Apply Enviro Flex FC junction fillets (where applicable)
label | ec1b1286-6a5c-50b3-87ab-2fbfdb5a5317 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing and Application. Mix Enviro 700X thoroughtly using mechanical mixer. Apply Enviro 700X using brush/roller achieving 1.6mm WFT / 1.5mm DFT.
label | 9a098103-cf35-5e95-9455-ca524baf8ddb |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Carry out Dry Film Thickness test & Holiday Testing & Pull Off Test, Repair any defects found using patch and repair method specified in procedures.
label | fd3485f5-5f56-55dc-b843-a41c17c64cae |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro BSM |  |  |  |  | Yes | Enviro BSM | 9a8606cd-eb59-4335-83d1-12ec677864fc
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 85a33b9d-2529-5a9a-9ed4-a302ec98b09b |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check substrate. Blinding sound and level, Trowel finished, no voids or leftover formwork or sharp edges. NCR any unacceptable items
label | ef718dae-5701-54b8-a4f0-f4aa335fd696 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Free substrate of Dirt and Debris where required.
label | cbc670e2-186b-59aa-9a6a-7a71bc78796d |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Reinspect substrate. Polyseal applicator - Area clean and dry, ready to instal sheet membrane
label | c7380323-0a26-541e-ac2f-a454d6479cec |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Lay BSM - Overlap as per manufacturers instructions, stragger cut joins where possible, detail strip to be installed at cut joins.
label | b03f6d88-fb6f-5c14-aa62-95b29371dd1c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply Hp 1600 to Dwall BEFORE bars ensure lap down onto BSM
label | ad426741-6676-59dd-8250-66d950a113ad |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Following bar install, bar to be detailed with flex fc, 700x to be applied with a 50mm return on the bar, bars to be epoxied in by others (generous amount of epoxy required)
label | 99930e7f-1e76-52cf-852d-4a98e067e729 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | epoxy incapulation to pipe penos, Pile cap to be incapsulated with epoxy grout 50mm finished height
label | 26a122c3-0611-5ef9-a047-55647bdbdda9 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | InspecInspection of Membrane - Pre Reo (Polyseal & Client & Enviro systems )tion of Membrane, All Elements to be reinspected. Corner terminations, overlaps, pile heads
label | a2a0a641-1cea-5373-b4b3-cce8f2e59184 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff and handover. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Sika Sarnafil |  |  |  |  | Yes | Sika Sarnafil | a4a57ae7-c514-4a15-9e2e-9fd2244660ed
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
text | 5efbfe6b-8d25-54c8-af8b-33379d8de4ed |  | textbox | Specification / Standard: AS4654.1-2012; AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | 8fccc835-c664-52f0-b14b-a77733ec803e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare Substrate. (moisture test if required) prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | ddb49203-73ee-5e82-bc7b-f51c69d43d5c |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply Sarnacol. Record atmospheric & substrate conditions & notate in QA Documents. Humidity <85%, Delta >3⁰, Air Temp 5-40⁰.
label | 5b50c109-5c01-5138-83b3-11497834844b |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply Sarnafil. Overlap as per manufacturers instructions,75mm, stagger cut joins where possible, detail strip to be installed at cut joins.
label | 490d1e7a-a078-585c-bec4-a111df604de9 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Weld all joins, Ensure PPE, Respirator, fire extuinguisher within vicinity. Weld overlap in one direction to avoid ribbons --Ensure 75mm overlap
label | bb9182e1-c0b4-5cef-9d38-188be7540e16 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Install Pressure Bar, Install as instructed by builder to finish termination height. Install sealant is placed above pressure bar. Every second hole on pressure bar to be drilled. 1 hole overlap on edge of termination bar
label | baed74dd-97ad-546c-bae8-ecc0d62225f7 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Check all welds with spatula/screwdriver for lifts. Use blunt pointed object to ensure all welds correctly sealed. Any lifts, circle to return to weld
label | 1f4fa506-6d2a-5637-ab33-c05a960b90d0 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | First signoff. Visually inspect and ensure adequately cured. Check for any potential defects. Sign-off from builder.
checkpoint-status |  |  | checkpoint | Inspection of welds. All Elements to be inspected. Corner terminations, overlaps, lifts, burns, joins, and pressure seal
checkpoint-status |  |  | checkpoint | Test Welds. All Elements to be reinspected. Corner terminations, overlaps, pile heads. ensure all action items from previous inspection have been resolved.
label | 1910286c-ced7-55b4-8943-eb79f7caa9be |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final signoff. Visually inspect and ensure adequately cured. Sign-off from builder and hand-over
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-sectioned |  |  | checklist | Pre-Inspection Checklist |  |  |  |  | Yes | Pre-Inspection Checklist | a8b2626a-4d7a-4ace-8d06-357a33bb5d0d
checkpoint-group |  |  | section | General Area
checkpoint-status |  |  | checkpoint | Has the builder provided a marked up plan on each area to be waterproofed?
label | 529f84a4-b4fc-5169-b541-e528bebae831 |  | note | Marked up plan has to be numbered if more than one area at a time is to be completed
checkpoint-status |  |  | checkpoint | Has the concrete been cured for 28 days, date of pour to be provided?
checkpoint-status |  |  | checkpoint | Has concrete moisture test been carried out and the result was provided for the locations on a marked up plan?
label | 5e0c2e24-7605-583b-87c3-331a243a41a7 |  | note | The moisture level should be around 7%
checkpoint-status |  |  | checkpoint | Is the concrete finished to an acceptable steel trowel class finish?
checkpoint-status |  |  | checkpoint | Have all tape, steel wire, nails, plywood or formwork, bracing, dyna bolt and/or steel brackets been removed and patched?
checkpoint-status |  |  | checkpoint | Is there any cracking in the substrate? If yes, an engineer’s report will need to be provided or the builder must sign off prior to commencement of works
checkpoint-status |  |  | checkpoint | Has any chemicals been used in the concrete process that may affect the membrane adhesion?
checkpoint-group |  |  | section | Hobbs
checkpoint-status |  |  | checkpoint | Spalling
checkpoint-status |  |  | checkpoint | Laitance
checkpoint-status |  |  | checkpoint | Boney Concrete
checkpoint-status |  |  | checkpoint | Prework was under standard
checkpoint-status |  |  | checkpoint | Form Ply Ridges
checkpoint-group |  |  | section | Wall
checkpoint-status |  |  | checkpoint | Spalling
checkpoint-status |  |  | checkpoint | Laitance
checkpoint-status |  |  | checkpoint | Boney Concrete
checkpoint-status |  |  | checkpoint | Prework was under standard
checkpoint-status |  |  | checkpoint | Form Ply Ridges
checkpoint-group |  |  | section | Floor
checkpoint-status |  |  | checkpoint | Spalling
checkpoint-status |  |  | checkpoint | Laitance
checkpoint-status |  |  | checkpoint | Boney Concrete
checkpoint-status |  |  | checkpoint | Prework was under standard
checkpoint-status |  |  | checkpoint | Form Ply Ridges
checkpoint-group |  |  | section | Access
checkpoint-status |  |  | checkpoint | Puddle flanges used or installed must be recessed flush to the top of the concrete surface
holdpoint |  |  | signoff | Builder to check correct falls to drains
checkpoint-status |  |  | checkpoint | Patching to be completed 3 days prior to waterproofing proposed start date and/or second inspection required
checkpoint-status |  |  | checkpoint | Adequate spacing to seal around each one for Cast in items (conduit, water pipes etc). No flexible conduits permitted
checkpoint-status |  |  | checkpoint | Would recommend using Enviro mortar 45 for all pin holes, overfilled then stoned back when dry
checklist-flat |  |  | checklist | Patching and Handover to Bondek |  |  |  |  | Yes | Patching and Handover to Bondek | afaef5df-e99d-4df8-a16d-14720dd6368f
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 8dfa984f-d5d7-5356-baaa-a01e2c95ddba |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check membrane - Check for damages to membrane.
label | 87413a02-9f71-5f4c-92b4-f5ada8b1cca8 |  | note | Attach Photo of damages
checkpoint-status |  |  | checkpoint | Patching. Apply Enviro HP1200 using a spray gun. Achieve 1.5mm DFT. Or Apply Enviro 700X.
label | 4db5805f-0533-5614-b16c-a5ab74d9adc8 |  | note | Attach photo of patching.
checkpoint-status |  |  | checkpoint | Lapping to blockwork prior to bondek being laid. Apply Enviro HP1200 using a spray gun. Achieve 1.5mm DFT. Or Apply Enviro 700X.
label | 43f4b2a3-ce3e-5392-a9d5-0b0db19d5b80 |  | note | Attach Photo of lap to blockwork.
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Document Upload Checklist |  |  |  |  | Yes | Document Upload Checklist | c0af1764-879f-4fdb-b81e-39c19c03f692
checkpoint-status |  |  | checkpoint | Documents attached below - details entered in comments
checklist-sectioned |  |  | checklist | Enviro AHS Injectable Hose System |  |  |  |  | Yes | Enviro AHS Injectable Hose System | c5334446-8d8a-4d97-a79d-eac3335a82b5
checkpoint-group |  |  | section | Batch Detail Number of Products
checkpoint-status |  |  | checkpoint | Enviro Hydrotite
checkpoint-group |  |  | section | Pre Commencement
checkpoint-status |  |  | checkpoint | Material Management & Storage
label | ff08e72f-3c07-5636-85ca-991618125626 |  | note | Material to be stored in a dry, clean place and directly out of sunlight.
checkpoint-status |  |  | checkpoint | Acceptance of Substrate
label | 35fe9ad2-1087-56af-872a-ca1dc7f28e96 |  | note | Obtain Clearance for work to commence. The Substrate shall be smooth, without protrusions, voids or formwork distortions. Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
checkpoint-group |  |  | section | Application
checkpoint-status |  |  | checkpoint | Installation of Hydrotite
label | c8ec4ab4-b233-522e-9c8b-d9da5aebf924 |  | note | Rectify Existing Sheet Membrane. Ensure overlap and correct bonding to existing sheets.
label | c9ea3098-b6eb-5f12-9cb6-ba22668962c3 |  | note | Hose/Injection. Installation of Enviro AHS / Sika Fuko Hose in accordance with Technical Data Sheets. Ensure all hose endings are located at the top corner of the openings and secured.
checkpoint-group |  |  | section | Detailing
checkpoint-status |  |  | checkpoint | Vertical / Horizontal Waterstop
label | 13f9d911-f1c6-57c9-853b-8ffe134e470f |  | note | Installation of Enviro Hydrotite within the body of the Infill Opening
label | c30da824-b80b-5dc5-bd4c-be8afd0c5025 |  | note | Installation of Enviro Leakmaster above the Enviro Hydrotite (adjacent) within the body of the Infill Opening.
checkpoint-group |  |  | section | Testing
checkpoint-status |  |  | checkpoint | QA Testing
label | d04ee50d-4bf2-5106-ae48-b4d8c68bfb4b |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Check all welds with spatula/screwdriver or blunt instrument to ensure all welds are correctly sealed. Any lifts, circle to return to weld to the sheet membrane.
label | abf1ab7f-993d-552c-9839-9cfe4a251cf1 |  | note | Final Builders Sign off.
holdpoint |  |  | signoff | Builders final sign off.
checklist-flat |  |  | checklist | Enviro Epoxy Screed / Rapid Screed |  |  |  |  | Yes | Enviro Epoxy Screed / Rapid Screed | dbd0918a-5e95-41c6-9119-d90025871833
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 5860926f-2d2b-5c54-951e-f39cd5ee361a |  | note | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Mixing - using horizontal forced action mixers or screed pumps, mix 20kg Enviro Rapid Screed with 100kg Gravel Mix 0 – 4mm; gradually add 9.5 – 11L of clean water (mixing water may vary depending on the moisture content of the Gravel Mix). Mixing time is 2 minutes.
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
checkpoint-status |  |  | checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Apply Screeding to Substrate in accordance with documentations and desired falls.
label | 0e89db79-2a7a-5d30-a864-e9e0f0f1e849 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro HP1200+Shield |  |  |  |  | Yes | Enviro HP1200+Shield | dca0f048-8578-4d75-9467-7be22009cf10
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | 4778de8c-bca9-5bec-8d60-f8a1f509b653 |  | note | AS4654.2-2012; Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate Check for cracks/defect in concrete. Check critical areas (puddle flanges, penetrations, expansion joints, rebates/setdowns).
label | 542dcfad-021b-56af-befe-89d1441a9ba7 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Prepare Substrate. (moisture test if required) and prepare surface to accept primer using a scraper or grinder and vacuum or sweep residual debris.
label | cb260632-6e2a-584d-9e1c-e1f22a7ad6ac |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Check label on drum(s) to ensure correct material is being used
checkpoint-status |  |  | checkpoint | Apply primer (Enviro prime P2 or Enviro Epoxy B-LV) by brush/roller
label | 338e2c73-dc59-502c-9517-edd85688964a |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking/ Joints. Apply bondbreaker at junctions
label | 99f59eec-44df-50f0-820c-c92efa74b1b5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Mixing. Mix HP 1200. Mixing by way of 1:1 mix ratio (by volume) in heated plural component spray equipment such as Graco E-10 or EXP-2. Both low and high pressure spray equipment can be used for the application of Enviro HP1200.
label | 597fdc4f-91e9-52b9-b04a-25e66296468f |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Application. Spray on Enviro HP1200. Achieve 1.5mm DFT.
label | 7beb8c57-3469-5208-9dd2-748a831578f8 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Testing. Carry out Spark Testing and adhesion tests. Repair pinholes and imperfections. Areas marked indicate location of Test.
label | 3e8e1c1b-fd83-5e6d-ab5b-94a33e0af214 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | First signoff. Visually inspect and ensure adequately cured. Check for any pinholes and bubbles. Sign-off from builder and hand-over if applicable.
checkpoint-status |  |  | checkpoint | Check Screed (areas where applicable) moisture test if required, Enviro Shield is moisture tolerant.
checkpoint-status |  |  | checkpoint | Apply first coat of Enviro Shield with a brush or roller.
label | 44fef0fb-fa87-56c4-9ea1-9651364cac57 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply second coat of Enviro Shield with a brush or roller.
label | 0c5841c3-d334-5d75-a3b4-08c9c0058477 |  | note | label
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Enviro 700X + 250NS |  |  |  |  | Yes | Enviro 700X + 250NS | de4bd4da-f648-4309-a289-65b9de4104dd
checkpoint-status |  |  | checkpoint | Specification / Standard Manufacturer's Technical Data Sheet / AS4654.1 - 2012
checkpoint-status |  |  | checkpoint | Batch Number
label | e3e8c07f-ce47-5106-8b21-58fd67146ccc |  | note | Record batch number
checkpoint-status |  |  | checkpoint | Substrate crack and falls inspection
label | 63b5b964-711d-547d-b3da-ded3d664854a |  | note | Obtain clearance for work to commence. Clean substrate so that is free of mould, paint, sealers, coatings, curing agents, loose particles, and other contamination or foreign matter that may interfere with the adhesion. for non metal surfaces: ICRI CSP-4 to CSP-6 for metal surfaces: ICRI CSP-1 to CSP-2.
checkpoint-status |  |  | checkpoint | Substrate crack and falls inspection
label | dbfb41e4-cea0-5f18-928a-036a651584b4 |  | note | Fill cracks less than 1.6mm with filler compatible (Enviro-Flex Pro) with the membrane system.Live cracks to be referred to engineers for treatment methodology. Builder to approve falls on substrate(Min 1:100) prior to application of membrane.
checkpoint-status |  |  | checkpoint | Moisture Content
label | 9a462eed-5003-5750-986d-c5419d9d9281 |  | note | Note. min. 3 tests per 15m2 Enviro Epoxy B-LV up to 6.9% Enviro Prime P2 up to 5%
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Ambient temperature and RH
label | fc8de219-b8a5-5071-ade8-3fd3859fc509 |  | note | Reading twice a day- every 4 hours Mirvac to confirm temperature between the ranges of 5-35 degrees celsius prior to application of membrane. RH must be greater than 50%
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Mechanical Mixing
label | 1975c4dc-d79c-5339-adb4-8f63ce8ad35b |  | note | If applying Enviro Epoxy B-LV: Mix Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base. Thoroughly mix with a mechanical mixer at low speed for not less than 5 minutes and until uniform.
checkpoint-status |  |  | checkpoint | Applying primer
label | 96b42542-7cf7-5a7c-a207-3778e346dda0 |  | note | Using a brush or roller apply the chosen primer. Allow to cure prior to over coating with sealants and/or membrane coats."Primer should be dry to touch and not be tacky when applying pressure to it. Enviro-Epoxy B-LV will take around 16-48 hrs @ 25 degrees C to dry (but could be longer depending on ambient temp and RH)
checkpoint-status |  |  | checkpoint | Seal/apply bondbreaker at junctions hob/floor
label | 7d4bda32-409d-5de2-9d77-8bccd1063969 |  | note | Apply Enviro Flex Pro to form smooth 15mm flexible cove to all internal corners, penetrations and joints.
checkpoint-status |  |  | checkpoint | Application of Enviro-700X
label | 13892e2e-3e43-5620-9265-6fb5567e3924 |  | note | Mix Bucket at low speed( 400RPM) until thoroughly mixed. Apply two coats of 700X. Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice
checkpoint-status |  |  | checkpoint | QA Testing
label | d7ca1e0e-bb4a-5732-a202-f5f88712fb75 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions. 5 tests per 15m2 Holiday/ spark testing of area.
holdpoint |  |  | signoff | Hold Point (Mandatory) - work not to proceed without approval
checkpoint-status |  |  | checkpoint | Application of 250N-S Top Coat
label | 42711146-8ec1-5edb-9ec8-2d91633642d1 |  | note | Mix Bucket at low speed( 400RPM) until thoroughly mixed. Apply 1 coats of 250N-S Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice
checkpoint-status |  |  | checkpoint | Protection of membrane edge
label | 21e432e6-92fb-509a-9b58-f291ba5b47af |  | note | Ensure vertical terminations of membranes on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge. Ensure vertical membrane termination junctions are caulked with Enviro FC pro.
holdpoint |  |  | signoff | Completion of Work Element
checklist-flat |  |  | checklist | Enviro 200P |  |  |  |  | Yes | Enviro 200P | ded6cec6-7198-4b30-8e8e-d110287a75ec
checkpoint-status |  |  | checkpoint | Relevant Australian Standards Checked
label | e3ec56a6-9e87-5c24-aaac-0bb9ef821b07 |  | note | Specification / Standard: AS3740 - 2010, Manufacturer’s Technical Data Sheet
checkpoint-status |  |  | checkpoint | Check Substrate - The surface must be clean, dry and free from all loose particles
checkpoint-status |  |  | checkpoint | Prepare surface to accept primer using scraper (and/or light grind) and vacuum/sweep residual debris. Remove all concrete/mortar projections.
label | 4fc253f4-6240-5416-9bc5-e4024884c72e |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Moisture Content Test
label | 8618ab7a-40c6-5c83-af93-9279ee7c28e5 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Caulking - Apply Enviro Flex FC / PRO to the junction between floor slab and walls
label | 9a2bc66f-7938-5c01-812e-4290b4f14380 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Apply primer using a brush or roller
label | e9d8e858-c732-5407-a9fb-7d36eb39a901 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Membrane Application (1st coat) - Apply Enviro 200P using a brush or roller
checkpoint-status |  |  | checkpoint | Curing - Allow to cure in accordance with Manufacturers Specifications
checkpoint-status |  |  | checkpoint | Membrane Application (2nd coat) - Apply Enviro 200P using a brush or roller
checkpoint-status |  |  | checkpoint | Flood Testing (if required)
label | e5800cc4-d658-5655-8df9-e2999b8f6a40 |  | note | Attach Photo
checkpoint-status |  |  | checkpoint | Final Inspection and Sign-off. Visually inspect and ensure adequately cured - DO NOT PASS UNTIL HOLDPOINT COMPLETE BELOW
holdpoint |  |  | signoff | HOLD POINT - CLICK HERE TO REQUEST BUILDER SIGN OFF
checklist-flat |  |  | checklist | Delivery Checklist |  |  |  |  | Yes | Delivery Checklist | f58efb6e-753b-48eb-b6a4-5dd61c12f50e
checkpoint-status |  |  | checkpoint | Check correct materials are received at least 24 hours prior to commencing work on site
text | 848e23e0-4589-5955-8294-ced723f7ece3 |  | textbox | Batch No.
label | df14911b-3144-5ad1-9a3e-8cd44d2d3f16 |  | note | Specification / Standard: AS4654.1-2012; Manufacturer’s Technical Data Sheet
label | 0b086bdb-76c3-53a2-8886-5218851bf809 |  | note | Attach Delivery Docket
checklist-sectioned |  |  | checklist | BluSeal PVC Liner |  |  |  |  | Yes | BluSeal PVC Liner | f845a673-8d07-4a40-b3a7-8e1a494e3973
checkpoint-group |  |  | section | Batch Detail Number of Products
checkpoint-status |  |  | checkpoint | BluSeal PVC Liner
checkpoint-group |  |  | section | Pre Commencement Checklist
checkpoint-status |  |  | checkpoint | Material Management & Storage
label | af4a5ed4-14b2-58e0-a73c-a02a322ac305 |  | note | Material to be stored in a dry, clean place and directly out of sunlight.
checkpoint-status |  |  | checkpoint | Acceptance of Substrate
label | 3c7475fc-67b3-5540-bcbb-8edf964e6830 |  | note | Obtain Clearance for work to commence. The Substrate shall be smooth, without protrusions, voids or formwork distortions. Clean Substrate so that it is free of mould, paint, sealers, coatings, curing agents, loose particles and other contamination or foreign matter that may interfere with the adhesion.
checkpoint-group |  |  | section | Membrane Application of System
checkpoint-status |  |  | checkpoint | Installation of PVC Liner
label | c12dec42-b9cf-516e-b3d5-d437e050270e |  | note | Overlap as per manufacturer's instructions,75mm, stagger cut joins where possible, detail strip to be installed at end of PVC requiring termination into substrate.
label | eac33004-3fa0-5a0b-a9a7-02a441f0aaa1 |  | note | Weld all joints and install pressure seals as required in accordance with PDS.
label | 693b61c7-a159-56bc-93a5-a9a47ef11377 |  | note | Abut Threaded Rods or anchors / fixings into PVC Liner with circular weld patch to base of anchor locations.
checkpoint-group |  |  | section | Detailing
checkpoint-status |  |  | checkpoint | Vertical & Horizontal Termination
label | 1361366b-9cde-5a92-9aee-6974dff312b8 |  | note | Ensure Vertical terminations of membrane on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
checkpoint-group |  |  | section | Testing
checkpoint-status |  |  | checkpoint | QA Testing
label | 61309816-a60d-573e-8fd8-740dc89c0de0 |  | note | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required. Check all welds with spatula/screwdriver or blutn instrument to ensure all welds are correctly sealed. Any lifts, circle to return to weld.
label | d50640d4-2f40-502e-9115-1649bf4dcac4 |  | note | Final Builders Sign off.
holdpoint |  |  | signoff | Builders final sign off.