## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 5bbe8c5c-9b69-4dad-9c16-e5f37254bc84 |  | checklist | ITP 003 Installation of Internal Partitions |  |  |  |  | Yes | ITP 003 Installation of Internal Partitions | a844ef4a-4f3f-447b-a600-597644132cae
checkpoint-group | b537695e-7570-4519-9d94-1187d8fc1dd1 |  | section | Wall Framing
checkpoint-status | 80c9536a-1276-47c7-bcdc-25f4fd338879 |  | checkpoint | Materials Inspected upon delivery
label | 13a49a45-7ffb-55e1-a114-11f5eca308cb |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | b3d80402-1b6e-562b-948a-1d3eda3b3e4e |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | f6f593a1-4967-5f46-974c-bcccacbc8120 |  | note | Buildup Inspection Code: W
label | 22875afb-e7a4-5620-a6e5-f40e8a62587c |  | note | Lendlease Inspection Code:
label | 86d32a46-fb4a-59d7-a157-a42e2ccdcc60 |  | note | Lendlease Sign/Date:
label | 12b0d1e8-caf7-5bae-8dd1-1f0ce93ad664 |  | note | Lendlease Comment/Result:
checkpoint-status | ee156d0d-cf87-4f4e-a2e9-4ba47c6f5351 |  | checkpoint | Wall framing completed to Rondo designs, checked for square, plumb and twisting
label | 66e4c320-c3c6-5411-a35d-394c4cb06f43 |  | note | Acceptance Criteria: 20mm clearance between the slab and the top track;slotted Deflection Track used; additional noggin installed for onside sheeting frame
label | d55713dc-1ea4-50bb-bd60-18ae6136b433 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 3947d5bd-1c8f-508c-a6a8-a35e11983fe0 |  | note | Buildup Inspection Code: W
label | 7fda5fc4-07c3-5fe2-8799-65c620f10d4d |  | note | Lendlease Inspection Code:
label | 8c1b9637-864c-5b44-8a6a-783e43345be4 |  | note | Lendlease Sign/Date:
label | 4355a9c1-e281-5dfc-85fc-9d7ecb01c38a |  | note | Lendlease Comment/Result:
checkpoint-status | 7a494586-cfeb-4ad0-b36c-e92b7def3d67 |  | checkpoint | Openings (Including doors, windows, removable parts) installed to correct position and height, with right opening towards, plumb and square, as per Rondo designs
label | 4d6a64d9-1845-5a64-9963-480791c88f57 |  | note | Acceptance Criteria: Jamb header or sill used correct components
label | bee72ffe-9c71-5eb3-9f5e-5e3d45ecc111 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | b8adf816-b102-5056-a41c-01844e773f13 |  | note | Buildup Inspection Code: H
label | bf6710c1-2178-540c-a1dd-e66cace5fe62 |  | note | Lendlease Inspection Code:
label | 135ca081-dfb6-5e85-85f3-dc27dd654b8e |  | note | Lendlease Sign/Date:
label | 0823d16b-4d9e-5064-86bb-ca1893ecef4c |  | note | Lendlease Comment/Result:
holdpoint | 13088ac5-219b-4004-adb2-bbb89774b560 |  | signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | 564d4152-77f0-4f30-b4df-29d7341cba71 |  | checkpoint | Plywood Noggins and structural stud installed for all fixtures
label | 8502ccc6-b334-5b50-8e4e-b88fffc89077 |  | note | Acceptance Criteria: Reference that set out of noggins to be checked against Room Layout sheet Elevations
label | d4b5f848-83f9-503e-97a6-e5fa127fb318 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 14102716-d377-53f8-ad19-aa5e35d37131 |  | note | Buildup Inspection Code: W
label | d8664bf6-ace3-54aa-a2c1-1f6bda6e13d2 |  | note | Lendlease Inspection Code:
label | d945d384-99bf-5f5a-b6ab-52e47f80929c |  | note | Lendlease Sign/Date:
label | 5c8a578c-d81f-5fb5-8a2a-e93a76d6543c |  | note | Lendlease Comment/Result:
checkpoint-status | d1887c80-4dca-44fc-b547-0b1e27c5b229 |  | checkpoint | Door and window Frame installed as per manufacturer's specification stud installed for all fixtures
label | 462fc384-44a2-5428-9c80-e3b87e06c68a |  | note | Acceptance Criteria: Plumb, square and same height, core-filled
label | b1c3469c-a5dd-56af-a475-8ed35a8e089c |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Internal partition designs: 10246-22001 SK00 - 1024622-001-SK15; Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | aad383eb-ac02-5bf9-a3dc-e7cc85b7a5d4 |  | note | Buildup Inspection Code: H
label | f1e24750-d17f-53ab-8466-cd40ae19d664 |  | note | Lendlease Inspection Code:
label | fa1613fe-e915-54f8-9a47-b12963b60cb7 |  | note | Lendlease Sign/Date:
label | 8a86ad12-8599-5e58-b85a-8882ec1f4d60 |  | note | Lendlease Comment/Result:
holdpoint | 41179d24-0fb6-4f22-9890-d92bfc4d5bf7 |  | signoff | HOLD POINT - Signed by Lendlease
checkpoint-group | b86fff1c-5a4b-4dce-92ab-740c065f6313 |  | section | Wall Sheeting
checkpoint-status | e017b43c-8690-4bc4-aea5-e6f3539942ea |  | checkpoint | Materials Inspected upon delivery
label | eb3163c4-2c21-58bc-902e-47267824ad73 |  | note | Acceptance Criteria: Correct Materials Delivered and Inspected of damaged / defected material
label | 313e782a-7c55-5da6-ac97-6afed05a093a |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | 464280f1-d573-5cc1-b834-f05824c7d1e4 |  | note | Buildup Inspection Code: W
label | a5a131ce-da69-539a-90dc-72553ff1a0fc |  | note | Lendlease Inspection Code:
label | 44772a4f-21ae-508b-a9e2-8263933394d0 |  | note | Lendlease Sign/Date:
label | d5222fff-8c9a-564b-b107-4b8c311256d0 |  | note | Lendlease Comment/Result:
checkpoint-status | bdd92908-8396-492d-bd47-9f986053b571 |  | checkpoint | Sheeting carried as per manufacturer’s specification, specified sheeting as per schedule. Ensuring correct layering and components and completed fixing as specification
label | 5078cb9e-c41b-5831-9c5e-78ddc7d11c03 |  | note | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | bb379f09-a8c4-56a2-9bb6-715bf8a11afa |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | d30e33ea-357f-561c-8ed5-36fa4610de27 |  | note | Buildup Inspection Code: W
label | 238fd45d-fe78-5fd8-9c9f-f3761df501ab |  | note | Lendlease Inspection Code:
label | 87846735-6a57-5e76-8369-5dbfd7d5342e |  | note | Lendlease Sign/Date:
label | 4798be3e-428b-5dc9-86a2-26e6dc839f20 |  | note | Lendlease Comment/Result:
checkpoint-status | 1524532f-02fa-490c-bdf1-a051634d69e3 |  | checkpoint | Caulking to acoustic / fire / smoke/ details.
label | 8cc6fe7b-f63d-56dd-a3f1-d43e85ae1021 |  | note | Acceptance Criteria: Max 20mm with slab/ column, flush
label | bcc8f347-4980-5c3c-a1a9-dba9a185bab7 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 70976d3e-274b-5704-9326-1dd1cb8e1139 |  | note | Buildup Inspection Code: W
label | 74e4b1ac-e146-58d9-97c9-e185999667fd |  | note | Lendlease Inspection Code:
label | b3553eaf-63a1-5170-98f3-b57ea26575f8 |  | note | Lendlease Sign/Date:
label | 886c0b19-e127-55bd-aff4-38f43c99eb94 |  | note | Lendlease Comment/Result:
checkpoint-status | 360db9cb-b86f-4425-97ce-6b7ded916138 |  | checkpoint | Penetration sheeted and sealed as per builder' drawings
label | ea8ba195-a15b-5e13-a4e7-3d65649306d7 |  | note | Acceptance Criteria: Opening square and flush, fully sealed
label | e3999168-bb7e-5c0c-a636-364b44fe29f1 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 0deb23f8-82a1-55eb-9acd-704b94ba1f34 |  | note | Buildup Inspection Code: H
label | 919ad29e-83cb-5899-ac17-fcf118dcb754 |  | note | Lendlease Inspection Code:
label | b6a4b066-6228-5a6b-8119-8d652cddd197 |  | note | Lendlease Sign/Date:
label | af5b9474-ff47-5350-9488-538aada5986e |  | note | Lendlease Comment/Result:
holdpoint | 3cbd28ac-e54c-41f3-a68d-5556a35d3977 |  | signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | 1e86c3f9-c43c-46a6-b33d-c37fc9638afd |  | checkpoint | All in wall Services signed off by other trades, wall closeout checklist received by Lendlease
label | 794bfe6a-de41-5e6b-90db-47ceb670cefd |  | note | Acceptance Criteria: Confirm with Lendlease that all wall service rough in have been completed and approved prior to sheeting
label | eaeb4714-4ee9-533a-90c3-8bc1dda51d8d |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | fd5ded1a-2653-5789-b338-f7c5b15d466a |  | note | Buildup Inspection Code: H
label | 1fc64be1-6d9a-5267-9ac1-8c94cff6f45b |  | note | Lendlease Inspection Code:
label | 1ddf5c0f-4dde-5724-9576-f128e6e7a155 |  | note | Lendlease Sign/Date:
label | 49185cce-9d94-5e66-b3d8-3daa411d02cd |  | note | Lendlease Comment/Result:
holdpoint | c30884da-b917-4f0c-95aa-ab17efc8d507 |  | signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | f1d050de-de1c-44ad-98d3-8eea694de8fa |  | checkpoint | Insulation completed as per acoustic report, partition plans and spec
label | 0ef5cdeb-8b1f-5749-a5bb-f1c23fe7b2b2 |  | note | Acceptance Criteria: As required Insulation, no gap can be seen
label | d60c1705-f220-5acc-b417-4d2b66eac655 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADL1-Wall Type
label | 6fe89575-57d8-58db-9bb0-9400811815fb |  | note | Buildup Inspection Code: W
label | fac79b21-d951-5445-bf41-d90d713bb2ca |  | note | Lendlease Inspection Code:
label | f02dfb8c-5d98-532b-8e65-f3c1ef636b9f |  | note | Lendlease Sign/Date:
label | 573fd56a-2ede-5e70-8071-4f3d83e40c09 |  | note | Lendlease Comment/Result:
checkpoint-status | 951a1db7-c257-4cc7-a876-8c4faea10418 |  | checkpoint | Plywood Noggins and structural stud installed for all FFE
label | 9347dbcc-509d-50db-94cf-db0dd7a13f5b |  | note | Acceptance Criteria: Checked against current RLS
label | e98d23d7-4e2b-5781-8003-45205de13925 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADL2Internal Architectural Details
label | e71dfc1f-26ba-59bd-89a5-c6d32113d2d6 |  | note | Buildup Inspection Code: W
label | 7dc4318c-a9ce-5d4e-8e1e-1c7564713dad |  | note | Lendlease Inspection Code:
label | 011759ad-3a1d-57c9-be17-1f01cc5e2c60 |  | note | Lendlease Sign/Date:
label | 081bdd59-1cd3-5960-9e75-b4770466a4cf |  | note | Lendlease Comment/Result:
checkpoint-status | 3b49e5bb-b7a0-4161-a021-37a64604e023 |  | checkpoint | Close wall
label | 61cf18ff-d9a6-5ba3-9abf-34a55c3d0852 |  | note | Acceptance Criteria: Staged Fixing at edges, fixing@50mm max centre in field, Staged joints min 300 mm between different layers
label | 84cba163-0da8-50a9-8b50-6dc428dd741e |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008;Series: BR3ADB2-Wall Setout Plans; And BR3ADL1-Wall Type
label | 387b449d-d776-5e89-a40f-603d4575fd98 |  | note | Buildup Inspection Code: W
label | 25c08144-ba61-5d01-8960-6bb5fccff15c |  | note | Lendlease Inspection Code:
label | fabe77c4-c960-5194-9d4c-a9377b25e21c |  | note | Lendlease Sign/Date:
label | 512b7e54-0854-5d39-8ca8-d5bbbbf1f693 |  | note | Lendlease Comment/Result:
checkpoint-status | 80cbbca3-e2fd-4977-b128-92b292a60661 |  | checkpoint | Caulking to acoustic / fire / smoke/ details
label | a284c615-f104-5275-9cbd-ea38560020d2 |  | note | Acceptance Criteria: Max 20mm with slab/ column, flush
label | f3a51f4e-4169-5d5e-bf03-44879f4ed448 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | 9254c353-0dec-5d67-b726-134a977679b0 |  | note | Buildup Inspection Code: H
label | 4c848bb1-f800-5de8-8307-50e48ec966ce |  | note | Lendlease Inspection Code:
label | eba792a3-a45e-5548-a91d-e4284b54dd96 |  | note | Lendlease Sign/Date:
label | 6d1b67f4-3020-5195-b541-70279b39a579 |  | note | Lendlease Comment/Result:
holdpoint | 738bf5c6-4703-4f80-9ba2-3303d068a31c |  | signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | 80c64737-8024-4728-b9c7-c4743bc34f9f |  | checkpoint | Set and sand ready for painting
label | 21bfaf70-bcc3-599b-8459-311b7f0768d5 |  | note | Acceptance Criteria: Meet Level 4 of finish requirement
label | c40687be-ae20-5aa4-b3c2-2a829d847e61 |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008
label | dfd1123a-c50d-5364-9008-cb59b2594187 |  | note | Buildup Inspection Code: H
label | 81c2e736-ad45-5549-af36-420a76b3bfc3 |  | note | Lendlease Inspection Code:
label | dac054b5-caf5-5381-91a0-31316f96a0e0 |  | note | Lendlease Sign/Date:
label | f88686ac-06ac-5731-b175-074082d71b65 |  | note | Lendlease Comment/Result:
holdpoint | 3ff9d7c7-acda-42b6-97a8-4f0fc206b08f |  | signoff | HOLD POINT - Signed by Lendlease
checkpoint-status | a8f27d61-67ab-4ee1-9837-4d12a528faef |  | checkpoint | COMPREHENSIVE FIRST-OF-TYPE INSPECTION
label | 67251a23-bd9c-5cb7-aa63-08b99148652e |  | note | References: Australian Standards AS 1170.4, AS/NZS 4600 and AS/NZS ISO 9001:2008; Siniat & Rondo Inspection
label | f03f7f60-17da-5dd4-8d69-07f4a1d3de8d |  | note | Buildup Inspection Code: H
label | 9047d65f-89e0-5a8e-8025-91524c574dff |  | note | Lendlease Inspection Code:
label | 07cdb5e4-eb51-5b0c-835e-5d11d1d20574 |  | note | Lendlease Sign/Date:
label | 2f590e3f-abfa-525a-ada4-8c01627e6e99 |  | note | Lendlease Comment/Result:
holdpoint | 068e6090-5420-4575-bac4-0566afc2f990 |  | signoff | HOLD POINT - Signed by Lendlease