## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
5fb17500-385f-4586-8fb7-a516ac9f0f9d | checklist | Checkers Checklist |  | Checkers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a0fd9a83-9c92-4e4c-9d91-2b675556d67b | checkpoint | Overall Measurements
10f5d015-9774-4785-b1f7-64fd634019ba | checkpoint | Lifters Correct - Position, Size, Orientation
f647d6ed-7223-48c7-b9e3-54f09723b878 | checkpoint | Fillet is Installed
b3722e3a-abcd-494b-ad66-35e840e3502e | checkpoint | Check Concrete cover around Reo 35mm
78724584-40ae-4c85-ad0c-5009bf16d3a8 | checkpoint | Panel Thickness confirmed
c954ca78-94f0-5c13-86fc-c954a7d1cb29 | dropdown | Panel Thickness: | 200mm
a70d2e69-92e0-44fa-8677-b7cd55b79214 | checkpoint | Magnets are 100% Secure
b93dd27d-1e9a-433a-ac27-aaaf01fe56f0 | checkpoint | Panel is Clean
7dbc6779-7137-4306-8407-0a45089603ef | checkpoint | Photo Taken
8917e0c3-ece0-4490-b201-75d798d871f4 | checklist | Installers Checklist |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
429575b5-1c90-4bf9-a8ea-c24e020a8755 | checkpoint | Complete Material "Bucket List"
5e4872ae-1543-5400-9b76-dedccbc71bfe | textbox | Panel Thickness
87c179ac-43aa-59c3-9522-bb47ee842fc5 | textbox | Nexus 2.5T Edge Lifter (T845)
5759358c-fdca-5a42-9f20-0d24312f2e09 | textbox | ID Plate
f6946caf-a1e8-4b8e-a142-c459ba32cf03 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
029c49d1-1c41-4d58-8be9-97b576e68c7e | checkpoint | Apply bond breaker or wax 1 2 3
d32e566d-c3a1-43a6-98ff-0434c1761e09 | checkpoint | Temporary Fix ID Plate to Formwork
a9d46aec-77a4-47a9-ba2a-155a7f8ab600 | checkpoint | Use Aluminimum Formwork
ecbae66a-0148-4475-a072-9b7650890dbc | checkpoint | Install Reo as-per Shop Drawing Plan
0413f058-4d95-446a-acd6-81eb9f8060d1 | checkpoint | Lifters to be Firm & Square against Formwork
e519d8b9-1a28-4661-8643-2ad5a54eb7a3 | checkpoint | Check Concrete cover around reo 35mm
1bf9696c-fd8e-46fd-bae6-cbc2a5cbaf26 | checkpoint | DOUBLE CHECK EVERYTHING
8aaaaff5-0df2-4512-a2fe-3740df100d62 | checkpoint | Finish Required - GOOD as near face is outside face of building
1587d5cb-b6f4-4fcd-bfe0-01574f1623a7 | checkpoint | QA - Final Check of ALL measurerments & Photos
f60c44b4-a45e-4344-9a2c-8305d4f9a2f1 | checkpoint | QA - Concrete Mix B80 - N40 Panel Mix
7de71d05-4d59-4ec6-ab18-3cc6456d2d9f | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
ca31a74c-c392-4c42-9675-bf8f284c886c | checkpoint | CONCRETE TEST TAKEN
2f27c061-960e-5fd3-8c3f-4dfa7d14eab5 | date | Pour Date
6abbcbd1-bc45-4f32-8919-8e817740f9e4 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
8c707374-58d4-4d6b-8954-ed23ee1a3294 | signoff | Request Signoff
2036f004-438f-4e30-abdd-1a2f8effc601 | checklist | Precast Components ITP |  | Precast Components ITP
6ff7df1a-fbfe-48e8-bf31-2c5a56f08b6d | section | Manufacturing Documents
4f40e841-1938-4756-87df-beca9a7afa39 | checkpoint | Shop drawings reviewed and updated. Issued "As For Construction"
4df5c8ec-90d1-4642-b727-06464896ce10 | section | Pre-Pour Checks
4a03d492-399a-4c7d-b730-c5d08e9bab7f | checkpoint | Final Inspection - all placed in accordance with approved shop drawings
0e13485d-5e8a-521d-9c50-85627e9ee2e6 | tickbox | Edge Lifter 2.5T
0ff5b6f0-1df1-5db3-9eee-525e75d8e9b1 | tickbox | Reinforcement
e75275af-2aa6-5eea-ab0c-acff90c522e0 | tickbox | ID Plate
920eb74f-0d5a-58e7-819d-2a773995f3ae | tickbox | 40 Panel Mix - B80
d5fafc81-ab80-44b3-9ed7-f20226a45357 | checkpoint | Upload sufficient number of photos pre pour
11ddbea4-2af5-445e-b086-607325c18d4e | section | Concrete Pour Checks
6312e5c4-7832-4f02-a7d8-19523394f403 | checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
a6808361-2189-5c59-bd31-78eb1da136df | tickbox | All Concrete Dockets Attached