## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
3a59d04e-6e53-5ceb-bb48-007148140dd5 | checklist | Planks Checklist |  | Planks Checklist
f08fa224-1de2-518e-aa1c-5f58f28bd147 | section | Pre-Pour Checklist
b7b4d05e-47a5-51f0-810a-d26f153000f2 | checkpoint | Cast Information
b9466601-e092-5e94-bda4-6eb27a54e470 | textbox | Cast Number
4a0612f3-051d-574d-a582-3b588fb5eeec | textbox | Plank ID 1
51b414fa-821b-517d-b3af-65af67f806b5 | textbox | Plank ID 2
72f04931-bd50-5612-b377-f8c5f7a4bbb9 | checkpoint | Shop Drawings approved for Works
ab6ca2fa-a309-5329-8358-c167957d493d | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
dbc7157e-0f26-54ac-97e4-bbfa102e4d78 | note | Length
8c9811c6-c88b-552d-a7dc-f750bce51335 | note | Width
668a78ce-d7b1-54e1-b77f-8809106bd431 | note | Height
c3999c8d-94fe-58f8-88be-71aa2abbc8c3 | note | Straightness
f496c980-ab47-5a63-8788-72e04b3ff7fd | note | Cross-section
d3d6f84f-ef56-5e96-94e2-afc9fbaa7275 | checkpoint | Mould Surface Checked
bbff2456-645b-5606-b2de-ea1b2534689a | note | Cleaned
be1c5893-85f7-522f-af95-616a58826d3f | note | Sealed
a56f0861-085c-535c-b4ed-938cc0e9be88 | note | Rubbers in Place
fff73d6f-e7ea-557c-a9f7-bc9f3f1a9d60 | note | Oiled
8814e6b0-8386-5a40-92ad-b1a9ab56d910 | note | Chamfers in Place
5a6a6596-206c-587e-a9de-33e7dc53347b | note | Check angle for shutter
92d17aa5-00ed-5c40-8f19-33f23c57d515 | checkpoint | Reinforcement in Accordance with Drawings
eac9aee2-e5b9-5f7b-b482-a931a01d551b | note | Reinforcement size
639e02cf-01dc-5316-8b61-a439d9bbc108 | note | Lap Length
3a3ae94d-394f-5c9c-899e-95ff1eed4f29 | note | Splicing
2cbbb4c1-0f4b-54df-a52f-2a0a330e799b | note | Bar Chairs
f0138e2d-b5be-5588-b158-e78acfe85484 | checkpoint | Cover maintained and within tolerance
705663b4-eb61-56e6-a646-37f6c3d0ef8d | checkpoint | All Cast-in Items are positioned in accordance with Drawings (if any)
e4641303-9e4b-51f3-bf92-a222bf5e0dd3 | checkpoint | All Polystyrene voids & PGI Sheets are positioned in accordance with Drawings
7c3507fe-8418-58d1-a077-0cb0e48ff88c | checkpoint | All Lifting Inserts are installed in accordance with Drawings
a85de436-597e-5819-953c-c526d27fd9f2 | checkpoint | Kerb Position along with Starter Bars are in accordance with Drawings
b6a15a0f-a4d5-5833-9314-1a841d276d06 | checkpoint | All Temperature Loggers are installed as per Approved WMS (if any)
9d21e0dc-2f92-5c1d-b338-0e7b4679afe3 | note | Ensure All temperature Loggers are Working
18126695-13fa-5c71-b1a0-4a1134c1ab28 | note | Number, location and installation of loggers matches WMS
012767fd-1aa1-5cd4-90b5-9f9742d15e41 | checkpoint | Permacast Representative (QC/PE) Check Completed by
7f7d7a42-0803-51f2-829f-57c51aea3319 | checkpoint | Client Inspector (if present)
1c72432c-40ee-5055-92f6-2698b7233f79 | section | Subcontractor Acceptance prior to Pour
0a56a431-2c8b-5bed-bb0f-efebaf80111c | checkpoint | Subcontractor Check Completed of Mould & Cage for Concrete Placement
789084cb-7fc5-5794-8638-4848859d2b58 | section | Casting Checklist
3fcbe0b6-efc2-57cf-bdec-e437c3479934 | checkpoint | Casting Information
c6e1a4eb-1afb-55aa-bf7b-d43416dc7b97 | textbox | Cast Date
28115d49-b84a-56ca-ad9f-64b24d12d36e | checkpoint | Concrete Delivery Dockets
c350d4d1-5e33-510f-86e3-e84b71e9c3d1 | textbox | Concrete Delivery Dockets (list all)
704a746b-6be5-50b9-ac5a-8a5dfa283a41 | checkpoint | Total Concrete Volume
73871dcb-1fb1-5b4c-a71e-0d822a0d6262 | textbox | Volume (m3)
b6201a3f-5de9-5384-9fa0-824fdb42d036 | checkpoint | Mix Design Verified
acc19c2c-3654-51f6-a534-f73405de4aa8 | textbox | Specify mix used
a4371627-db94-5bbb-8d71-b1816bae2be4 | checkpoint | Ambient Temperature within Limits
42b614f9-a518-568f-a7fd-61ed3f7d28dd | note | max 38°C
bed93563-c38c-51c7-91b6-8e768e5ba876 | checkpoint | Concrete Temperature
ec1fa6ba-a454-5828-8256-c9667071a8d6 | note | max 32°C
9de8d7ed-c015-5743-8def-7943ac02d342 | checkpoint | Slump within Allowable Tolerance (180mm +/- 40)
5480b33b-0dc7-5641-b0c3-c2061e81ebae | note | If volume <=20m3, 2 sets min required. sample every 20m3
737e55bc-7b31-5f86-a6d6-4b8fe303e86c | checkpoint | Truck Tested for strength
49ea44fc-1a15-574a-95bb-ed792931c567 | textbox | Test Report Reference Number
80c7f3cd-bb8c-50dd-a975-e108ee3311f4 | checkpoint | Time Lag Between Trucks is not exceeded
ac942120-150f-54dd-ac6d-f0b6cf6da9f8 | checkpoint | Concrete Placed within allowable time from Batching Plant
e94cf7f5-8044-5e82-9d9f-d32f85543b87 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
66e85e9f-0988-51ff-bd77-6972a786f31b | checkpoint | Required Finish Applied as per Drawings
14807022-93ea-5920-ae91-d2dbbfb0454f | checkpoint | Concrete Covered Overnight
390da9ac-196c-5b38-bd69-fb27964ebf86 | checkpoint | Cylinders Stored next to Bed and covered as per AS1012
d864682e-90c5-53e0-a4e3-b1ab8a731815 | section | Stripping Checklist
5e8be59e-c74e-5b8c-907d-822ceae41037 | checkpoint | Date Stripped
3f893cff-5f69-5837-93df-d75ab73d1854 | textbox | Date Stripped
4ead7a55-1e9a-5c9c-b9bd-581a20e5e2f0 | checkpoint | Minimum Required Strength for Stripping & Lifting Achieved (20 MPa)
52070b95-97da-5b5c-b602-2ea7115cfc72 | textbox | Specify Strength
82360f1f-9177-51d6-88af-0dc37d9860c6 | textbox | Specify if Strength Determined by Crushing Cylinders or Maturity Report
67650e13-4700-5cf3-991a-15370fae4f0f | checkpoint | Lifted and Handled as per Drawings
3c9399df-179b-543e-ac40-9aa01aff10e0 | checkpoint | Product Clearly Labelled
e3e7faac-a472-57e5-9462-cfd5a2d70e27 | checkpoint | Storage as per Approved Temporary Works Drawings
bd9288b9-c7e1-5c29-a7ab-4d7621176a6d | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
949e692a-fc13-5a33-9e24-80a9bd498710 | note | Length
3d0d6af4-a56c-5205-a03b-65c013d94f7e | note | Width
be8f0a3f-bd29-5636-ae8d-484cd89f0325 | note | Height
a896501d-7501-5685-9256-7f60a25ab985 | note | Straightness
081cb72d-198f-5e20-91c8-7ee179218c7f | note | Cross-section
33cc4dfe-38fb-5a0c-a266-beb7f458a195 | checkpoint | Specified Concrete Finish Achieved
443e754e-890c-5de3-8260-2e5a910ab541 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
77ace5b0-b21d-5d71-856d-94d377ab05ef | checkpoint | Generic Post-Pour Works Completed (As Required)
04ef86bb-64c8-59e8-b743-f7e7e1083d32 | checkpoint | Temperature Logging Completed and Conforming. Attach Results (if any)
82714ed1-ad56-54f6-bb8f-c35c2f5fb2cb | section | Any Defect Identified
3f9c3e4c-2e53-572c-b7e7-3f079bf2786b | checkpoint | Punchlisting Completed for all Units
0e13c281-7783-583b-8e05-80233649b921 | checkpoint | Repairs Completed as per approved WMS (if applicable) (Specify Plank Name + Yes/ No)
6e680a02-f936-59a0-a898-87f1a0c7bb55 | textbox | Plank Punchlist Completed
675b0b4d-63b2-5642-94d0-9a6071174562 | textbox | Plank Punchlist Completed
5e2a7a68-6462-504e-b4f5-03c1cbd88f1b | checkpoint | Crack Map Completed (if any cracks observed)
0485a51e-9c30-5bb1-a737-796165be473d | checkpoint | Any NCR Required (if applicable)
3c21c9ed-8a83-591a-b46a-0be92087eb7c | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
ee58e19b-ff6b-578b-8dbe-985fc88298cd | checkpoint | Plank free of Defects and QC Stamp Placed on plank (Specify Plank Name + Yes/ No)
baeadd51-fca7-51c6-9c4b-fcee699e83fe | textbox | Plank Accepted
6987e644-6d6d-5e94-ad54-5ccb92f48295 | textbox | Plank Accepted
6dee7a22-2dbc-5a4e-bf8b-7ed31a3e39dc | section | As-Built Drawings
d2c74ef1-6e3c-5989-8443-f576a5207186 | checkpoint | As-Built Drawings Completed, Stamped and Attached
8b80f22f-30cd-5652-ae3d-f97e2ba75fc3 | section | Concrete Strength Test Report
2c0327a6-df91-52e1-b234-788128f14e1e | checkpoint | Concrete Strength Test Report Received
1b752c30-cd77-563a-8784-51dccf0fb5b2 | textbox | Concrete Test Report Number
117707dc-a8e3-58c1-b951-e1c296e20c1f | textbox | 7 Day Strength (List all)
8948bdac-92fd-59bf-b2bb-1a79d6970b19 | textbox | 28 Day Strength (List all)
261923d1-bcf1-4ed4-a10e-364f5b835639 | section | Transportation Requirements
a77dd0cc-a05a-4d2a-9aa7-27cf9141a24c | checkpoint | Transportation Requirements
| checkpoint | Certificate of conformance
| checkpoint | Inspection Release Certificate
| checkpoint | Delivery Notes
| checkpoint | Delivery Dockets
058a7d09-ae01-562f-8921-9e31e9ba2ba5 | section | Final Acceptance
2064c690-894d-5cab-8947-40a9df86e443 | checkpoint | Completed by
87159759-0253-5729-9bcb-b99c5329aeea | checkpoint | Reviewed by
30688b9f-3d01-57b7-bb6d-84d429d43158 | checkpoint | Client Representative Reviewed By