## Project Structure (hidden)
Folder Structure |  | Checklists
Prelim Activities | To Contain Preliminary Checklist | Preliminary Activities and Materials Approval
BRE Planks | To Contain Planks Checklist | Ability to Add Planks Checklists

## Planks Resources
type | name | values
checklist-sectioned | Preliminary Activities and Materials Approval
section | Preliminary Activities (Approved by Client)
checkpoint | Compliance to AS/NZ ISO 9001:2015
checkpoint | Permacast Project Quality Management Plan
checkpoint | Inspection & Test Plan
checkpoint | MDR Index
checkpoint | Work Method Statement (WMS) - Curing
checkpoint | Work Method Statement (WMS) - Concrete Repair Methodology
checkpoint | Work Method Statement (WMS) - Earthing and Bonding
checkpoint | Shop Drawings
checkpoint | Test Panel Prepared and Inspected by Client
checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
section | Concrete
checkpoint | S65/14/180 (WE654TD04) Concrete Mix Design Approved by Client
checkpoint | Notify Concrete Supplier of Pour
section | Steel Reinforcement
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
section | Polystyrene voids and PGI Sheets
checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
section | Lifting Anchors
checkpoint | Lifting Design Approved by Client
checkpoint | Lifting Devices Approved by Client
checkpoint | Inspection of Delivery for Completeness and Quality
section | Cast-in Items
checkpoint | All Cast in Materials Approved
checkpoint | Inspection of Delivery for Completeness and Quality
checklist-sectioned | Planks Checklist
section | Pre-Pour Checklist
checkpoint | Cast Information
text | Cast Number | 1
text | Plank ID 1 | 2
text | Plank ID 2 | 3
checkpoint | Shop Drawings approved for Works
checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Mould Surface Checked
label | Cleaned
label | Sealed
label | Rubbers in Place
label | Oiled
label | Chamfers in Place
label | Check angle for shutter
checkpoint | Reinforcement in Accordance with Drawings
label | Reinforcement size
label | Lap Length
label | Splicing
label | Bar Chairs
checkpoint | Cover maintained and within tolerance
checkpoint | All Cast-in Items are positioned in accordance with Drawings (if any)
checkpoint | All 100 Dia Blockout are positioned in accordance with Drawings
checkpoint | All Lifting Inserts are installed in accordance with Drawings
checkpoint | Plinth Position along with Starter Bars are in accordance with Drawings
checkpoint | All Temperature Loggers are installed as per Approved WMS (if any)
label | Ensure All temperature Loggers are Working
label | Number, location and installation of loggers matches WMS
checkpoint | Permacast Representative (QC/PE) Check Completed by
checkpoint | Client Inspector (if present)
section | Subcontractor Acceptance prior to Pour
checkpoint | Subcontractor Check Completed of Mould & Cage for Concrete Placement
section | Casting Checklist
checkpoint | Casting Information
text | Cast Date | 9
checkpoint | Concrete Delivery Dockets
text | Concrete Delivery Dockets (list all) | 11
checkpoint | Total Concrete Volume
text | Volume (m3) | 10
checkpoint | Mix Design Verified
text | Specify mix used
checkpoint | Ambient Temperature within Limits
label | max 38°C
checkpoint | Concrete Temperature
label | max 32°C
checkpoint | Slump within Allowable Tolerance (180 +/- 40)
label | If volume <=20m3, 2 sets min required. sample every 20m3
checkpoint | Truck Tested for strength
text | Test Report Reference Number
checkpoint | Time Lag Between Trucks is not exceeded
checkpoint | Concrete Placed within allowable time from Batching Plant
checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
checkpoint | Required Finish Applied as per Drawings
checkpoint | Concrete Covered Overnight
checkpoint | Cylinders Stored next to Bed and covered as per AS1012
section | Stripping Checklist
checkpoint | Date Stripped
text | Date Stripped | 13
checkpoint | Minimum Required Strength for Stripping & Lifting Achieved (20 MPa)
text | Specify Strength | 14
text | Specify if Strength Determined by Crushing Cylinders or Maturity Report
checkpoint | Lifted and Handled as per Drawings
checkpoint | Product Clearly Labelled
checkpoint | Storage as per Approved Temporary Works Drawings
checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | Length
label | Width
label | Height
label | Straightness
label | Cross-section
checkpoint | Specified Concrete Finish Achieved
checkpoint | Cast-in Items are all in Place and within Specified Tolerance
checkpoint | Generic Post-Pour Works Completed (As Required)
checkpoint | Temperature Logging Completed and Conforming. Attach Results (if any)
section | Any Defect Identified
checkpoint | Punchlisting Completed for all Units
checkpoint | Repairs Completed as per approved WMS (if applicable) (Specify Plank Name + Yes/ No)
text | Plank Punchlist Completed
text | Plank Punchlist Completed
checkpoint | Crack Map Completed (if any cracks observed)
checkpoint | Any NCR Required (if applicable)
checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
checkpoint | Plank free of Defects and QC Stamp Placed on plank (Specify Plank Name + Yes/ No)
text | Plank Accepted | 18
text | Plank Accepted | 19
section | As-Built Drawings
checkpoint | As-Built Drawings Completed, Stamped and Attached
section | Concrete Strength Test Report
checkpoint | Concrete Strength Test Report Received
text | Concrete Test Report Number | 15
text | 7 Day Strength (List all) | 16
text | 28 Day Strength (List all) | 17
section | Tranportation Requirements
text | Certificate of conformance
text | Inspection Release Certificate
text | Delivery Notes
text | Delivery Dockets
section | Final Acceptance
checkpoint | Completed by
checkpoint | Reviewed by
checkpoint | Client Representative Reviewed By