## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
f0faa64c-4def-4e7b-9879-2fc8ae965c02 | checklist | Combined ITP - Willow Avenue (Q-VC-200-01) |  | Combined ITP - Willow Avenue (Q-VC-200-01)
6a6fcece-0237-4b0e-a379-1aa73f1647f5 | section | 1.0 PRELIMINARIES – PROJECT MANAGER RESPONSIBILITY
b4e5705b-773b-4fd9-8bf9-c6bf88ded72c | checkpoint | 1.1 - Possession of Site
02b399d6-abac-5238-bdf4-310352f6d7d6 | note | Inspected - Responsible: RCC
942ef739-bd18-59dc-b1da-f1242a0cd2fd | textbox | Remarks - Date of possession:
572f1576-eb04-4cea-9eae-9f0545b3846d | checkpoint | 1.2 - Dial Before You Dig (DBYD) and Permit to Excavate completed and signed onto by personnel
bd0e8458-2d9e-5e06-b31a-ff2c73e332fc | note | Inspected - Responsible: RCC
95771dfc-eb73-4e41-9bde-accc957d5fa8 | checkpoint | 1.3 - Confirmation of Scope and Extent of Works with Project Team, including RCC, S28 and TSC
1258a1eb-4f29-5156-b288-29e26301576e | note | Inspected - Responsible: RCC /S28 & Pinnacle
b8a2e311-9cea-5f23-bbd3-17290e379e8b | textbox | Remarks - Consultant Engineering / TSC Approval / Direction:
85b389a4-dd28-4429-b743-24fa934e3dc7 | checkpoint | 1.4 - Testing required for the scope:
0dbc38f5-bc20-51f8-8926-69603e307eac | tickbox | Concrete testing
e734dc4e-df87-5c0c-8c8e-db25847aa9b7 | tickbox | Density Testing
35de1b3b-0608-5f1d-be21-2fa7f78ea1eb | tickbox | Gravel Testing
0bbd7720-f145-52bd-93a0-db15aa01bb78 | textbox | Other:
6f432cea-69b1-5974-af2c-ce1c2569d0e1 | note | Inspected - Responsible: RCC
de8d9146-a426-46ba-9dcb-883085a2130e | checkpoint | 1.5 - Traffic Control – TGS approved and appropriately selected for the works
cbd01ea3-84d3-5bc0-82de-d69c94012b20 | note | Inspected - Responsible: RCC
806343c1-181f-5cfe-906d-86a7502ee674 | textbox | Remarks - TGS No.:
3e803ef4-fd3c-4e09-b38f-4d81146b919c | checkpoint | 1.6 - Erosion and Sediment Control:
db3d0d45-4c66-5ecc-ab4d-bf0efa92b769 | tickbox | Silt Boom
0b519a55-79d7-5628-86af-0915ca2f9271 | tickbox | Earth Bund /Sediment Fence
c2ba80bd-dbe0-5fc8-be3e-5addf4f56bef | textbox | Other:
f573ff99-ef07-5083-8749-965e89c35733 | note | Inspected - Responsible: RCC
2fbcb660-77e9-4522-9b11-27b2baa846fa | section | 2.0 C213 EARTHWORKS
5fa21b7c-7751-4ee6-9def-2c80350f168c | checkpoint | 2.1 - Minor clearing of vegetation undertaken – where applicable.
36f5f310-1940-50f8-a707-84d06dff9746 | note | Inspected - Responsible: RCC
7931055b-29a5-4fc2-84ba-20ced6266236 | checkpoint | 2.2 - Demolition works / Spoil Removal undertaken and spoil removed from site to approved fill site.
fc7dded1-4b8a-5459-9ea8-8b8fff897507 | note | Inspected - Responsible: RCC
47fbc415-a982-4b2d-ae2b-c625dc18bf6f | checkpoint | 2.3 - HOLD POINT: If unsuitable is encountered TSC to be notified prior to works continuing
ea1cd16a-7dbc-5f9c-bba6-40d70adbc814 | note | Inspected - Responsible: Certifying Engineer
dd7bc0e6-dcad-58cb-8759-7befa8fe68a0 | textbox | Remarks - Consultant Engineering / TSC Approval / Direction:
6ed380ec-b7f9-4d2c-94b4-c2aba90f7d83 | signoff | AUTHORITY HOLDPOINT
64528687-d306-47ff-a663-f05a69637891 | checkpoint | 2.4 - Table drains shaped to allow water to flow freely and best marry into existing surfaces.
a7f09d97-ee97-528f-b254-d3f57141f88e | note | Inspected - Responsible: RCC
db0905c3-e8ff-4c48-9d35-98cc8b30df4a | section | 3.0 C242 FLEXIBLE PAVEMENTS
9d128f67-1d13-461c-ab59-f86847daf77d | checkpoint | 3.1 - HOLD POINT: Proof roll subgrade: If foundation fails TSC to be notified and to provided direction
c700a74f-fba4-526a-bfa0-01d8e8d5fe33 | note | Inspected - Responsible: Certifying Engineer
270f2755-623f-549b-a4d3-afc2b24be311 | textbox | Remarks - Consultant Engineering / TSC Approval / Direction:
42aa73b8-b63e-4600-90ca-587bb387ff08 | signoff | AUTHORITY HOLDPOINT
d29e4791-db68-470a-a948-9f9a021fd1b4 | checkpoint | 3.2 - Road base Material: Material source along with conforming material NATA test certificates have been submitted and approved by the Principal (Material Stockpile Lot)
c623a643-305e-53a6-ab4c-5fce451b7eaf | note | Inspected - Responsible: RCC
e7f04b76-c950-4102-8234-a92dda09cf89 | checkpoint | 3.3 - If testing required - Layers compacted to 100% Standard compaction for full formation width. Compaction testing to be done 1 test per 500m2, minimum of 3 test taken at a time (per lot) or as directed otherwise.
2493471b-8508-58f8-8f6b-d3ad7e8149aa | note | Inspected - Responsible: RCC
595d5b97-9fcf-40c8-810e-251829453e70 | checkpoint | 3.4 - Levels of gravel marry into existing and deviation does not exceed 12mm over the length of a 3m straight edge.
363ec9e7-bfa0-58f1-af68-9c34873ad3eb | note | Inspected - Responsible: RCC
7d41ccd0-ab00-422b-ade5-51aac1a768a0 | checkpoint | 3.5 - HOLD POINT – Carry out a proof roll of finished pavement where applicable
9bc85429-d8b1-56e1-805d-b7195e03f902 | note | Inspected - Responsible: Certifying Engineer
295e6599-f4fb-5f19-a81c-97cc785b83f8 | note | Remarks - Consultant Engineering / TSC Approval / Direction:
75bff890-ba66-4fcc-8947-04c254765308 | signoff | AUTHORITY HOLDPOINT
20a44b44-be12-4e14-9a6a-fd8be3a25d98 | section | 5.0 CONCRETE WORKS
0145733e-6270-4478-9db6-098fc90a5c33 | checkpoint | 5.1 - EXCAVATION AND PREPARATION
e1fea4e3-a9fb-5832-8047-9eaa0e407094 | note | · Suitable subgrade material and prepared to suitable surface
1dcb29ea-23aa-558d-b417-2b4bfbe0a603 | note | Inspected - Responsible: RCC
cc25a0d0-9a8c-4f52-a395-ee58587bf479 | checkpoint | 5.2 - FORMWORK AND REINFORCEMENT
4c0da1e6-3ce4-5b6a-b930-7b9da00831e4 | note | Dimensions and positions of forms shall be carefully checked after the forms are erected. Forms shall be aligned accurately and the location of all fittings, hold formers etc. checked prior to placing of concrete.
6cff1fc9-a2cd-50af-8deb-2d1a1f3ff178 | note | Placing of reinforcement as per agreed scope, with reference to Typical Construction Details. Reinforcement to maintain a 50mm vertical and horizontal cover unless directed otherwise.
77211b36-0c5b-5eee-8248-283c969ecaca | note | Inspected - Responsible: RCC
3606307f-baca-4bca-858d-aea05c684557 | checkpoint | 5.2.3 - HOLD POINT – PRE-POUR INSPECTION The formwork shall be inspected by the Superintendent, and the placing of reinforcement in the spaces formed, where specified, shall not commence until the formwork is approved by the Superintendent.
ef652a4f-ea0d-5f43-b8fa-438febd2e221 | note | Inspected - Responsible: Certifying Engineer
cb4994f0-7b43-5baf-b2dd-cbf0267a961f | note | Remarks - Consultant Engineering / TSC Approval / Direction:
7b08c038-e26b-4386-a8a8-a16373b0aba1 | signoff | AUTHORITY HOLDPOINT
9e686d3c-dad0-45f2-92fd-bcbad43d0468 | checkpoint | 5.3 - READY MIX CONCRETE
8994418b-6156-58aa-b8e6-4e9dded05f17 | note | The concrete shall be mixed and delivered in accordance with the requirements of AS 1379 relating to: - Concrete Mix Used:
55dd630f-6713-5cfb-bb65-0171078516fe | tickbox | 20/20/80
8edda039-9e0e-5108-a9cd-4a2c33ce8366 | tickbox | 25/20/80
aac73355-928b-536a-b32b-248a705d117f | tickbox | 32/20/80
307bbb8a-21d7-51d2-8f55-75f6bfcd4348 | tickbox | 32/20/100
e0dd8a4e-d1d4-5e11-b57c-54d4fd86cb7d | tickbox | 40/20/80
df63dbaa-9b50-5cee-8e0d-52a703357b75 | tickbox | Grout
0e7fc8a3-7aa5-52d9-8f86-44e6ead9ca04 | tickbox | Shotcrete
1727a52e-5053-5eb1-b05a-78282e4d258a | tickbox | Shotcrete w/ poly-fibre
6bfc14e4-c3b8-59bb-a91d-b2b5f0109573 | textbox | Other
fd49dd95-9782-5035-8937-3c525520c8ae | note | Inspected - Responsible: RCC
71637705-0390-4585-8547-fcd8ec674e28 | checkpoint | 5.4 - CONCRETE PLACEMENT
743102cb-0dff-5f0c-a4a1-0c77d2f42149 | note | · The freshly placed concrete compacted by continuous spading, slicing or by vibrator units. Exposed surfaces of the concrete shall be struck off and finished with a wooden float. Corners and edges should be as per the drawings.
11bde601-5456-5afd-b690-a55113631870 | note | · Surfaces are floated, finished and cured as required to a quality finish. Broom finish as required.
6ed3d866-7e4c-51a8-86ae-cfb5533a5439 | note | Inspected - Responsible: RCC
f59fa7b3-b892-4b87-8bb6-3056f3b4d32a | checkpoint | 5.5 - TESTING – WHERE REQUIRED
5e38e095-a52a-5bd4-84ce-7038b32f4e83 | note | 5.5.1
01cfb755-6c09-5b0a-8090-31656fca3b25 | note | Two pairs of test specimens shall be moulded for each 15 cubic metres of concrete, or part thereof, one pair being intended for the 7-day test if required and the other pair for a 28-day test. WITNESS POINT: Concrete test specimens to be taken in presence of Superintendent or Superintendent’s representative
8dbdc286-7ac0-5ca6-b2be-4612c0d0e129 | note | Inspected - Responsible: Certifying Engineer
0ffdabae-2931-569a-b8d2-dee9fc582b32 | textbox | Remarks - Consultant Engineering / TSC Approval / Direction:
f7948c3a-53d2-4784-8196-b2b770a4c160 | section | 6.0 STORMWATER DRAINAGE
79096871-e89b-42b2-b692-3ac51b956b0e | checkpoint | 6.1 - Stormwater components installed as per scope of works
1a81e919-20f3-5973-9ace-1e73eea1eb72 | textbox | Size of pipe installed as per scope:
b69dee8e-a25a-5e16-8124-069151172512 | textbox | Other:
517bd3c7-1630-5237-9ee9-3fbafd313fc3 | note | Inspected - Responsible: RCC
a34384bf-aefc-490f-b769-8c78fb4442d7 | checkpoint | 6.2 - HOLD POINT: Inspection prior to backfill
1f0c4ebd-3247-55ff-a9f0-5a24aeaf28ad | note | Inspected - Responsible: Certifying Engineer
d7beaef1-1107-5d6b-ac02-df4edf7a5582 | note | Remarks - Consultant Engineering / TSC Approval / Direction:
2156714a-99d2-4638-a8bb-3eb5dd9c6dca | signoff | AUTHORITY HOLDPOINT
efa4f5c2-a718-4931-8ca0-97b15ee8589f | checkpoint | 6.3 - Density testing of pipeline required if within roadway:- 100% compaction to be achieved
530fb8da-666d-5e13-a743-763a948d5ebe | note | Inspected - Responsible: RCC
cb03a157-173e-4bb3-8f4e-f05f37db145f | section | 7.0 CLOSE OUT.
02093da6-1642-40cf-a40b-4df572b4bcef | checkpoint | 7.1 - SITE HANDOVER: All works complete, demobilised and site handed back to TSC
77ad5da8-71e4-5c34-bb95-da22058363d4 | note | Inspected - Responsible: RCC, TSC, Sanctuary28, Certifying Engineer
59e7d81d-ce43-547f-b21a-cecabba33095 | textbox | Remarks - Date of handback:
30d892ad-c421-5395-927d-1c9f29c5c33a | textbox | TSC Signature:
83bf5a07-bd6f-5a0e-a9d9-04c53891efc1 | textbox | Client Signature:
81f33fae-dbad-5688-a006-1699e0fe1d76 | textbox | Consulting Engineer Signature:
eba98229-ad39-49cd-8f8e-1b0e5feb9a91 | signoff | Add Signature
b9bf766e-9ef8-4041-96f3-e18df6f725ad | checkpoint | 7.2 - Verify conformance including close out of NCR’s - Records:
6404ccae-06c8-5d1d-ae75-eba1aa1c9c61 | tickbox | NATA Certificates
58463506-9169-511e-a302-d323f6df164c | tickbox | Survey Report
b904daef-93fe-5167-893b-e241ff9ff658 | tickbox | Geotechnical testing reports
21769612-b197-5f56-ae3f-ef0e93e72d9a | tickbox | Concrete test reports
3e25b94c-1e2f-557c-96d3-9bd27f52b1a6 | tickbox | Proof of works report
628ab8f0-7393-5802-97c9-25f6b9d50267 | tickbox | Photographs of completed work
849d9c9d-abc4-55a8-b333-1948737961dd | note | Inspected - Responsible: RCC
e78c81ca-3f86-52dd-aabe-80c1d4e5661e | textbox | Remarks - NCR No:
eda60480-66be-4cd8-8bea-2cb8fccd1d08 | checkpoint | 7.3 - Damage No. (DM) signed off and closed by PM or representative
a10912cb-f9ed-5b3b-9141-e3d867da2958 | textbox | Name:
c0c898f2-13cc-57cb-8af3-5e0db6728cf0 | textbox | Title:
c294f888-54b9-52eb-9623-ff95ca00edd1 | note | Inspected - Responsible: RCC
b8d5804b-5796-49ea-abd0-cc7a8d1b207b | signoff | Add Signature