## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 201-ITP-001 Clearing & Grubbing | [5 empty] | 201-ITP-001 Clearing & Grubbing-V1
section | Clearing and Grubbing
checkpoint | Preliminaries
label | TYPE - Written
label | CONFORMANCE CRITERIA - CEMP prepared and provided to TSC for approval by the Environmental Project Manager or their delegate
label | ○ Site specific ESCP to be included in CEMP
label | FREQUENCY - As required
label | RECORDS - REF
label | BY - PM
checkpoint | JSEA
label | TYPE - Written
label | CONFORMANCE CRITERIA - JSEA prepared and signed off
label | FREQUENCY - As required
label | RECORDS - JSEA
label | BY - SS
checkpoint | Limitation on clearing operations [C212.01]
label | TYPE - Survey
label | CONFORMANCE CRITERIA - Survey Setout complete and Extent of Works confirmed
label | ○ IFC Drawings used for setout
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Location of services identified [C212.01]
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Permit to disturb in place
label | ○ Services protected where required
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Trees & flora outside area [REF]
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Preclearing Inspection undertaken 24hr prior to works.
label | ○ Endangered Community to be identified by suitably qualified ecologist and area to be flagged off. Refer Section 10.1 of REF. Delineate and protect trees and flora
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | ○ Preclearing Report
label | BY - SS
checkpoint | Clearing & Grubbing [C212.03, C212.04]
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Witness Point
label | ○ Specification
label | ○ Drawings
label | ○ Cleared & grubbed material pushed of to the side of works alignment
label | FREQUENCY - Each Lot
label | RECORDS - Witness Point
label | ○ Checklist
label | BY - SS, INSP
holdpoint | WITNESS POINT
checkpoint | Lot Closed
label | TYPE - Written
label | CONFORMANCE CRITERIA - Lot conforms to specifications
label | ○ All NCRs actioned and closed out
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - PM
checklist | 201-ITP-002 Topsoil Stripping | [5 empty] | 201-ITP-002 Topsoil Stripping-V1
section | Topsoil Stripping
checkpoint | Preliminaries
label | TYPE - Written
label | CONFORMANCE CRITERIA - CEMP prepared and provided to TSC for approval by the Environmental Project Manager or their delegate
label | ○ Site specific ESCP to be included in CEMP
label | FREQUENCY - As required
label | RECORDS - REF
label | BY - PM
checkpoint | JSEA
label | TYPE - Written
label | CONFORMANCE CRITERIA - JSEA prepared and signed off
label | FREQUENCY - As required
label | RECORDS - JSEA
label | BY - SS
checkpoint | Drainage and Dust Controls in place if required
label | TYPE - Visual
label | CONFORMANCE CRITERIA - As per the Construction Environmental Management Plan
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Limitation on stripping operations
label | TYPE - Survey
label | CONFORMANCE CRITERIA - Survey set out and complete
label | ○ IFC drawings used
label | FREQUENCY - As Required
label | RECORDS - Checklist
label | BY - SS
checkpoint | Stripping
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Strip 100mm Topsoil to stockpile
label | ○ Specification & Drawings
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Survey
label | TYPE - Survey
label | CONFORMANCE CRITERIA - Post strip survey completed where required
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Work Complete
label | TYPE - Written
label | CONFORMANCE CRITERIA - Field work complete
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - SS, INSP
checkpoint | Lot Closed
label | TYPE - Written
label | CONFORMANCE CRITERIA - Lot conforms to specifications
label | ○ All NCRs actioned and closed out
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - PM
checklist | 201-ITP-003 Foundation Prep | [5 empty] | 201-ITP-003 Foundation Prep-V1
section | Foundation Prep
checkpoint | Authority to Proceed
label | TYPE - Written
label | CONFORMANCE CRITERIA - Underlying lots completed
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - PM
checkpoint | JSEA
label | TYPE - Written
label | CONFORMANCE CRITERIA - JSEA prepared and signed off
label | FREQUENCY - As required
label | RECORDS - JSEA
label | BY - SS
checkpoint | Drainage and Dust Controls in place if required
label | TYPE - Visual
label | CONFORMANCE CRITERIA - As per the CEMP
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Foundation Inspection [Civil Plans] [C223.09]
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Hold Point
label | ○ Foundations to be inspected by a suitably qualified geotechnical engineer to confirm they achieve bearing capacities prior to pouring
label | ○ Where rock is encountered over part of the foundation only, or lies within 300mm below the underside of the mass concrete or selected fill, all material shall be removed to a depth of 300mm below the mass concrete or selected fill for the full width of the foundation over the length where the rock is encountered. This additional excavation shall be backfilled with ordinary backfill material.[C222.09]
label | FREQUENCY - Each Lot
label | RECORDS - Hold Point
label | ○ Checklist
label | BY - SS, INSP
holdpoint | HOLD POINT
checkpoint | Unsuitable Materials
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Hold Point
label | ○ Remove unsuitable material identified after superintendent inspection & instruction
label | FREQUENCY - As required
label | RECORDS - Hold Point
label | ○ Checklist
label | BY - SS, INSP
holdpoint | HOLD POINT
checkpoint | Authorisation to proceed
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Hold Point
label | ○ Authorisation to proceed with replacement
label | FREQUENCY - Each lot
label | RECORDS - Hold Point
label | ○ Checklist
label | BY - SS, SR
holdpoint | HOLD POINT
checkpoint | Compaction of Ground Surface
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Witness Point
label | ○ Specifications
label | ○ IFC drawings Layout plan & Notes
label | ○ Proof rolling to be carried out by water truck if directed by superintendent
label | FREQUENCY - Each lot
label | RECORDS - Witness Point
label | ○ Test results
label | ○ Checklist
label | BY - SS, INSP
holdpoint | WITNESS POINT
checkpoint | Survey Pick up
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Survey pick up of foundation.
label | ○ Survey pick up and confirmation of quantities and extent of any unsuitable materials removed.
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Work Complete
label | TYPE - Written
label | CONFORMANCE CRITERIA - Field work complete subject to any outstanding test results being within allowed tolerance
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS, INSP
checkpoint | Lot Closed
label | TYPE - Written
label | CONFORMANCE CRITERIA - Lot conforms to specifications
label | ○ All NCRs actioned and closed
label | ○ All test results available
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - PM
checklist | 201-ITP-004 Concrete Works | [5 empty] | 201-ITP-004 Concrete Works-V1
section | Concrete – Minor Concrete Works
checkpoint | Mix Design and Methodologies
label | TYPE - Written
label | CONFORMANCE CRITERIA - Hold Point
label | ○ Site specific Mix designs and or methodologies submitted to superintendent or their delegate for approval.
label | FREQUENCY - Each lot
label | RECORDS - Hold Point
label | ○ Checklist
label | BY - PM, SR
holdpoint | HOLD POINT
checkpoint | Authority to Proceed
label | TYPE - Written
label | CONFORMANCE CRITERIA - Underlying lots completed
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - PM
checkpoint | JSEA
label | TYPE - Written
label | CONFORMANCE CRITERIA - JSEA prepared and signed off
label | FREQUENCY - As Required
label | RECORDS - JSEA
label | BY - SS
checkpoint | Earthworks
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Detailed excavation completed to design tolerances
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Survey and set-out
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Concrete vertical & horizontal dimensions set-out
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Foundations [C223.09]
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Suitable subgrade material and prepared to suitable surface for construction.
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Formwork
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Dimensions and positions of forms shall be carefully checked after the forms are erected. Forms shall be aligned accurately and the location of all fittings, hold formers etc. checked prior to placing of concrete.
label | ○ Rigid construction
label | ○ Constructed within tolerances
label | ○ Form oil applied to forms where required
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Reinforcing
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Hold Point
label | ○ Steel supplied suitable for use
label | ○ Laps as per IFC drawings and Standards
label | ○ Reinforcing steel located as per IFC drawings
label | ○ Correct min 50mm cover maintained as per IFC drawings
label | FREQUENCY - Each lot
label | RECORDS - Hold Point
label | ○ Checklist
label | BY - SS, INSP
holdpoint | HOLD POINT
checkpoint | Testing of concrete
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Test for slump as required
label | ○ Take cylinders for strength testing as specified
label | ○ Crack cylinders at specified times for conformance
label | ○ For RCBCs base slab obtain:
label | – 2 x 3 day
label | – 2 x 7 day
label | – 2 x 28 day
label | – 2 x spare cylinders
label | FREQUENCY - Min 2 pairs of test specimens shall be moulded for each 15m3 of concrete, or part thereof.
label | RECORDS - Checklist
label | BY - SS
checkpoint | Concrete Placement
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Concrete ordered correct strength and type
label | ○ For RCBCs ensure approved mix is ordered
label | ○ Place close to final position
label | ○ Vibrate in layers
label | ○ Avoid dropping from excessive height to avoid segregation
label | ○ Finish type as specified by drawings or specifications
label | FREQUENCY - Each lot
label | RECORDS - Witness Point
label | ○ Checklist
label | ○ Docket
label | BY - SS, INSP
holdpoint | WITNESS POINT
checkpoint | Geometrics
label | TYPE - Survey
label | CONFORMANCE CRITERIA - As built survey complete and within tolerance
label | ○ Concrete finished within design tolerances
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Work Complete
label | TYPE - Written
label | CONFORMANCE CRITERIA - Field work complete, subject to any outstanding test results being within allowed tolerance
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS, INSP
checkpoint | Lot Closed
label | TYPE - Written
label | CONFORMANCE CRITERIA - Lot conforms to specifications
label | ○ All NCRs actioned and closed
label | ○ All test results available
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - PM
checklist | 201-ITP-005 Drainage Table Drains | [5 empty] | 201-ITP-005 Drainage Table Drains-V1
section | Drainage Table Drains
checkpoint | JSEA
label | TYPE - Written
label | CONFORMANCE CRITERIA - JSEA prepared and signed off
label | FREQUENCY - As required
label | RECORDS - JSEA
label | BY - SS
checkpoint | Survey
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Drains set out for excavation
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - SS, INSP
checkpoint | Construction
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Specification
label | ○ Drawings layout plan & notes
label | ○ Conforms to design lines
label | ○ Modify to match drainage structures where necessary
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Work Complete
label | TYPE - Written
label | CONFORMANCE CRITERIA - Field work complete subject to any outstanding test results being within allowed tolerance
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS, INSP
checkpoint | Lot Closed
label | TYPE - Written
label | CONFORMANCE CRITERIA - Lot conforms to specifications
label | ○ All NCRs actioned and closed
label | ○ All test results available
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - PM
checklist | 201-ITP-006 Drainage Pipeline | [5 empty] | 201-ITP-006 Drainage Pipeline-V1
section | Drainage Pipeline
checkpoint | JSEA
label | TYPE - Written
label | CONFORMANCE CRITERIA - JSEA prepared & signed off
label | FREQUENCY - As Required
label | RECORDS - JSEA
label | BY - SS
checkpoint | Survey & set out
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Survey set out as per drawings
label | FREQUENCY - As required
label | RECORDS - Survey
label | BY - SS
checkpoint | Material supply
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Applicable standards
label | ○ Pipes supplied as per Specification
label | ○ Pipes supplied as per schedule
label | ○ Pipes supplied as per drawings layout plan & notes
label | ○ Precast components are checked against the Acceptance Criteria provided in C222.19-2 (Refer table checklist attached)
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | ○ Dockets
label | ○ Photos
label | BY - SS
checkpoint | Construction
label | CONFORMANCE CRITERIA - Excavation of trenches per specification
label | ○ Laying and jointing as per specification
label | ○ Layed to level and alignment as per specification
label | Hold Point
label | ○ Backfilling specification
label | ○ Grouted rock pitching at outlet as per plans
label | FREQUENCY - Each Lot
label | RECORDS - Hold Point
label | ○ Checklist
label | ○ Photos
label | BY - SS, INSP
holdpoint | HOLD POINT
checkpoint | Compaction
label | TYPE - Written
label | CONFORMANCE CRITERIA - As per specification
label | ○ As per drawings layout plan and notes
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Geometrics
label | TYPE - Survey
label | CONFORMANCE CRITERIA - As per specification
label | ○ ±5mm level, ±10mm line for < 900mm
label | ○ ±10mm line & level > 900mm
label | FREQUENCY - Each Lot
label | RECORDS - Survey
label | BY - SS
checkpoint | Work Complete
label | TYPE - Written
label | CONFORMANCE CRITERIA - Field work complete, subject to any outstanding test results being within allowed tolerance
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - SS, INSP
checkpoint | Lot Closed
label | TYPE - Written
label | CONFORMANCE CRITERIA - Lot conforms to specifications
label | ○ All NCRs actioned and closed
label | ○ All test results available
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | ○ Photos
label | BY - PM
checklist | 201-ITP-007 Drainage Box Culverts | [5 empty] | 201-ITP-007 Drainage Box Culverts-V1
section | Drainage – Reinforced Concrete Box Culverts (RCBC)
checkpoint | JSEA
label | TYPE - Written
label | CONFORMANCE CRITERIA - JSEA prepared & signed off
label | FREQUENCY - As Required
label | RECORDS - JSEA
label | BY - SS
checkpoint | Survey & set out
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Survey set out as per drawings
label | FREQUENCY - As required
label | RECORDS - Survey
label | ○ Photos
label | BY - SS
checkpoint | Material supply
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Applicable standards
label | ○ Pipes supplied as per Specification
label | ○ Pipes supplied as per schedule
label | ○ Pipes supplied as per drawings layout plan & notes
label | ○ RCBCs supplied are checked against the Acceptance Criteria provided in C222.19-2 (Refer table checklist attached)
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Foundation
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Hold Point
label | ○ No bedding material shall be placed until the foundations have been inspected and approved by the Certifying Engineer. [C222.10]
label | ○ Mass concrete bedding for reinforced concrete bases shall not be placed on earth or rock foundations until the foundations have been inspected and approved by the Certifying Engineer. Following such approval, the surface of the foundation shall be dampened and a layer of concrete not less than 50mm thick shall be placed over the excavated surface and shall be finished to a smooth even surface.[C223.09]
label | FREQUENCY - Each Lot
label | RECORDS - Hold Point
label | ○ Checklist
label | ○ Photos
label | BY - SS, INSP
holdpoint | HOLD POINT
checkpoint | Construction
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Witness Point
label | ○ Laying and jointing as per specification
label | ○ Layed to level and alignment as per specification
label | ○ Filling in between cells as per specification
label | FREQUENCY - Each Lot
label | RECORDS - Witness point
label | ○ Checklist
label | ○ Photos
label | BY - SS, INSP
holdpoint | WITNESS POINT
checkpoint | Backfill and Compaction
label | TYPE - Visual
label | CONFORMANCE CRITERIA - As per specification
label | ○ As per drawings layout plan and notes
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | ○ Compaction Test results
label | BY - SS
checkpoint | Geometrics
label | TYPE - Survey
label | CONFORMANCE CRITERIA - As per specification
label | ○ ±5mm level, ±10mm line for < 900mm
label | ○ ±10mm line & level > 900mm
label | FREQUENCY - Each Lot
label | RECORDS - Survey
label | BY - SS
checkpoint | Work Complete
label | TYPE - Written
label | CONFORMANCE CRITERIA - Field work complete, subject to any outstanding test results being within allowed tolerance
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - SS, INSP
checkpoint | Lot Closed
label | TYPE - Written
label | CONFORMANCE CRITERIA - Lot conforms to specifications
label | ○ All NCRs actioned and closed
label | ○ All test results available
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - PM
checklist | 201-ITP-008 Earthworks & Site Won Materials | [5 empty] | 201-ITP-008 Earthworks & Site Won Materials-V1
section | EARTHWORKS & SITE WON MATERIAL
checkpoint | JSEA
label | TYPE - Written
label | CONFORMANCE CRITERIA - JSEA prepared and signed off
label | FREQUENCY - As required
label | RECORDS - JSEA
label | BY - SS
checkpoint | Survey
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Drains set out for excavation
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | ○ Photos
label | BY - SS
checkpoint | Rip and Compact existing surface
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Specification
label | ○ Drawings layout and pavement types
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | ○ Photos
label | BY - SS
checkpoint | Site Won Material
label | TYPE - Visual & Written
label | CONFORMANCE CRITERIA - Witness Point
label | ○ Confirm extents and location of referred alluvial materials to be won
label | ○ Quantify excavation amounts and used amounts
label | ○ Test Samples: CBRs, plasticity and grading
label | Hold Point
label | ○ Visual inspections of material to confirm suitability; testing required to generally comply with C213.36
label | ○ Monitoring of processing materials to ensure consistency and usability
label | FREQUENCY - As required
label | RECORDS - Witness Point
label | ○ Record
label | ○ Photos
label | ○ Test results
label | ○ Hold Point when lay and compacting
label | BY - SS, PM, INSP
label | REMARKS - Maximum lifts of 200mm of SMZ layers provided as relaxation.
holdpoint | HOLD POINT / WITNESS POINT
checkpoint | Construction
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Specification
label | ○ Drawings layout plan & notes
label | ○ Conforms to design lines
label | ○ Modify to match drainage structures where necessary
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | ○ Photos
label | BY - SS
checkpoint | Work Complete
label | TYPE - Written
label | CONFORMANCE CRITERIA - Field work complete subject to any outstanding test results being within allowed tolerance
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS, INSP
checkpoint | Lot Closed
label | TYPE - Written
label | CONFORMANCE CRITERIA - Lot conforms to specifications
label | ○ All NCRs actioned and closed
label | ○ All test results available
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | ○ Photos
label | ○ QTY Records
label | BY - PM
checklist | 201-ITP-009 Pavement | [5 empty] | 201-ITP-009 Pavement-V1
section | Pavement [TYPE 3]
checkpoint | Authority to Proceed
label | TYPE - Written
label | CONFORMANCE CRITERIA - Underlying lots closed
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - CQR
checkpoint | JSEA
label | TYPE - Written
label | CONFORMANCE CRITERIA - JSEA prepared & signed off
label | FREQUENCY - As Required
label | RECORDS - JSEA
label | BY - SS
checkpoint | Material source assessment
label | TYPE - Written
label | CONFORMANCE CRITERIA - Hold Point
label | ○ Specification
label | ○ Material delivered for testing for source approval
label | FREQUENCY - Per material source
label | RECORDS - Hold Point
label | ○ Checklist
label | BY - PM, SR/INSP
holdpoint | HOLD POINT
checkpoint | Proof roll subgrade / subbase
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Hold Point:
label | ○ Visual deflection monitoring shall consist of proof rolling with truck dual wheels with a minimum axel weight of 9 tonnes which does not reveal any visible deflection
label | FREQUENCY - Each lot
label | RECORDS - Hold Point
label | ○ Checklist
label | BY - SS, INSP
holdpoint | HOLD POINT
checkpoint | Placement
label | TYPE - Visual
label | CONFORMANCE CRITERIA - DGB20 Layer thickness 100mm
label | ○ Blend into existing when no site won material is reused.
label | ○ Ensure segregation of material does not occur
label | ○ No placement on wet subgrade
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | ○ Photos
label | BY - SS
checkpoint | Compaction & Material Properties
label | TYPE - Written
label | CONFORMANCE CRITERIA - Specification
label | ○ Drawings layout plan & notes
label | ○ 100% STD compaction
label | FREQUENCY - 1 per 500m2, With minimum 3 tests per lot.
label | RECORDS - Test Results
label | ○ Checklist
label | BY - SS
checkpoint | Geometrics
label | TYPE - Survey
label | CONFORMANCE CRITERIA - Specification
label | ○ Straight edge deviation 10mm lower, 5mm upper
label | ○ Vertical tolerance ±15mm
label | FREQUENCY - As required
label | RECORDS - Survey Records
label | BY - SS
checkpoint | Work Complete
label | TYPE - Written
label | CONFORMANCE CRITERIA - Field work complete subject to any outstanding test results being within allowed tolerance.
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS, INSP
checkpoint | Lot Closed
label | TYPE - Written
label | CONFORMANCE CRITERIA - Lot conforms to specifications
label | ○ All NCRs actioned and closed
label | ○ All test results available
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | ○ Test results
label | BY - PM
checklist | 201-ITP-010 Rock Placement | [5 empty] | 201-ITP-010 Rock Placement-V1
section | Rock Placement
checkpoint | JSEA
label | TYPE - Written
label | CONFORMANCE CRITERIA - JSEA prepared & signed off
label | FREQUENCY - As Required
label | RECORDS - JSEA
label | BY - SS
checkpoint | Survey
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Survey set out of placement area
label | FREQUENCY - As required
label | RECORDS - Survey
label | BY - SS
checkpoint | Construction
label | TYPE - Visual
label | CONFORMANCE CRITERIA - Witness Point
label | ○ Correct sized rock to be placed in completed drain profile and or revetment area to specification
label | ○ Rock placement to conform to IFC drawings
label | ○ Rock placed on geofabric where shown on drawings
label | FREQUENCY - Each lot
label | RECORDS - Witness Point
label | ○ Checklist
label | BY - SS
holdpoint | WITNESS POINT
checkpoint | Geometrics
label | TYPE - Survey
label | CONFORMANCE CRITERIA - Rock placed to line and level as per IFC drawings
label | FREQUENCY - Each Lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Work Complete
label | TYPE - Written
label | CONFORMANCE CRITERIA - Field work complete, subject to any outstanding test results being within allowed tolerance
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS, INSP
checkpoint | Lot Closed
label | TYPE - Written
label | CONFORMANCE CRITERIA - Lot conforms to specifications
label | ○ All NCRs actioned and closed
label | ○ All test results available
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - PM
checklist | 201-ITP-011 Road Furniture | [5 empty] | 201-ITP-011 Road Furniture-V1
section | Road Furniture
checkpoint | JSEA
label | TYPE - Written
label | CONFORMANCE CRITERIA - Prepared & signed off
label | FREQUENCY - As required
label | RECORDS - JSEA
label | BY - SS
checkpoint | Survey setout
label | TYPE - Written
label | CONFORMANCE CRITERIA - Setout to correct locations as per IFC drawings
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Materials
label | TYPE - Written
label | CONFORMANCE CRITERIA - As specified
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | ○ Delivery docket
label | BY - SS
checkpoint | Installation of Footings
label | TYPE - Written
label | CONFORMANCE CRITERIA - As per IFC drawings
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - SS
checkpoint | Erection of Signs
label | TYPE - Written
label | CONFORMANCE CRITERIA - Witness Point
label | ○ As per IFC drawings
label | FREQUENCY - Each lot
label | RECORDS - Witness Point
label | ○ Checklist
label | BY - SS
checkpoint | Work Complete
label | TYPE - Written
label | CONFORMANCE CRITERIA - Field work complete
label | FREQUENCY - Each lot
label | RECORDS - ITP
label | BY - SS, INSP
checkpoint | Lot Closed
label | TYPE - Written
label | CONFORMANCE CRITERIA - Lot conforms to specifications
label | ○ All NCRs actioned and closed
label | ○ All test results available
label | FREQUENCY - Each lot
label | RECORDS - Checklist
label | BY - PM