## Master List Templates
Id | Type | Name | Values | Prompting Name
1a2fff2a-d08e-4b2a-8e91-1b2c3f147aef | checklist | Add Daily Cassette Log |  | Daily Cassette Log -
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
321425a7-94be-4be2-b9a0-e78e47941e5b | checkpoint-no-value | Date:
e5ab19af-90b5-4328-9a8b-ee0707087643 | textbox
f1323933-0487-418a-8506-5c82bad6e7c7 | checkpoint-no-value | Cassette Number:
8e11a44b-51f7-4a8f-9494-ec9e467452ec | textbox
d505f606-dacc-47d3-8a82-efa5a7cff62a | checkpoint-no-value | Record any delays:
22cd20b8-86af-49a9-97d4-39d5b860ca1a | textbox
5b450e26-aabb-4816-b46c-58c2e60bfd44 | checkpoint-no-value | Wind/Weather Conditions:
5114a122-dcf7-44a7-be38-8623182196af | textbox
ec5e4a74-6b69-421b-b838-cfba7a7b03b2 | checkpoint-no-value | Comments/Issues/Observations:
a6aebd36-6433-4aca-b8f4-ef6216c059cf | textbox
968d117f-840b-4ed6-bf20-322e59ce807b | checklist | Add Dayworks Checklist |  | Dayworks -
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7b5360d7-b44c-4805-a188-53ed39a97e68 | checkpoint | Day Work Details
d27d8079-cce6-47f2-bc8f-5447bd0b63c3 | textbox | NTSC / SI #:
d63889f7-ee5a-4b1a-8284-614d5f938189 | textbox | Labours (HR)
926bb36c-59db-4b70-828c-6bc1bf2ce049 | textbox | Work Description:
693bbb1a-ade5-4140-a549-223cae16f4cb | textbox | Materials:
6d1abe7d-16c2-45ff-b354-7f74775359b8 | textbox | SWP Representative. Prepared By:
7e548609-67fa-4b3f-91fa-027d546e556f | textbox | Client Representative. Confirmed By:
7c9eb4c5-3467-404e-bb3b-b5a3f3bf2fbc | signoff | Request Signature Signoff
b7933698-5149-4db3-98df-6de64387748f | checklist | Add Defect Checklist |  | Defect -
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a4870e12-5081-4f72-b482-ffcd64cd1cd0 | checkpoint | Defect details recorded
9b18e909-7530-4d08-ad54-acb417409980 | textbox | Explanation of defect:
3af60290-922d-4e09-aeb9-b795186cbbd5 | textbox | Area:
da7b5fcc-182d-4ccf-ade5-02dfaae6dedb | textbox | Party responsible for damages:
f37cdc9e-47d2-43c7-b8ce-36034d624bbc | textbox | Efforts required for repair:
16d78d9b-0a7d-4e07-bb38-68e664e6d30e | textbox | Man hours required for repair:
b3439fc9-2c5e-441b-9d46-b70dcd0b067b | signoff | Request Approval from Main Contractor
0d234556-1399-499a-ae6a-428b9a3a845e | checkpoint | Defect Fixed
366206e8-e21f-4d9c-9a15-07583196b25f | signoff | Request Defect signoff
038fa8aa-e288-4712-a6f4-dc61023cf4d7 | checklist | Add Delay Checklist |  | Delay Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
782f8160-e48e-41f9-bc6a-9ddd18006c89 | checkpoint-no-value | Delay details.
ae5b692f-ee75-4a3d-90e7-43a6b2bca49e | textbox | Date:
8e11a44b-51f7-4a8f-9494-ec9e467452ec | textbox | Description:
22cd20b8-86af-49a9-97d4-39d5b860ca1a | textbox | Area/Grids:
e5ab19af-90b5-4328-9a8b-ee0707087643 | textbox | Wind/Weather Conditions:
96bc9561-07c1-49ef-a284-ebec36ee05c2 | checklist | Add Final Inspection Checklist |  | Final inspection
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
dd3b14a1-d91a-4486-b2ae-996bc7348a50 | checkpoint | Final inspection
5c48b2f9-7155-5010-a625-9c61273b1f4a | textbox | Date
cd590b2d-dfd9-5926-aa7f-cbbffee96ba3 | textbox | Area/elevation/grids
f185db39-ef5a-566f-a627-b84ed061402b | textbox | Description
bc73c8d4-7e08-5fa4-a4f2-97028cc937d1 | note | Attach Photos
2dbc8c3d-f85b-4323-836c-a0bc406ba0e5 | signoff | Request Signature Signoff
79588131-363d-4444-aeb2-90061d840d5c | checklist | Add Flood Testing Checklist |  | Flood Test Area:
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
89dc2a73-6624-4553-ad0b-82f8a358612d | checkpoint | Is area fully finished, QA’d and ready to be tested
4029d5cc-8d7e-4a63-8bd6-c88c7c3e8f80 | checkpoint-no-value | Flood test details
dc968f8f-9cf1-485a-a65f-e4087427ee32 | textbox | Date:
b0fb2bc4-3c3c-47bb-93fe-add4a651804d | textbox | Area tested:
befd486d-6456-4e39-ba95-1395566ebfda | textbox | Duration:
3fff6840-5866-4f4c-96c8-494f7e9efd79 | button | Have you checked regularly for leaks | Yes, No, N/A
050fef10-15f2-4590-ba62-2a0b1b1b0a29 | button | Is there rain in the forecast | Yes, No, N/A
b9de0cd4-9c7a-42cb-89ee-535d7ebdcd00 | button | Have all leaks been repaired | Yes, No, N/A
c46e1a0d-81aa-40c6-b80e-d24049a89e25 | checkpoint | Flood test complete
5d04628a-e7a1-4bd7-b9ee-92a88ef12e94 | button | Have the plugs been removed from the drains | Yes, No, N/A
b74c91b9-0371-4641-ad5b-1c9d76ee0c77 | button | Debris and materials removed from the gutter/membrane/roof | Yes, No, N/A
292fd899-b6d2-49ed-9905-69a723b5db29 | signoff | Sign Off
3e5d6867-7b74-4b94-84ba-516fecaa0c8d | checklist | Add Variation Checklist |  | Variation Details -
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
dfc1c769-8831-4b63-b5ba-ab241c239b57 | checkpoint | Variation Details Approved
28d26279-c304-4689-8317-1deb797dc8fe | textbox | Reference/Drawing/Instruction Number
2247155b-6de8-434c-a1e1-058d724a6a62 | textbox | Variation Area
ae7fc046-dca9-4fab-98f8-374caeb044ec | textbox | Materials & labour breakdown
fde69a37-90a5-43eb-ad5d-bdf3a5b03775 | signoff | Request Variation Acknowledgement
2c0d558f-9276-4de7-aac4-3ae894a54005 | checkpoint | Variation Completed
2d02ce28-b78c-4140-b365-4ee5029b40a9 | signoff | Request Variation Signoff
1eeacef6-d140-43e0-9f5c-7c66100941c8 | checklist | FiberTite to concrete checklist |  | FiberTite to concrete checklist
3088bfca-6f54-43ef-85ba-79d7c828354d | section | Pre start
5739858a-a600-4eac-8d8f-1e316352d9ef | checkpoint | Area accessible
8ea0587e-926e-4424-905d-7db8edd35a13 | checkpoint | Edge protection and safety installed
5b04e09d-fba5-4bdc-a99c-48524883ccf1 | checkpoint | Visual inspection of substrate ready for SWP
46b421cc-bf2a-45af-ac81-c4a1973e65da | checkpoint | QA document received from previous trade from main contractor
dd290e0f-94ed-4f6d-a711-aa0c9982cfd1 | checkpoint | Large holes filled with grout by others
e5c3a331-c16a-4f83-914b-d5af8a68b9e5 | checkpoint | All lumps and sharp concrete bits ground/hammered down
1afe1919-c1da-41f0-bbe6-875ea4fdd723 | section | Concrete substrate
1f7affc5-0899-4e01-b550-b6b3c62959eb | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
ff5df835-05a7-4921-ade9-bf866f51aa48 | section | FiberTite
829a78f9-9d76-4408-8232-4bcd166d98e5 | checkpoint | Prime substrate where required
1359e390-9f2e-4c04-bf3b-9e756d94b9b9 | checkpoint | Adhesive installed to substrate
0378273c-fbdd-4d67-a538-51a1cb0c8e7b | checkpoint | Laying of membrane into adhesive
0743d8e8-7ec8-46af-b8d4-9160a29c0371 | checkpoint | Broom/rolling of membrane
8e7bb147-2bd5-432e-8dc3-5f4d9150fafa | checkpoint | Wipe and clean laps prior to welding
b2c62fb8-8b98-4278-b0cd-cafc823c90f7 | checkpoint | Test weld with welding machine
8177b086-107b-40e7-b50d-f0092e01d38a | checkpoint | Probe of seam with QA hook
ab5ecf1d-5a82-402e-b472-9c003d5aeb2d | section | Sumps
e9d6d077-f298-4b50-804a-98bc2f427715 | checkpoint | Sealant installed to dropper flange under membrane
5794a1e1-92f8-447d-bdba-a8a0fcdda1f3 | checkpoint | Membrane dressed in to outlets
4c397b80-0567-4b80-9c72-b7c1fbe4de8e | checkpoint | Clamp/rings/basket installed
32bce821-8c07-47fc-b306-2e4e11b763ac | checkpoint | Flood test
166be4b9-cd5f-46b9-97db-3ad0fbb23b9a | section | ILD report
97b2786b-abf4-4245-b6a4-d7326aab1cda | checkpoint | ILD report
ed7f1c03-81a5-479d-ae82-95f11da33eb9 | section | Fiberclad flashing
32da4df2-8fa6-4805-a1d7-e51b0dff977e | checkpoint | Installed correctly according to specifications ( right way around )
cab01d8d-ba9a-4d2c-a016-a0958eef8f0d | checkpoint | Fixing and welding done according to specifications and details
b9e74125-2dec-4b7d-a896-016ef34568cd | checkpoint | Probe of seam with QA hook
e3d69b7f-3b7c-4026-bbb3-700bca0d9d8c | section | Pressure bar installed
4d82d0a0-881e-4d1a-b7b5-4d8a9901dd87 | checkpoint | Installed correctly according to specifications ( right way around )
7766120a-5f82-45a4-9a0e-d7ee197c778c | checkpoint | Fixings done according to specifications and details
ef841394-4008-4a93-a6fa-7fbae7d03330 | checkpoint | Prime of Substrate where required
e727cad0-db56-4b23-8340-8d5bf147f56e | checkpoint | Sealant installed
c107cfbf-985a-4362-bde6-efa131a40bb5 | section | Over flashings
e470339a-05c6-472d-abed-60aa82925fbf | checkpoint | Over flashings has a separation barrier
938fa780-51cc-4aba-b1b6-4197f44497d9 | checkpoint | Fixings done according to specifications and details
8285512f-7d10-4cc9-87d7-7c304d2c67c9 | checkpoint | Primer of Substrate
101a1353-fa92-4c3c-9e66-3f5d9e3f739b | checkpoint | Sealant installed
612f27d2-33a0-49bb-a045-05cb8ae9a4cd | section | Review and sign off
7a1909a9-e22b-4ac6-97ce-e1cf5307b9e5 | checkpoint | Area left clean and tidy
3393e358-a54e-489a-9a89-ad1932955656 | checkpoint | All installation work completed, checked and reviewed as per specifications
e1c4328a-7c7c-40ad-886e-8b935e221fdd | signoff | Client/main contractor sign off
1de77c43-f5b0-4b19-8938-4b89b8027784 | checklist | FiberTite to plywood checklist |  | FiberTite to plywood checklist
e597f651-b7cf-4197-b1a3-47d65229f8c4 | section | Pre start
b1a266d8-5c97-48ec-bed3-c6dafbbb70df | checkpoint | Area accessible
6438325d-8c46-462f-a142-e50ca436dc56 | checkpoint | Edge protection and safety installed
a05e0a4b-10c8-4e49-b627-dc5b5683b253 | checkpoint | Visual inspection of substrate ready for SWP
f4a1c833-e30b-4d3c-8d41-86d06bd71bd9 | checkpoint | QA document received from previous trade from main contractor
a72d1446-cf15-4ad5-8c7c-034e3dcef7ba | checkpoint | Visual check no screws/nails/fixings popping up
8e564863-d52b-4d33-a034-f6e22cb23c61 | checkpoint | Visual check that joints are flush and even
b45aef9e-67b7-49ce-aea2-1c9278c8a72a | section | Plywood Substrate
8a95ca85-b187-4848-bca5-29e82114b287 | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
56531c07-c6f1-40fd-8d2b-aa699322c21f | section | ILD Mesh System installed
f31b2e04-d74c-4952-bff2-70731f59ab07 | checkpoint | ILD System installed as per specification
d45757cb-2fba-4d07-a162-1deede9fc226 | checkpoint | ILD test plate installed
f8c63576-ca2f-4681-b704-38484db9da38 | section | FiberTite
ca39d303-81c9-4625-9b1a-b538655968a0 | checkpoint | Prime substrate where required
5cb9d079-ee83-49d2-9f50-bb0ec8a05347 | checkpoint | Adhesive installed to substrate
a64b0754-9b9c-4745-82db-c412960bba0d | checkpoint | Laying of membrane into adhesive
0d979b2d-ea08-4096-8e5e-ef301ef498f2 | checkpoint | Broom/rolling of membrane
d44b70f0-1255-4548-acd8-7f58aca42169 | checkpoint | Wipe and clean laps prior to welding
d5545d88-dcac-4d67-ada4-bbd33834112d | checkpoint | Test weld with welding machine
0e8b7478-e822-408d-9c57-9356fef9a043 | checkpoint | Probe of seam with QA hook
68b4756a-5c78-4305-9148-3624a1324e5c | section | Sumps
5e2c3ded-71a1-4499-bb81-c16d507d0a8b | checkpoint | Sealant installed to dropper flange under membrane
467de2ff-543f-4918-bace-299c3617bd79 | checkpoint | Membrane dressed into outlets
4c817c61-8624-4825-9477-ffc6459fbf0f | checkpoint | Clamp/rings/basket installed
9b5520d9-d007-4d44-bb04-59c11f84fda8 | checkpoint | Flood test
8cdc850a-3286-4d8f-bb3d-a29c4019e179 | section | ILD report
23e70349-2898-428e-bcc1-c2bb5c2eb376 | checkpoint | ILD report
0e6af602-72f5-4495-9265-08a2dcb82baf | section | Fibre clad flashing
06f92e53-b30f-4323-8cd2-6b102aebc14d | checkpoint | Installed correctly according to specifications ( right way around )
2e750f46-c942-4756-afec-0a7d82bb28eb | checkpoint | Fixing and welding done according to specifications and details
eaa7e6c2-d348-41ce-ab27-77329bc05dd5 | checkpoint | Probe of seam with QA hook
5ea0ec9e-d90b-4400-ae88-83227a5d5070 | section | Pressure bar installed
a6c0b4f8-6f2d-4963-9b7e-f594a848ea7e | checkpoint | Installed correctly according to specifications ( right way around )
009953a8-f85f-43d8-9a1e-c946987b3e0d | checkpoint | Fixings done according to specifications and details
362e6266-400f-4239-9ca1-566885e7d3ac | checkpoint | Prime of Substrate where required
eee6e8f0-babb-4576-afc7-25a263c94df3 | checkpoint | Sealant installed
e0620ea5-a64c-4fbb-8c7d-c54648b962c9 | section | Over flashings
9f279fd7-315c-486e-9917-301f7aa13d3e | checkpoint | Over flashings has a separation barrier
3996b49b-a2aa-447f-9f50-5aed5a0c63e2 | checkpoint | Fixings done according to specifications and details
23737ed0-8c5d-4f43-8c9a-390148b2b2db | checkpoint | Prime of Substrate where required
99eb4e45-36c4-4950-98e5-71f010a909de | checkpoint | Sealant installed
ef8a5f66-9cde-487c-b5f7-a38000c9d3f6 | section | Review and sign off
3add357d-82c9-4f77-a73d-0f0e9499b27d | checkpoint | Area left clean and tidy
25458fc0-a7ef-41f3-8483-1270d8440264 | checkpoint | All installation work completed, checked and reviewed as per specifications
e7d1bae9-774d-4786-af13-b84a0d288651 | signoff | Client/main contractor sign off
675e5e65-2d8a-4f1f-9bfc-3a24b61fdd24 | checklist | FiberTite to plywood warm roof checklist |  | FiberTite to plywood warm roof checklist
6dd62f2e-4510-4da7-a1b2-399787f2f0d7 | section | Pre start
5d7d7a40-0a40-49c4-b936-cb4f2f316910 | checkpoint | Area accessible
0ba5e497-6c9e-40e4-bf75-21de8d44c36b | checkpoint | Edge protection and safety installed
0eaa1251-4d37-4746-8457-64c51ae6a548 | checkpoint | Visual inspection of substrate ready for SWP
ba4c7f07-4502-4d3f-8f70-b039c20d37c6 | checkpoint | QA document received from previous trade from main contractor
fc47a929-7009-418a-99cc-82578453571f | checkpoint | Visual check no screws/nails/fixings popping up
c3d353b8-0171-4cf9-927a-e53dbe67935c | checkpoint | Visual check that joints are flush and even
572021ef-ea6d-400f-acc4-c3f26393030f | section | Plywood Substrate
6b871e79-1277-4409-ab11-e39bb5c0d4e2 | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for VCL
2cd39232-80e3-4bce-bf39-f85f2496836e | section | Vapor control layer
5aefaffd-805a-4042-94c1-6f8198a92acf | checkpoint | Substrate clean, dry, free of debris
62e16807-6401-41b1-84af-4475b51ab751 | checkpoint | Z flashing installed
00f01f75-7421-448a-b242-15ac630a1b25 | checkpoint | VCL installed and covered all surface
2b2ccddb-a842-4169-956c-bc40d8bbcaab | checkpoint | VCL lapped with a minimum of 100mm side and end laps
13025fc4-e428-427e-ad01-f2f013a26b5e | section | Insulation
536417d3-6e81-4550-86b2-8efa0d9068de | checkpoint | VCL clean, dry, free of debris prior to install
7860c28a-6f45-48ab-93e9-538948b7532a | checkpoint | VCL has been checked for damages and repaired
c4b4c180-85ab-4c6c-8f16-bd61733db162 | checkpoint | Closure flashings installed correctly
02b4246c-0cd4-4282-8aee-a491421151e7 | checkpoint | Specified insulation board installed
a75a2080-0f67-4a81-8c20-1bfa9bf7c1fb | checkpoint | Boards tightly butted
f67a323d-1c4b-4437-8645-4de5f8a77d63 | checkpoint | Fixing plan attached
efb3b022-cf8f-4f8a-b5af-c638016c1d25 | checkpoint | Installed as per fixing plan if no HDP board
5a996323-f28c-4d2c-b875-2c9996696e92 | section | ILD system installed
da63a8d6-3ac3-4868-82b4-6575628e95ba | checkpoint | ILD System installed as per specs
9b51c42c-1f63-4c33-9517-b05bf7ebd021 | checkpoint | ILD test plate installed
709073e0-6a5c-451a-8879-073005b3c376 | section | HDP board
68f97c87-f5e4-4c97-861c-e132b57f39f4 | checkpoint | PIR clean, dry, free of debris prior to install
f40b29f0-8eb9-4ddc-93ee-29cc61ffda03 | checkpoint | Fixing plan attached
a64a021b-76f3-461a-9d88-11e5f73c0ebe | checkpoint | HDP installed tightly butted in brick pattern
d670e1e8-5462-4bc1-a4f4-555eaf2c69a2 | checkpoint | Installed as per fixing plan
0df22fda-209d-448e-a72d-cf5d27754dd7 | section | FiberTite
31a3dc2d-d719-47b8-b769-5cf9f5afdd0e | checkpoint | Prime substrate where required
b06a30c1-1ba3-4d00-b7c2-b7845bd96c23 | checkpoint | Adhesive installed to substrate
3844c5e6-ba3b-4c74-acb5-9c4b2f1d2095 | checkpoint | Laying of membrane into adhesive
91490883-9260-4897-a644-dcbef85a5106 | checkpoint | Broom/rolling of membrane
94c4a879-66da-4a86-ab1e-64ef176be780 | checkpoint | Wipe and clean laps prior to welding
c2ac0d9e-d927-4718-8e72-6228db19305a | checkpoint | Test weld with welding machine
2eb26f80-44a7-466c-b556-ebd995c98ccd | checkpoint | Probe of seam with QA hook
093ade4a-174a-4488-b13a-a30a51341968 | section | Sumps
503e2c5e-8e20-465a-b351-d720235e473a | checkpoint | Sealant installed to dropper flange under membrane
9c19ed3b-8fa6-45b3-81f1-911c7a55b395 | checkpoint | Membrane dressed in to outlets
17d19bdf-1c9c-4dda-a450-8b9bbb446811 | checkpoint | Clamp/rings/basket installed
cd9f3794-ff8c-4f39-8139-79e648da6db3 | checkpoint | Flood test
fb600f1f-1711-46ac-9e84-95b8fdff27df | section | ILD report
c27eef68-0cc9-47dd-9eda-5b7d35b782d1 | checkpoint | ILD report
747c8075-80f9-465e-ab5e-645b87dcb1c5 | section | Fibre clad flashing
1e2a64ff-bb75-4c43-96f9-07d1a536356b | checkpoint | Installed correctly according to specifications ( right way around )
e4b90229-df5e-45be-bc82-50755cd05018 | checkpoint | Fixing and welding done according to specifications and details
ff2992dc-eab0-403f-beba-48764e8fc4b5 | checkpoint | Probe of seam with QA hook
92d504a5-d559-4765-b29e-4e5f8e2d92a2 | section | Pressure bar installed
3fc99d1b-1b13-49fe-88af-68c8a90314fd | checkpoint | Installed correctly according to specifications ( right way around )
7ddd2b60-c618-49c0-86d7-c177babbb6e9 | checkpoint | Fixings done according to specifications and details
6db40763-7b8b-4d6a-b21f-51778dcaa9a6 | checkpoint | Prime of Substrate where required
90a07e2d-9312-4868-93d0-b2f97084be62 | checkpoint | Sealant installed
a66391d2-6b04-455c-b031-0c908c578d4a | section | Over flashings
bb8c7a56-7bf4-44c2-9345-5d834893339b | checkpoint | Over flashings has a separation barrier
cee9eeca-f435-415c-8713-f395a1cae8c4 | checkpoint | Fixings done according to specifications and details
8a6fe777-5989-473b-85d6-7366d8bd13ea | checkpoint | Prime of Substrate where required
7d9d3ddf-3be1-4e62-8103-7c1f9c102b2c | checkpoint | Sealant installed
29417431-7a98-4a08-8f05-6d5a9acface7 | section | Review and sign off
a13157be-e7e0-43d0-8927-7afe2d5d3d50 | checkpoint | Area left clean and tidy
6c8ad148-e5e9-48dc-bc46-2fc9c8d48441 | checkpoint | All installation work completed, checked and reviewed as per specifications
10c992f5-fef5-4753-92dd-1381266c33ec | signoff | Client/main contractor sign off
04fc3bb6-ee8d-4297-9ccf-02cd206a935f | checklist | FiberTite warm roof to Base deck checklist |  | FiberTite warm roof to Base deck checklist
cd742c9c-4703-42a4-9526-35bbc15e9627 | section | Pre start
c0d3f467-1251-4fda-8236-d77bf177cce7 | checkpoint | Area accessible
8f69cc2e-1f90-42a0-997c-0e254f5094f3 | checkpoint | Edge protection and safety installed
79a2f5f2-f530-4c0f-8014-3edef69a0392 | checkpoint | Visual inspection of substrate ready for SWP
c8dd9889-55ff-4ae5-ba0b-0da80db065fc | checkpoint | QA document received from previous trade from main contractor
61cdf6f0-87e1-49a0-8d4b-c9efd9a005aa | section | Metal deck
bb23eae0-2f77-4764-ae9f-5740b8632256 | checkpoint | Base deck screwed down in every pan and every purlin
684c0cda-86b6-4418-bf6d-cf069193d683 | checkpoint | Base deck laps stitched together at 300mm centres
b19a19d5-8527-4d7e-9d23-0017e9b58f6f | checkpoint | Correct fixing
d9bde373-b77d-46e5-a37e-37110a0bd287 | section | Vapor control layer
91bd4fb6-8e1c-4dd2-9eff-6440cd51e2c8 | checkpoint | Substrate clean, dry, free of debris
bd25cf24-bc54-4e87-a352-231018df367a | checkpoint | Z flashing installed
8a067962-437b-4eb5-94b0-9ad595f74454 | checkpoint | VCL installed and covered all surface
039e7fc0-2041-4f42-8133-1953d25a1ac3 | checkpoint | VCL lapped with a minimum of 100mm side and end laps
8c8cfee7-842d-4219-a4cd-1dbae096cbc8 | section | Insulation
a089b67e-4ff8-4d8a-b5da-e694ac89ff87 | checkpoint | VCL clean, dry, free of debris prior to install
de64e00f-01e3-4f97-b211-e046928a4b2e | checkpoint | VCL has been cheeked for damages and repaired
9bd8c1ca-811d-4a78-b4a1-ca4501ab9d95 | checkpoint | Closure flashings installed correctly
6f85a248-dd4d-4d63-b1fc-465c4edd0a56 | checkpoint | Specified insulation board installed
c1f464af-7a08-473d-afcf-9dbec9a402f6 | checkpoint | Boards tightly butted
3d021913-c0ba-4b4f-942d-e9af00a7a46d | checkpoint | Fixing plan attached
ea1216f9-d343-4a81-8abe-03ad3db7d914 | checkpoint | Installed as per fixing plan if no HDP board
26d062c4-392f-4456-bdc3-f6af6f09c3f7 | section | ILD system installed
a1e76c68-ae74-4fb7-ab3f-36b792f5ff34 | checkpoint | ILD System installed as per specs
77cbdbd8-661e-4eb0-b0a5-92ceca8b92d3 | checkpoint | ILD test plate installed
7dfdc065-87d7-45a0-807f-9a0f60cece72 | section | HDP board
744eba48-1652-46db-b259-d5c8ead136b5 | checkpoint | PIR clean, dry, free of debris prior to install
bfd25121-c304-4dcf-bed9-4cc343594898 | checkpoint | Fixing plan attached
8196b450-ddf1-4cff-bc91-d8c83ffd487c | checkpoint | HDP installed tightly butted in brick pattern
5523fedf-49e5-4ec7-b497-435765e8677f | checkpoint | Installed as per fixing plan
a51f726f-ab5b-4904-ad4a-cdc7f16b747e | section | FiberTite
93ab67b9-4204-4522-900e-d2c0952bb9fe | checkpoint | Prime substrate where required
9c7ac83b-2fa7-456f-bf2c-e727cb89d563 | checkpoint | Adhesive installed to substrate
40cbbacf-eb34-4872-9ffe-8ce0ea34c824 | checkpoint | Laying of membrane into adhesive
404859e9-f4d1-4f9e-9436-d4631301ef86 | checkpoint | Broom/rolling of membrane
f2e57eca-7100-4904-9a29-e31c5118beb6 | checkpoint | Wipe and clean laps prior to welding
f79ed159-1f5f-4020-9fc8-f9a3b5f926fe | checkpoint | Test weld with welding machine
582e91ee-97cd-465e-bade-32a7a2775cd6 | checkpoint | Probe of seam with QA hook
f65f10a3-2053-4ba6-bfa6-9ab26dde8a60 | section | Sumps
827c87e3-7b9b-451e-8d4e-cf51bd646d6f | checkpoint | Sealant installed to dropper flange under membrane
fe9e2661-b920-4a74-b2e5-e0bdeecf9dde | checkpoint | Membrane dressed in to outlets
6eb15891-d301-48fb-a0e7-456687587e94 | checkpoint | Clamp/rings/basket installed
c92a4b41-f1cc-4590-9f4f-87aac2a523a3 | checkpoint | Flood test
8573a631-50be-4337-ba34-f6c69acfed46 | section | ILD report
8f82e8f9-0d4e-4121-8efb-9a73ec5c3931 | checkpoint | ILD report
7b7c4524-c411-4998-a36d-0fffbadb0a64 | section | Fibre clad flashing
5bc7e2ae-bf89-4b9b-9822-fd58743a5a77 | checkpoint | Installed correctly according to specifications ( right way around )
bd9a92b9-09ad-40fb-9d84-a79ada6f771d | checkpoint | Fixing and welding done according to specifications and details
73c2a4a5-0240-425b-a580-26ea782a10e6 | checkpoint | Probe of seam with QA hook
3c130288-e167-4911-9788-ebe842540581 | section | Pressure bar installed
bd2026af-11ee-4704-b719-d3a158cae305 | checkpoint | Installed correctly according to specifications ( right way around )
fe0c9bf8-88ce-49b8-b8ca-382e32a75151 | checkpoint | Fixings done according to specifications and details
e619e70b-d450-480f-a740-f61578f66580 | checkpoint | Prime of Substrate where required
0f7443b8-78b4-4029-9525-50c552d49b98 | checkpoint | Sealant installed
dd9a68ce-7180-4d77-9710-c498fc9321ad | section | Over flashings
8591ae6e-2358-4870-93ec-5d1e3efb077f | checkpoint | Over flashings has a separation barrier
26db565e-3728-4e90-a267-c1f73c4acbc0 | checkpoint | Fixings done according to specifications and details
45a1016f-7307-48e4-8e9a-029634ea7243 | checkpoint | Prime of Substrate where required
15c83c4d-c2b4-44c3-94ed-397fa04eb224 | checkpoint | Sealant installed
1ccf01b2-c844-4a25-a09d-dc3f5548341f | section | Review and sign off
0b22f824-af1e-4163-9282-bf9134cf930e | checkpoint | Area left clean and tidy
d20058d4-0a5b-4395-b4ee-5c22753e8aed | checkpoint | All installation work completed, checked and reviewed as per specifications
d669977f-785e-478b-816d-53b1405efc16 | checkpoint | Client/main contractor sign off
04e1e3a8-80da-449f-a512-dfd5130bcdce | checkpoint | All installation work completed, checked and reviewed as per specifications
5562da57-3511-4c9e-a0b8-4da4c25b1f97 | signoff | Client/main contractor sign off
1ce9a275-fd16-4f0e-91e7-bfe3426bb274 | checklist | FiberTite warm roof to CLT mechanically fixed and adhered checklist |  | FiberTite warm roof to CLT mechanically fixed and adhered checklist
c8a4b948-c454-408c-b6c7-163b836edaed | section | Pre start
8846217e-b354-430e-b5c5-884aff123f3b | checkpoint | Area accessible
309e6307-8a0d-4ee2-a3b4-ec0b660bfe95 | checkpoint | Edge protection and safety installed
97724b1b-8580-4810-b8da-40e28b8554e8 | checkpoint | Visual inspection of substrate ready for SWP
fc3e7a44-cfe4-4e60-a900-42b8156a2fe9 | checkpoint | QA document received from previous trade from main contractor
b3e2614a-77c4-40a4-8179-10e0247229d8 | section | CLT Substrate
bf3b5aeb-ef5b-4b3f-bf9a-b56a3144d527 | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for primer
e4a6149c-4714-4e5d-9a4b-56308ba4a30d | checkpoint | Installation of SA primer
39e079af-f0ba-4512-a86f-3f9ae76ce4d3 | section | Vapor control layer
2e717d13-aa4f-4557-bf34-eb9d71e265a0 | checkpoint | Substrate clean, dry, free of debris
845411a9-ccd5-48ac-9960-a5f0b9cf292a | checkpoint | Z flashing installed
2c2863b3-2f14-46d5-a181-3a9f41aceb89 | checkpoint | Install VCL over primer
628c2962-328e-4fa3-a446-ce00e5093b73 | checkpoint | VCL lapped with a minimum of 100mm side and end laps
c7acd7f7-1103-46e6-b68b-f471d0c592a0 | checkpoint | Installation of SA primer
089da43d-a92d-4b3b-9e5a-fb5ceddb72ca | section | Insulation
8bfb8da8-df33-4e0c-b5e4-6aa38260f3bc | checkpoint | VCL clean, dry, free of debris prior to install
712a0226-efa9-4b52-a2e9-120f3bf32023 | checkpoint | VCL has been checked for damages and repaired
48204a11-28db-4259-aea1-b54cc1a0c269 | checkpoint | Closure flashings installed correctly
5cd2c8de-b02a-4f74-a0bc-9a516b13c1fc | checkpoint | Install board adhesive in specified pattern
c30ff92b-89b9-491b-95ac-7a5bd6bdc89f | checkpoint | Boards tightly butted
9ae86308-0bc3-489c-8626-9bb9c1f46ce4 | section | Tapered EPS
bbd1b01c-65dd-4b19-a303-fc4b319fdde3 | checkpoint | Insulation boards clean and dry. Free from dirt/debris ready for adhesive
9b79cc5d-4546-4fc3-a1d6-64869ec4cbb6 | checkpoint | Install board adhesive in specified pattern
8dd6cc7f-827e-4ce9-b1ed-56a263228345 | checkpoint | EPS board installed into adhesive
3b2f5083-224d-4ffe-b588-a522c15ebf7c | section | ILD system installed
905bd55d-05e4-4b94-b03f-cfb795f38b50 | checkpoint | ILD System installed as per specs
8ba4e84d-4d56-4bd6-aaed-24a40bb41c13 | checkpoint | ILD test plate installed
8b454efa-092e-419b-bfec-214586cc0e4c | section | HDP board
6a5c94c9-701f-415a-8dd0-e5e5705c3b80 | checkpoint | PIR clean, dry, free of debris prior to install
04f00431-d92b-4dbb-afbc-2cf3776fc000 | checkpoint | Install board adhesive in specified pattern
e5dca2ca-6f4c-4750-8d4d-564aa8aade0a | checkpoint | HDP board installed in brick pattern where possible
ad6754c7-1269-4369-b3b2-b73bdfaff64d | section | FiberTite
4754f577-daf9-4339-91b6-792a24e8e49e | checkpoint | Prime substrate where required
0b2c64c0-094e-429a-a51f-f8066ff11830 | checkpoint | Adhesive installed to substrate
29198802-bb39-4298-bca4-01cc0210df18 | checkpoint | Laying of membrane into adhesive
0ee712ee-ef6c-4480-aa2f-3deb8ffa5df3 | checkpoint | Broom/rolling of membrane
6548e7bb-6bb8-4f24-b1f2-a2c07ef8d21a | checkpoint | Wipe and clean laps prior to welding
d8b16ff3-9567-498b-806c-53fb67261511 | checkpoint | Test weld with welding machine
48575782-0381-4be7-aede-9255dd544231 | checkpoint | Probe of seam with QA hook
64bcf540-990b-4114-97ac-d1ba328fe140 | section | Sumps
4e2ddfd0-9912-4685-ae91-c5dc741c2116 | checkpoint | Sealant installed to dropper flange under membrane
f3fbca30-a64d-498c-92af-9e6924d1523a | checkpoint | Membrane dressed in to outlets
3177aaaf-fcec-41ba-a7fd-ddd33156d959 | checkpoint | Clamp/rings/basket installed
184c6cb8-af78-4e56-a998-4ad57781c1d1 | checkpoint | Flood test
14f1190f-278e-494e-9b58-0811698c530a | section | ILD report
bdc96325-1a57-43e5-8ee5-d92bc366b692 | checkpoint | ILD report
9193a041-87d7-4816-b027-8bb9d0396116 | section | Fiberclad flashing
afcbf94c-97b6-496b-92db-f2f36ce3536a | checkpoint | Installed correctly according to specifications ( right way around )
61a967e9-b832-49dc-964c-5b40cc7aa16a | checkpoint | Fixing and welding done according to specifications and details
0b91964e-2b9a-46b2-86dd-2ef049ce0b42 | checkpoint | Probe of seam with QA hook
38acbcee-80ab-475c-8e1f-546b03c9c77c | section | Pressure bar installed
7072f772-fb7f-456e-bf6b-f01ae08751f2 | checkpoint | Installed correctly according to specifications ( right way around )
e887ee35-330b-4870-abe2-b2755d2614b1 | checkpoint | Fixings done according to specifications and details
10d1221a-4d29-4604-9f7a-ffe213c953ff | checkpoint | Prime of Substrate where required
27cb798e-ed38-4974-a21c-e605c1140527 | checkpoint | Sealant installed
96dc168b-7a6d-4d5d-9fcc-e5f2712fd45b | section | Over flashings
8d9095bb-fbb7-4afb-9f37-5d5d70b5bdc3 | checkpoint | Over flashings has a separation barrier
dbf01c90-958b-42b4-823e-210c48dc698d | checkpoint | Fixings done according to specifications and details
2d98be56-0148-427d-90b1-f33f2a3f4080 | checkpoint | Primer of Substrate
e7dd3e2c-6fb4-419a-9da9-3a847b5b5fd4 | checkpoint | Sealant installed
86a4d3e1-b634-4ce5-af84-45ad53411afa | section | Review and sign off
e283d462-2854-4e42-938b-c781ecf7d1d5 | checkpoint | Area left clean and tidy
8423db0f-388c-4b1a-bf2c-639288865ca1 | checkpoint | All installation work completed, checked and reviewed as per specifications
6102f46f-3d14-49ff-b4e2-aefaf952f220 | checkpoint | Client/main contractor sign off
c3e01c6a-015e-44c7-b75d-2c5e4dd9f873 | checklist | FiberTite warm roof to concrete fully adhered checklist |  | FiberTite warm roof to concrete fully adhered checklist
81152373-a506-4233-aa4c-99172d777f2d | section | Pre start
96475f53-9aa2-4fab-98b9-b3b9f5e8e65f | checkpoint | Area accessible
cbe4883e-e454-4e06-b0c6-5edabb4133ac | checkpoint | Edge protection and safety installed
42351308-5156-41e0-bb6e-9a59eab0d7cf | checkpoint | Visual inspection of substrate ready for SWP
0b96c192-3f1a-400a-a903-ad7fe725dd47 | checkpoint | QA document received from previous trade from main contractor
94207f56-d9c9-49dd-8e3e-bf0e4f50c2ee | checkpoint | Large holes filled with grout by others
4c8087a0-4b11-4b0c-b7b8-05996442a1a6 | checkpoint | All lumps and sharp concrete bits ground/hammered down
f2bdf473-79a1-48cd-9a13-e890579b4687 | section | Concrete Substrate
28f286c4-9791-40a1-ab66-98709d5d36e4 | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for primer
7d8c1be1-c48c-403e-a9c8-054927cfc2f3 | checkpoint | installation of SA primer
3083bc68-61de-436e-860b-ae7094516baa | section | Vapor control layer
fb63bdd6-2ed4-4f99-869a-d05a913fa447 | checkpoint | Substrate clean, dry, free of debris
826d92e3-1b84-40d8-8bc3-0b92ee6a9441 | checkpoint | Z flashing installed
6a344705-5f63-4ca2-ae22-a57be279bf1d | checkpoint | Install VCL over primer
3625e558-d03e-46b2-8f01-192ad821cc3b | checkpoint | VCL lapped with a minimum of 100mm side and end laps
96507a1d-38cb-45cc-b550-a2b13f7f27f8 | checkpoint | Installation of SA primer
982b1eec-eb18-468d-85ee-f47fb845dc2f | section | Insulation
6c4cd208-4720-4b37-b432-4f1d31f2319f | checkpoint | VCL clean, dry, free of debris prior to install
a3aeea91-43ec-4f70-8dc4-69fbb15708f6 | checkpoint | VCL has been checked for damages and repaired
75f73e34-dcb1-4c98-89ab-d5bd8a3cbb11 | checkpoint | Closure flashings installed correctly
8cd7664f-b1ab-4778-94ff-4abe273d59ae | checkpoint | Install board adhesive in specified pattern
0b8f94d9-1936-4b1f-beac-940927ff718a | checkpoint | Specified insulation board installed
ad0101d6-99e9-4ae2-8cda-a251f9fde007 | checkpoint | Boards tightly butted
6ea40f8a-2580-4f8d-8de5-05030b0e4008 | section | ILD system installed
6ad708bd-4158-49e4-ac5e-d15bd19d41c7 | checkpoint | ILD System installed as per specs
c0ba7cdf-28f6-4b51-8958-f8a76d02e1d1 | checkpoint | ILD test plate installed
96ecfbba-a6e0-4ab4-ae70-f84618de7085 | section | HDP board
a1c496f3-b199-4faf-af87-71e919cc5125 | checkpoint | PIR clean, dry, free of debris prior to install
f00a6397-032f-4ecd-9665-5fce2abd182a | checkpoint | install board adhesive in specified pattern
328eb71b-67fc-4c85-b182-f9486162e10b | checkpoint | HDP board installed in brick pattern where possible
0e51dea2-f93f-4480-b6e5-ae3079a749d8 | section | FiberTite
4cc4d723-4279-4527-8166-df918b6acdc6 | checkpoint | Prime substrate where required
fd1e2c16-b9a1-4b45-94f5-a057c7b5c947 | checkpoint | Adhesive installed to substrate
e43eb87c-79a3-4f9f-ac29-d8164999f555 | checkpoint | Laying of membrane into adhesive
b497401c-192e-4f2c-80d5-281d79296223 | checkpoint | Broom/rolling of membrane
a0cb7d27-5231-43a2-9ec3-7ea37303ecb5 | checkpoint | Wipe and clean laps prior to welding
4a98dd36-b371-464e-9762-b216322dae84 | checkpoint | Test weld with welding machine
a0519236-0c71-499f-81cc-6aae7038b5ee | checkpoint | Probe of seam with QA hook
afd63248-51ab-45ad-8e4c-bfd685df582f | section | Sumps
026c25f6-4b43-4af3-a3b6-124aac906884 | checkpoint | Sealant installed to dropper flange under membrane
0ce714bd-6f10-414b-ab9b-f31f82089b27 | checkpoint | Membrane dressed in to outlets
11ca991f-7b33-480c-80f5-b355894fd007 | checkpoint | Clamp/rings/basket installed
c0eb142c-ddab-46bb-89b2-61680b8e48a4 | checkpoint | Flood test
2ebf7e39-adb7-4c60-ab69-65c8851f0242 | section | ILD report
4cf69a10-2ca7-4975-a02e-a49ec406564e | checkpoint | ILD report
0ea6b728-a631-47dd-a23d-aeee4e53f69b | section | Fiberclad flashing
c3f78ab7-9b2a-4b9e-b26b-5323d75c0aab | checkpoint | Installed correctly according to specifications ( right way around )
3f3c30eb-994f-49c3-b55d-75eeabb248d4 | checkpoint | Fixing and welding done according to specifications and details
c7d7a070-3c9b-4161-bfa5-a63b708566b5 | checkpoint | Probe of seam with QA hook
4982f130-3d83-4bb0-b19b-04be84abaa6b | section | Pressure bar installed
ff5bbd23-49ea-4d46-9d6b-0f1efeb66c44 | checkpoint | Installed correctly according to specifications ( right way around )
4d57b427-af88-46ad-9968-9e752cfa2e97 | checkpoint | Fixings done according to specifications and details
16d0b06c-2ce6-4691-b846-5bd4ea917f7e | checkpoint | Prime of Substrate where required
5b6597aa-274e-440f-b5bc-8062986606f8 | checkpoint | Sealant installed
7fbd7b5a-2baf-458c-a1b6-06b50967ac2c | section | Over flashings
e7325c6d-5740-4bf0-a1bb-bc11e892c91e | checkpoint | Over flashings has a separation barrier
8ab5821c-4411-453d-b2a1-acd3fe372e71 | checkpoint | Fixings done according to specifications and details
f11deae2-6ae4-448d-8d7c-81cef7a2cbed | checkpoint | Primer of Substrate
11b81e5b-a1b3-40fb-8dbb-356174a5b9a1 | checkpoint | Sealant installed
e0432470-5461-4931-9a2a-f5da286043cc | section | Review and sign off
ad8bbb7c-2b8f-448b-996b-e17fa17a4aab | checkpoint | Area left clean and tidy
34a7cb3f-b446-4564-82a4-93aca07d488a | checkpoint | All installation work completed, checked and reviewed as per specifications
616d1536-08ef-4ecf-80cb-4081720bd81e | signoff | Client/main contractor sign off
ac7a1d7f-e20a-42ee-bbba-6a19638bfef8 | checklist | Metal cladding checklist |  | Metal cladding checklist
a5723d83-d63e-45b9-aae0-8d19730efe3e | section | Pre start
d0bde905-292f-4181-88b4-6ff4de3ba15a | checkpoint | Area accessible
1745f9d4-2880-42cb-931d-f124dc6c5356 | checkpoint | Edge protection and safety installed
0c174743-d2d5-46bd-8fc3-85465e7bf479 | checkpoint | Building wrap installed check plans and specifications and QA / handover received from main contactor
f8c99833-4fb9-4be8-a2f7-12493d3dc682 | checkpoint | Battens installed with the correct spacings check plans and specifications QA / handover received from previous trade from main contactor
97964898-e2c3-46b3-86ca-5a16d0e48a6e | checkpoint | visual inspection by SWP
82f78afe-0cc8-4c57-9a0e-1fed874404e4 | section | Rohm rails Install
450992cc-ea76-4b41-ba32-cb4bced3f6f9 | checkpoint | flashing tape installed check plans and specifications
4e2e8387-dd3d-44b5-b8ed-2e61de3bd078 | checkpoint | Rohm rails installed with the correct spacings check plans and specifications
ec9afa13-949d-4569-ad27-8865a6f81ee9 | checkpoint | Rohm rails installed to fixing plan
a9d50e42-3332-4210-9879-d0fd4719e37a | section | Cladding install
4ba925bf-6c63-45a0-99c6-2330267fa40f | checkpoint | Cladding installed plump and straight
96b36566-2851-4d5b-8972-012c516d2bcc | checkpoint | Screw pattern according to plan/specs/best practice
fdd2e8fd-8001-438d-a410-616c95e29848 | checkpoint | Closure foam installed
b6be2a3c-fe62-43e3-9c61-f570751e2e14 | checkpoint | Top end turned up
2188a862-538b-4381-87c0-66bfb7269bbf | section | Flashing install
329b0ded-95a9-438f-9248-1949c21e8e03 | checkpoint | Sealant installed with 2 continues beads
a47aa922-15a2-405c-a41d-ab02a25ecb1e | checkpoint | Clean excess sealant
1fc4db23-b03d-4809-8d67-05ec24988e98 | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
06a954ff-600e-47f6-8f62-ff793a5cae71 | checkpoint | Flashings installed as per drawings and specifications
d7d72c8d-9385-4f4f-9947-036e8e53ff02 | checkpoint | Fixings installed as per drawings and specifications
3e068f1d-bc7e-479e-a3ee-89686c95ca63 | section | Review and sign off
a69f7a7b-4271-4ca9-8e97-7b56ffd8bf2e | checkpoint | Area left clean and tidy
0029dcd1-aeaf-417a-baa4-2a6e4f70f11b | checkpoint | All installation work completed, checked and reviewed as per specifications
3dcfcb76-95b2-4642-9cda-0d2a5438d1e3 | signoff | Client/main contractor sign off
c4e23d4e-3d71-49f7-b48a-bdcfdbf01f57 | checklist | Metal Flashing Install |  | Metal Flashing Install
a8500b0f-d612-49c3-b90c-06bbfe81757e | section | MetalFlashing install
bcd3e677-4db1-4913-813a-4c72733f398a | checkpoint | Sealant installed with 2 continues beads
096afad3-4c3a-4cfd-a1be-a70e395f5c1b | checkpoint | Clean excess sealant
75077c9b-a95c-4ad8-9fcf-4c68cf6dae22 | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
66fa10ee-ad70-4053-8d46-cbb6ab42eff9 | checkpoint | Flashings installed as per drawings and specifications
c652270a-6420-430a-b363-a6e68d61db23 | checkpoint | Fixings installed as per drawings and specifications
b3348b45-9342-457e-bd41-c2a63da96303 | section | Review and sign off
38b7d54f-eb20-4adf-9857-4a9f8a9c2da5 | checkpoint | Area left clean and tidy
79fce31a-f87a-4528-8359-60d9906867a7 | checkpoint | All installation work completed, checked and reviewed as per specifications
940770ca-6a02-40d8-9fe6-069e47cab663 | signoff | Client/main contractor sign off
dadf05b0-27e1-4818-bf63-d2f46e9874cc | checklist | Metal gutter and downpipe checklist |  | Metal gutter and downpipe checklist
4d876315-7377-4c8f-9e2a-0cafc869be00 | section | Pre start
9d003f34-268a-46a5-9ddd-66b9a35f959f | checkpoint | Area accessible
c6eff65e-fe20-4335-a6f1-1acad0474685 | checkpoint | Edge protection and safety installed
e8328fb6-21fc-4558-ad4d-de04636c7860 | checkpoint | Visual inspection of substrate ready for SWP
ef6898e2-6f2a-4ea0-bc86-f5abd84b5e3b | checkpoint | QA document received from previous trade from main contractor
a40646fe-6ea4-4bbb-b3d7-c528e5665091 | section | Gutter install
f1b68372-6e7f-44d9-93fa-2d52256c7034 | checkpoint | Brackets installed according to drawings and specifications
19568a75-bfcc-4b96-87fd-fcc561e88b4c | checkpoint | Gutter lapped and sealed correctly according drawings and specifications
7f1cdef5-8eb2-47a9-9515-e7cb291663a9 | checkpoint | All terminations and ends folded and sealed
c0dd2498-f941-4c33-b2df-10620fbd21f3 | checkpoint | Expansion joints installed
13a0e89e-a416-4ab3-b346-9ce4cc2dc756 | checkpoint | Expansion joints roof flashings installed
43054355-8c4e-488b-b5dd-0ff66023f3ad | section | Downpipe install
12f04a3e-59e9-4a6a-a63c-4353b086093c | checkpoint | Correct size dropper installed, riveted and sealed
bb2bc607-e0c4-48aa-9e43-7de93aa28f43 | checkpoint | Correct downpipe brackets installed with the correct spacings
5b266eef-b27d-47ae-b630-a9553a6a1f5a | checkpoint | Down pipe installed plumb and straight
02330e0c-5e6c-43d6-b83e-b6a313c501f7 | section | Review and sign off
dd8fba57-466a-43e4-af20-14954f5eaafb | checkpoint | Area left clean and tidy
0787be8b-f9cf-4b04-8966-05d895bcfa1e | checkpoint | All installation work completed, checked and reviewed as per specifications
e2a37c76-4282-4f08-95a3-c3cafa22068f | signoff | Client/main contractor sign off
42ca9d96-5df9-40a4-9a79-a44600374a77 | checklist | Metal Roof checklist |  | Metal Roof checklist
5d07342c-9c0e-4062-8143-585d26ccd054 | section | Pre start
37374755-05c1-461d-aec3-e53c800be421 | checkpoint | Area accessible
b4556c4e-29f5-414e-bcfc-feba3d194092 | checkpoint | Edge protection and safety installed
af610651-1fe6-4931-908d-8ffd54f97772 | checkpoint | Purlins installed and QA / handover received from previous trade from main contractor
6d4f6f6a-568c-46ab-8a13-f7bf9e270fc7 | checkpoint | visual inspection by SWP
fb32b9a2-7308-4aa9-b2da-5716e019e446 | section | Safety Mesh install
2729e24b-b01b-4501-8afa-a542b2a90f7a | checkpoint | Laid and secured perpendicular to the purlins
00e9dc08-24bf-4fff-a09e-f255a2c32011 | checkpoint | Lap side joins by min 1 grid section
d5601df8-78f1-4038-8da7-f45aef17fe43 | section | Underlay installed
4d4645eb-25bc-41f7-9840-d9d1a2b8e00e | checkpoint | Correct underlay installed as per specifications
13add5e9-c8a1-4e55-993e-25590a5382f0 | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
080f23d1-0223-43e6-a0da-50d63d70343a | checkpoint | All areas covered
e75f183f-ebb3-4d07-950f-eac389696e2e | checkpoint | Underlay installed as per specifications
5d561702-abbd-455b-b425-817dbfe8dad8 | checkpoint | Joints taped together as per drawings and specifications
af2ebb26-5654-4ca2-8229-886d8822d7b0 | section | Metal roof installation
1dd31775-5348-47b7-91b1-b6abddf4697a | checkpoint | Drip edge installed as per drawings and specifications
faeefd5e-8158-4c20-9802-f7d0d08cc6a7 | checkpoint | Laid straight and perpendicular to gutter/purlins
ef0baa8b-d075-4ddb-af75-d346f8463295 | checkpoint | Gutter overhang as per drawings and specifications
79b005e8-8988-4bd9-8597-1ca211658839 | checkpoint | Top end turned up
495bb774-2c0c-4760-b4cf-18982489d7ef | checkpoint | Bottom ends turned down
34642f27-5ef3-499a-81bc-04baa725d4ac | checkpoint | Closure foam installed
e1a4a6d9-c52d-48f9-b7d2-204eb164e1d5 | checkpoint | Sheets fixed in to the purlins
a60045eb-bc12-4ef6-a45e-d07869bf7875 | checkpoint | Screw pattern according to plan/specs/best practice
50dfa345-8514-4da7-8eb7-eedd02478f02 | section | Flashing install
74ce4b81-902f-4c2d-b16d-19b64d14e0ad | checkpoint | Sealant installed with 2 continues beads
7bd674b5-4672-4200-9449-db6913d4bf7d | checkpoint | Clean excess sealant
8b9bd562-4449-4ba9-97fb-7b5de6fd7081 | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
7d4a75a3-c4c5-4814-9904-0bd52a3e8d65 | checkpoint | Flashings installed as per drawings and specifications
af36dce3-6936-4811-ab3f-39d6dcad9aaf | checkpoint | Fixings installed as per drawings and specifications
46b2e5af-dec2-49ad-85d0-b7e58e7d8c52 | section | Review and sign off
7a4a436d-8eaa-4aaa-8d4e-c16c9e4dbe3a | checkpoint | Area left clean and tidy
80263145-aae9-4cfe-834a-37021d171b69 | checkpoint | All installation work completed, checked and reviewed as per specifications
10476280-0a50-4ed8-b0dd-abc17b84efce | signoff | Client/main contractor sign off
e84d246f-9543-4cfa-9fa5-4cbcc372b879 | checklist | MSR checklist |  | MSR checklist
b8a8f304-14f7-4224-b309-2617a133431c | section | Pre start
93bc44b0-4e51-4cc1-9613-4fb3e5626874 | checkpoint | Area accessible
4c8e6075-ea88-4394-8c1d-c2448559c0f4 | checkpoint | Edge protection and safety installed
f483f45a-2d0d-4d1c-b247-cd8d20292279 | checkpoint | Purlins installed and QA / handover received from main contractor
21dda602-c70b-4f15-82f1-5e64dfa09c71 | checkpoint | visual inspection by SWP
7a0806c8-40c7-4455-a220-4c43fd21a97a | section | Liner deck
e03c3bfd-320e-4cca-8039-036534f3a13c | checkpoint | Liner deck fixed down in every purlin and every pan
ed162435-8f24-4582-8095-80a6bc48c828 | checkpoint | Correct fixing installed
8353ba8d-c365-4929-a780-49a1e32c1efa | section | Vapor control layer
881c074c-6898-4fe7-ac64-219e89865326 | checkpoint | Substrate clean, dry, free of debris
9eea35b2-f78d-4d35-8a1c-beee58bfe593 | checkpoint | Z flashing installed
2c39b3d9-9f3d-443f-9bb5-6ee7a085009e | checkpoint | VCL installed and covered all surface
32aec664-14bf-46f4-b0e8-72fdb2a9547e | checkpoint | VCL lapped with a minimum of 100mm side and end laps
005c791d-09d3-46c9-8142-56e29fa3af2b | section | Acoustic board install
ff640de5-4e8b-418d-9f67-e1a0e145ee8b | checkpoint | VCL clean, no ponding water, free of debris prior to install
f3e59c52-a8e7-413c-b6de-2c83eb13ee51 | checkpoint | VCL has been cheeked for damages
329886b8-2687-4e76-9393-555a50cb3f36 | checkpoint | All holes/penetrations patched
9e6dfc74-ba20-48de-9130-bdc51558533c | checkpoint | Acoustic board installed
3b4be2ca-bb96-4324-8781-52eeea61ec59 | section | Insulation
941c4cfe-3ab6-4bd5-8ef7-584782274da5 | checkpoint | Boards tightly butted all areas covered
ec5a443d-885a-45b0-a9c4-f41b37eea21f | checkpoint | Correct insulation installed as per spec
c070ba5f-1572-4b07-ac26-20f67ae9c9f2 | section | Underlay installed
9ef4f242-ede2-49bc-9fab-12b3eb61ab88 | checkpoint | Correct underlay installed as per specifications
39dc77ce-085f-4711-9cfc-191fcd28b694 | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
750fb3e8-3c3b-4b51-afd5-2d917a332498 | checkpoint | All areas covered
a600ed5a-47d2-4424-ba8b-2c61d401b98a | checkpoint | Underlay installed as per specifications
7c9f649b-1a55-4619-a2d3-8f3ea6c7a781 | checkpoint | Joints taped together as per drawings and specifications
95499289-9c98-4231-a873-aaacb42a22eb | section | Metal roof installation
3bfa975d-815e-477d-bc64-ddcfa7d1258b | checkpoint | Drip edge installed as per drawings and specifications
8aefe82a-9d96-42d0-b06f-a3436c396701 | checkpoint | Laid straight and perpendicular to gutter/purlins
ae28352f-c750-43ce-ac47-21b2583ed014 | checkpoint | Gutter overhang as per drawings and specifications
c6a1a8d2-1aa9-49a7-86ef-b082479a0f17 | checkpoint | Top end turned up
fdfea377-f92d-4dda-a4a7-55bd0fd5fbd5 | checkpoint | Bottom ends turned down
6151cc44-09b2-4ad0-9fd2-9d9fd298d641 | checkpoint | Closure foam installed
b43c4417-36d9-407b-973b-2902d34ad259 | checkpoint | Screw pattern according to plan/specs/fixing plan
f8a7ba6d-1475-4b81-bb02-d6c4649a5051 | section | Flashing install
bb24306a-88fb-4572-9f17-0e74c9015aa8 | checkpoint | Sealant installed with 2 continues beads
3ca96127-7e8d-4a4c-8f52-e08dc0f47757 | checkpoint | Clean excess sealant
e2d30843-164f-4c08-b436-85b8139c06a5 | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
7f2be742-b219-4935-b68f-d6644114c0ae | checkpoint | Flashings installed as per drawings and specifications and facing away from waterflow
17c190f4-d79f-4599-b54c-2c1ffcdd5a41 | checkpoint | Fixings installed as per drawings and specifications
3fe7355e-f0c8-4459-807c-e80066355fc1 | section | Review and sign off
74699caf-0d04-4f92-be42-a28769a9705e | checkpoint | Area left clean and tidy
f0004d93-3bbf-4e99-bff0-bb6d8b0c9c1f | checkpoint | All installation work completed, checked and reviewed as per specifications
33a51cc7-668a-4aa2-a0b6-a17de72cd476 | signoff | Client/main contractor sign off
4c035737-94f0-40c7-a117-659dc7be0c1f | checklist | MSR cladding checklist |  | MSR cladding checklist
5bce65de-2c5a-4756-b31b-9bcc9f22f6c7 | section | Pre start
4c9ad89d-5814-4f37-a448-7e2f1a6d09c8 | checkpoint | Area accessible
d532b2c1-dccf-4184-b2da-bcf44e1388a2 | checkpoint | Edge protection and safety installed
0b71e057-2501-4317-899b-1e369da0c5c2 | checkpoint | Purlins installed and QA / handover received from previous trade from main contractor
adc54aad-e172-4b0b-b6f9-95d250453928 | checkpoint | visual inspection by SWP
7459569a-7abc-4ae4-b304-73a6e85a368d | section | Vapor control layer
d79405e1-7eb1-467f-977d-9d6862eba4a9 | checkpoint | Substrate clean, dry, free of debris
6f469ccf-0d5c-4d91-ac41-eaf34b2716d3 | checkpoint | VCL installed and covered all surface
978828e3-3020-45fa-8dfb-851582a51daf | checkpoint | VCL lapped with a minimum of 100mm side and end laps
e740ed01-8abd-4ebf-b246-d4f15b0eaacd | section | Rohm rails Install
ff91b90b-9be5-4524-b7f2-caee835c2623 | checkpoint | C channel flashings installed
62a0baac-54a6-4027-b1da-eb1adcab0f11 | checkpoint | flashing tape installed check plans and specifications
9047d8fc-3159-4335-a257-85466a2304aa | checkpoint | Rohm rails installed with the correct spacings check plans and specifications
9e77631f-f4fd-4bf8-a212-ea9c4a28742b | checkpoint | Rohm rails installed to fixing plan
8a9f9fd1-1998-4d43-8dbb-104d88a84f5a | section | Insulation
2784d034-17f1-4da3-b723-2387cb74ca12 | checkpoint | Boards tightly butted all areas covered
2c4001aa-14fd-45db-92f2-a92f4b6f2f6b | checkpoint | Correct PIR installed as per spec
9c88c8b5-b1a1-4a60-bd46-85c054efba83 | section | Underlay installed
66fd4dac-744a-41eb-b31b-87e3e9f7dd69 | checkpoint | Correct underlay installed as per specifications
fcbafd01-67f5-4cc6-9221-7b9ab1d77cb4 | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
46f6214f-233f-4355-8e91-1b0b51f0bc86 | checkpoint | All areas covered
72c5f5aa-4754-4e73-9ce2-6dd4e0d4b827 | checkpoint | Underlay installed as per specifications
89c33b46-ef30-4acd-9efa-8a590bbb18a3 | checkpoint | Joints taped together as per drawings and specifications
6e66ac7e-0710-49b1-a2fd-aac0ed8277e9 | section | Cladding installation
f424bd53-b42f-4f20-8c1a-9c7ca835f0d8 | checkpoint | Starter flashings installed
21c3648e-c599-41c6-8558-74ff8feeeaa7 | checkpoint | Laid straight and perpendicular to gutter/purlins
da9ab8a1-fe2e-4a96-99c0-a81cbff06925 | checkpoint | Top end turned up
0a422249-2c38-4a8e-a6ab-ff7ca53453a8 | checkpoint | Closure foam installed
97532b97-82e6-43d7-b160-b3937ce351f4 | checkpoint | Screw pattern according to plan/specs/fixing plan
756e7f26-16ac-40b8-99eb-f626a7f98230 | section | Flashing install
a5d3af98-9fea-487c-acc4-fba7c4cbb75b | checkpoint | Sealant installed with 2 continues beads
cfef8299-3054-4c62-97ae-9909e2ec7d22 | checkpoint | Clean excess sealant
05498211-af2f-4811-9615-db8ca0e13bc6 | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
b8d335d8-7283-4fb1-90eb-dd5fd5504427 | checkpoint | Flashings installed as per drawings and specifications
bb9a6df2-9586-4770-976d-c6a302f88b0b | checkpoint | Fixings installed as per drawings and specifications
898707c7-c9e4-4a36-868b-4932a6e09307 | section | Review and sign off
4adb5546-cce3-4dcb-bea1-c91fe6fb9ccf | checkpoint | Area left clean and tidy
41b6d1b5-592e-4054-b735-3ac30213d4df | checkpoint | All installation work completed, checked and reviewed as per specifications
87c30d03-d719-4a7c-9e00-34906f4ce5d0 | signoff | Client/main contractor sign off
e140351c-6d15-47e0-85c7-a813115a13e3 | checklist | New Files |  | New Files
dcff6604-e7cc-4424-a5d8-223bec916488 | section | Details
bc6b5db3-313e-4252-9cca-3411bb0d7dbb | checkpoint | Upload Files
16186d75-0a57-41cd-a18f-80495fe7bcd6 | checklist | QA - Carpark MMA Checklist |  | Carpark MMA Checklist
98f42cde-7ab9-40dc-9fd3-fcce7103ae3d | section | Pre Start
f8c0867c-7b6a-4e73-b487-ce7bcfb995ff | checkpoint | SSSP onsite
3bca8654-95b0-4699-93be-ebcde8d12a9c | checkpoint | Fencing demarcation installed
e1ac86d3-4962-49f1-8ddf-efd3afd1b0b1 | checkpoint | Site signage installed
47fce3dc-512b-43e0-a8e6-49936640465e | checkpoint | Area Accessible
ec497dc8-4d01-4560-98cd-27c5469e2afc | checkpoint | Substrate complete and ready for SWP
312eb937-bbef-4932-90d7-eac0251b18d0 | section | Surface Prep
01a46ef5-0826-436a-abe3-3e02177dfbd2 | checkpoint | Removal of coatings
f2132b07-d699-42d7-aaf7-1bbd123c39bd | checkpoint | Grind of substrate
ab330fd1-057a-4847-b8bd-26226bbfb687 | checkpoint | Shotblast of substrate to achieve suitable profile
2215fc68-ba02-456f-a836-90741ed575e1 | section | Pre-start of membrane install
f57e723b-75d6-419d-aee2-4151a5359630 | checkpoint | Substrate dry
5b6ab694-3499-495e-928d-8de671230d6e | section | Membrane install
f5da8f6d-89b9-4c97-b998-1e805736f725 | checkpoint | Prime of substrate
eadefd27-b326-4ad5-8cdf-1f7dcee02bd2 | checkpoint | Stripe out cracks
ada4c073-cc6e-4f00-8e3e-4cc4787fc6f5 | checkpoint | Map out areas based on coverage rates for install
5f8f9f93-08ce-4f1a-8a6b-6eb7db680c0d | checkpoint | Membrane layer installed
094ca968-3753-4d38-8cd4-d7e34cd0e349 | checkpoint | Wear layer installed and broadcast
821a7125-6b7d-4538-936d-e40056a33e29 | checkpoint | Excess broadcast swept and removed
bd761a51-c537-4839-afce-0cc2b892a1d0 | checkpoint | 1st Top coat
9c88e4ce-a425-48a0-b0a3-9940087294d6 | checkpoint | 2nd top coat
7630b0e6-6a74-47c5-8365-44fea4c50625 | checkpoint | Site cleared and broken down
7ae41c9a-c3d5-4c57-9704-c47c3f637dc3 | checkpoint | Site cleared and broken down
3363827a-487b-4ad5-af06-051a69554c03 | checklist | QA - Fiberglass System Checklist |  | Fiberglass System Checklist
d4874ee4-405e-4ab8-9e92-a82f6d25f2ea | section | Prestart
d07fa4dc-4cb1-4a0d-82aa-7c59b2b7c5e3 | checkpoint | Area accessible
c1814771-48fc-4bd7-a3a2-bfcec544764d | checkpoint | Edge protection and safety installed
bbc500c9-82ff-405a-b032-6553a08a460c | checkpoint | Substrate complete and ready for SWP
78dfa13a-a3ab-4aa2-a076-c42581e74828 | section | Surface Prep
81231584-331a-4b8f-a176-b71f0bf276f2 | checkpoint | Concrete free of contaminants
da7af930-7394-4b2e-8e79-dfe8d28f4273 | checkpoint | Concrete flat and smooth
735f5256-eb7f-44f4-8446-60fc1f827d93 | checkpoint | Bug holes in plinths filled and smooth
37744951-a861-4f1d-9785-e6fa4765385e | section | Membrane install
3f07a08b-dcbf-425c-ae6e-02dc692acbd4 | checkpoint | Install sealant angle fillets to all wall floor junctions
143b302b-66d9-4f16-9996-184458a77b55 | checkpoint | Prime surfaces with Epistixx
d0f55942-b597-40be-96b0-baa5e57d1807 | checkpoint | 2nd body coat
8647fbaa-9991-4dce-829a-48b0631eabe9 | checkpoint | 3rd body coat
7b4eecff-dcdb-4f9c-af07-1aad254be721 | checkpoint | Traxx 2000 wear coat.
96d1fe53-36f8-4e32-8d59-97350427bb3e | section | Review and Sign Off
2a481b25-d207-4507-ab51-9553f7bd0f04 | checkpoint | Area left clean and tidy
26cd5ca3-df20-4357-9f4d-086686a311f3 | checkpoint | All installation work complete, checked and reviewed as per specification
d6dd49da-e0a9-47f3-942b-0e1dce38afe8 | checkpoint | Client / Main Contractor sign off
ed9516bf-4c7e-4a4f-8af9-5f15743a3ff4 | checklist | QA - Fibertherm Checklist |  | Fibertherm Checklist
5cc1b99d-b367-450f-9fd9-5c5a8dbc686f | section | Prestart
f63cab34-a8e5-4e48-8bbb-18bd053a9092 | checkpoint | Area accessible
cb999f19-793d-4e10-835b-acfc613f761c | checkpoint | Edge protection and safety installed
79fe9bd7-88b7-4bd9-b3fb-8eb031726916 | checkpoint | Substrate complete and ready for SWP
9d36850e-7e78-47d3-a29b-6736db707149 | section | Metal Deck
b61ac1b7-4fc5-4aa8-9f40-c83dd92788b0 | checkpoint | Timber to have separation
f3916cfa-d501-4081-96c9-59a778fb32a4 | checkpoint | End openings to have closure foam installed
9277e306-e266-47fb-8cb2-dad004c8c194 | checkpoint | Base deck screwed down in every pan
c731ec29-934b-4549-8ed8-4a9d8d4e8b93 | checkpoint | VCL tape to be installed to all sheet laps
830ecc27-1f29-4901-9eb5-d7c324a0a902 | checkpoint | VCL tape to all upstands
111a84c5-ef16-4721-b9b5-71204d7eb955 | section | Post and Rail install
a7e32393-41ba-4c8d-a9e4-f8e9eed02777 | checkpoint | Post installed at correct fixing centers
3912ec9e-8313-4dc2-817a-f407e5662c02 | checkpoint | Thermal break pad under post foot
4afd6938-4185-49a4-b098-b4c8a34ee5c4 | checkpoint | Rail installed to posts
c61012af-5244-4e94-9232-0ac56ffe2ffc | section | Insulation install
e5cad2d2-72b2-47c5-ad3b-0e08bb0cc5e2 | checkpoint | Specified Insulation installed
a9702695-bdda-48d0-a170-9e180a5970c2 | checkpoint | No Gaps
bd3020cf-a387-486e-bed8-a444f86e04a1 | section | Top Deck install
72d0b518-7ecd-4450-9d21-7e73f1e11a56 | checkpoint | Lay sheets straight
f0b07a71-f3b8-4569-90b3-ab5cc8b701f5 | checkpoint | Hang over into gutter min 75mm
57a3ef58-730c-41b9-aea1-62683b33ef9a | checkpoint | Top end of sheets turned up
40b473cd-e8dd-44a9-885e-afc9666395bd | checkpoint | Bottom end of sheets turned down
c43481b5-239e-4cd8-a1b8-aa21fbacdef5 | checkpoint | Fixing back to rail
12e85bc8-937a-42f6-8666-2b2252bc0668 | checkpoint | Profile washers
f8bbb80f-6461-4ba0-9600-7e3ffbbd0d8c | checkpoint | Screwed off as per fixing plan
3af20425-7e3d-49cb-8955-a6ec08056029 | section | Flashing install
e36867e6-2c91-4e18-afac-e9c347f63ccc | checkpoint | Fixings according to specs & details
a0f5f1e6-6949-496a-b5fc-18d3be89ed8c | section | Review and Sign Off
02b3d610-bfba-468e-a22b-73555c43d055 | checkpoint | Area left clean and tidy
a9c04d33-b702-4f88-ae07-e374ebeb7ad1 | checkpoint | All installation work complete, checked and reviewed as per specification
35b1a0b8-0bf7-4efc-a93f-b2cfc9873f14 | checkpoint | Client / Main Contractor sign off
b63d52bf-0d5e-4676-886b-0c7e97ee910f | checklist | QA - Sheet Tanking System Checklist |  | Sheet Tanking System Checklist
d4588da8-5d37-411b-87d9-0c15b10d096f | section | Pre Start
29ae9ff3-942f-4a47-9140-df4265ac4777 | checkpoint | Area Accessible
e586b72a-da1e-43bc-957a-be92e397cbb4 | checkpoint | Edge protection and safety installed
ff4c528f-c901-4d6e-98b3-4d910016493a | checkpoint | Substrate complete and ready for SWP
6b91351d-601a-4883-b28e-456127a125fd | section | Primer
099e1918-2a07-4d7a-8174-ff238ad4cbd5 | checkpoint | Applied as per specification on dry substrate at 5m2 per litre
bfe643e0-d461-4193-b020-522175a45cda | section | Membrane
4bc08157-255c-489c-99a7-0b1051a777e8 | checkpoint | Temperature must be over 4 degrees for membrane install
97c2f031-28d7-4e6c-b4ca-a6bbda3ba91c | checkpoint | Is the substrate clean, dry and clear
fc2072c0-43d4-422d-81c0-966472380f70 | checkpoint | Membrane applied with min 50mm overlap
1a703ab8-8b69-4fc0-bc48-d7aba7028d47 | checkpoint | Overlap is to pressure applied or rolled for seal
45361f36-a9bf-4fcd-beeb-639b28feeda0 | section | Protection
c706296e-8f17-4e13-b9a8-b23266bfc899 | checkpoint | Works to be protected by main contractor
7156e37e-e1d0-451b-9e02-f10190afcf78 | checklist | QA - Torch On to Concrete Checklist |  | Torch On to Concrete Checklist
06245677-6916-44b8-9035-d304ad539c17 | section | Prestart
f5a59eaf-a6d7-4b48-8768-4b4594fc8109 | checkpoint | Area accessible
efe9f44e-d893-4baa-91e5-99ad8d15c112 | checkpoint | Edge protection and safety installed
981c1919-ad3a-4d0c-9e63-144d2aed5cbe | checkpoint | Substrate complete and ready for SWP
0528b95e-8322-4587-9e9d-8f363aba0321 | section | Concrete Substrate
5e1d3918-dfca-4034-90a3-a40053400d1e | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
11751199-9070-4900-8d41-fe2b9b089ed4 | checkpoint | All lumps and sharp concrete bits ground/hammered down
ae68ec02-ed28-4696-a3f5-f8b9dbc99b35 | checkpoint | Large holes filled with grout
656aa748-fa33-4e93-83fa-3dab03e5da31 | section | Prime of Substrate
84f6aa22-9cd7-49ab-80bf-f7e06dbf46ef | checkpoint | Substrate clean and free from debris
59f859a5-a330-4b04-8422-09e92ab44e14 | checkpoint | Primer installed
e0341a45-85c3-475f-94d2-79534fc82e9f | section | Base Sheet
a30615f4-2476-4bb3-8c23-be8283654461 | checkpoint | Install from low to high
b5c90c0d-81b8-4d22-bd99-1dfa417a2df5 | checkpoint | Side laps a minimum of 80mm and end laps 150mm
f86a79a6-aa57-4ee9-a147-7bdcc4883261 | checkpoint | Check all welds at the end of the day
9cc9eda5-1ea1-4ff4-992e-68bb6add089f | section | Cap Sheet
708ef390-cb28-4eeb-ad19-f63e9158bf64 | checkpoint | Install low to high
4246b863-c38e-4753-b95a-6a63dc5173cf | checkpoint | Side laps a minimum of 80mm and end laps 150mm
56246c3d-3b5d-4391-aede-3c6e5ce9b4f9 | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
7e0a3278-42f3-445a-aee7-f0de0f50f22a | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
b2e95f87-80ed-407a-a89a-df9b0d488a3e | checkpoint | Membrane dressed into drains/outlets
b5eec35a-1a6e-4aa2-9723-dc813332ac6c | checkpoint | Install clamps/rings/baskets
3b75226b-9b1e-4c29-a726-da314eb04a82 | checkpoint | Flood/ILD test
aec9f557-eab2-4c92-a30d-ec1e77123d66 | section | Review and Sign Off
af2155a5-9365-42e1-aecf-fbadcf31ccd9 | checkpoint | Area left clean and tidy
43e4f7e9-8439-4fc9-92f8-eb0ead1c4074 | checkpoint | All installation work complete, checked and reviewed as per specification
7f720b66-a177-45f6-95b5-99f06cfe5758 | checkpoint | Client / Main Contractor sign off
77803f14-22c8-482e-bae3-966dc5c2325f | checklist | QA - Torch On to Plywood Checklist |  | Torch On to Plywood Checklist
b3d2b1e1-9e22-4429-a200-da00d53d5fc3 | section | Prestart
35c0a3af-6c1c-4038-9800-f26fb830fd0f | checkpoint | Area accessible
2b1d49df-1850-4f7a-8d8d-b25caf017fdf | checkpoint | Edge protection and safety installed
ef28bc36-60ce-486d-962c-4c5bc78b66c7 | checkpoint | Substrate complete and ready for SWP
31ea0412-123d-4c76-b805-b7d9e4ad4ee4 | section | Plywood Substrate
969c8a18-bc14-4b20-88da-de279a25f262 | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
506b84fa-b266-42bc-8d2f-b2935f077d78 | checkpoint | No Screws/nails/fixings popping up
e3267744-9112-49fd-8377-a6b1fae853c8 | checkpoint | Joints flush and even
5687f4fb-11c8-4822-bd4c-fcf55e449bcd | section | Prime of Substrate
5e0bda65-8571-4907-9c56-f54d8048193c | checkpoint | Substrate clean and free from debris
987a7243-5d33-487c-9a97-1ae985eb77ad | checkpoint | Primer installed
c9fdeded-e392-4991-87da-ba9fb75dd5b6 | section | Base Sheet
8a243a91-ec72-4427-a3ee-b272b5013f1f | checkpoint | Install from low to high
e1c521aa-774c-4e82-8dc5-6dc2c1af103a | checkpoint | Side laps a minimum of 80mm and end laps 150mm
355a33fc-9a18-49e3-b283-bcd62dc27529 | checkpoint | Check all welds at the end of the day
61e3364b-5fa7-4227-9eb2-d983041bd43c | section | Cap Sheet
ea8b5f52-3979-441a-83a0-9f63195072a4 | checkpoint | Install low to high
8fd3b93f-3c14-4477-8457-960b8d40507a | checkpoint | Side laps a minimum of 80mm and end laps 150mm
ad7614c5-f9ac-4d3c-a02c-3e3d385088f5 | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
f32a1393-e96d-4a44-9f44-426cc42aa222 | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
3e5fcec4-abfb-428e-b452-81521ee31470 | checkpoint | Membrane dressed into drains/outlets
d57a9383-4e20-4215-802d-fa5a33e0d1d8 | checkpoint | Install clamps/rings/baskets
6892eb69-aacf-47e2-94c1-66ad70903a43 | checkpoint | Flood/ILD test
2e065ac7-f421-4951-a78a-b2162b10b22d | section | Review and Sign Off
193c46be-61ba-418b-9fb3-5fce68b7c8aa | checkpoint | Area left clean and tidy
d2e66506-325c-4c6d-8f14-befcfa2fa7b3 | checkpoint | All installation work complete, checked and reviewed as per specification
11b4835b-5c31-4515-bb0c-432ee5232c87 | checkpoint | Client / Main Contractor sign off
232f0aae-dea5-4e43-8822-e7d0ee09c7af | checklist | QA - Torch on Warmroof Over Metal Deck Checklist |  | Torch on Warmroof Over Metal Deck Checklist
77394548-b3c8-4bc6-9171-ea08d56f1469 | section | Pre Start
4f65564f-0c37-441e-b154-658d96ce6460 | checkpoint | Area accessible
69f500be-9c33-4a39-a977-d639aa05683a | checkpoint | Edge protection and safety installed
e645d025-d0c5-4d54-b5f7-1ba076c917e2 | checkpoint | Substrate complete and ready for SWP
33555df9-0192-4a60-98a6-54a442c0fe33 | section | Metal Deck
1b1be2c9-ecae-40dd-b566-8efc93ebc019 | checkpoint | Timber to have separation barrier
e4d9ceae-52dc-4992-befa-ad3ede78b003 | checkpoint | Base deck screwed down in every pan
9fe1d488-b9ac-494b-b0a3-8382b78d3d4c | checkpoint | Sheet edges stitched together at 300mm centres
c7fb8c02-302c-442d-928c-0391aa3b9c70 | checkpoint | No sharp edges protruding
331edd7c-dd4e-4f17-97cd-7488090766ba | section | Vapour Control Layer
140982ac-9e9d-4169-a95f-6705b238838a | checkpoint | Is the substrate clean, dry and clear of swarf
d9abcc9d-8d8e-43a7-bb8e-3e2aa27610f9 | checkpoint | All areas covered and sheets lapped 50mm
e3390280-96e2-4ecc-9fe4-e57a6b1b1b57 | checkpoint | All holes/penetrations patched and water tight
c7f61498-7447-4a57-9591-0613b2f3f544 | section | Insulation
501973bd-8979-459b-8648-1e344baecd40 | checkpoint | Surface is dry prior to install
ed2545b5-7b5a-4d2d-9c6b-bdcdcb2e7c3a | checkpoint | Vapour control layer has been checked for no damage
952070de-d6d4-4901-812b-d70b7cafd37b | checkpoint | Insulation board installed
bd6ebde8-d67c-4133-8494-53b4b8162899 | checkpoint | Joints flush (no gaps between boards on ends)
86c9d913-db49-4320-8cb3-5419ac32e171 | section | Securock
154f7a37-6fb9-4f9e-ad6a-d433ebe4b377 | checkpoint | Is the surface dry
5ae243cd-c18d-4be6-9930-9f3e6c605dfe | checkpoint | Installed in brick pattern
dd07f32d-4881-4b93-b71f-79827a5e366c | checkpoint | Correct length screw with recessed flat plates
a1d73607-0935-4918-92e3-0d6cc433ce47 | checkpoint | Installed as per wind uplift fixing plan
f4c4b37e-0767-42e3-8260-d8dbaae911b7 | checkpoint | Prime of Securrock
d56afa5d-da61-4904-9994-25ccfe9f7fba | section | Base Sheet
c3c3fddd-e7d5-48c7-9952-f366610812b4 | checkpoint | Install from low to high
e9376fb3-2358-425b-a206-65b4940e0fac | checkpoint | Bleed of bitumen on overlap should be up to 10mm
0cdc8e26-9a1e-4d6d-af02-de98b7a014ce | checkpoint | Side laps a minimum of 80mm and end laps 150mm
ecae2ce9-1e98-4c01-a934-81d9a18f2e20 | checkpoint | Check of all welds at the end of the day
38c70c6f-8dd1-4ef7-bb18-aa4133dcb628 | section | Cap Sheet
13377fb6-3e4e-4094-991f-0fa4b75da15e | checkpoint | Install from low to high
4a723ed3-68df-4f5f-9fd7-65e4c16e828f | checkpoint | Side laps a minimum of 80mm and end laps 150mm
5f543895-f611-4f14-8451-09404d28e090 | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
9cd006e6-a64d-47fa-8728-2c4783814b09 | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
d49d543e-17c4-459e-978d-562e305a025d | checkpoint | Clamps / rings / baskets installed and press into overflows and outlets
bf741e5f-bc8e-4a7f-b2eb-fbad22c2a8c7 | checkpoint | Flood test / ILD tested
4b1081a1-14d0-4dda-a3b1-cd0649b55307 | section | Review and Sign Off
bb229b66-bfc2-4218-8436-68fd62a107be | checkpoint | Area left clean and tidy
57152840-0466-4d02-8cfd-efdbf94e67b5 | checkpoint | All installation work complete, checked and reviewed as per specification
0b38ee66-6a39-4bc5-8371-dd1a93664616 | checkpoint | Client / Main Contractor sign off
968042b7-d4ac-458c-acc3-5fc6216db67f | checklist | QA - Torch on Warmroof Over Plywood Checklist |  | Torch on Warmroof Over Plywood Checklist
d14f5340-be65-4003-a355-091bee84f256 | section | Pre Start
105b6423-97e6-4178-8de1-ae2dca06f579 | checkpoint | Area accessible
b8f94980-93bb-487f-a8fb-ca8884598674 | checkpoint | Edge protection and safety installed
3a2f3ec6-b7c6-48e7-bc5c-30c8db00af0b | checkpoint | Substrate complete and ready for SWP
4851ff82-d894-40d7-bc77-345fc6e868eb | section | Plywood
eb687085-0b6f-4724-953d-83368aa81112 | checkpoint | Plywood clean and dry. Free from dirt/debris and and ready for priming
67832b5a-f4f3-4d87-bf9c-ec3ad18946cb | checkpoint | No screws/nails/fixings popping up
afeac817-4a78-4bc6-9e9f-8003e80b240b | checkpoint | Plywood joints flush and even
f3100e1e-8a74-40c5-906d-12e41c38ad18 | section | Vapour Control Layer
50d51641-36e9-4e53-a4d0-939fc692753a | checkpoint | Is the substrate clean, dry and clear of swarf
b86d1300-27fb-4f37-a490-3c14c83e4af7 | checkpoint | All areas covered and sheets lapped 50mm
95331787-3760-4122-b3fe-17ed4a3a45b8 | checkpoint | All holes/penetrations patched and water tight
0bae44e8-d0fe-424d-b8b6-9e94aa3a2ddd | section | Insulation
a030f242-104d-4c61-bf20-814f40f352b1 | checkpoint | Surface is dry prior to install
12481597-5931-42cf-ac66-45ad96695fff | checkpoint | Vapour control layer has been checked for no damage
6890e408-7794-4e00-b1b0-b1ee2b327959 | checkpoint | Insulation board installed
007ec437-741a-4c10-bf5d-d1f45ec7030b | checkpoint | Joints flush (no gaps between boards on ends)
89df01de-1066-4941-9b6d-01aaff0829a8 | section | Securock
eba6acb2-7230-49c2-b2d8-61910c6e9157 | checkpoint | Is the surface dry
a459d960-3ee0-494f-91b0-4770b15e59e6 | checkpoint | Installed in brick pattern
566ae8c4-0848-4636-bcc9-b214f4c761b5 | checkpoint | Correct length screw with recessed flat plates
a2c26c63-47a9-4643-b9b6-2225645c7b30 | checkpoint | Prime of Securrock
f40e7265-f8d8-42ab-a8b7-356214ac5e3f | checkpoint | Installed as per wind uplift fixing plan
2f533505-822d-4e60-92e2-7ac5c97dea48 | section | Base Sheet
56fcd95a-57c3-4c7e-a785-3b2aadb71a8f | checkpoint | Install from low to high
eca98cb7-6ec8-424c-9abe-cf07058aa230 | checkpoint | Side laps a minimum of 80mm and end laps 150mm
e96cedcb-cbe9-4a78-9f7c-d7995ab1f028 | checkpoint | Check of all welds at the end of the day
3b2155e9-a2d8-4d3c-89d3-f7571ef59ef5 | section | Cap Sheet
4247130a-0a12-4470-a4b2-5d25c0a3500f | checkpoint | Install from low to high
ab67884a-c74d-47da-a2ea-cc03397be1f0 | checkpoint | Side laps a minimum of 80mm and end laps 150mm
0a2c739f-740f-4293-a6af-74f7f02cc3d1 | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
294a12fb-4dab-4a68-9d88-19dfdac3ea7a | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
f0c56533-706f-426b-bbed-d678ecc78212 | checkpoint | Clamps / rings / baskets installed and press into overflows and outlets
a5ab5558-cb24-4cdc-96b3-d4c1efeece9d | checkpoint | Flood test / ILD checked
cc4e1fda-4e4f-4ab4-8368-33b13ada89db | section | Review and Sign Off
505da9eb-a283-47de-b32f-2d085f873edb | checkpoint | Area left clean and tidy
da0accb2-74d6-4885-9fa1-fc32734f30b0 | checkpoint | All installation work complete, checked and reviewed as per specification
1ddf4f29-1bf1-4582-937e-aa25c8bdcf9e | checkpoint | Client / Main Contractor sign off
abe6635c-e062-48d3-b3b0-bafa9cd42440 | checklist | QA - Torch On Warmroof to Concrete Checklist |  | Torch On Warmroof to Concrete Checklist
f4f7a32d-5739-4231-b8f5-38286d9941e5 | section | Pre Start
a4b1adec-b3dd-46f6-942a-b88711012187 | checkpoint | Area accessible
c7e5f67e-cbd0-4875-80d2-6a1d339300b2 | checkpoint | Edge protection and safety installed
d7b19af3-7c08-4e59-9bbb-bdb164562e5f | checkpoint | Substrate complete and ready for SWP
44bf2d72-0354-42a7-9ed3-5f06bdfcae4b | section | Concrete
51620d20-4fd2-4ec3-85bb-7ab6ee796c72 | checkpoint | Concrete clean and dry. Free from dirt/debris and ready for priming
b4faa21f-717b-4edc-89cd-7104309544dc | checkpoint | All lumps and sharp concrete bits ground down/hammered down
f33d5691-6b71-4a97-a22c-d5d270e7f1fc | checkpoint | Large holes filled with grout
20832f07-cfdb-423a-af87-88126a38b1a0 | section | Vapour Control Layer
bad4f9fc-3b7c-4647-a85b-28acc6b9c45b | checkpoint | Is the substrate clean, dry and clear of swarf
bb1e601d-44ac-4c22-8f88-41d1672b62ea | checkpoint | All areas covered and sheets lapped 50mm
c9c8440e-65c8-4861-a9fa-537a15bedf65 | checkpoint | All holes/penetrations patched and water tight
e8278e06-c460-491b-8cd6-b69e6eb29dbc | section | Insulation
37553585-6192-48de-bf79-5ba65c381b30 | checkpoint | Surface is dry prior to install
ae8d4d1f-2464-4ac8-9f66-31075da964ca | checkpoint | Vapour control layer has been checked for no damage
fd45bcad-b217-42bd-ac60-05b6f52beb1d | checkpoint | Insulation board installed
469d7848-3da5-4822-ac24-50c4f879d53b | checkpoint | Joints flush (no gaps between boards on ends)
9a7db285-b672-450d-b87e-e58527eecfe5 | section | Securock
628a50f7-b84f-4b30-a304-3607269998e2 | checkpoint | Is the surface dry
d1b393c9-34fa-4b7c-9e36-bc221cce1bab | checkpoint | Installed in brick pattern
07b1c0fa-45dd-4d79-86c2-07df5f041089 | checkpoint | Correct length screw with load washer
a9dfd441-79d8-465e-84b1-12d4446e5f39 | checkpoint | Prime of Securrock
8c2560b2-3424-4130-972f-1d7c5d44e8ea | checkpoint | Installed as per wind uplift fixing plan
1e325f59-8bb5-43f6-98af-6cf54048062b | section | Base Sheet
39162d84-6f21-4e40-8cfc-2a81c58948e8 | checkpoint | Install from low to high
34d37eae-6c1f-4004-ad8d-75be78e90881 | checkpoint | Side laps a minimum of 80mm and end laps 150mm
65ca8e42-b9d7-4cf5-91c3-e2cd6bbfaf53 | checkpoint | Check of all welds at the end of the day
9edfedc9-61bc-4a33-aeeb-8bcdde798225 | section | Cap Sheet
e6488670-fc50-4dd4-aa2c-b66a3adb6dd8 | checkpoint | Install from low to high
89eaf531-09f8-4cd5-bcf5-56857533c22d | checkpoint | Side laps a minimum of 80mm and end laps 150mm
d7fcc3ec-9f92-41ee-843b-d1030a89c1a7 | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
60dd7ac7-ab1e-46d2-b969-b20d88c6fd94 | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
8410159c-3bc9-4def-b3ab-a2e315eeea9b | checkpoint | Clamps / rings / baskets press into overflows and outlets
00c432a5-05a3-450c-afe9-184cae95ad69 | checkpoint | Flood test / ELD tested
0ad3d7f5-9c92-4c78-8a5c-42722ddacb76 | section | Review and Sign Off
d844b1fc-2f54-4a29-abd3-9585e8eb4aae | checkpoint | Area left clean and tidy
ecf9002b-c06e-4ead-a8c0-c4b61e2abec4 | checkpoint | All installation work complete, checked and reviewed as per specification
87ae6d7e-eba2-4b51-bf67-cdd102e4d1c1 | checkpoint | Client / Main Contractor sign off
2ed2a50b-0b4c-4f7c-867f-0f8d69ee2235 | checklist | Supplier Site Visit |  | Site Visit date:
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
109d277e-bbe0-4f98-90fd-9e0c52493e00 | checkpoint-no-value | Site Details
6d41fa6a-4e1a-577e-a624-6bd736f97876 | textbox | Job Name
22044acf-ec81-5b86-a826-c71cabe41273 | textbox | Who is in attendance
1235194d-88da-53a0-854a-ce85145c2b1e | textbox | Area/Gridlines/Detail
6501caa1-756a-44d4-946f-6cbb27d16515 | checkpoint | Photos
e4f72de6-232e-5c0f-a8f5-0b30ac9ea698 | textbox | Inspection Notes
7374fd05-c95c-48e7-b2b3-1a705e8b607f | signoff | Signoff Required
5bbd62da-9df5-4091-bc01-560ad6b20884 | checklist | SWP - QA - Fibertite Overlay Install Checklist |  | Fibertite Overlay Install Checklist
9f1a5084-0681-4cfa-861a-116047e97aa9 | section | Prestart
2511ffab-72be-45af-9409-615eaa65ffe7 | checkpoint | Area accessible
8d2c60b5-8e49-4964-a0a2-825835fcfdca | checkpoint | Edge protection and safety installed
5eae10ca-a49d-485c-9c6f-8b3c7691bea0 | checkpoint | Substrate complete and ready for SWP
3baac257-db9f-48b6-8753-4876e6ae1ce5 | section | Substrate
57c0cb26-b03d-4d10-8c70-8b4ba7982118 | checkpoint | Mechanically Fix existing roof pans to Purlins after checking underneath from inside that we're not going to puncture pipes or wires
60c5c30d-3a0f-4859-a409-dbbcc3a18391 | checkpoint | Cut back existing roof edge at gutter
11066363-35f4-4055-9a47-0a81b18b2aa6 | checkpoint | Remove ridge as we go
6ba439ce-a14b-43a2-9dcc-e249a4bef352 | section | VCL-Vapour Control Layer
a7cc8212-4c11-43c9-89de-427dffd0bfc8 | checkpoint | Surface/Substrate is dry, clean and free from sharp edges
d139efe6-fa37-4cde-ba4e-e528154e8c3f | checkpoint | All areas covered and lapped a minimum of 100mm
c5d6d6c9-1543-4d61-981d-e36710914dbb | checkpoint | All holes/penetrations patched and made watertight
fb9d2624-a4a0-43a5-b89a-27a12dea0c9b | section | Roof Pan Infills
0cacb634-e8a5-4f6f-8e31-544ce9596e05 | checkpoint | Surface is dry before installing Poly
25b3d2f9-58b5-4ffd-bb13-eb045ba25ed2 | checkpoint | Infills to be a minimum 5mm above ridges on roof
094016f9-18b7-4c92-b852-212d4f8b1b22 | checkpoint | Every pan has been infilled
96931f12-88ac-47ac-817b-54aa03ef71d1 | section | Roofboard
2ce4b61c-a6e3-4d15-9db4-b690b021679d | checkpoint | Substrate/surface dry & clean prior to being installed
9204791c-540a-4ea1-8393-94ff9ceb9a2a | checkpoint | Installed in brick pattern
382cb6c9-f075-445a-b7d2-91e789fe415b | checkpoint | Correct screws with load washer
2c1b035a-d775-41b0-b839-f056e6f8b86a | checkpoint | Installed as per wind uplift fixing plan
21385575-13fb-4627-86fe-de7f34eba28c | checkpoint | Install 70mm X 100mm zincalume flashing at gutter edge for strength
6326799b-2558-4139-a661-78076c27bf66 | section | Fibertite
9ba12a2a-e49e-4adb-95cd-ac6abf891bcb | checkpoint | Correct Glue being used for substrate
2f6386b8-afd8-4c54-9867-f324e83734d9 | checkpoint | Fibertite fully glued to substrate
6823a9bb-668f-44bf-8705-fd5d992373ee | checkpoint | Broom/rolling of fibertite
996bbce8-a18e-43c4-8926-bcd75011a41b | checkpoint | Wipe/clean laps with acetone prior to welding
488203c8-1da5-4cfd-b79f-d978e490d1bd | checkpoint | All laps, details, penetrations fully welded/closed and QA'd with hook
bec6d345-44f2-4eef-b1db-090c2fc4a669 | checkpoint | Clamps / rings / baskets installed
5f7d7522-e981-4751-9de2-b0457f2d734e | checkpoint | Flooded / ILD checked
6a44c69e-996c-45bc-85c9-0aee6d604d21 | section | Fiberclad Flashings
e9fe4164-35a9-46e4-8a1e-c08ec95d6186 | checkpoint | Installed correctly
dc913626-704c-4faa-a60e-a7e71404a12a | checkpoint | Fixed down according to specification
1f8ea4b5-e277-4a50-9a17-a01bbea4ef2e | checkpoint | Cleaned down with acetone prior to welding
b7dd5ec9-76a0-4453-8c21-032599a382cd | checkpoint | Fibertite fully welded to flashing and QA'd with hook
4fb1b19c-b1b7-47cd-8d6f-a5897d5765c6 | section | Review and Sign Off
85acddc5-0c72-47bd-b007-e7706e096238 | checkpoint | Area left clean and tidy
f958d955-9ac9-4060-b06f-e5d257e96bb6 | checkpoint | All installation work complete, checked and reviewed as per specification
bba179f9-eb1c-437d-a91c-ef64f0eb037a | checkpoint | Client / Main Contractor sign off
ae5a6e4d-69db-4b0c-b39d-0981d53c0600 | checklist | SYS - PT - Job Details |  | Job Details
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
576c4e47-9f4b-4ee5-8062-6f9a20787ab2 | checkpoint | Site Info
4e739149-fe6d-425d-b45e-4a4ff63e7c1e | textbox | Site Address
e326d577-6e3a-40b7-870a-8e178eda7195 | textbox | Main Contractor Details
6c1ef37c-4d31-4405-b668-f398c4ad1275 | textbox | Project Managers Details
351c3436-2ae9-42ae-9ee9-1146e81bffa2 | textbox | Site Manager Details
f5800bbe-7c32-466d-8886-9878163ae1e2 | checkpoint | Latest Drawings
af459d4b-c4f3-423c-9cc8-95dde4efb567 | checkpoint | Scope of Works Attached
281a0ac9-8328-4d05-a088-8f7d68ec18b7 | checkpoint | Additional Pre Start Docs
a19b7e78-d4a4-45d8-b936-b4708a4f83f7 | checkpoint | Fixing Plan Attached
1e6ec163-a6b6-4f06-8f7d-57ccc433e15a | checklist | Weather Monitoring |  | Weather Monitoring
d6b774cb-130a-42c0-a21c-cc9929a42ba4 | section | Current Weather
238bfd3c-992c-41fb-9835-3997f56a6a9f | checkpoint | Wind / weather conditions
fe7887fc-304d-4c50-a589-0b6507f694c9 | checkpoint | Record any delays
4984f6be-5de4-4e2d-a2a2-a05bd6f97570 | checkpoint | area / gridlines
1fa11026-15e3-486a-a759-76758d985f6f | checkpoint | Comments / issues / observations
da632d1a-b844-427a-8686-1c0589ee7964 | section | Weather Forecast
c4f92cda-1e85-436f-bac8-58ffdfae37e6 | checkpoint | What is the weather forecast this week
6ca2a89c-0ed1-4f53-b146-8944c25919e0 | checkpoint | Record any delays
8fd408d8-4c83-437b-ba95-0f2e460de2dd | checkpoint | area / gridlines
005ddd7a-76bc-48b8-98b7-252bfbf0dca3 | checkpoint | Comments / issues / observations
4a1e8c1b-86ee-4b8e-b3d6-d2872aab6823 | checklist | Xtreme FibreTite Checklist |  | FiberTite Checklist - Area:
b5170213-cb05-46b1-bee6-34df80181b96 | section | Pre Start
b60ec657-6280-4608-952f-86fea30961d3 | checkpoint | Area Accessible
9c67e580-c4e7-427e-9c25-1b214d2aa885 | checkpoint | Edge protection and safety installed
bc66f1b8-562e-4009-8f98-7ee7a562c715 | checkpoint | Substrate complete and ready for SWP (metal/concrete/ply)
bacec411-caf3-41b9-b668-d1940c9681b8 | checkpoint | Perimeter support installed installed if metal deck substrate
aa1e89c2-9eb5-4db3-8c99-4fd3a292d3a9 | section | Metal Deck
e318fc34-6fed-4f4f-8e49-eabfab2bd4e4 | checkpoint | Timber to have separation barrier
ba572315-51bd-4192-a199-afee16ba3fd2 | checkpoint | Base deck screwed down in every pan
88ea16e7-fb99-496c-a58c-ee7b9c1dd1b8 | section | Vapour Control Layer
a6970b0d-9e46-433a-a6a8-e04b741597e9 | checkpoint | Is the substrate clean, dry and clear of swarf
529b1367-763e-4e98-82e7-6582b729e362 | checkpoint | All areas covered and sheets lapped 50mm
43101268-3b60-4818-93a4-74c3d1d465ca | checkpoint | All holes/penetrations patched and water tight
b96d9c27-0c36-4f8e-8395-673cde1f32e7 | section | Acoustic Board
534915ec-07dc-4ff1-a496-705064c1e332 | checkpoint | Is the surface dry
aa5a9fc5-8c63-4844-b428-f73d820fcb1c | checkpoint | Installed in brick pattern
6193b6cd-baf6-4264-b9de-4fa3d998facd | checkpoint | correct length screw with recessed flat plates
505e9651-bd4d-4709-a6a5-fb062e1ab40b | checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
c55f4c9f-2e5a-42cc-b8f0-55c6c2771842 | section | Insulation
f0946de9-40d7-4d99-80e2-71d323b8d83e | checkpoint | Surface is dry prior to install
ad06cf6a-26fa-4e64-a360-51dceef2bb2b | checkpoint | Vapour control layer has been checked for no damage
703de73b-d8c1-4046-9963-a2bc9e6f840c | checkpoint | Insulation board installed in a brick pattern
49fd1ff6-0831-4e2d-8584-234276aa840a | checkpoint | Joints flush (no gaps between boards on ends)
7520646e-f8d4-49a8-ad51-fe6f24fa71b2 | checkpoint | Fixings at correct spacing according to spec if no Securock in system.
cad39d0f-f87d-4c84-9cf7-cc8991f96e6b | section | HDP Roofboard
f1fa1c92-2785-44f2-94be-661610f84965 | checkpoint | Is the surface dry
7ca25981-403a-40a3-9596-60f9590b0294 | checkpoint | Installed in brick pattern
20e4bf34-13fc-4e2c-a820-8c90311c5e96 | checkpoint | correct length screw with recessed flat plates
28d6730c-856f-4a44-803b-510b25a305a1 | checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
a98b3e72-812d-4830-bf6e-85011e1a4016 | section | FiberTite
11f20c4b-069e-45ee-9353-05eb0ca5f6fa | checkpoint | Test weld with welding machine
0ea6caa8-5fa3-4363-b485-874f22a41734 | checkpoint | Adhesive installed to substrate
7c6766fa-2d3b-4608-885b-fdfbc259eb1b | checkpoint | Laying of membrane into the adhesive
7d5f4626-7048-41fe-b786-299412d443b0 | checkpoint | Broom/rolling of membrane
d117ae10-b7d4-440f-a10c-0a59e0eeeb01 | checkpoint | Wipe and clean of laps prior to welding
f8510daa-73b1-48a2-aa76-6920c3d1255b | checkpoint | Probe of seams with QA hook
24d957b9-c474-4421-a542-5d18e5ccc0d3 | checkpoint | Clamp and weld of outlets and overflows
d0a021e9-8733-4be1-8edc-d15bc20136d2 | checkpoint | Flood test of outlets
c5d6cba2-5ea0-4ae2-b08e-b50769928529 | section | Fiberclad flashings
f814d358-f585-4e0b-8511-050370d52495 | checkpoint | Installed correctly according to specifications (Right way around)
6ed75c3b-6f52-4d07-aa8a-07b1cc88e80c | checkpoint | Fixings and welding done according to specifications and details
3dce01fe-6711-4598-a03b-3d467c69436c | checkpoint | Probe of weld with QA hook
a56e8124-bfbb-42e3-904e-1df89928a02b | checkpoint | Area Complete (Request MC Signoff)

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
9800ea21-c34c-4b8a-b64d-3b8dbb4e7038 | checklist | SWP - QA - Fibertite Overlay Install Checklist (No Fiberclad Flashings) |  | Fibertite Overlay Install Checklist
9f1a5084-0681-4cfa-861a-116047e97aa9 | section | Prestart
2511ffab-72be-45af-9409-615eaa65ffe7 | checkpoint | Area accessible
8d2c60b5-8e49-4964-a0a2-825835fcfdca | checkpoint | Edge protection and safety installed
5eae10ca-a49d-485c-9c6f-8b3c7691bea0 | checkpoint | Substrate complete and ready for SWP
3baac257-db9f-48b6-8753-4876e6ae1ce5 | section | Substrate
57c0cb26-b03d-4d10-8c70-8b4ba7982118 | checkpoint | Mechanically Fix existing roof pans to Purlins after checking underneath from inside that we're not going to puncture pipes or wires
60c5c30d-3a0f-4859-a409-dbbcc3a18391 | checkpoint | Cut back existing roof edge at gutter
11066363-35f4-4055-9a47-0a81b18b2aa6 | checkpoint | Remove ridge as we go
6ba439ce-a14b-43a2-9dcc-e249a4bef352 | section | VCL-Vapour Control Layer
a7cc8212-4c11-43c9-89de-427dffd0bfc8 | checkpoint | Surface/Substrate is dry, clean and free from sharp edges
d139efe6-fa37-4cde-ba4e-e528154e8c3f | checkpoint | All areas covered and lapped a minimum of 100mm
c5d6d6c9-1543-4d61-981d-e36710914dbb | checkpoint | All holes/penetrations patched and made watertight
fb9d2624-a4a0-43a5-b89a-27a12dea0c9b | section | Roof Pan Infills
0cacb634-e8a5-4f6f-8e31-544ce9596e05 | checkpoint | Surface is dry before installing Poly
25b3d2f9-58b5-4ffd-bb13-eb045ba25ed2 | checkpoint | Infills to be a minimum 5mm above ridges on roof
094016f9-18b7-4c92-b852-212d4f8b1b22 | checkpoint | Every pan has been infilled
96931f12-88ac-47ac-817b-54aa03ef71d1 | section | Roofboard
2ce4b61c-a6e3-4d15-9db4-b690b021679d | checkpoint | Substrate/surface dry & clean prior to being installed
9204791c-540a-4ea1-8393-94ff9ceb9a2a | checkpoint | Installed in brick pattern
382cb6c9-f075-445a-b7d2-91e789fe415b | checkpoint | Correct screws with load washer
2c1b035a-d775-41b0-b839-f056e6f8b86a | checkpoint | Installed as per wind uplift fixing plan
21385575-13fb-4627-86fe-de7f34eba28c | checkpoint | Install 70mm X 100mm zincalume flashing at gutter edge for strength
6326799b-2558-4139-a661-78076c27bf66 | section | Fibertite
9ba12a2a-e49e-4adb-95cd-ac6abf891bcb | checkpoint | Correct Glue being used for substrate
2f6386b8-afd8-4c54-9867-f324e83734d9 | checkpoint | Fibertite fully glued to substrate
6823a9bb-668f-44bf-8705-fd5d992373ee | checkpoint | Broom/rolling of fibertite
996bbce8-a18e-43c4-8926-bcd75011a41b | checkpoint | Wipe/clean laps with acetone prior to welding
488203c8-1da5-4cfd-b79f-d978e490d1bd | checkpoint | All laps, details, penetrations fully welded/closed and QA'd with hook
bec6d345-44f2-4eef-b1db-090c2fc4a669 | checkpoint | Clamps / rings / baskets installed
5f7d7522-e981-4751-9de2-b0457f2d734e | checkpoint | Flooded / ILD checked
4fb1b19c-b1b7-47cd-8d6f-a5897d5765c6 | section | Review and Sign Off
85acddc5-0c72-47bd-b007-e7706e096238 | checkpoint | Area left clean and tidy
f958d955-9ac9-4060-b06f-e5d257e96bb6 | checkpoint | All installation work complete, checked and reviewed as per specification
bba179f9-eb1c-437d-a91c-ef64f0eb037a | checkpoint | Client / Main Contractor sign off