## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | SWP - QA - Fibertite Overlay Install Checklist (Non-masterlist) |  | Fibertite Overlay Install Checklist
9f1a5084-0681-4cfa-861a-116047e97aa9 | section | Prestart
2511ffab-72be-45af-9409-615eaa65ffe7 | checkpoint | Area accessible
8d2c60b5-8e49-4964-a0a2-825835fcfdca | checkpoint | Edge protection and safety installed
5eae10ca-a49d-485c-9c6f-8b3c7691bea0 | checkpoint | Substrate complete and ready for SWP
3baac257-db9f-48b6-8753-4876e6ae1ce5 | section | Substrate
57c0cb26-b03d-4d10-8c70-8b4ba7982118 | checkpoint | Mechanically Fix existing roof pans to Purlins after checking underneath from inside that we're not going to puncture pipes or wires
60c5c30d-3a0f-4859-a409-dbbcc3a18391 | checkpoint | Cut back existing roof edge at gutter
11066363-35f4-4055-9a47-0a81b18b2aa6 | checkpoint | Remove ridge as we go
6ba439ce-a14b-43a2-9dcc-e249a4bef352 | section | VCL-Vapour Control Layer
a7cc8212-4c11-43c9-89de-427dffd0bfc8 | checkpoint | Surface/Substrate is dry, clean and free from sharp edges
d139efe6-fa37-4cde-ba4e-e528154e8c3f | checkpoint | All areas covered and lapped a minimum of 100mm
c5d6d6c9-1543-4d61-981d-e36710914dbb | checkpoint | All holes/penetrations patched and made watertight
fb9d2624-a4a0-43a5-b89a-27a12dea0c9b | section | Roof Pan Infills
0cacb634-e8a5-4f6f-8e31-544ce9596e05 | checkpoint | Surface is dry before installing Poly
25b3d2f9-58b5-4ffd-bb13-eb045ba25ed2 | checkpoint | Infills to be a minimum 5mm above ridges on roof
094016f9-18b7-4c92-b852-212d4f8b1b22 | checkpoint | Every pan has been infilled
96931f12-88ac-47ac-817b-54aa03ef71d1 | section | Roofboard
2ce4b61c-a6e3-4d15-9db4-b690b021679d | checkpoint | Substrate/surface dry & clean prior to being installed
9204791c-540a-4ea1-8393-94ff9ceb9a2a | checkpoint | Installed in brick pattern
382cb6c9-f075-445a-b7d2-91e789fe415b | checkpoint | Correct screws with load washer
2c1b035a-d775-41b0-b839-f056e6f8b86a | checkpoint | Installed as per wind uplift fixing plan
21385575-13fb-4627-86fe-de7f34eba28c | checkpoint | Install 70mm X 100mm zincalume flashing at gutter edge for strength
6326799b-2558-4139-a661-78076c27bf66 | section | Fibertite
9ba12a2a-e49e-4adb-95cd-ac6abf891bcb | checkpoint | Correct Glue being used for substrate
2f6386b8-afd8-4c54-9867-f324e83734d9 | checkpoint | Fibertite fully glued to substrate
6823a9bb-668f-44bf-8705-fd5d992373ee | checkpoint | Broom/rolling of fibertite
996bbce8-a18e-43c4-8926-bcd75011a41b | checkpoint | Wipe/clean laps with acetone prior to welding
488203c8-1da5-4cfd-b79f-d978e490d1bd | checkpoint | All laps, details, penetrations fully welded/closed and QA'd with hook
bec6d345-44f2-4eef-b1db-090c2fc4a669 | checkpoint | Clamps / rings / baskets installed
5f7d7522-e981-4751-9de2-b0457f2d734e | checkpoint | Flooded / ILD checked
4fb1b19c-b1b7-47cd-8d6f-a5897d5765c6 | section | Review and Sign Off
85acddc5-0c72-47bd-b007-e7706e096238 | checkpoint | Area left clean and tidy
f958d955-9ac9-4060-b06f-e5d257e96bb6 | checkpoint | All installation work complete, checked and reviewed as per specification
bba179f9-eb1c-437d-a91c-ef64f0eb037a | checkpoint | Client / Main Contractor sign off