## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | FiberTite to plywood checklist (Sound Stage Gutters) |  | FiberTite to plywood checklist
e597f651-b7cf-4197-b1a3-47d65229f8c4 | section | Pre start
b1a266d8-5c97-48ec-bed3-c6dafbbb70df | checkpoint | Area accessible
6438325d-8c46-462f-a142-e50ca436dc56 | checkpoint | Edge protection and safety installed
a05e0a4b-10c8-4e49-b627-dc5b5683b253 | checkpoint | Visual inspection of substrate ready for SWP
f4a1c833-e30b-4d3c-8d41-86d06bd71bd9 | checkpoint | QA document received from previous trade from main contractor
a72d1446-cf15-4ad5-8c7c-034e3dcef7ba | checkpoint | Visual check no screws/nails/fixings popping up
8e564863-d52b-4d33-a034-f6e22cb23c61 | checkpoint | Visual check that joints are flush and even
b45aef9e-67b7-49ce-aea2-1c9278c8a72a | section | Plywood Substrate
8a95ca85-b187-4848-bca5-29e82114b287 | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
f8c63576-ca2f-4681-b704-38484db9da38 | section | FiberTite
ca39d303-81c9-4625-9b1a-b538655968a0 | checkpoint | Prime substrate where required
5cb9d079-ee83-49d2-9f50-bb0ec8a05347 | checkpoint | Adhesive installed to substrate
a64b0754-9b9c-4745-82db-c412960bba0d | checkpoint | Laying of membrane into adhesive
0d979b2d-ea08-4096-8e5e-ef301ef498f2 | checkpoint | Broom/rolling of membrane
d44b70f0-1255-4548-acd8-7f58aca42169 | checkpoint | Wipe and clean laps prior to welding
d5545d88-dcac-4d67-ada4-bbd33834112d | checkpoint | Test weld with welding machine
0e8b7478-e822-408d-9c57-9356fef9a043 | checkpoint | Probe of seam with QA hook
0e6af602-72f5-4495-9265-08a2dcb82baf | section | Fibre clad flashing
06f92e53-b30f-4323-8cd2-6b102aebc14d | checkpoint | Installed correctly according to specifications ( right way around )
2e750f46-c942-4756-afec-0a7d82bb28eb | checkpoint | Fixing and welding done according to specifications and details
eaa7e6c2-d348-41ce-ab27-77329bc05dd5 | checkpoint | Probe of seam with QA hook
e0620ea5-a64c-4fbb-8c7d-c54648b962c9 | section | Over flashings
9f279fd7-315c-486e-9917-301f7aa13d3e | checkpoint | Over flashings has a separation barrier
3996b49b-a2aa-447f-9f50-5aed5a0c63e2 | checkpoint | Fixings done according to specifications and details
23737ed0-8c5d-4f43-8c9a-390148b2b2db | checkpoint | Prime of Substrate where required
99eb4e45-36c4-4950-98e5-71f010a909de | checkpoint | Sealant installed
ef8a5f66-9cde-487c-b5f7-a38000c9d3f6 | section | Review and sign off
3add357d-82c9-4f77-a73d-0f0e9499b27d | checkpoint | Area left clean and tidy
25458fc0-a7ef-41f3-8483-1270d8440264 | checkpoint | All installation work completed, checked and reviewed as per specifications
e7d1bae9-774d-4786-af13-b84a0d288651 | signoff | Client/main contractor sign off