## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DTM-ITP-007- Concrete - Kerb, Footpaths & Islands | itp |  |  |  |  | DTM-ITP-007- Concrete - Kerb, Footpaths & Islands Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.3 - Submission & Approval of Concrete Mix Design
label | FREQUENCY: Prior to first concrete pour
label | ACCEPTANCE CRITERIA: The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent
label | REFERENCE DOCUMENTS: 610.07(b)
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed, Mix design approval
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works
label | REFERENCE DOCUMENTS: 703.17
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Excavation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
label | REFERENCE DOCUMENTS: 703.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Bedding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Depth and type of bedding material varies, refer to IFC and LGAT drawings
label | ○ Bedding shall be not less than 150 mm thick compacted for shared use paths
label | ○ Bedding shall be not less than 100 mm compacted thickness for footpaths and other surfacings
label | ○ Bedding trimmed, moistened, and compacted
label | REFERENCE DOCUMENTS: 703.21 Drawings, LGAT standard drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
date | Date Completed:
checkpoint | 2.5 - Formwork
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
label | REFERENCE DOCUMENTS: 703.12, AS 3610
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.6 - Reinforcement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Reinforment used shall consist of SL72 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
label | ○ Reinforcement must comply with the requirements of AS/NZS 4671
label | REFERENCE DOCUMENTS: 703.13, 703.16 LGAT TSD-R18
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed, Pre Pour Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.7 - Sampling Strength and Consistency
label | FREQUENCY: Each 50m3
label | ACCEPTANCE CRITERIA: Sampling and testing of the strength of concrete shall be carried out in accordance with clause 6.2 of AS 1379.
label | ○ The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and clause 5.2 of AS 1379.
label | ○ The temperature of concrete,measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | REFERENCE DOCUMENTS: 703.11, Table 703.111, 703.09, 610.17, AS1379
label | INSPECTION/TEST METHOD: Pre Pour Checklist
label | RECORD OF CONFORMITY: ITP Signed, Pre Pour Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.8 - Concrete Placement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
label | ○ Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
label | – N20 for island infills
label | – N25 for footpath, mowing strip, pram ramps
label | – N32 for kerb
label | REFERENCE DOCUMENTS: 703.05(a), 703.08, AS1379
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed, Pre Pour Checklist
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.9 - Record location of each batch
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Batch location recorded on Load Batch Traceability Checklist
label | REFERENCE DOCUMENTS: 610.15
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: This ITP Signed, Load batch tracebility checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.10 - Surface Finish
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete elements shall have a Class 3 surface finish (Good visual quality when viewed as a whole) for external surfaces and a Class 4 surface finish (Texture not important. Good general alignment) for permanently hidden surfaces in accordance with AS 3610.
label | ○ Footpaths and other Surfacing shall be compelted with a wooden float.
label | REFERENCE DOCUMENTS: 703.25
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.11 - Pram Crossings
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure that pram crossings are constructed in accordance with requirements for access and mobility.
label | ○ Type A and B pram crossings to be constructed as per LGAT Drawings TSD-R18
label | REFERENCE DOCUMENTS: IFC Drawings, LGAT TSD-R18
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.12 - Driveways - Acommodation Works
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Driveways to be constructed as per Accommodation Works Drawings and LGAT Drawings TSD-R09
label | REFERENCE DOCUMENTS: IFC Drawings, LGAT TSD-R09, Accommodation Works Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.13 - Joints
label | FREQUENCY: Each Joint
label | ACCEPTANCE CRITERIA: Expansion joints shall be installated at 18.3m regular intervals using 10mm compressible joint filler. Connolly joints at 6.1m regular intervals.
label | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
label | REFERENCE DOCUMENTS: 703.26, LGAT TSD-R11-v1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.14 - Protection of concrete
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | ○ No crossing until a minimum of 4 days from casting of concrete.
label | ○ Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | REFERENCE DOCUMENTS: 703.27
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
date | Date Completed:
checkpoint | 2.15 - Curing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete shall be cured immediately either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | ○ Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance
label | REFERENCE DOCUMENTS: 703.1
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed, Post Pour Checklist
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Tolerances
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
label | Section dimensions shall be constructed within the following tolerances:
label | ○ 5mm and 15mm for width; or
label | ○ ±3mm for dimensions less than 25mm.
label | REFERENCE DOCUMENTS: 703.15 Drawings
label | INSPECTION/TEST METHOD: As-Built Records
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 3.2 - Backfilling
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: After curing, no earlier than 3 days, backfilling shall be completed as per the below:
label | ○ Topsoil compacted in layers < 150mm
label | ○ Width ≥ 300mm behind edging to top of edging
label | REFERENCE DOCUMENTS: 703.29
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
date | Date Completed:
checkpoint | 3.3 - Compressive Strength Conformance
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The minimum compressive strength requirements for each concrete grade shall be as shown in Table 703.111.
label | ○ Compressive strength testing shall not be required for concrete used in extruded kerbs.
label | REFERENCE DOCUMENTS: 703.11, Table 703.111
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed, Test records
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | QAV - Print Name:
textbox | QAV - Position:
textbox | Fulton Hogan - Print Name:
textbox | Fulton Hogan - Position:
date | Work Completed On:
signoff | Add Signature