## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 561469-ITP-0001 - Culverts (DG-QA-TP018) | itp |  |  |  |  | 561469-ITP-0001 - Culverts (DG-QA-TP018)
section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint | 3.1 - Review all Drawings and Documents
label | Inspection Point: Quality Control Activity - Review all drawings and documentation provided to the Contractor.
label | Acceptance Criteria - Prior to the commencement of Works it must be ensure that all necessary documentation has been provided.
label | Verifying Document - ITP
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - R
label | Inspection: By (Role Key) - PM/QE
checkpoint | 3.2 - Setting Out Levels and Alignment
label | Inspection Point: Quality Control Activity - All setting out shall be performed by or under the control of a licensed surveyor, who shall certify the accuracy of key dimensions of the as constructed works. Specs 1000: 3.2.4
label | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
label | Verifying Document - Compliance surveys or spot checks
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual, Instrumental
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP/QE/SV
holdpoint | HOLD POINT
checkpoint | 3.3 - Service location and Hydro Vacumming
label | Inspection Point: Quality Control Activity - Physically locate the services inside and close to the alignment area and levels depth. Specs 1131: 15.2.1
label | Acceptance Criteria - All services identified in B4UDig, plans and mark outs has been physically located
label | Verifying Document - Plans Mark out, photos
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - H
label | Inspection: By (Role Key) - CR
holdpoint | HOLD POINT
checkpoint | 3.4 - Pipes Delivery
label | Inspection Point: Quality Control Activity - Pipes and pipe fittings shall be of the material, pipe class and joint type nominated on the Drawings. Specs 1131: 14.1 and Drawings C152 - C153
label | Acceptance Criteria - The charasteritics of the pipes delivered to site match the corresponding drawings details or approved equivalent
label | Verifying Document - Delivery docket, Supplier certificate, Photo
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/CR
checkpoint | 3.5 - Drainage Pipes Delivery
label | Inspection Point: Quality Control Activity - Drainage pipes shall be slotted smooth bore PVC or PE pipes, or corrugated polyethylene subsoil drainage pipes in accordance with NZTA F/5 for light duty applications or NZTA F2 for heay-duty applications. Specs 1131: 14.8
label | Acceptance Criteria - The charasteritics of the pipes delivered to site match the specifications and the duty requirments or approved equivalent
label | Verifying Document - Delivery docket, Supplier certificate, Photo
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/CR
checkpoint | 3.6 - Subsoil drain bedding
label | Inspection Point: Quality Control Activity - Material used for bedding, duct surround and haunching shall be selected granular, non cohesive, free draining material with grading between 0.6mm and 19mm. Maximum Dry Density (MDD) and Optimum Water Content (OWC) of the aggregate must be provided. Specs 1131: 14.8
label | Acceptance Criteria - Visual Inspection, Engineer approval
label | Verifying Document - Delivery Docket, Laboratory test results
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual, Lab Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - QE/SP/MC
holdpoint | HOLD POINT
checkpoint | 3.7 - Pipe Bedding Agregate
label | Inspection Point: Quality Control Activity - Pipe bedding should be AP20 and in accordance with AS/NZS 2566.2. Maximum Dry Density (MDD) and Optimum Water Content (OWC) of the aggregate must be provided. Specs 1131: 14.9.1
label | Acceptance Criteria - Visual Inspection, Engineer approval
label | Verifying Document - Delivery Docket, Laboratory test results
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual, Lab Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - QE/SP/MC
holdpoint | HOLD POINT
checkpoint | 3.8 - Drainage Aggregate
label | Inspection Point: Quality Control Activity - Drainage aggregate shall be 19 mm uniformly graded, clean, durable aggregate having a crushing resistance of not less than 100 kN when tested in accordance with NZS 4407. Material used for backfilling the trench above any geotextile wrapping shall be free draining granular material. Specs 1131: 14.9.2
label | Acceptance Criteria - Visual Inspection
label | Verifying Document - Delivery docket, Supplier certificate, Photo
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP/MC
checkpoint | 3.9 - Backfill Aggregate
label | Inspection Point: Quality Control Activity - Backfill aggregate should be GAP 65. Samples of backfill material should be tested in accordence of NZS 4402 to determine the MDD at OMC. The solid density of aggregate should be tested in accordance with NZS 4407. Specs 1131: 16.1.1
label | Acceptance Criteria - Visual Inspection, Engineer approval
label | Verifying Document - Delivery Docket, Laboratory test results
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual, Lab Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - QE/SP/MC
holdpoint | HOLD POINT
checkpoint | 3.10 - Concrete Manhole
label | Inspection Point: Quality Control Activity - Precast concrete manholes shall comply with NZS 3106. Specs 1131: 14.5
label | Acceptance Criteria - Manhole charasteritics Match NZS 3106
label | Verifying Document - Delivery docket, Supplier certificate, Photo
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP/MC
checkpoint | 3.11 - Wingwalls
label | Inspection Point: Quality Control Activity - Precast wingwalls as specified in Drawings or equivalent approved. Drawings C122 - C123
label | Acceptance Criteria - Procured precast wingwall comply with specifications
label | Verifying Document - Delivery docket, Photo, Engineer approval
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP/MC
checkpoint | 3.12 - Geotextile
label | Inspection Point: Quality Control Activity - Geotextile underlay bidim A37 or similar approved material. Drawings C122 - C123
label | Acceptance Criteria - Procured Geotextile comply with specifications
label | Verifying Document - Delivery docket, Photo, Engineer approval
label | Frequency - Prior to the commencement of Works
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP/MC
checkpoint | 3.13 - Backfill Trail Compaction Testing
label | Inspection Point: Quality Control Activity - Prior to commencement of fill compaction. Trial compaction plateau test should be conducted under presense of Engineer or principal. Methodology to be confirmed in advance generally in accordance with TNZ B/02 specification. Specs 1131: 16.1.1, 16.1.2, 16.1.4.
label | Acceptance Criteria - Compaction Value ≥ Specification Value
label | Verifying Document - Nuclear Density Meter (NDM) Results Sheet, or Clegg Hamer test records
label | Frequency - Prior to the commencement of Works.
label | Inspection Type (Visual, other) - On site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - QE/CR
holdpoint | HOLD POINT
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Site Clearance
label | Inspection Point: Quality Control Activity - The material obtained from site celarance must be dumped at an approved location outside the Site. Specs 1100: 5.1
label | Acceptance Criteria - Location approved by the Engineer
label | Verifying Document - Dumping Docket
label | Frequency - After site clearance
label | Inspection Type (Visual, other) - Document Check
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP/CR
checkpoint | 4.2 - Trees Removal
label | Inspection Point: Quality Control Activity - No tree shall be cut down until the Engineer has given written authorisation for such work to commence. Specs 1100: 6.2
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - Engineer Writen Authorisation
label | Frequency - Before remove any tree
label | Inspection Type (Visual, other) - Client Consultation
label | Inspection: Key - H
label | Inspection: By (Role Key) - CR
holdpoint | HOLD POINT
checkpoint | 4.3 - Removal of Topsoil
label | Inspection Point: Quality Control Activity - Topsoil shall be stockpiled in areas approved by the Engineer for this purpose. stockpiling operations must ensure the maximum utilisation of each area. Specs 1110: 9.4, TNZ F/1 Clause 4
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - Engineer Writen Authorisation
label | Frequency - Before Topsoil Removal
label | Inspection Type (Visual, other) - Client Consultation
label | Inspection: Key - C
label | Inspection: By (Role Key) - CR
checkpoint | 4.4 - Hazardous Waste and Contaminated soils
label | Inspection Point: Quality Control Activity - Contaminated soils (Type H materials) encountered shall be treated and/or disposed off site in accordance with statutory requirements. Specs 1110: 9.3
label | Acceptance Criteria - Dumping site approval for contamiantion type
label | Verifying Document - Dumping Docket
label | Frequency - If constaminated soils are found
label | Inspection Type (Visual, other) - Document Check
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP/CR
checkpoint | 4.5 - Trench Excavation
label | Inspection Point: Quality Control Activity - Trenches for flexible pipes shall be excavated within tollerances in table from Specs 1131: 15.2.5 unless otherwise stated.
label | Acceptance Criteria - Trench width and pipe clearance to walls comply with requirements
label | Verifying Document - Installation Check Sheet
label | Frequency - During trench excavation
label | Inspection Type (Visual, other) - Visual, Measurement Check
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.6 - Pipe Bedding and Haunching
label | Inspection Point: Quality Control Activity - Bedding and Haunching for flexible pipes should be in accordance with AS/NZS 2556.2 and have minimum embedment zone as shown in tabke from Specs 1131: 15.2.8.2
label | Acceptance Criteria - Bedding and haunching high and with comply width requirements
label | Verifying Document - Installation Check Sheet
label | Frequency - During bedding and haunching installation
label | Inspection Type (Visual, other) - Visual, Measurement Check
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.7 - Pipe Line and Level
label | Inspection Point: Quality Control Activity - Pipes shall be laid true to the design line and level within the tolerances specified in Specs 1131: 15.9. Invert levels shall take precedence over depths. Specs 1131: 15.3.12
label | Acceptance Criteria - Pipe levels are within the tolerance and according to the drawings, 2D data and linework provided or agreed with the Engineer
label | Verifying Document - Grade Check sheet
label | Frequency - During pipe installation
label | Inspection Type (Visual, other) - Visual, Instrumental
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP/QE/SV
checkpoint | 4.8 - PE Pipe Installation
label | Inspection Point: Quality Control Activity - Buried PE pipes shall be installed in accordance with AS/NZS 2033 and AS/NZA 2566.2, as applicable. Specs 1131: 15.3.2.2
label | Acceptance Criteria - PE Pipe Joints and Intallation comply with standard and specifications
label | Verifying Document - Pipe welds QA records, welding checksheets and machine printouts, destructive tests results (if required)
label | Frequency - Per weld, and during pipe installation
label | Inspection Type (Visual, other) - Visual, Document Check, Lab test (if required)
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.9 - PVC Pipe Installation
label | Inspection Point: Quality Control Activity - Buried PVC pipes shall be installed in accordance with AS/NZS 2032 and AS/NZS 2566.2, as applicable. Fusible PVC pipes shall be welded and installed in accordance with the pipe manufacturers recommendations. Specs 1131: 15.3.1.
label | Acceptance Criteria - PVC Pipes Joints and Intallation comply with standard and specifications
label | Verifying Document - Methodology, Pipe welds QA records, welding checksheets and machine printouts, destructive tests results (if required)
label | Frequency - Per joint or weld, and during pipe installation
label | Inspection Type (Visual, other) - Visual, Document Check, Lab test (if required)
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.10 - Precast Concrete Pipe Installation
label | Inspection Point: Quality Control Activity - Joints between precast pipe units shall be self-centering and shall be sealed with butyl mastic or similar approved to form a watertight joint. Concrete pipes shall be installed in accordance with AS/NZS 3725. Specs 1131: 15.3.6
label | Acceptance Criteria - Precast concrete pipes Joints and Intallation comply with standard and specifications
label | Verifying Document - Methodology. QA records
label | Frequency - Per joint, and during pipe installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.11 - Aggregate Compaction
label | Inspection Point: Quality Control Activity - Compaction shall be as stated in Specs 1131: 15.4.4. For concrete pipes the verification testing of compaction shall use a method recommended in table 3 of the CPAA Technical Note on Installing Concrete Pipe and approved by the Engineer. Specs 1131: 15.3.6
label | Acceptance Criteria - Compaction Value ≥ Specification Value
label | Verifying Document - Depending of Pipe material or Aggregate: CBR Checksheet, Nuclear Density Meter (NDM) Results Sheet, Clegg Hamer test records
label | Frequency - Every 50m of trench (not confirmed) or specified by Engineer
label | Inspection Type (Visual, other) - On site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - QE/CR
holdpoint | HOLD POINT
checkpoint | 4.12 - Backfill Compaction
label | Inspection Point: Quality Control Activity - Selected fill within 0.8m depth from finished surface shall be AP 65. Subgrade and subbase shall be compacted in layers no greater than 200 mm thick unless otherwise agreed with the Engineer. Under carriageway basecourse shall be compacted in layers no greater than 150mm thick unless otherwise aggred with the engineer. Specs 1131: 15.4.3.2, 15.4.3.3
label | Acceptance Criteria - Dry Density ≥ 95% MDD (Under Carriageway). Dry Density ≥ 90% MDD (Outside Carriageway)
label | Verifying Document - Nuclear Density Meter (NDM) Results Sheet or Clegg Hamer test records
label | Frequency - Every 20m of trench, each layer (Under Carriageway). Every 50m of trench, each layer (Outside Carriageway)
label | Inspection Type (Visual, other) - On site Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - QE/CR
holdpoint | HOLD POINT
checkpoint | 4.13 - Cutting pipes
label | Inspection Point: Quality Control Activity - Where pipes need to be cut to form non-stardard lengths, pipes shall be cut by a method which complies with manufacturers recommendations and provides a clean square profile. Specs 1131: 15.3.7
label | Acceptance Criteria - Pipe cutted up to the specifications
label | Verifying Document - Methodology, Photos
label | Frequency - During pipe installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.14 - Manhole Benching
label | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days. Semi-circular channels and fittings shall be placed in possition simultaneously with concrete benching and be embedded in true to grade level and line. All benching and sloping surfaces on manhole floor shall be rendered in 20mm thick 1:3 mortar and finished with steel trowel and rounded at corners. Specs 1131: 15.5
label | Acceptance Criteria - Benching built up to the specifications
label | Verifying Document - Methodology, Delivery Dockey, Photos
label | Frequency - During benching contruction
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.15 - Subsoil Drains Installation
label | Inspection Point: Quality Control Activity - Drains shall be constructed, geotextile layed and backfill carried out in accordance with TNZ Specification F/6. Specs 1131: 15.7
label | Acceptance Criteria - Benching built up to the specifications
label | Verifying Document - Methodology, TNZ Specifications F/6 and F/7, Photos, QA records
label | Frequency - During Drains Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.16 - Topsoiling and grassing
label | Inspection Point: Quality Control Activity - Topsoil shall be used to dress areas disturbed by the contrat works to a minimum thickness of 100mm. Grass seed shall be sown evenly over the prepared topsoil area. Specs 1131: 15.8.6
label | Acceptance Criteria - Topsoil installed and grass seed spread in the specified rate and mixture.
label | Verifying Document - QA records, Photos
label | Frequency - After compaction of final layer of backfill
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
checkpoint | 4.17 - Rock Riprap Instllation
label | Inspection Point: Quality Control Activity - Rock riprap shall comply with the dimensions and specifications shown in drawings. Drawings C123, C 152 - C155
label | Acceptance Criteria - Rock rip rap intalling according dimensions and specifications shown in cross sections of project drawings
label | Verifying Document - Installation Check Sheet, QA records, Photos
label | Frequency - During rock riprap installation
label | Inspection Type (Visual, other) - Visual, Measurement Check
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP
section | SECTION 5 – FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - As-built Drawings
label | Inspection Point: Quality Control Activity - Two hard copies and one electronic copy of As-built drawings shall be prepared in draft and final versions following Schedule 1D in NZS4404:2010. Specs 1000: 3.9.2
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - QA records
label | Frequency - At completion
label | Inspection: Key - H
label | Inspection: By (Role Key) - QE/CR
holdpoint | HOLD POINT
checkpoint | 5.2 - Gravity Pipes Testing
label | Inspection Point: Quality Control Activity - Stormwater pipes shall be by visual inspection for pipe diameters greater than 750mm and by water testing for diameters up to 750mm. Testing shall be in the presence of the engineer. Specs 1131: 16.2.1
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - Test Records
label | Frequency - For every section of pipe installed (24hr prior notice to the engineer before test)
label | Inspection Type (Visual, other) - Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - QE/CR
holdpoint | HOLD POINT
checkpoint | 5.3 - Manholes
label | Inspection Point: Quality Control Activity - Manholes should be tested seperately to pipeline for water tightness up to lower rim of manhole cover frame. Testing shall be in the presence of the engineer. Specs 1131: 16.2.2.5
label | Acceptance Criteria - A maximum drop in water level over 30 min should not exceed 2mL/hr/mm of diameter/meter height of the manhole. Engineer Approval
label | Verifying Document - Test Records
label | Frequency - For every manhole installed (24hr prior notice to the engineer before test)
label | Inspection Type (Visual, other) - Test
label | Inspection: Key - H
label | Inspection: By (Role Key) - QE/CR
holdpoint | HOLD POINT
checkpoint | 5.4 - CCTV Inspection
label | Inspection Point: Quality Control Activity - All pipelines shall pass a CCTV instpection. All pipelines shall be free of debris and flushed 24hrs prior to inspection. Specs 1131: 16.2.3
label | Acceptance Criteria - A pipeline will fail its inspection if:
label | – The pipe is horizontally misaligned or deformed by more than 5 % of the pipe diameter.
label | – The pipe has visible dips or ponding of water.
label | – The pipe has visible defects, such as open or displaced joints, defective or protruding laterals, cracked barrels or similar defects.
label | – There is evidence of infiltration at joints or laterals.
label | Verifying Document - CCTV footage and log sheets
label | Frequency - At every section of pipe installed.
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - H
label | Inspection: By (Role Key) - QE/CR
holdpoint | HOLD POINT
checkpoint | 5.5 - Surplus Materials and Refuse Disposal
label | Inspection Point: Quality Control Activity - All surplus, redundant and faulty materials must be removed from the Site and dispose of them in a safe and legal manner. Any demolition material or rubbish coming from the execution of the project must be removed as well. Specs 1000: 3.13.2
label | Frequency - At completion
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP/CR
checkpoint | 5.6 - Cleaning
label | Inspection Point: Quality Control Activity - Completed items of construction about to be placed in service or occupied for their intended use must be properly and thoroughly cleaned of all foreign matter and other debris. Specs 1000: 3.13.3
label | Frequency - At completion
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - QE/SP/CR