## ITP Cover Page
Earthworks Inspection and Test Plan - Berm backfill
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 003 - Berm backfill - Rev 0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 003 - Berm backfill
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | Issued For Construction
ITP Description: |  |  | Earthworks Inspection and Test Plan Berm backfill |  |  |  |  | Revision: | 1000 |  | 0
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-GEO
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Contract Specification
Quality Specified: |  |  | ISO9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-11-08 |  | Cordelia Girdler-Brown |  | Approved - Earthworks ITP split into 3 separate ITP's |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | Chris Benson | [5 empty] | Downer PM
Downer QM |  | Cordelia Girdler Brown | [5 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## Berm Backfill
Earthworks Inspection and Test Plan - Berm backfill
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 003 - Berm backfill - Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – PRE-CONSTRUCTION HOLD POINTS ( MATERIAL TESTING & APPROVALS)
1.1 | Imported Material Testing - Source Property Tests for Type A1 Imported Structural Fill - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
1.1.1 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB, or CA | Appendix XVIII PS 16.5.5 Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.2 | Los Angeles Abrasion Test | NZS4407:2015, Test 3.12 - The Abrasion Resistance of Aggregate by use of the Los Angeles Machine | 50% | PS 16.5.5 Appendix V | IANZ Accredited Report | 1 Test Required Results to Engineer 2 wks before importing | HP | ENG
1.1.3 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | No Particles >200mm Maximum fines 10% passing 75micron sieve | Appendix XVIII PS 16.5.5 Appendix V | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.1.4 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | Appendix XVIII Appendix V | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.5 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | >25% | PS 16.5.5 Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.6 | Solid Density | NZS4407:2015, Test 3.7.1 - The Solid Density of Aggregate Particles | Report Value Only | Appendix XVIII Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.7 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | Appendix XVIII Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.8 | Geotextile -Only Under Strutual Fill | The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation. | Engineers Approval | PS 16.5.7 Appendix V | Data Sheets | Results to Engineer for Approval | HP | ENG
1.1.9 | Laboratory Testing for Soil Suitability | Soil Test Results from Hill Laboratories to confirm that topsoil suitable to for reuse Soil Reaction Electrical Conductivity Mechanical Analysis (texture) Stone Content Nutrient Levels of nitrogen, available phosphorus, available potassium and available magnesium Organic Matter Content Check for Toxic or Hazardous substances | Engineers Approval | NZTA P39:2013 3.1 | Hill Laboratories Test Report | 10 equal samples taken from site, mixed together, then 1kg of soil sealed into a plastic bag and sent to lab for sampling | I | SE
SECTION 2 – CONSTRUCTION - STRUCTURAL FILL ON BERM AREA
2.1.1 | Compaction -Clegg Hammer | ASTM D5874-16:2016 Clegg Hammer Testing | Structural Fill Min CIV 18 Ave CIV 20 Non-Structural Fill Min CIV 10 Max CIV 12 | Appendix XVIII | Clegg Hammer Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift | I | SE
2.1.2 | Compaction-NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD Non Granular Material Max Air Voids 8% | Appendix XVIII | IANZ Accredited Report | 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed | I | SE
SECTION 3 – CONSTRUCTION - SITE WON LANDSCAPING FILL
3.1 | Type A3 Material - Site Won Landscaping Fill - Field Test
3.1.1 | On Site track-able Testing | Fine grained Type A3 site won materials may be considered suitable for use as landscape fill providing that it is ‘track-able’ by the contractor’s plant. | Trackable by Contractors Plant | PS 16.5.5 | Site Engineer Site Record | Before placing any fill each day for each area worked. | R | SE
3.1.2 | Shear Vane | NZ Geotechnical Society 2001 - Guideline for Hand Held Shear Vane Test. Fine grained Type A3 site won materials may be considered suitable for use as landscape fill providing that it meets minimum shear vane strength of 30kPa. | Min >30KPA | PS16.5.5 | Shear Vane Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed fill per 200mm vertical ‘lift’. | R | SE
3.1.3 | Proof Roll | Visual Inspection of Proof Roll | Visual Inspection | Appendix XVIII | Visual Site Record | Across Finished Area | I | ENG
SECTION 4 – CONSTRUCTION - TOPSOIL PLACEMENT
4.1 | Cut and fill embankments
4.1.1 | Topsoil Placement on cut and fill embankments | Confirmation of thickness and material suitability | Meets spec and thickness requirements as per drawings | PS 16.6.3 b) | Visual Observation | Once per lot after topsoil re-spread | I | SE
SECTION 5 – AS-BUILTS
5.1.1 | As-Builts | As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets. |  | PS 16.7.6 | Survey Records / Redpen markups | During Earthworks | D | SE