## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | HPP-UGL-CIV-GN-GEN-ITP-007 Kerb and Channel - Rev.0 | itp |  |  |  |  | HPP-UGL-CIV-GN-GEN-ITP-007 Kerb and Channel - Rev.0
section | 1.0 Preliminaries
checkpoint | 1.1 - Determine lot size
label | Ref docs - Spec. 0161 Quality [Cl 7.3]
label | Acceptance criteria - Lots to be broken up accordingly and outlined on a lot map
button | Acceptance | Yes,No,N/A
label | HPP Con Key - S
label | HPP QA Key - S
checkpoint | 1.2 - Concrete Mix Design
label | Ref docs - Spec. 1121 Open Drains [Cl 3.1]
label | Acceptance criteria - Submission of Mix Design and compliance certificates for concrete constituents
label | ○ HOLD POINT
button | Acceptance | Yes,No,N/A
label | HPP Con Key - H
label | HPP QA Key - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot map
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Underlying Lot Conformance
label | Ref docs - Underlying Lot ITP
label | Acceptance criteria - Underlying services and/or assets have been installed prior to commencing works over and/or above.
label | ○ Refer underlying lot ITP(s)
button | Acceptance | Yes,No,N/A
label | HPP Con Key - S
label | HPP QA Key - S
checkpoint | 1.4 - Survey set out
label | Ref docs - Drawings
label | Acceptance criteria - Set out the alignment and level of the kerb
button | Acceptance | Yes,No,N/A
label | HPP Con Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material Test Reports
section | 2.0 Kerb and channel placement
checkpoint | 2.1 - Foundation
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
label | Acceptance criteria - Shape and compact foundation material to the requirements of the respective pavement course
label | ○ HOLD POINT
label | ○ Notice: 1 working day before forming
button | Acceptance | Yes,No,N/A
label | HPP Con Key - H
label | HPP QA Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Concrete supply and placement
label | Ref docs - Spec. 0319 Minor Concrete Works [Cl 4.8, 4.9, 4.10, 4.11]
label | ○ Drawings
label | Acceptance criteria - Check docket to ensure strength and slump is as per design requirements
button | Acceptance | Yes,No,N/A
label | HPP Con Key - S
label | HPP QA Key - S
checkpoint | 2.3 - Finish
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
label | Acceptance criteria - Finish true to line: The top and face of the finished kerb and channel.
label | ○ Top surface: Uniform width, free from humps, sags and other irregularities.
label | ○ Type: Steel float finish or as otherwise shown on drawings.
button | Acceptance | Yes,No,N/A
label | HPP Con Key - H
label | HPP QA Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Joints - Contraction
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
label | Acceptance criteria - Contraction joints to conform to the following:
label | ○ Width: 5mm min.
label | ○ Depth: 20mm
label | ○ Intervals: every 3m for a min of 50% cross sectional area
label | ○ Tooling: 20mm depth / 5mm width
button | Acceptance | Yes,No,N/A
label | HPP Con Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
checkpoint | 2.5 - Joints – Expansion
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.3]
label | Acceptance criteria - Expansion joints to conform to the following:
label | ○ Width: 15mm
label | ○ Depth: Full depth of kerb/channel
label | ○ Intervals: Max interval 15m
label | ○ To be provided where channel/gutter abuts against pits, retaining walls, overbridges and both sides of kerb laybacks unless otherwise shown on drawings.
button | Acceptance | Yes,No,N/A
label | HPP Con Key - S
label | HPP QA Key - S
checkpoint | 2.6 - Backfill
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.4]
label | Acceptance criteria - Timing: Backfill behind kerb no earlier than 3 days after concreting.
label | ○ Material: Granular material, free of organic material, clay and rock in excess of 50mm or approval material
label | ○ Layers: Compact in layers not greater than150mm
label | ○ WITNESS POINT
label | ○ 1 Working days before backfilling behind kerb
label | ○ 3 Working days before to backfilling gutter pavement
button | Acceptance | Yes,No,N/A
label | HPP Con Key - S
label | HPP QA Key - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test reports
section | 3.0 Conformance check
checkpoint | 3.1 - Survey Report
label | Ref docs - Spec. 1121 Open drain including K&C [Cl 4.0]
label | Acceptance criteria - Survey report verifying kerb and gutter has been constructed within tolerance:
label | ○ Finish levels of channel/gutter surface: within ± 10mm of design level
label | ○ Surface deviation of kerb face and channel surface: ±5 mm from edge of a 3m straight edge, except at laybacks, grade changes or curves, or at gully pits requiring channel/gutter depression.
button | Acceptance | Yes,No,N/A
label | HPP Con Key - S
label | HPP QA Key - S
checkpoint | 3.2 - Acceptance and closure of non-conforming items
label | Ref docs - Spec. 0161 Quality [Cl 3.8]
label | Acceptance criteria - NCRs to be opened for non-conforming items and closed prior to closing construction lot.
label | ○ HOLD POINT
button | Acceptance | Yes,No,N/A
label | HPP Con Key - H
label | HPP QA Key - H
holdpoint | AUTHORITY HOLDPOINT