## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Brickwork |  |  |  |  | Yes | Brickwork | 8ab589a5-822f-498e-9b49-0722664fb86c
checkpoint-group |  |  | section | Mortar
checkpoint-status |  |  | checkpoint | Mortar Colour
label | 16e879fe-e5dc-5232-9b72-113c351a896f |  | note | As per sample panel
checkpoint-status |  |  | checkpoint | Mortar Classification
label | e2dc197a-c7c4-5007-8d2f-d72e1195a34d |  | note | Class M3 as per AS 3700 adequate (composition e.g. 1 cement, 1 lime, 6 sand)
checkpoint-group |  |  | section | Deliveries
checkpoint-status |  |  | checkpoint | Material inspection on delivery
label | ca7d852a-b896-5935-8414-913233243ffa |  | note | Check for defective bricks, including any chips or cracks.
checkpoint-group |  |  | section | Lay Work
checkpoint-status |  |  | checkpoint | Verify set – out drawing reference
checkpoint-status |  |  | checkpoint | All joints & perps are to be filled
checkpoint-status |  |  | checkpoint | Check cavity flashings for correct installation and cleanliness
checkpoint-status |  |  | checkpoint | Check for correct spacing of weep holes. Ensure weep holes are installed in first two courses as per the inhabit design
label | cb169622-86c7-5abf-98c8-d84d0e6e6f48 |  | note | Weep Holes to be no less than immediately above the flashing, at centers not exceeding 1200mm as per 14522-CAN-FC0001(02)
checkpoint-status |  |  | checkpoint | Provide sliding horizontal ties across joints in unreinforced walls
checkpoint-status |  |  | checkpoint | Check Masonry ties are galvanised steel (Grade Type 316) must be provided at 600mm maximum centre and at 300mm centres along edges of all openings and vertical joints.
label | 1942fdc6-7a79-5a03-95f6-4dc1064114fa |  | note | As per ST-0002[6]SG01-03
checkpoint-status |  |  | checkpoint | Non-load bearing brick walls shall finish 10-20mm short of slab soffit and shall be fastened to the soffit using the specified ties
label | 72fb1376-4f73-5655-9121-6d9e432158ba |  | note | As per 14522-CAN-FC0001(02)
checkpoint-status |  |  | checkpoint | Check expansion joint frequency is at maximum 6m and expansion joints over construction joints
label | 7fa2f813-7eb7-539d-b79c-286274f6b0c8 |  | note | As per 14522-CAN-FC0001(02)
checkpoint-status |  |  | checkpoint | Door jambs and openings check for plump, level, correct position and height
label | ff4db881-eb90-5729-9258-c9253f16af95 |  | note | As per AR-9200 and AR-9201
checkpoint-group |  |  | section | Clean Up
checkpoint-status |  |  | checkpoint | Brush down exposed faced walls
checkpoint-status |  |  | checkpoint | Check all preps & horizontal joints filled
checkpoint-status |  |  | checkpoint | Rubbish removed & placed in bins
checkpoint-status |  |  | checkpoint | Floors Scraped & brushed clean
checkpoint-group |  |  | section | Inspection
checkpoint-status |  |  | checkpoint | Check brick alignment, consistency & positioning
checkpoint-status |  |  | checkpoint | Check mortar finish
checkpoint-status |  |  | checkpoint | Check clean up
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | Work area has been cleaned up and made safe.
checkpoint-status |  |  | checkpoint | ITP has been completed all actions signed off and records referenced have been reviewed and collected and attached.