## Manukau Health Park - Tracker
Window No | Frame Type | Frame size (HxW) | Opening check (HxW) | Batch No | Delivery ETA | Handover | LEVEL/ PLUMB | PEF ROD/ PACKERS | SEALANT | SEISMIC WEDGED | GLAZED | Status | Comments
Shop drawing
Short assembly
prestarts
toolbox
Access
Phlebotomy
D.G12A.01 | 100MM SHOPFRONT | 3065X3990 | 3065x3950 |  | 2023-10-05 | [6 empty] | Glazed | 3965-15mm jib, 1262+1802mm=3064mm, Auto door installed
W.G12.01 | 100MM SHOPFRONT | 3080X5294 | 3072X5255 |  | 2023-10-05 | [6 empty] | Glazed | 5270-15mm jib, 5mm high spot sill 1095+1976=3071mm H
W.G13.01 | VANTAGE 40mm WINDOW | 1940X895 | 1955x905 |  | 2023-09-05 | [6 empty] | Glazed | Timber
W.G13.01 | VANTAGE 40mm WINDOW | 1940X895 | 1955x905 |  | 2023-10-05 | [6 empty] | Glazed
W.G14.01 | VANTAGE 40mm WINDOW | 1940X895 | 1960x905 |  | 2023-10-05 | [6 empty] | Glazed
W.G14.01 | VANTAGE 40mm WINDOW | 1940X895 | 1960x905 |  | 2023-10-05 | [6 empty] | Glazed
East Building
Ground Floor West |  |  |  | 3 | [7 empty] | Ordered
WE-00.B46-2 | 125mm Flush glaze | 2660x1270 |  | 3 | [7 empty] | Ordered
WE-00.B46-1 | 125mm Flush glaze | 2660x620 |  | 3 | [7 empty] | Ordered
WE-00.B02-1 | 125mm Flush glaze | 2660x920 |  | 3 | [7 empty] | Ordered
WE-00.B05-1 | 125mm Flush glaze | 2660x620 |  | 3 | [7 empty] | Ordered
WE-00.B09-1 | 125mm Flush glaze | 2660x920 |  | 3 | [7 empty] | Ordered
WE-00.B12-1 | 125mm Flush glaze | 2660x620 |  | 3 | [7 empty] | Ordered
WE-00.B13-1 | 125mm Flush glaze | 2660x920 |  | 3 | [7 empty] | Ordered
DE-00.B14-1 | 125mm Flush glaze open out Magnum door | 2805x960 |  | 3 | [7 empty] | Ordered
WE-00.B14-1 | 125mm Flush glaze | 2660x620 |  | 3 | [7 empty] | Ordered
Ground floor north
WE-00.BO1-1 | 40mm seismic | 2657x620 |  | 3 | [7 empty] | Ordered
WE-B01.G01-1 | 40mm seismic | 3871x620 |  | 3 | [7 empty] | Ordered
WE-00.B01-2 | 40mm seismic | 2657x620 |  | 3 | [7 empty] | Ordered
WE-B01.G01-2 | 40mm seismic | 3871x620 |  | 3 | [7 empty] | Ordered
WE-00.B14-2 | 125mm Flush glaze | 2660x920 |  | 3 | [7 empty] | Ordered
WE-00.B14-3 | 125mm Flush glaze | 2660x2170 |  | 3 | [7 empty] | Ordered
WE-00.B15-1 | 125mm Flush glaze | 2660x920 |  | 3 | [7 empty] | Ordered
WE-00.B16-2 | 125mm Flush glaze | 2660x620 |  | 3 | [7 empty] | Ordered
WE-00.B21-1 | 125mm Flush glaze | 2660x920 |  | 3 | [7 empty] | Ordered
WE-00.B22-1 | 125mm Flush glaze | 2660x920 |  | 3 | [7 empty] | Ordered
Ground floor East
WE-00.B22-2 | 125mm Flush glaze | 2660x620 |  | 4 | [7 empty] | Ordered
WE-00.B22-3 | 125mm Flush glaze | 2660x620 |  | 4 | [7 empty] | Ordered
WE-00.B24-1 | 125mm Flush glaze | 2660x920 |  | 4 | [7 empty] | Ordered
WE-00.B26-1 | 125mm Flush glaze | 2660x920 |  | 4 | [7 empty] | Ordered
WE-00.B28-1 | 125mm Flush glaze | 2660x620 |  | 4 | [7 empty] | Ordered
WE-00.B33-1 | 125mm Flush glaze | 2660x920 |  | 4 | [7 empty] | Ordered
WE-00.B31-1 | 125mm Flush glaze | 2660x620 |  | 4 | [7 empty] | Ordered
WE-00.B34-1 | 125mm Flush glaze | 2660x2170 |  | 4 | [7 empty] | Ordered
WE-00.B35-1 | 125mm Flush glaze | 2660x620 |  | 4 | [7 empty] | Ordered
WE-00.B36-1 | 125mm Flush glaze | 2660x920 |  | 4 | [7 empty] | Ordered
Ground floor south
WE-00.B36-2 | 125mm Flush glaze | 2660x920 |  | 4 | [7 empty] | Ordered
WE-00.B36-1 | 125mm Flush glaze | 2660x620 |  | 4 | [7 empty] | Ordered
WE-00.B39-2 | 125mm Flush glaze | 2660x920 |  | 4 | [7 empty] | Ordered
WE-00.B39-1 | 125mm Flush glaze | 2660x620 |  | 4 | [7 empty] | Ordered
WE-00.B46-4 | 125mm Flush glaze | 2660x620 |  | 4 | [7 empty] | Ordered
WE-00.B46-3 | 125mm Flush glaze | 2660x920 |  | 4 | [7 empty] | Ordered
WE-00.BO1-4 | 40mm seismic | 2657x620 |  | 4 | [7 empty] | Ordered
WE-01.G01-4 | 40mm seismic | 3871x620 |  | 4 | [7 empty] | Ordered
WE-00.BO1-3 | 40mm seismic | 2657x620 |  | 4 | [7 empty] | Ordered
WE-01.G01-4 | 40mm seismic | 3871x620 |  | 4 | [7 empty] | Ordered
Level 1 West
WE-01.G39-2 | 125mm Flush glaze | 2820x1260 |  | 1 | [7 empty] | Ordered
L!-LV-16 | Louvre | 741x670 | [9 empty] | Ordered
WE-01.G39-1 | 125mm Flush glaze | 2820x670 |  | 1 | [7 empty] | Ordered
GL-LV-16 | Louvre | 1127x670 | [9 empty] | Ordered
WE-01.G03-1 | 125mm Flush glaze | 2820x1048 |  | 1 | [7 empty] | Ordered
L!-LV-15 | Louvre | 741x1372 | [9 empty] | Ordered
WE-01.G05-1 | 125mm Flush glaze | 2820x1372 |  | 1 | [7 empty] | Ordered
GL-LV-15 | Louvre | 1127x1372 | [9 empty] | Ordered
WE-01.G06-2 | 125mm Flush glaze | 2820x1080 |  | 1 | [7 empty] | Ordered
WE-01.G06-1 | 125mm Flush glaze | 2820x595 |  | 1 | [7 empty] | Ordered
L1-LV-12 | Louvre | 741x1359 | [9 empty] | Ordered
WE-01.G09-2 | 125mm Flush glaze | 2820x1359 |  | 1 | [7 empty] | Ordered
GL-LV-12 | Louvre | 1127x1359 | [9 empty] | Ordered
L1-LV-14 | Louvre | 741x746 | [9 empty] | Ordered
WE-01.G09-1 | 125mm Flush glaze | 2820x746 |  | 1 | [7 empty] | Ordered
GL-LV-14 | Louvre | 1127x746 | [9 empty] | Ordered
L1-LV-13 | Louvre | 741x580 | [9 empty] | Ordered
WE-01.G11-1 | 125mm Flush glaze | 2820x580 | 2815x606 | 1 | [7 empty] | Ordered
GL-LV-13 | Louvre | 1127x580 | [9 empty] | Ordered
WE-01.G12-1 | 125mm Flush glaze | 2820x1420 | 2815x1455 | 1 | [7 empty] | Ordered
Level 1 north
WE-01.G12-2 | 125mm Flush glaze | 2820x884 |  | 1 | [7 empty] | Ordered
WE-01.G12-3 | 125mm Flush glaze | 2820x602 |  | 1 | [7 empty] | Ordered
L1-LV-04 | Louvre | 741x1970 | [9 empty] | Ordered
WE-01.G15-1 | 125mm Flush glaze | 2820x1970 |  | 1 | [7 empty] | Ordered
GL-LV-04 | Louvre | 1127x1970 | [9 empty] | Ordered
L1-LV-03 | Louvre | 741x720 | [9 empty] | Ordered
WE-01.G13-1 | 125mm Flush glaze | 2820x720 |  | 1 | [7 empty] | Ordered
GL-LV-03 | Louvre | 1127x720 | [9 empty] | Ordered
WE-01.G18-1 | 125mm Flush glaze | 2820x770 |  | 1 | [7 empty] | Ordered
L1-LV-1-02 | Louvre | 741x1481 | [9 empty] | Ordered
WE-01.G19-1 | 125mm Flush glaze | 2820x1481 |  | 1 | [7 empty] | Ordered
GL-LV-02 | Louvre | 1127x1481 | [9 empty] | Ordered
L1-LV-1-01 | Louvre | 741x1075 | [9 empty] | Ordered
WE-01.G19-2 | 125mm Flush glaze | 2820x1075 |  | 1 | [7 empty] | Ordered
GL-LV-01 | Louvre | 1127x1075 | [9 empty] | Ordered
WE-01.G20-1 | 125mm Flush glaze | 2820x1904 |  | 1 | [7 empty] | Ordered
Level 1 East
WE-01.G20-2 | 125mm Flush glaze | 2820x818 |  | 2 | [7 empty] | Ordered
L1-LV-11 | Louvre | 741x1130 | [9 empty] | Ordered
WE-01.G20-3 | 125mm Flush glaze | 2820x1130 |  | 2 | [7 empty] | Ordered
GL-LV-11 | Louvre | 1127x1130 | [9 empty] | Ordered
L1-LV-10 | Louvre | 741x570 | [9 empty] | Ordered
WE-01.G22-1 | 125mm Flush glaze | 2820x570 |  | 2 | [7 empty] | Ordered
GL-LV-10 | Louvre | 1127x570 | [9 empty] | Ordered
WE-01.G24-1 | 125mm Flush glaze | 2820x1216 |  | 2 | [7 empty] | Ordered
WE-01.G28-1 | 125mm Flush glaze | 2820x482 |  | 2 | [7 empty] | Ordered
WE-01.G29-1 | 125mm Flush glaze | 2820x482 |  | 2 | [7 empty] | Ordered
WE-01.G29-2 | 125mm Flush glaze | 2820x463 |  | 2 | [7 empty] | Ordered
WE-01.G30-1 | 125mm Flush glaze | 2820x463 |  | 2 | [7 empty] | Ordered
WE-01.G30-2 | 125mm Flush glaze | 2820x503 |  | 2 | [7 empty] | Ordered
WE-01.G32-1 | 125mm Flush glaze | 2820x790 |  | 2 | [7 empty] | Ordered
L1-LV-09 | Louvre | 741x2170 | [9 empty] | Ordered
WE-01.G33-1 | 125mm Flush glaze | 2820x2170 |  | 2 | [7 empty] | Ordered
GL-LV-08 | Louvre | 1127x2170 | [9 empty] | Ordered
L1-LV-08 | Louvre | 741x1270 | [9 empty] | Ordered
WE-01.G35-6 | 125mm Flush glaze | 2820x1270 |  | 2 | [7 empty] | Ordered
GL-LV-08 | Louvre | 1127x1270 | [9 empty] | Ordered
WE-01.G35-5 | 125mm Flush glaze | 2820x920 |  | 2 | [7 empty] | Ordered
Level 1 south
WE-01.G35-4 | 125mm Flush glaze | 2820x1270 |  | 2 | [7 empty] | Ordered
WE-01.G35-3 | 125mm Flush glaze | 2820x919 |  | 2 | [7 empty] | Ordered
L1-LV-07 | Louvre | 741x1770 | [9 empty] | Ordered
WE-01.G35-2 | 125mm Flush glaze | 2820x1770 |  | 2 | [7 empty] | Ordered
GL-LV-07 | Louvre | 1127x1770 | [9 empty] | Ordered
L1-LV-06 | Louvre | 741x1122 | [9 empty] | Ordered
WE-01.G35-1 | 125mm Flush glaze | 2820x1122 |  | 2 | [7 empty] | Ordered
GL-LV-06 | Louvre | 1127x1122 | [9 empty] | Ordered
L1-LV-05 | Louvre | 741x1318 | [9 empty] | Ordered
WE-01.G36-1 | 125mm Flush glaze | 2820x1318 |  | 2 | [7 empty] | Ordered
GL-LV-05 | Louvre | 1127x1318 | [9 empty] | Ordered
L1-LV-03 | Louvre | 741x720 | [9 empty] | Ordered
WE-01.G38-1 | 125mm Flush glaze | 2820x720 |  | 2 | [7 empty] | Ordered
GL-LV-03 | Louvre | 1127x720 | [9 empty] | Ordered
WE-01.G39-4/DE-01.G39-1 | 125mm Flush glaze/Magnum door |  |  | 2 | [7 empty] | Ordered
West Building
North Elevation |  |  |  | 5 | [8 empty] | 14
D.N.0.01 | 125mm Flush glaze/magnum swing | 2730x1860 |  | 5
W.N.0.16 | 125mm Flush glaze | 2530x980 |  | 5
W.N.0.01 | 125mm Flush glaze | 980x2380 |  | 5
W.N.0.02 | 125mm Flush glaze | 980x2380 |  | 5
W.N.0.03 | 125mm Flush glaze | 980x914 |  | 5
W.N.0.04 | 125mm Flush glaze | 980x963 |  | 5
W.N.0.05 | 125mm Flush glaze | 980x1180 |  | 5
W.N.0.06/Jockey sash | 125mm Flush glaze | 980x1180 |  | 5
W.N.0.07 | 125mm Flush glaze | 980x2380 |  | 5
W.N.0.08 | 125mm Flush glaze | 980x1180 |  | 5
W.N.0.11 | 125mm Flush glaze | 980x1180 |  | 5
W.N.0.12 | 125mm Flush glaze | 980x1180 |  | 5
W.N.0.13 | 125mm Flush glaze | 980x1180 |  | 5
W.N.0.14 | 125mm Flush glaze | 980x1180 |  | 5
West Elevation |  |  |  | 5 | [8 empty] | 10
W.W.0.01, W.W.0.02, D.W.0.01 | 125mm Flush glaze/Magnum door | 2730x3860 |  | 5
W.W.0.03 | 125mm Flush glaze | 2530x1980 |  | 5
W.W.0.04 | 125mm Flush glaze | 2530x980 |  | 5
W.W.0.05 | 125mm Flush glaze | 980x1980 |  | 5
W.W.0.06 | 125mm Flush glaze | 2530x1980 |  | 5
W.W.0.07 | 125mm Flush glaze | 980x1180 |  | 5
W.W.0.08 | 125mm Flush glaze | 2530x1980 |  | 5
W.W.0.10 | 125mm Flush glaze | 980x1180 |  | 5
W.W.0.11 | 125mm Flush glaze | 980x1180 |  | 5
W.W.0.12 | 125mm Flush glaze | 980x1180 |  | 5
East Elevation
W.E.0.01/Jockey sash | 125mm Flush glaze | 980x1780 |  | 6
W.E.0.02/Jockey sash | 125mm Flush glaze | 980x1780 |  | 6
W.E.0.03/Jockey sash | 125mm Flush glaze | 980x1780 |  | 6
W.E.0.04/Jockey sash | 125mm Flush glaze | 980x1780 |  | 6
W.E.0.05/Jockey sash | 125mm Flush glaze | 980x1780 |  | 6
EAST LINK ELEVATION
W.E.0.06 | 125mm Flush glaze | 2530x1980 |  | 6
W.E.0.07 | 125mm Flush glaze | 2530x1980 |  | 6
W.E.0.08 | 125mm Flush glaze | 2530x980 |  | 6
W.E.0.09 | 125mm Flush glaze | 2530x980 |  | 6
W.E.0.10 | 125mm Flush glaze | 2530x980 |  | 6
W.E.0.11 | 125mm Flush glaze | 2530x1980 |  | 6
W.E.0.12 | 125mm Flush glaze | 2530x980 |  | 6
W.E.0.13 | 125mm Flush glaze | 2530x1980 |  | 6
W.E.0.14 | 125mm Flush glaze | 2730x4403 |  | 6
W.E.0.15 | 125mm Flush glaze | 2730x2533 |  | 6