## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 26ef4c60-a9ab-4ad1-a794-9132723b6cad |  | checklist | SPLIT AC Commissioning |  |  |  |  | Yes | Commissioning ITP - SPLIT AC Commissioning Checklist | 03f88aa9-3c28-4878-af48-4f437639328a
checkpoint-status | 92a7ae86-cfcb-481a-b062-f1bf4c3d171b |  | checkpoint | Check all terminations
checkpoint-status | 054b1d78-c1f6-4c59-aabd-f9c64a6e475e |  | checkpoint | Power supply to condensing unit Voltage
checkpoint-status | 209a07b6-2b0d-40ed-87b1-c8999b6952b6 |  | checkpoint | Power on indoor unit
checkpoint-status | 8ed19f5f-15e6-4710-b128-ef93abb4e1f2 |  | checkpoint | Local controller operational
checkpoint-status | 283e5e61-ec53-4861-9dee-85ed3ea44fbe |  | checkpoint | Cool Tested
checkpoint-status | 27f1f5fe-94d4-4503-8d91-400fa914ac5a |  | checkpoint | Heat Tested
checkpoint-status | 60b7f6ee-48cf-4f20-9da5-2dd829982c67 |  | checkpoint | AMP draw tested
checkpoint-status | bef45fa3-8c59-4ec2-ab66-bdf7263fc46d |  | checkpoint | Labels installed on all equipment
checklist-flat | 233f082b-22c6-48cf-9136-bac1f0f90185 |  | checklist | Switchboard Commissioning |  |  |  |  | Yes | Switchboard ITP - Switchboard Commissioning | 047bc649-1ff7-4151-aebc-71b4e2229117
checkpoint-status | 4668ea25-6bd0-414b-b7c4-7787c24e7c0e |  | checkpoint | All circuits operational
checkpoint-status | c450f88e-0a85-43c5-b644-ddddd0ddbc34 |  | checkpoint | Power meter tested
checkpoint-status | 20b19336-f93c-41c7-bf84-ca9c4a73ab0e |  | checkpoint | Fire Trip Tested
checklist-flat | 031cc24d-345b-462d-96c4-93f5b50d9106 |  | checklist | Remote Sensor/AHPB Rough-in |  |  |  |  | Yes | Rough-in ITP - Remote Sensor/AHPB Rough-in Checklist | 04df591c-9ec0-4147-a740-c864074cc7df
checkpoint-status | 128969d3-97f7-4087-a958-8ec68d816f52 |  | checkpoint | Wall installed
checkpoint-status | 0071ad46-6cc5-48e6-a3e4-a05c59abf7bb |  | checkpoint | Remote sensor and 2 pair cable roughed in
checkpoint-status | 1ab336f5-82e7-4842-b8be-5ce2342af17b |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | 1dec5d0b-6fd5-455b-a4ba-f7a855664731 |  | checklist | BMS Cubicle Installation |  |  |  |  | Yes | Switchboard ITP - BMS Cubicle Installation | 06a292f8-d4bf-465d-9676-b83a1c0aea54
checkpoint-status | 8f2a6ce1-0632-42bd-94fe-56bf3cb65aec |  | checkpoint | Wall Avaliable for Mounting Switchboard
checkpoint-status | b23c0489-5931-454e-9297-0b5ee189c51e |  | checkpoint | Cubicle Installed on Wall
checkpoint-status | 92664887-31cd-4c9a-8dd3-07042c3fb16e |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | 8334bfc5-b582-4df5-9075-f0d52ad73d30 |  | checklist | AHPB Rough in |  |  |  |  | Yes | Rough-in ITP - AHPB Rough in Checklist | 0dfab17c-e5f7-4216-992f-286c06b7b329
checkpoint-status | a852eb51-b0b2-4ecb-a0e5-1b03295c92e3 |  | checkpoint | Wall installed
checkpoint-status | 373b2a75-9b22-45e4-b886-605c5644679c |  | checkpoint | 2 pair cable roughed in
checkpoint-status | bce75e27-a4c2-4f75-9626-88561c59513e |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | d698e2ef-303f-4fca-be2d-8c760d70f770 |  | checklist | Cable Tray Install |  |  |  |  | Yes | Rough-in ITP - Cable Tray Install Checklist | 0f6a18d6-46b0-4f88-841d-f0a39ccddf3e
checkpoint-status | 9cbf60cc-bd47-4117-aa7a-a0258d1cb520 |  | checkpoint | Hangars Installed
checkpoint-status | 2700c8be-7c65-4425-b833-3a9daf0ea836 |  | checkpoint | Cable Tray Installed
checkpoint-status | 33601877-a417-4776-8dd7-ff3c293660cd |  | checkpoint | Bolted down, ready for rough-in
checklist-flat | 46382a24-8754-498c-9cd0-422d9b303083 |  | checklist | Central Controller Fit off |  |  |  |  | Yes | Fitoff ITP - Central Controller Fit off checklist | 12f3ddb2-1533-4f66-9f75-4a9d19e188c4
checkpoint-status | 17c57336-8292-4b1c-aa2c-682e54d218b1 |  | checkpoint | All transmission cabling and interfcae cards installed and fitoff
checkpoint-status | 9ce61aca-9405-4e7e-a9e5-c8fde03bd577 |  | checkpoint | Central controller controller Fit off to correct wall position
checklist-flat | 9eab9820-1a07-4b51-93e8-73e20bc6e462 |  | checklist | VSD FAN/PUMP Fit off |  |  |  |  | Yes | Fitoff ITP - VSD FAN/PUMP Fit off Checklist | 1e795370-bf28-4a23-b0da-468391ed6412
checkpoint-status | b9c42059-e9c2-46e9-b73e-9b4f58649d72 |  | checkpoint | VSD installed
checkpoint-status | 170cc617-ec14-43f3-bc14-6c42310bc48b |  | checkpoint | Power supply terminated/Isolator installed
checkpoint-status | 8be113d6-760e-4353-afbf-1e472b6872e6 |  | checkpoint | EMC cable fit off
checkpoint-status | d3f035c7-6218-4296-b727-3257aa06b8d4 |  | checkpoint | Control cable fit off
checkpoint-status | 64046a44-f059-4fa6-a753-e324e6e40427 |  | checkpoint | Ready for energisation
checkpoint-status | 1031bdbd-92ae-406d-a836-fc5dd5bb93d9 |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | 75c822b6-4df1-4f8f-be58-5e6d66693b65 |  | checklist | Fire Control Panel Installation |  |  |  |  | Yes | Switchboard ITP - Fire Control Panel Installation | 1fa64bc2-86ea-4b48-9a7e-419366fd8a94
checkpoint-status | 8b9e8225-8b03-4441-9780-438d28fde778 |  | checkpoint | Wall Avaliable for Mounting Switchboard
checkpoint-status | 40e607f8-d68c-4ff7-9241-0def9046fbdb |  | checkpoint | Cubicle Installed on Wall
checkpoint-status | 853057f9-93b0-4b4c-b0f8-ad07e9142171 |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | 85ac0aff-6ab0-41d9-94d6-ca636e19dfc5 |  | checklist | SPLIT AC Rough-In |  |  |  |  | Yes | Rough-in ITP - SPLIT AC Rough-In Checklist | 205a2b94-1696-485e-8db3-3389492b6567
checkpoint-status | 2f8c9e73-ecbb-4257-89ea-4effd8f8d8ce |  | checkpoint | Area ready & accessible
checkpoint-status | 5d3a6827-c4e3-4163-8053-654c01676019 |  | checkpoint | Outdoor unit installed in final position
checkpoint-status | 9baa619b-ce4a-45ec-abab-58b9b51f71ed |  | checkpoint | Power supply to Outdoor unit roughed in
checkpoint-status | 7bd326ea-9d61-41ee-a610-54f053ac6a44 |  | checkpoint | Interconnecting cabling installed
checkpoint-status | 81c7bf4b-9d8b-4ab1-9d1e-c1a8cd12a271 |  | checkpoint | Hard-wired controller roughed in
checkpoint-status | e2032537-1b8c-4075-814d-2191dfe10fe4 |  | checkpoint | Floor marked for plasterer
checkpoint-status | 075d3517-5015-4ff7-9eca-9d008fe5e396 |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | 95ced2bf-348c-44c3-9063-7e81c0d03f60 |  | checklist | AA - MSSB AUDIT |  |  |  |  | Yes | AA - MSSB AUDIT | 2309e6a3-9c52-4ce0-9dc7-a5f69628944b
checkpoint-status | a6591ead-4ed9-4850-b04b-607b530b234a |  | checkpoint | APAM ASSET NUMBER
checkpoint-status | 06e772e2-4918-4c6c-8217-4a4d27f03918 |  | checkpoint | LOCATION
checkpoint-status | e46992a0-d3fd-4a7f-997b-8824ab178cde |  | checkpoint | FED FROM
checkpoint-status | 8e3a3579-95d6-4293-b153-4cd4483d2b94 |  | checkpoint | EXISTING SCHEMATICS
checkpoint-status | 1844376e-b1ea-4c5f-8b48-9a714d198208 |  | checkpoint | GENERAL CONDITION
checkpoint-status | 40952df0-d597-461a-9ea4-f93338960b20 |  | checkpoint | FIRE CONTROLS/PANEL
checkpoint-status | b1c0f32e-d4f1-4ea1-80d3-b14b68e1ddf1 |  | checkpoint | RECOMMENDATIONS
checklist-flat | b3774b24-e86d-402f-8aad-a266094065ea |  | checklist | WC FCU Fit off |  |  |  |  | Yes | Fitoff ITP - WC FCU Fit off checklist | 2652e30d-733c-40e1-9339-e853a1cd31a1
checkpoint-status | 86477592-1458-4466-9378-967008c50b7b |  | checkpoint | FCU installed in final location
checkpoint-status | 58318cab-d5a3-459b-91bf-3c2107ec4cb5 |  | checkpoint | Power supply fit off
checkpoint-status | 7af31598-dcaa-4b35-a698-0974838e0dfa |  | checkpoint | Wall sensors fit-off
checkpoint-status | cd5c549c-138b-4ea3-9d5c-d301a27834fb |  | checkpoint | All control points fit-off (Valves, sensors etc.)
checkpoint-status | 836bbc3d-de64-4dd2-b467-bdccccfaea76 |  | checkpoint | Ready for energisation
checkpoint-status | d4be8665-5a3f-4735-a6af-17d441d3ad93 |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | 5212c295-5e07-4ef0-8777-e6b8acf541bb |  | checklist | VRF FCU/BB Rough-in |  |  |  |  | Yes | Rough-in ITP - VRF FCU/BB Rough-in Checklist | 267beae9-6eac-43dd-a1f7-f1cff5dce62d
checkpoint-status | 1087d401-7082-49a0-94ca-0adad1dc2c74 |  | checkpoint | FCU/BB Installed
checkpoint-status | 8c9e7372-f63b-4054-9299-36a5de152d85 |  | checkpoint | Transmission cabling Roughed In
checkpoint-status | 923656ff-a6f6-45e6-9b31-ab1f5bad2ab7 |  | checkpoint | Hard-wired controller Roughed In
checkpoint-status | 40a7b443-d04d-40eb-82bb-85084a09d77e |  | checkpoint | Floor marked for plasterer
checklist-flat | 9ddd66a4-f0db-4ac9-bfd2-77f38b5c12c3 |  | checklist | AA - DGP AUDIT |  |  |  |  | Yes | AA - DGP AUDIT | 272adc09-dbbf-4733-a612-9e78a6dda356
checkpoint-status | cceffff7-43de-4ebb-84f2-276b4c12a09e |  | checkpoint | APAM ASSET NUMBER
checkpoint-status | 714b2849-33a3-478d-bc76-9b2231113f6c |  | checkpoint | LOCATION
checkpoint-status | 2db7be98-eb7b-40d7-b34c-dad9cf5b1916 |  | checkpoint | FED FROM
checkpoint-status | 0da93edd-cd88-4323-84db-3158711e4ee5 |  | checkpoint | EXISTING SCHEMATICS
checkpoint-status | 185a2fcd-8f93-4b67-a363-de244a1f9472 |  | checkpoint | GENERAL CONDITION
checkpoint-status | a5f555af-9153-475d-ba7b-b56177248853 |  | checkpoint | RECOMMENDATIONS
checklist-flat | 556919f9-d6b7-4c04-9e23-a8aeb9dc25bc |  | checklist | SPLIT AC Fit off |  |  |  |  | Yes | Fitoff ITP - SPLIT AC Fit off Checklist | 28232078-cf9e-441a-84e8-f39d2ef1e348
checkpoint-status | 4d3cb1be-ef3d-41b3-9952-08d90e19e8d7 |  | checkpoint | Outdoor unit installed in final position and piped
checkpoint-status | e1fb2433-a993-4d69-ba8e-620438c360be |  | checkpoint | Power supply to condensing unit Fit off
checkpoint-status | 4e9cddb7-6da7-4d41-8ed7-6180f9954f83 |  | checkpoint | Interconnecting cabling Fit off
checkpoint-status | 6d61cf99-9476-49c1-af10-6e2881948612 |  | checkpoint | Local thermostat Fit off
checkpoint-status | d1bc2107-7e27-47b5-b930-bf1736cce626 |  | checkpoint | Ready for energisation
checkpoint-status | d956bec7-a3f4-4447-9b80-a690dce137b2 |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | a6943857-c158-4bbd-bb2c-911ee6f540a2 |  | checklist | BMS Cubicle Commissioning |  |  |  |  | Yes | Switchboard ITP - BMS Cubicle Commissioning | 29ba1623-339a-4d77-9c4f-c2bfd0cfef0c
checkpoint-status | 47cbefb2-b904-4559-a9ff-6ab83814a9c0 |  | checkpoint | BMS Cubicle powered up
checkpoint-status | 2ca42c5d-2baa-446f-b43e-5902886ce015 |  | checkpoint | All Cards Online
checkpoint-status | 9acb4d83-3648-42a1-979c-b8f0df287848 |  | checkpoint | All labels, drawings etc installed
checkpoint-status | ba8b511c-e99e-4e2e-a374-42ef05252ded |  | checkpoint | BMS Cubicle cleaned out and ready for Handover
checklist-flat | b16ed5ff-229f-43aa-8f62-90372ce49264 |  | checklist | Switchboard Installation |  |  |  |  | Yes | Switchboard ITP - Switchboard Installation | 34aa3324-da5d-4379-994a-7f233923c93e
checkpoint-status | 7143115c-be8f-4636-b4ae-b9f08f07f715 |  | checkpoint | Wall Avaliable for Mounting Switchboard
checkpoint-status | 16f56297-2856-4b13-802f-001aeb635230 |  | checkpoint | Switchboard Installed on Wall
checkpoint-status | 5cc15514-d04d-404b-930a-cb3d5a42fa5e |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | 7e7cec91-4217-4500-8359-6543bb5900d6 |  | checklist | Circuit Energisation from switchboard |  |  |  |  | Yes | Energisation ITP - Circuit Energisation from switchboard checklist | 3f1a8c5f-42e3-4ccb-a895-57b09365a6db
checkpoint-status | 81e2b50e-c9f1-4bd3-ba3b-e6cfc9b47121 |  | checkpoint | Power cable installed in switchboard
checkpoint-status | 7a81f0b0-519d-4eb1-b158-73f51cb6daaf |  | checkpoint | Power cable tests completed
checkpoint-status | fa02e844-bd52-4a8e-b5a4-9153117b97c1 |  | checkpoint | Circuit breaker installed
checkpoint-status | de281dba-8ff9-4847-bad7-a826ab1b9418 |  | checkpoint | Power cable terminated at switchboard
checkpoint-status | 281d8e74-5d10-48c4-82ad-b67f71b919ab |  | checkpoint | Power cable terminated at Equipment
checkpoint-status | b556e0c8-9e47-464e-b9cb-53c79b63baa5 |  | checkpoint | All AS3000 Tests complete and passed
checkpoint-status | 4327e417-c2df-4581-8a77-bbdd4168e9f7 |  | checkpoint | Circuit energised
checkpoint-status | 3f51e7bc-5ee3-440a-834a-11f3d9be67a5 |  | checkpoint | Voltage Tested at equipment
checklist-flat | adbd4dda-b480-4a2c-aa34-9cce008f56c1 |  | checklist | AHPB Commissioning |  |  |  |  | Yes | Commissioning ITP - AHPB Commissioning | 4000ffc4-fd4e-4d10-b015-f64d1a81e0fe
checkpoint-status | 28c77339-06f3-4957-8a71-8a6be32966ce |  | checkpoint | AHPB operating
checkpoint-status | 2761b904-6abe-4ddb-8704-d8027000b827 |  | checkpoint | Neon working
checkpoint-status | 1d0b4d2a-53e8-4c8f-949f-13d4f0900795 |  | checkpoint | Label installed
checklist-flat | 4045f38b-1674-461d-90fd-11536752c266 |  | checklist | VRF Condensing unit Commissioning |  |  |  |  | Yes | Commissioning ITP - VRF Condensing unit Commissioning Checklist | 45c5eb90-7fd1-4765-8828-f2c0bd6d05f0
checkpoint-status | f91a9833-d48c-4b67-9612-55fac8186326 |  | checkpoint | Check all terminations
checkpoint-status | 325a7544-7013-491d-96c6-17ac480ec748 |  | checkpoint | Power supply Tested Voltage
checkpoint-status | a2d34008-b459-4b1c-b91d-b4592510f452 |  | checkpoint | AMP Draw Tested
checkpoint-status | 8343d7d6-8d50-44ca-bcb9-97abcafc3651 |  | checkpoint | Labels installed on all equipment
checklist-flat | bfff9a2d-ecf4-40ea-8e84-c4afcfa6321c |  | checklist | BMS Zone Sensor Rough In |  |  |  |  | Yes | Rough-in ITP - BMS Zone Sensor Rough In checklist | 52a191f2-ec46-4635-9013-bf3f6cb15c5b
checkpoint-status | 3ef611a9-73d2-4ce2-be6e-d5262e193906 |  | checkpoint | Wall installed
checkpoint-status | cd939d86-85f7-42f4-b17f-7e1a83efbded |  | checkpoint | 1 pair cable roughed in
checkpoint-status | c993d385-760c-4f39-87b0-9501b63db209 |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | 38ff8d85-df32-4eab-8aa9-0a1215553438 |  | checklist | Fire Control Panel Fit-off |  |  |  |  | Yes | Switchboard ITP - Fire Control Panel Fit-off | 57020859-cdb6-4274-b38d-b5a988338968
checkpoint-status | d1668f97-8167-49ea-ab74-f87f39bdc82f |  | checkpoint | All interconnecting cabling to MSSB installed and terminated
checkpoint-status | 26d834bd-dbb2-4e2f-a3b3-d41140ed405f |  | checkpoint | Fire cabling by others installed and terminated
checklist-flat | aea474fb-2ca1-41c2-9bb6-42d181c3e11c |  | checklist | FAN PBO Commissioning |  |  |  |  | Yes | Commissioning ITP - FAN PBO Commissioning Checklist | 5a3af061-7781-4baa-ab4a-59de4d989ba1
checkpoint-status | 2aaa15c5-4421-4499-98b8-3e53a39f8027 |  | checkpoint | Power supply tested Voltage
checkpoint-status | 59bf57e4-f6ad-45e2-afea-d7c29b7be458 |  | checkpoint | Fan rotation tested
checkpoint-status | 7cf8dd09-5bbb-4a67-b3fb-1fd765c93f41 |  | checkpoint | Local switch tested
checkpoint-status | 7a08bea1-b129-4647-95c5-af23bf0936e8 |  | checkpoint | Fan rotation tested
checkpoint-status | e434eea8-c679-4466-a51c-7bc3772b4d96 |  | checkpoint | AMP Draw tested
checkpoint-status | 821f264f-dc50-455f-997a-373a96601f5c |  | checkpoint | Labels installed on all equipment
checklist-flat | 00efda91-6d53-4de9-818d-831071782138 |  | checklist | Switchboard Energisation |  |  |  |  | Yes | Switchboard ITP - Switchboard Energisation | 60d5e048-fffd-4a57-9b53-7a16ae6b2d61
checkpoint-status | 8e7e26b9-50df-4007-add7-992ebc3e0ec1 |  | checkpoint | All field cabling terminated
checkpoint-status | 6a506990-4a55-4b84-8521-c5038baa9726 |  | checkpoint | All field tests completed
checkpoint-status | 9d77c4f0-49af-4b6c-9d6c-f20cc1a7e403 |  | checkpoint | Power provided at Main Switch and tested
checklist-flat | 7483755a-9749-411b-aac0-6a254ba53163 |  | checklist | STANDARD EQUIPMENT PBO Rough-in |  |  |  |  | Yes | Rough-in ITP - STANDARD EQUIPMENT PBO Rough-in Checklist | 62049659-d796-4781-b4f4-eef7ea2f5252
checkpoint-status | 90f09377-1fc4-4e2c-ae1a-a15b4a21b709 |  | checkpoint | Equipment installed in final position
checkpoint-status | 1134e3ce-3d09-4194-a362-8b6eee165b16 |  | checkpoint | Isolator installed by others
checkpoint-status | 5ed06337-3e89-450d-aa0e-284f67a87fd6 |  | checkpoint | Control cabling roughed in
checkpoint-status | 2233a77b-06b7-4e16-b60b-22603c3a0d3e |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | be29150f-926e-42c4-99ab-2f4ee6adc3e1 |  | checklist | SEF VSD FAN Fitoff |  |  |  |  | Yes | Fitoff ITP - SEF VSD FAN Fitoff Checklist | 6325efb7-116a-4474-ae90-9d92ade70937
checkpoint-status | 0e66a6ee-a185-459d-8976-7d5d2fe24a37 |  | checkpoint | VSD installed
checkpoint-status | 800680e2-a9b4-4407-b412-723058fbd1e8 |  | checkpoint | Power supply terminated
checkpoint-status | 08863095-f5c5-4803-850c-d8698777d0ce |  | checkpoint | EMC cable fit off
checkpoint-status | 596be4ab-491a-49f0-ae10-f70021913779 |  | checkpoint | Control cable fit off
checkpoint-status | 0806c5b1-9eef-440e-a288-b591358c4536 |  | checkpoint | Ready for energisation
checkpoint-status | bdca43f9-4226-442d-9b55-dcc34c23d7e0 |  | checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint-status | b92d5ff2-5372-4e39-9f8d-ff41282c8142 |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | 804756f5-3a6a-4487-ab88-3c5fda20435c |  | checklist | DOL FAN Commissioning |  |  |  |  | Yes | Commissioning ITP - DOL FAN Commissioning Checklist | 69f54aa4-c723-41fb-802a-52dfebd12584
checkpoint-status | d36e1f37-c7b3-430a-a595-8f6a0fbb6fc8 |  | checkpoint | Check all terminations
checkpoint-status | ca5674b4-dd04-4f06-85a3-72737e427deb |  | checkpoint | Power supply tested Voltage
checkpoint-status | d647089a-57f9-4de5-b10a-45737ae88112 |  | checkpoint | Enable tested
checkpoint-status | 4273ed80-f0d4-429d-bab9-2c0fbd73d1c9 |  | checkpoint | Run Proof tested
checkpoint-status | 7b7617ed-82bf-49e1-8fa4-c72bc787ebbd |  | checkpoint | Fault Tested
checkpoint-status | fdc8e8c4-9660-428c-9440-a2726ffe5ec1 |  | checkpoint | Fan rotation tested
checkpoint-status | 53288f14-5faa-40b4-abd9-feacc2f809cd |  | checkpoint | AMP Draw tested
checkpoint-status | f83de08a-1769-4063-b0e3-8b10b1f8051f |  | checkpoint | Labels installed on all equipment
checklist-flat | 5144290b-9496-4b0c-97aa-a806b44c5cae |  | checklist | AA - VSD REPLACEMENT |  |  |  |  | Yes | AA - VSD REPLACEMENT | 6ac08ce6-ca19-4f94-86a9-b7d948190b4d
checkpoint-status | 324fa1c1-3457-470d-8d4d-444653d49c47 |  | checkpoint | APAM ASSET NUMBER
checkpoint-status | 82dfdf2e-567b-4c0a-8176-6fe011e3adb5 |  | checkpoint | EXISTING CONDITION/LOCATION
checkpoint-status | d266fddf-9bd5-4644-b30d-f49ba0070d09 |  | checkpoint | EXISTING CONTROL
checkpoint-status | 8364f55a-2a66-428a-9b2b-f141bd4193de |  | checkpoint | EXISTING OPERATION
checkpoint-status | 9ce42069-db5b-4f09-b6f7-89b9715c556b |  | checkpoint | EXISTING MSSB CONDITION
checkpoint-status | 5000394a-f0ad-4034-a82d-4d2cd44e6da3 |  | checkpoint | EXISTING SETTINGS
checkpoint-status | 5fde239f-c5fe-4b33-a300-99aafa7e66e2 |  | checkpoint | NEW VSD INSTALLATION
checkpoint-status | c9090fe5-f0e5-4629-9e49-876698ed7000 |  | checkpoint | NEW VSD SETTINGS
checkpoint-status | 18be86f6-c5f7-488d-a6d4-821ff6f16c21 |  | checkpoint | NEW VSD TEST
checkpoint-status | 2945c2f1-6722-494e-9934-66bbc681f5ed |  | checkpoint | RECOMMENDATIONS
checkpoint-status | 963f86f8-6fc1-45ff-b2f6-273815b7a391 |  | checkpoint | DOCUMENTATION
checklist-flat | 8253d4d2-8c25-400a-a4c9-995a4057907c |  | checklist | Central Controller Rough In |  |  |  |  | Yes | Rough-in ITP - Central Controller Rough In checklist | 6b5037e7-ea82-4f55-983c-e6c0f5fb38fc
checkpoint-status | 3e7d22b4-f7fb-4c12-9099-b2a2ee04f4ad |  | checkpoint | All transmission cabling installed
checkpoint-status | b5aafaf3-fbc2-483b-849b-1512ee3439cc |  | checkpoint | Central controller cable roughed in to correct wall position
checklist-flat | be290900-30d5-4f96-b7a4-2494efcb104e |  | checklist | VSD/EC FAN Commissioning |  |  |  |  | Yes | Commissioning ITP - VSD/EC FAN Commissioning Checklist | 6fac210f-8b6e-4012-bbd2-785f20e2f0f3
checkpoint-status | 996f76ca-1382-400e-bb36-6e7806dd122c |  | checkpoint | Check all terminations
checkpoint-status | 2e343c43-1327-4ef5-b100-e1f7d3f7e652 |  | checkpoint | Power supply tested Voltage
checkpoint-status | 8219dbad-10b1-446e-b3d4-c9cb5e7d0f81 |  | checkpoint | AOM, local switch tested
checkpoint-status | e789693e-d9f5-4760-91a1-37c1eb3b211e |  | checkpoint | Run light tested
checkpoint-status | 5b02faf9-73f6-44c0-8d46-51d9086c4c80 |  | checkpoint | Fault light tested
checkpoint-status | 61c8b14b-9711-4939-9234-fbe3b744558d |  | checkpoint | Speed tested
checkpoint-status | 0ac2851a-28df-46ab-94fe-7e8b0d828f93 |  | checkpoint | Rotation tested
checkpoint-status | 9d194919-7f0a-4b9e-8df4-9da77873c8ec |  | checkpoint | AMP Draw tested
checkpoint-status | 7a46cef3-4b45-4933-ac6d-c1d266853297 |  | checkpoint | Labels installed on all equipment
checklist-flat | 33b9c449-f151-4987-aa35-3bc14dc6d3f6 |  | checklist | SEF VSD FAN Commissioning |  |  |  |  | Yes | Commissioning ITP - SEF VSD FAN Commissioning Checklist | 70390ef8-ac20-4599-96c3-b786ec1d65c7
checkpoint-status | 89ab5233-c8de-4c25-b92c-896fa9718de4 |  | checkpoint | Power supply tested Voltage
checkpoint-status | 6b70c709-5cd2-42e0-8730-078d120fdbdb |  | checkpoint | Start relay tested
checkpoint-status | 217ae9bd-a70c-4a62-9316-2a549f5db172 |  | checkpoint | Firemans Start tested
checkpoint-status | 9e022d1e-5f26-4ba3-ac56-d5c89e5c04f2 |  | checkpoint | Firemans Stop tested
checkpoint-status | 4cfd0ad3-9a9a-441d-9c1f-6e79e1c1e38d |  | checkpoint | Run Proof tested
checkpoint-status | 2521b0a8-9102-4230-9699-0b4ad4d58745 |  | checkpoint | Fault Tested
checkpoint-status | fc8b669a-8457-446e-a16d-1e6826c688d9 |  | checkpoint | Speed tested
checkpoint-status | a2cd3e9b-61ac-49d1-936c-be75eab22419 |  | checkpoint | Fan rotation tested
checkpoint-status | de037014-369a-4b35-a05b-e758a1fe03a3 |  | checkpoint | AMP Draw tested
checkpoint-status | e9f38181-0ccd-428b-91b4-841b347cdb19 |  | checkpoint | Fire label and padlock installed
checklist-flat | 5a9980b2-e990-4b6f-97b1-6c7945da29c9 |  | checklist | Essential FAN Rough-in |  |  |  |  | Yes | Rough-in ITP - Essential FAN Rough-in Checklist | 737fe614-6eb3-4e85-be8f-7ac761c62911
checkpoint-status | 9a714fb3-4023-4114-9b0a-71d9420ba7b2 |  | checkpoint | Roof penetration marked out
checkpoint-status | afe84239-dbf8-4eb0-945e-8e07930935b0 |  | checkpoint | Fire Rated Supply rouged-in
checkpoint-status | 76f233c3-1fe5-4e6b-bc10-b87eb2300081 |  | checkpoint | Fire Rated Control cable roughed-in
checkpoint-status | 0594a260-76d0-4098-a4ac-89a8ac4bccf4 |  | checkpoint | Stainless Steel cable ties installed
checkpoint-status | 23589192-bd41-4f5e-97ba-39d75299732f |  | checkpoint | Cables through roof
checkpoint-status | 9b2c1e91-28eb-4b93-a284-e3226c7b4971 |  | checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint-status | 01a2d71e-23ec-499d-be8d-bff50622e20c |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | 6af46a8c-aec1-44ae-ae2e-db7c7b27e6bb |  | checklist | AA - SWITCHBOARD TO AS1851-2012 (Yearly) |  |  |  |  | Yes | AA - SWITCHBOARD TO AS1851-2012 (Yearly) | 775a3cde-9bbe-4d63-aba5-1f8e206e0d2f
checkpoint-status | f7ce3a5a-6d13-4bdc-a189-aae03379aa4b |  | checkpoint | Check, clean or replace as necessary, any faulty contacts or relays
checkpoint-status | 715bbb9c-8e23-4483-8376-f96d7c0a401c |  | checkpoint | Check overload ratings against motor nameplate ratings
checkpoint-status | 2b3e9710-35e2-4028-81ec-0f934a16d938 |  | checkpoint | Check all fuses for correct ratings
checkpoint-status | 449b7e57-243e-4bf9-a219-0537a3eec812 |  | checkpoint | Check connections at motors, switchboards and equipment subject to vibration. Retighten cable terminations as necessary
checkpoint-status | 8d603b75-eef6-489d-a881-7a181a5db8f1 |  | checkpoint | Inspect interpole barriers and shrouds where fitted
checkpoint-status | 2a2915f4-29a6-4748-a70d-155cae0e6169 |  | checkpoint | Check and rectify any damaged or faulty exposed cable insulation
checkpoint-status | be2dbbfa-54e0-4d21-990a-787b0fa549e4 |  | checkpoint | Vacuum clean the switchboard interior and remove any rubbish
checkpoint-status | 13fd42bc-4db3-47a3-bc82-cd205ff5b184 |  | checkpoint | Check panel seals, and rectify if faulty
checkpoint-status | 5a67148f-338b-490a-b077-9890576c7fc3 |  | checkpoint | Check and report where wiring diagram(s) are considered to be incorrect
checkpoint-status | 5b0586f3-4691-4733-b684-1e8164c859e3 |  | checkpoint | Check continuity to earth
checkpoint-status | 02584386-362e-45ce-b42e-59aab1f78ed0 |  | checkpoint | Check and record neutral current
text | 50a043fb-bece-51b7-9df3-7c853c835362 |  | textbox | Neutral current
checkpoint-status | aa0c766a-e5ff-4146-936c-86ee47a3505e |  | checkpoint | Check for loose busbar connections and cable terminations and tighten any loose connections
checkpoint-status | a9595d3b-b4ae-4dbf-ba5c-c62d24c62d5c |  | checkpoint | Examine the general condition of conduits, connectors, switches and wiring
checklist-flat | 214e746f-ce07-449d-9157-7545076da625 |  | checklist | DOL FAN/PUMP Fit off |  |  |  |  | Yes | Fitoff ITP - DOL FAN/PUMP Fit off Checklist | 7938e2e0-426c-4729-857c-fe8357ee8c4f
checkpoint-status | 5e8cdabe-70e1-42e7-8f75-bb2df2a4b902 |  | checkpoint | Isolator installed
checkpoint-status | ae9a4645-dd1f-4d54-9901-fa50587a8733 |  | checkpoint | Power supply terminated
checkpoint-status | 5d44e29e-daab-4e65-bbb0-d73b685b5d02 |  | checkpoint | Control cable fit off
checkpoint-status | 53f94be1-8128-4551-a5e9-40ecad43180d |  | checkpoint | Ready for energisation
checkpoint-status | 04be85eb-eee6-43db-82e5-9582b65943f4 |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | 9c8ed999-f76f-45df-a36d-ba0333614ef0 |  | checklist | WC FCU Commissioning |  |  |  |  | Yes | Commissioning ITP - WC FCU Commissioning checklist | 7f46a80c-e88b-40a4-944c-cb0bdb83ffa5
checkpoint-status | 6401ce67-3748-4c90-86a6-3b1a6f81dc9e |  | checkpoint | Check all terminations
checkpoint-status | 9d290fb8-10fa-4919-820d-69d0dc99bdb3 |  | checkpoint | Power supply Tested
checkpoint-status | fdc42a05-3f11-4971-8657-b9f6a3edde51 |  | checkpoint | Space temp Tested
checkpoint-status | 261a8c7b-ff10-43d6-9b66-6a300e23a560 |  | checkpoint | Supply air temp Tested
checkpoint-status | f6bf96b7-1208-4cb4-8e74-2228c824003a |  | checkpoint | Cooling Valve Tested
checkpoint-status | eabf1571-c4ae-4a2c-85b4-a529cdef2e92 |  | checkpoint | Heating Valve Tested
checkpoint-status | 8ce5f58e-2256-4a35-b811-3e5a8f3783d5 |  | checkpoint | Air DP Tested
checkpoint-status | 0f33e3b1-918d-45f6-926b-98f4c0155009 |  | checkpoint | SAF Enable Tested
checkpoint-status | 879241a0-8120-4b9e-bb65-4afb43085d81 |  | checkpoint | AMP Draw tested
checkpoint-status | 5dd750b2-c3c6-4bdf-bc48-f1497cd51a11 |  | checkpoint | Labels installed on all equipment
checklist-flat | cc04d05f-4f98-4da2-9fae-284f99fd4d39 |  | checklist | AA - HVAC REPLACEMENT |  |  |  |  | Yes | AA - HVAC REPLACEMENT | 8542bff5-f0ce-4b5d-93cc-f3b7827239b9
checkpoint-status | 237e0f89-9355-4e51-9ad6-6334a0898474 |  | checkpoint | APAM ASSET NUMBER
checkpoint-status | a22ea4c5-5b9e-4322-ae18-0c29c9c58c02 |  | checkpoint | EXISTING CONDITION/LOCATION
checkpoint-status | d8dc1509-ac39-4851-aca1-1cff50b53db1 |  | checkpoint | EXISTING CONTROL
checkpoint-status | d8af9190-97e9-4462-b742-f03bf55c7c66 |  | checkpoint | EXISTING OPERATION
checkpoint-status | 9d77563d-a16d-4306-b238-91167cef7d61 |  | checkpoint | EXISTING MSSB CONDITION
checkpoint-status | 22121a89-9632-4587-9923-7425a28a959d |  | checkpoint | NEW INSTALLATION
checkpoint-status | 6e63fe0f-7cd0-412a-9613-1909e74db1d8 |  | checkpoint | TESTING
checkpoint-status | 4d0a7d33-7112-4c65-af6b-4e548082b405 |  | checkpoint | RECOMMENDATIONS
checkpoint-status | a0318a71-d0e1-4aa8-8ec0-9aa95b0350ab |  | checkpoint | DOCUMENTATION
checklist-flat | 652e6ba6-6fb6-4226-8639-d796775915da |  | checklist | BMS Cubicle Fit-off |  |  |  |  | Yes | Switchboard ITP - BMS Cubicle Fit-off | 87007ae8-0661-46f4-9c85-66e2d0f6370b
checkpoint-status | f3ae6560-cf11-4b53-bd55-5b3a19691505 |  | checkpoint | All BMS cabling terminated
checkpoint-status | 866d07e8-53d8-4960-a1a7-f669a1d12d5c |  | checkpoint | Network cabling terminated
checkpoint-status | 9032d73f-d950-477b-ac7f-3d8209be276f |  | checkpoint | Ready for power
checklist-flat | 0f513ed9-371d-4d51-a59f-c3a61d0a5ce9 |  | checklist | Remote sensor Fit off |  |  |  |  | Yes | Fitoff ITP - Remote sensor Fit off checklist | 89cdfd8c-9aa5-4436-9127-328a18da6b61
checkpoint-status | 097d7b18-9106-4cd8-9bd7-5112576caa39 |  | checkpoint | Wall plastered/painted
checkpoint-status | a6a9d73c-98cb-43fb-87bd-764e98d24c98 |  | checkpoint | Remote sensor cable Fit off on wall
checkpoint-status | 40d8cb19-a8fd-4a14-8703-3394a1f973c8 |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | 643c1d51-12eb-4366-943d-16dfa3015979 |  | checklist | Circuit Energisation from Isolator |  |  |  |  | Yes | Energisation ITP - Circuit Energisation from Isolator checklist | 8e2ead97-d5fc-4042-9b4e-cdb9c614a128
checkpoint-status | 28e48da5-1200-465a-9f23-ebc4c7faa265 |  | checkpoint | Isolator installed in correct position
checkpoint-status | 6e6b308c-9a62-42cb-9e15-6f1d3c3aec8c |  | checkpoint | Power cable terminated by others
checkpoint-status | cc4e5453-66cb-49c1-8a61-9d5f81276ecf |  | checkpoint | Power cable terminated at Equipment
checkpoint-status | 788ede91-ac4d-464f-8130-5de58cbd91da |  | checkpoint | All AS3000 Tests complete and passed
checkpoint-status | e0e1b975-3a1b-409b-84fb-684cfa4b17e7 |  | checkpoint | Circuit energised by others
checkpoint-status | a1ab5c10-0984-45cd-bdff-daa7bd94bd90 |  | checkpoint | Voltage Tested at equipment
checklist-flat | e0d752fc-f811-4c25-9a3b-4f064bd972a5 |  | checklist | DOL FAN PBO Fit-off |  |  |  |  | Yes | Fitoff ITP - DOL FAN PBO Fit-off Checklist | 9a216f13-a5bb-46bf-94ba-51dafe6c93e7
checkpoint-status | 21617b36-f395-499c-aa86-958ab7e9f220 |  | checkpoint | Fan Fitoff
checkpoint-status | 94759385-ed99-4564-8fcb-018b88ef66c0 |  | checkpoint | Local switch fitoff
checkpoint-status | 29a589af-02f5-4372-898c-aed4873469ed |  | checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint-status | 35d201fd-abf9-42c5-9691-927feb5eee3b |  | checkpoint | Ready for energisation
checkpoint-status | 598f1f06-e418-4294-b337-89adc21e1e81 |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | 2d33b867-2c1a-488b-a782-00116f6628d0 |  | checklist | AA – VARIABLE FREQUENCY INVERTER TO AS1851 |  |  |  |  | Yes | AA – VARIABLE FREQUENCY INVERTER TO AS1851 | 9bc3efe3-1d80-48ca-b7b3-465dfe32fb4b
checkpoint-status | 2e63151a-d7d7-447f-ac3d-ab126abb771f |  | checkpoint | Check for dust and accumulated dirt on vents and circuit boards and clean where necessary
label | bd1a1062-1c89-5ea8-8451-9c5b98f8236b |  | note | When there is evidence of moisture inspect on a monthly basis or replace enclosure with one having an appropriate IP rating
checkpoint-status | 79e9d1ee-94e6-449e-b1ad-3b182d3824cc |  | checkpoint | Check electrical connections and tighten where necessary
checkpoint-status | c92ce853-1af2-4823-97ac-24450f52e307 |  | checkpoint | Check the operation of all cooling fans
checklist-flat | 3d840a90-9af8-4206-98c6-7bc34d8e7eff |  | checklist | Fire Control Panel Commissioning |  |  |  |  | Yes | Switchboard ITP - Fire Control Panel Commissioning | a342325e-959c-4a80-b3ce-673c934cde26
checkpoint-status | 54148358-fa72-430e-a895-2eba1da35362 |  | checkpoint | All fire relays and points test with fire contractor
checkpoint-status | 8b30a030-f98c-46bc-a5e5-690f5a6e99e5 |  | checkpoint | All labels, drawings etc installed
checkpoint-status | 2284c6aa-433f-458f-9b63-c093a27e6932 |  | checkpoint | Fire Control Panel cleaned out and ready for Handover
checklist-flat | 420f2d32-73a9-49a6-bb42-4644da56ccaf |  | checklist | STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in |  |  |  |  | Yes | Rough-in ITP - STANDARD EQUIPMENT (Fan, AHU, FCU, PUMP, Boiler etc). Rough-in Checklist | acc12bee-ce50-4dad-8c62-8f6d7471fee2
checkpoint-status | c64e21b3-598b-47b0-b5e8-cbccbb509ba7 |  | checkpoint | Equipment installed in final position
checkpoint-status | 00caf31c-fa00-4957-a216-d524ee56c33b |  | checkpoint | Power cabling roughed in
checkpoint-status | fc3c1e8b-e264-4282-ba72-7bb959341582 |  | checkpoint | Control cabling roughed in
checkpoint-status | 8d3c8aa1-4cb1-47c2-af0c-097465c73ad5 |  | checkpoint | Cables through roof
checkpoint-status | 108dbca1-5b29-492e-b2f7-77e2934ab281 |  | checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint-status | 278d1179-c109-4db9-a0a8-a7a15ebd8a06 |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | 37494e54-00c6-4de6-90f1-c0e4b81faa79 |  | checklist | VRF Condensing unit Rough In |  |  |  |  | Yes | Rough-in ITP - VRF Condensing unit Rough In Checklist | bc622c8d-9976-4c47-8bea-946fde1a8a12
checkpoint-status | 7ed63763-0423-4634-b11c-c74b53584f7b |  | checkpoint | Condensing unit installed in final position
checkpoint-status | 7534e69c-a0a2-4996-9451-5f471bc0a36d |  | checkpoint | Power supply roughed in
checkpoint-status | 258a42a4-ebb6-4a96-a33c-c1e6cb78c009 |  | checkpoint | Transmission/Interconnecting cabling Roughed In
checkpoint-status | 2ff5ecc5-97a1-49a3-9241-233144c3b133 |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | b8aaefcf-0878-44de-a0b3-82f790af5ecb |  | checklist | BMS Zone Sensor/AHPB Rough-in |  |  |  |  | Yes | Rough-in ITP - BMS Zone Sensor/AHPB Rough-in Checklist | bcdb8a08-f7e6-4735-9c17-4376ccf723f2
checkpoint-status | fdc95acc-5cff-49f9-bede-6a7f444abeb3 |  | checkpoint | Wall installed
checkpoint-status | 6edbe709-6304-4767-b72a-a3a29747ea5e |  | checkpoint | 3 pair cable roughed in
checkpoint-status | bd37f262-3b7a-4533-9e5e-c2327300539a |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | 70083faa-0886-4b9f-a690-e79e399ff407 |  | checklist | BMS Control Point Field off |  |  |  |  | Yes | Fitoff ITP - BMS Control Point Field off Checklist | be93b4a1-f8a7-428f-8160-dbef91711e02
checkpoint-status | b946a3a1-9560-4130-93ba-a17092c77982 |  | checkpoint | Control Point fitoff
checkpoint-status | d3808a17-6ea2-41db-b9df-add1cb3a5b40 |  | checkpoint | Any penetrations sealed
checkpoint-status | 46840c39-7fc4-482e-800d-f7c6212c8c84 |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | 02cb3807-509c-42aa-80de-a0db083bfe65 |  | checklist | VRF FCU Commissioning |  |  |  |  | Yes | Commissioning ITP - VRF FCU Commissioning Checklist | c61e4afc-2fa0-4654-b0ef-8cfe973d6027
checkpoint-status | 8fdb5db2-4023-44a6-bd52-71d8f6358d49 |  | checkpoint | Check all terminations
checkpoint-status | 68569065-4796-4c4d-abb0-419efb1bd7b3 |  | checkpoint | Power supply Tested Voltage
checkpoint-status | 401a797a-4911-47e7-923a-61514811cf26 |  | checkpoint | AMP Draw Tested
checkpoint-status | fa5b3182-d45c-4bcb-8911-6013e3b87ae7 |  | checkpoint | Controller Online
checkpoint-status | 19e01052-a2aa-4b6c-9339-817a4cd46df3 |  | checkpoint | Heat tested
checkpoint-status | e7d2b519-9c37-4844-83fa-7e7bc62a547f |  | checkpoint | Cool Tested
checkpoint-status | e2c12e72-9882-4572-8be1-68a0812ff8fd |  | checkpoint | Labels installed on all equipment
checklist-flat | 09bc7d00-b7db-43ab-9f2e-51e699a74ac1 |  | checklist | Variable Frequency Inverter |  |  |  |  | Yes | Variable Frequency Inverter | ca9a6fe3-1225-4467-b3a4-1ce92a05b3da
checkpoint-status | ae8dec63-0a5c-4613-bf00-b129cbe470e3 |  | checkpoint | Check for dust & accumulated dirt on vents & circut boards & clean where neccesary
label | c222c527-347e-56e1-866d-5e68cbe172d1 |  | note | Where there is evidence of moisture inspect in a monthly basis or replace enclosure with one having an appropriate IP rating
checkpoint-status | d7259cd6-a20c-4067-8513-4348a4e8a28d |  | checkpoint | Check electrical connections and tighten where necessary
checkpoint-status | e6c13d2d-d558-4cc4-9cf5-78c51661c988 |  | checkpoint | Check the operation of all cooling fans
checklist-flat | 42de5ca2-ecee-4550-9ab3-accb79bf7823 |  | checklist | EC FAN Fit off |  |  |  |  | Yes | Fitoff ITP - EC FAN Fit off Checklist | d078554a-d72a-4027-b8a0-af70a9f15a7b
checkpoint-status | a3cf4726-30fa-4dcb-ae0e-9883299e89a9 |  | checkpoint | Power supply terminated
checkpoint-status | 858ee3c2-5000-4a23-9d52-fb457a9ce241 |  | checkpoint | Control cable fit off
checkpoint-status | abd23e1f-774e-4c9e-ab9f-8e14f2d1bb27 |  | checkpoint | Ready for energisation
checkpoint-status | a51932bc-2466-421b-a503-f57e85eced78 |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | fac87ddc-7d92-4440-964a-81f97f5e21c2 |  | checklist | FAN Commissioning |  |  |  |  | Yes | Commissioning ITP - FAN Commissioning Checklist | d372f8e6-38d2-4fc8-8813-fb8a0bded114
checkpoint-status | df5afff0-0039-4775-beec-e6011f6ff7fd |  | checkpoint | Power supply tested Voltage
checkpoint-status | 671e930d-eb23-48a2-8365-7c62e3da84a1 |  | checkpoint | Fan rotation tested
checkpoint-status | 68722d85-93ba-4b27-b538-65acddc70ba2 |  | checkpoint | Local switch tested
checkpoint-status | e2d78181-692d-4c01-9b82-46c2fd8942b0 |  | checkpoint | Fan rotation tested
checkpoint-status | 0aaa2646-4801-4dc4-bfd4-6c7cf606b3ac |  | checkpoint | AMP Draw tested
checkpoint-status | f62242cd-ead0-455d-ae73-54e1bdda4e64 |  | checkpoint | Labels installed on all equipment
checklist-flat | e810a5d1-ea1f-45d4-b638-212cfad73bb5 |  | checklist | VRF Condensing unit Fitoff |  |  |  |  | Yes | Fitoff ITP - VRF Condensing unit Fitoff Checklist | dc8d744b-59ff-4ed8-9576-9f00a0ab4b58
checkpoint-status | 64f1d70b-fa24-4cf9-bde8-43ada2ebcc08 |  | checkpoint | Condensing unit installed
checkpoint-status | d8ae154a-6d87-407b-aa63-dd3edb0c7682 |  | checkpoint | Isolator and power supply installed
checkpoint-status | cdf1685b-a3cf-4067-8c87-bbd18cc5bc33 |  | checkpoint | Power supply fit off
checkpoint-status | 9b32e64d-7da0-4700-be6f-d2c3c91da407 |  | checkpoint | Transmission cabling Fit off
checkpoint-status | 6f6c18ff-fc3d-4794-b4c2-7b66b6af3163 |  | checkpoint | Ready for energisation
checkpoint-status | 7ebb6f68-7bd9-4a51-8454-c0b2631aed66 |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | 5bd19391-eb56-479a-881c-03711902db01 |  | checklist | DOL FAN Rough-in |  |  |  |  | Yes | Rough-in ITP - DOL FAN Rough-in Checklist | df9a6158-33b7-4fd8-a668-eaed9dd6e3c2
checkpoint-status | 6263deb4-64d6-41b1-91e7-9c5585c2ced7 |  | checkpoint | Fan Installed
checkpoint-status | a111772a-f1d3-4ff6-8f84-eb47113d6eb7 |  | checkpoint | Local switch roughed in
checkpoint-status | aec61eec-2a7e-4ddd-a642-fd1713f6a7a1 |  | checkpoint | Cables through roof
checkpoint-status | ab36e461-5df9-4b7d-add6-8add35d0620b |  | checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint-status | 079c08ce-5f79-42be-9cef-85d46e551461 |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | 23b5f79b-935d-48b0-9ff2-4f8543861753 |  | checklist | Central Controller Commissioning |  |  |  |  | Yes | Commissioning ITP - Central Controller Commissioning checklist | e4d89cd0-a39e-45c8-ac80-b1a7f21fcf75
checkpoint-status | ad1ce321-7b18-4e1d-b688-cc514dc2f7ae |  | checkpoint | Power supply tested
checkpoint-status | a6d6d57a-8c1f-4f26-b802-2d451247c7d2 |  | checkpoint | Central controller online
checklist-flat | fb356811-b526-4b50-8322-b58c7d7060f3 |  | checklist | VRF FCU Fit off |  |  |  |  | Yes | Fitoff ITP - VRF FCU Fit off Checklist | eebbdb30-51af-4d09-a4ea-4becaf82a1ae
checkpoint-status | 1dcf2be1-535d-4015-9bab-7fc0637f0126 |  | checkpoint | VRF Indoor unit installed
checkpoint-status | 869e7522-d73c-42cf-aa14-d4a2a147066f |  | checkpoint | Isolator and power supply installed
checkpoint-status | 1fb22bcf-2451-4a0a-a6bf-d37adf9851eb |  | checkpoint | Power supply fit off
checkpoint-status | e8648c22-b25c-4699-8de5-4779df1c527c |  | checkpoint | Wall plastered/painted
checkpoint-status | 1bce142a-ee48-4081-a6cc-a0f9c09961d7 |  | checkpoint | Hard-wired controller fit off both ends
checkpoint-status | ec338c2d-5ef1-4758-8890-c440cf75312c |  | checkpoint | Transmission cabling Fit off
checkpoint-status | ac75f098-fb4c-4b22-a440-512cfc503982 |  | checkpoint | Interface card installed
checkpoint-status | 74f56d85-d28a-482d-abc7-7f464b2d9e46 |  | checkpoint | OA Damper installed and wired
checkpoint-status | 8853daa6-c6ce-4448-a7e4-96c72df05de6 |  | checkpoint | Ready for energisation
checkpoint-status | 27437c5c-5cfc-41e9-b48a-dc60144abbab |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | 4d5be4a2-4296-4dc9-9c14-aaa7459549e8 |  | checklist | Electrical SWB |  |  |  |  | Yes | Electrical SWB | f131992b-2b0a-409f-9392-fcad60a751af
checkpoint-status | 428395ba-b8a4-499c-b3e5-9a4b08b6168c |  | checkpoint | Check, clean or replace as necessary, any faulty contacts or relays
checkpoint-status | 41cda1f0-3a2d-4315-9f8a-64206859c77e |  | checkpoint | Check overload ratings against motor nameplate ratings
checkpoint-status | 3af73172-038d-4cc0-9309-aee2c6626e62 |  | checkpoint | Check all fuses for correct rating
checkpoint-status | 028643d3-913b-467c-8a81-5999537a6255 |  | checkpoint | Check connections at motors, switchboards and equipment subject to vibration. Retighten cable terminations as necessary
checkpoint-status | b818cc8d-b4a1-4fa3-9b2f-4e4b1b75b63c |  | checkpoint | Inspect interpole barriers and shrouds where fitted
checkpoint-status | 9d56a59d-5acf-4c07-8f39-545f05eb137d |  | checkpoint | Check and rectify and damaged or faulty exposed cable insulation
checkpoint-status | c6292db1-c9c6-40d0-9d63-8e4c1df6756f |  | checkpoint | Vaccum clean the switches interior and remove any rubbish
checkpoint-status | 77975ed6-1083-4391-93f8-02f168b7eb85 |  | checkpoint | Check panel seals, and rectify if faulty
checkpoint-status | 9c8f3731-d374-4c86-b241-af30ffd0dbe6 |  | checkpoint | Check and report where wiring digram(s) are considered to be incorrect
checkpoint-status | 8cb97996-8a32-4f34-8518-3eb06521f46e |  | checkpoint | Check continuity to earth
checkpoint-status | 2aee3d00-cba4-421e-8625-fbe079c60603 |  | checkpoint | Check and record neutral current
checkpoint-status | 37893293-962a-43ee-bedf-d28015a8e1c5 |  | checkpoint | Check for loose busbar connections and cable terminations and retighten any loose connections
checkpoint-status | 9e00c99a-bd2e-44a2-a22a-33eeae85a77b |  | checkpoint | EXAMINE the general condition of conduits, switches and wiring
checklist-flat | ed723a41-850e-49c2-9127-47d6596a37de |  | checklist | DOL FAN PBO Rough-in |  |  |  |  | Yes | Rough-in ITP - DOL FAN PBO Rough-in Checklist | f3ffc440-2a37-42ec-8027-231e69eac8da
checkpoint-status | cfe6ef52-b130-4b0e-aa4d-43de80d19dad |  | checkpoint | Fan Installed
checkpoint-status | e9ab79f8-f821-4733-8240-9e6095db31f3 |  | checkpoint | Isolator installed by others
checkpoint-status | 0804f641-cdc5-4529-8b1b-72fca2476ab3 |  | checkpoint | Local switch roughed in
checkpoint-status | b7c7cd9b-af25-4635-8581-b05e7e5a220d |  | checkpoint | Cables through roof
checkpoint-status | ad2503bb-84c9-43ae-9aa9-5a24e9f9ef1c |  | checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint-status | 73e669c3-e7c8-43a9-b839-7369ba5c5e61 |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
checklist-flat | c6260c1d-a2b7-4aa0-a87d-fc8ffdb8e725 |  | checklist | Remote sensor Rough In |  |  |  |  | Yes | Rough-in ITP - Remote sensor Rough In checklist | fb3c04ff-2dbc-4887-90e6-3c59542252f9
checkpoint-status | 8e656b0f-d0c0-40f6-9135-68fccba5f193 |  | checkpoint | Wall installed
checkpoint-status | 6d2bf761-af8d-4719-8778-ac0f3e6d1f31 |  | checkpoint | Remote sensor cable roughed in
checkpoint-status | 63384149-66d7-40d0-a5cf-aff2d9224a6a |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | 13098433-52b6-4cc5-8173-9a2da06dd9b2 |  | checklist | BMS Control Point Wall Mounted off |  |  |  |  | Yes | Fitoff ITP - BMS Control Point Wall Mounted off Checklist | fbe179a7-f241-4ee5-b414-9df5da93e1bf
checkpoint-status | 64d3581b-9a64-4755-800b-2324fa15f31e |  | checkpoint | Wall plastered/painted
checkpoint-status | ce996cf2-3a93-4e44-9016-1842c1581704 |  | checkpoint | Fit off on wall
checkpoint-status | e6f7a8d7-423b-4004-a4d6-abdb23b6228c |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checklist-flat | a62bd22a-99d6-4216-b215-c9595f0c300f |  | checklist | Switchboard Fit-off |  |  |  |  | Yes | Switchboard ITP - Switchboard Fit-off | fc465ce8-58af-46e8-bd1b-711a1d43d2c3
checkpoint-status | 63a5859e-f42d-481b-bc84-f3eec1ff5974 |  | checkpoint | All field cabling terminated
checkpoint-status | 21a90eef-758c-4056-a401-6fbbc41d64ba |  | checkpoint | Fire Signal supplied by others and terminated
checkpoint-status | 87bfe5a0-57a6-43a5-b88d-e56a38c44797 |  | checkpoint | Sub-mains supplied by others and terminated
checkpoint-status | ff6be0bd-0bff-4864-8005-f3f2c18ce4df |  | checkpoint | BMS cables installed and terminated
checkpoint-status | 3c5de1ae-01bc-4018-ae29-6136c9c45107 |  | checkpoint | All Field Tests completed
checkpoint-status | 2720f170-894a-4815-aed0-86e304807cfd |  | checkpoint | Ready for Energisation
checklist-flat | 541c11d3-e7a6-4783-988d-7cc40216db64 |  | checklist | EC FAN Commissioning |  |  |  |  | Yes | Commissioning ITP - EC FAN Commissioning Checklist | ffb6b5b7-f5cc-4859-9f72-83450f0f0b90
checkpoint-status | ae4ad453-0671-458f-a758-57d6475511c8 |  | checkpoint | Power supply tested Voltage
checkpoint-status | 0fc8393c-6bdd-49dc-b22d-6a034bee0df2 |  | checkpoint | AOM, local switch tested
checkpoint-status | e24179b4-2f8e-4914-b95d-ec389df3f68e |  | checkpoint | Run light tested
checkpoint-status | e7037c5c-c6ec-4935-a529-36bba5e46b97 |  | checkpoint | Fault light tested
checkpoint-status | cd70c19a-b316-4e9e-b382-a2f7e4868ed5 |  | checkpoint | Speed tested
checkpoint-status | 2d89df6c-09fb-4904-95f5-0063acac89a5 |  | checkpoint | Fan rotation tested
checkpoint-status | 845b6cfe-986d-49ae-8d54-fb5f390fd291 |  | checkpoint | AMP Draw tested
checkpoint-status | 5c81845a-3347-4da5-a002-f75343ee5841 |  | checkpoint | Labels installed on all equipment