## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | DS2672-ITP-S116 - Wall And Slab Installation - Rev 2 | itp |  |  |  | Yes | DS2672-ITP-S116 - Wall And Slab Installation - Rev 2 | 93a78a01-86f2-4551-9c67-5fd10b389d49
checkpoint-group | 5.04 Placement and Compaction of Fill General
checkpoint-status | 5.04.01 - Retaining Wall foundation Inspection
label | Acceptance / Conformance Criteria - Excavated natural ground in foundation area of retaining wall upgrade/extension works prior to placement of fill or concrete must be inspected by the Engineer prior to further work being carried out in the area.
label | Standard / Specification - 14AED/AD4-C - 030.3
label | Verifying Document - Hold Point Release
label | Frequency - 48 Hours Notice Prior to Each Occurrence
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | 8.01 Concrete Subgrade Preparation
checkpoint-status | 8.01.01 - Wall Type 1 Subgrade Preparation
label | Acceptance / Conformance Criteria - Concrete of the existing dam surface to be water blast cleaned and roughened to provide NZS3109 Type B Construction Joint.
label | Standard / Specification - RSV - GS - 1.1
label | Verifying Document - Approved Surface
label | Frequency - Prior to Pour
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 8.01.02 - Wall Type 2 Subgrade Preparation
label | Acceptance / Conformance Criteria - Existing concrete under and to the sides of the foundation to be thoroughly water blasted back to sound concrete.
label | Standard / Specification - RSV - GS - 1.1
label | Verifying Document - Approved Surface
label | Frequency - Prior to Pour
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 8.01.03 - Wall Type 3 & 4 Subgrade Preparation
label | Acceptance / Conformance Criteria - Any soft soil or silts to be removed from site and subgrade to be inspected. Fill to underside of foundation with AP40 or approved fill. Fill to be compacted in 200mm layers.
label | Standard / Specification - RSV - GS - 1.1
label | Verifying Document - Approved Subgrade
label | Frequency - Prior to Pour
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | 8.01.04 - Return Wall Subgrade Preparation
label | Acceptance / Conformance Criteria - Ground excavated to footing level. Backfill as required with AP40 or approved fill. Fill to be compacted in 200mm layers.
label | Standard / Specification - RSV - GS - 1.1
label | Verifying Document - Approved Backfill
label | Frequency - Prior to Pour
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint-group | 8.02 Concrete Pour (Pre and Post Pour Checksheet)
checkpoint-status | General Details
text | Pre Pour Date
text | Concrete Strength (mPa)
text | Volume (m3)
text | Mix Design
text | Additives
checkpoint-status | Reinforcing has been checked and conforms to the drawings included:
text | Bar Size & Grade, Lap Lengths, Lap Locations, Bar Supports, Bar Spacing, Cover
checkpoint-status | 8.02.01 - Construction Joint Locations
label | Acceptance / Conformance Criteria - Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour.
label | Standard / Specification - RSV - CS - 1.15
label | Verifying Document - Approval
label | Frequency - Prior to Pour
label | Activity - HP
label | By - ENG
checkpoint-status | 8.02.02 - Grouting of Bars
label | Acceptance / Conformance Criteria - Reinforcement installed into existing concrete shall be epoxied into the cured concrete with Hilti HIT RE 500 V3 epoxy mortar to the depth shown on the drawings and all strictly installed to the manufacturers written instructions.
label | Standard / Specification - RSV - CS - 1.18
label | Verifying Document - Photos
label | Frequency - Prior to Pour
label | Activity - R
label | By - SE
checkpoint-status | 8.02.03 - Reinforcement Washdown
label | Acceptance / Conformance Criteria - Washdown all steel reinforcement prior to pouring concrete to remove salts.
label | Standard / Specification - RSV - CS - 1.19
label | Verifying Document - Pre-Pour Checksheet
label | Frequency - Prior to Pour
label | Activity - R
label | By - SE
checkpoint-status | 8.02.04 - Pre-Pour Inspections
label | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
label | Standard / Specification - P&G 14
label | Verifying Document - Signed Pre-Pour
label | Frequency - 48 Hours Notice Prior to Each Occurrence
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint-status | Pour Details
text | Weather:
checkpoint-status | 8.02.05 - Delivery Dockets
label | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
label | Standard / Specification - RSV - CS - 1.9
label | Verifying Document - Dockets
label | Frequency - Each Pour
label | Activity - R
label | By - PE
checkpoint-status | 8.02.06 - Slump Testing
label | Acceptance / Conformance Criteria - Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor.
label | Standard / Specification - RSV - CS - 1.12
label | Verifying Document - Pre Pour
label | Frequency - Each Pour
label | Activity - R
label | By - PE
checkpoint-status | 8.02.07 - Compression Testing
label | Acceptance / Conformance Criteria - A set of specimens for concrete tests shall consist of four specimens from each major pour of concrete, one of which shall be tested at 7 days and the remaining three at 28 days after casting.
label | Standard / Specification - RSV - CS - 1.12
label | Verifying Document - Test Results
label | Frequency - Each Pour
label | Activity - R
label | By - PE
checkpoint-status | Post Pour Acceptance and Survey
checkpoint-group | 8.03 Pre-Past Concrete Placement
checkpoint-status | 8.03.01 - Bearing for Precast Concrete Tolerances
label | Acceptance / Conformance Criteria - In addition to the requirements of NZS 3109 insitu concrete surfaces to provide a bearing for precast concrete work shall be cast with a level tolerance of +0mm and -3mm.
label | Standard / Specification - RSV - CS - 1.17
label | Verifying Document - Survey
label | Frequency - Prior to Placement
label | Activity - D
label | By - SV