## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | Job Details | 841ba4cc-0c31-44ad-8f67-bccbe870fcb5
checkpoint-status |  |  | checkpoint | Project details entered below
text | 6f7ed719-f54b-5e1d-a15f-b26d7c90068a |  | textbox | Job Number
text | d42e2a61-6c58-5ab2-b4c7-702040568762 |  | textbox | Project Name
text | d535d267-309f-58b4-93e7-0f993b2139c6 |  | textbox | Site Address
text | 8d724ffb-eedd-550f-b035-150b925b91f8 |  | textbox | Builder
text | d87991e1-a2b1-5932-abfa-e362d149c62a |  | textbox | Euro Precast Project Manager
text | de55437e-18d3-59fa-a866-3f90636981e6 |  | textbox | Euro Precast Lead Draftsperson
text | c054ca3c-a80a-54fa-a413-c82ed4a3edff |  | textbox | Euro Precast Installer
checkpoint-status |  |  | checkpoint | Grouts submitted for approval (UPLOAD TDS and SDS for each grout submitted)
checkpoint-status |  |  | checkpoint | Have submitted grouts been approved? (UPLOAD copy of approval)
checkpoint-status |  |  | checkpoint | Caulking products submitted for approval (UPLOAD TDS and SDS for each caulking product submitted)
checkpoint-status |  |  | checkpoint | Have submitted caulking products been approved? (UPLOAD copy of approval)
checkpoint-status |  |  | checkpoint | Patching products submitted for approval (UPLOAD TDS and SDS for each patching product submitted)
checkpoint-status |  |  | checkpoint | Have patching products been approved? (UPLOAD copy of approval)
checklist-flat |  |  | checklist | Safe Load Declaration Checklist |  |  |  |  | Yes | Safe Load Declaration Checklist | 9b18916b-3fc8-4495-90c8-a3d3b1f453da
checkpoint-status |  |  | checkpoint | Details complete
text | 3f7eb459-930a-564b-912c-9ede888a7d67 |  | textbox | Date:
text | e3ec4814-c7b8-5523-85eb-d9feded10ff7 |  | textbox | Time truck arrived at Factory:
text | 929db439-bc9f-5c4d-89cd-86c29d5ce81f |  | textbox | Time truck departed Factory:
text | 611c3083-8396-55c7-add1-7e80a36e0f35 |  | textbox | Transport Company:
text | f9c4f028-e6f0-595d-ba0b-73c79d2831af |  | textbox | Truck Registration #
text | 96103593-91e4-5c17-bfff-c951e73ca931 |  | textbox | Trailer Registration
select | aa2beac4-f2fc-5875-acf1-0bfe630f4c68 |  | dropdown | Trailer Type: | Drop Deck, Drop Deck No Frame, Flat Top, Layover, Super Layover, Commission
checkpoint-status |  |  | checkpoint | Upload photo of Load List used for load
checkpoint-status |  |  | checkpoint | Upload photos of both sides of loaded truck (after being chained down)
checkpoint-status |  |  | checkpoint | Load Declaration
label | 9cc01920-c297-5bc1-85b6-205f7a7eecba |  | note | In signing below, you agree and acknowledge that:
label | 59709192-9b40-5d4e-a798-3a9779949285 |  | note | You are not permitted to leave the Euro Precast factory unless a Safe Load Declaration has been completed
label | 570b85b3-70f7-52e7-afd9-aa05c45c915b |  | note | You have been provided with a copy of the load list that indicates individual element weights and total approximate load weight (excluding trailer/frame weight)
label | 767d2c5b-bc06-5bf2-b424-8b736e04a652 |  | note | You have chained down all units/elements in a safe and secure manner and in accordance with the latest published government/industry best practice guidance material
label | d4a2fafa-dd85-50f1-a82f-f33e1d9bf65b |  | note | You will abide by all safety rules, PPE requirements and client instructions on the project site at all times.
label | 05fdeed7-8860-5c0f-8238-0c4a46275295 |  | note | You as an individual, the truck, the trailer and load comply with the latest requirements of the Heavy Vehicle National Law and Regulations (HVNL)
holdpoint |  |  | signoff | Driver Signature (must include Company)
checklist-flat |  |  | checklist | Level Sign Off |  |  |  |  | Yes | Level Sign Off | cbc9b7f4-63d9-452f-a154-8f97a6128c3c
checkpoint-status |  |  | checkpoint | Details complete
text | 2ca15c98-a3ee-5b51-b778-c0d23e0f4cf6 |  | textbox | Date:
text | 777e190c-0cca-5686-bde5-13aa3bee9772 |  | textbox | Level:
checkpoint-status |  |  | checkpoint | Builder Sign Off
label | 9b5ef753-87eb-5894-99fe-7a9c993df5e6 |  | note | In signing the below, you agree and acknowledge that on this level:
label | 6a19231d-0850-5b72-a1aa-a654b5b6869a |  | note | All props have been removed
label | 63a7106e-41ad-555d-af26-c6613e3d96fe |  | note | All grouting has been completed
label | 83a0fe9e-88da-52ec-b602-a44496cf7c82 |  | note | All patching has been completed
label | 9db588e0-86ce-50e5-8bd0-f89cd666f4ac |  | note | All sealing has been completed
label | 79023a19-1fcd-59b3-a2ab-42d9d8707734 |  | note | All issued defects have been completed
holdpoint |  |  | signoff | BUILDER SIGNATURE (MUST INCLUDE NAME)
checklist-flat |  |  | checklist | Daily Diary / Timesheet (Site Details) |  |  |  |  | Yes | Daily Diary / Timesheet (Site Details) | a7a53ebc-4c36-4058-969e-804bd2bdbd57
checkpoint-status |  |  | checkpoint | Site details entered below
text | 35b4ac55-48ce-5b57-86be-31014989646d |  | textbox | Name of site:
select | cbf45531-7496-59f8-a999-b4c08ea0a5c8 |  | dropdown | Time started at site: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 49eb3bde-e6be-58ba-b1b3-fb668cc9630f |  | dropdown | Time finished at site: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-status |  |  | checkpoint | Activities completed entered below
boolean | cd3185e4-9569-5dfa-b32e-5388d15bbd84 |  | tickbox | Set out
select | 9136a372-bd6c-5587-aae2-67f18841d320 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1.5hr, 2hr, 2.5hr, 3hr, 3.5hr, 4hr, 4.5hr, 5hr, 5.5hr, 6hr, 6.5hr, 7hr, 7.5hr, 8hr, 8.5hr, 9hr, 9.5hr, 10hrs
boolean | dc4cf249-9ce1-5b6f-ba0a-c8236ad3fa15 |  | tickbox | Panel Install
select | f312c2cf-4bf7-5124-aee6-698187229f7b |  | dropdown | Time spent | N/A, 30mins, 1hr, 1.5hr, 2hr, 2.5hr, 3hr, 3.5hr, 4hr, 4.5hr, 5hr, 5.5hr, 6hr, 6.5hr, 7hr, 7.5hr, 8hr, 8.5hr, 9hr, 9.5hr, 10hrs
boolean | 8ef71f72-03c0-53f8-95cb-5a0a0454c805 |  | tickbox | Patching
select | e1d35989-b114-5447-82f6-0342c16932e8 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1.5hr, 2hr, 2.5hr, 3hr, 3.5hr, 4hr, 4.5hr, 5hr, 5.5hr, 6hr, 6.5hr, 7hr, 7.5hr, 8hr, 8.5hr, 9hr, 9.5hr, 10hrs
boolean | 9c9f56ff-78d9-5339-b5b9-8aee9893cd40 |  | tickbox | Joint Sealing
select | 9cdc0efc-c762-5767-bb39-60f2681a79b3 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1.5hr, 2hr, 2.5hr, 3hr, 3.5hr, 4hr, 4.5hr, 5hr, 5.5hr, 6hr, 6.5hr, 7hr, 7.5hr, 8hr, 8.5hr, 9hr, 9.5hr, 10hrs
boolean | 82a841c6-72e5-505a-83ba-d96d5981419e |  | tickbox | Prop Removal
select | 9076e250-11a6-5dd9-b72e-3087b3c12e8d |  | dropdown | Time spent | N/A, 30mins, 1hr, 1.5hr, 2hr, 2.5hr, 3hr, 3.5hr, 4hr, 4.5hr, 5hr, 5.5hr, 6hr, 6.5hr, 7hr, 7.5hr, 8hr, 8.5hr, 9hr, 9.5hr, 10hrs
text | f64ddd0a-5503-5471-9831-411746136a1e |  | textbox | Other (add in comments)
select | 0e20b38f-a238-5189-9f1a-3f1455a7ba10 |  | dropdown | Time spent | N/A, 30mins, 1hr, 1.5hr, 2hr, 2.5hr, 3hr, 3.5hr, 4hr, 4.5hr, 5hr, 5.5hr, 6hr, 6.5hr, 7hr, 7.5hr, 8hr, 8.5hr, 9hr, 9.5hr, 10hrs
select | c175b2e8-374e-5c00-b6a2-66df53b59fe5 |  | dropdown | Was any of the work today on this site part of a site instruction/variation? | Yes, No
checklist-sectioned |  |  | checklist | Installation Checklist |  |  |  |  | Yes | Installation Checklist | 3dc88a61-8e45-41e4-89c8-d4ab0d700e80
checkpoint-group |  |  | section | Element Install & Grouting
checkpoint-status |  |  | checkpoint | Bedding grout placed and finished as per project requirements
boolean | f35a015c-a7c5-5e72-b3c0-f1d2f643089a |  | tickbox | Bedding grout (trowelable) used is as per project specification (PHOTO REQUIRED of the grout bag)
boolean | be66fcda-3418-5f56-a849-c68c2faefaf0 |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | 13820dd0-c5ff-55f9-8df5-12a9765cb004 |  | tickbox | Grout bed sufficient to ensure full coverage (PHOTO REQUIRED of grout bed prior to landing element)
checkpoint-status |  |  | checkpoint | Element installed to (PHOTO REQUIRED to show survey pins and spirit level bubble):
boolean | 449b627d-d390-5c67-9f54-c718876a88c7 |  | tickbox | Survey Pins
boolean | 5e61a5c5-4fc8-5a74-8466-e29d35a6cc0f |  | tickbox | Within 5mm of vertical plumb
boolean | 5eebb43a-e842-5ef7-87f0-9917d0348752 |  | tickbox | Face alignment within 5mm
checkpoint-status |  |  | checkpoint | Element propped as per Euro Precast PEDS (PHOTO REQUIRED of element propped)
boolean | f7172c76-62ad-5c80-beaa-6bb5c20aea5d |  | tickbox | Prop bolts installed with tool to ensure locking mechanism can't be removed by hand
checkpoint-status |  |  | checkpoint | Dowel tube (flowable) grout placed and finished as per project requirements
boolean | 0e5243ed-4fa4-5b70-b76d-d4112eb6a4b9 |  | tickbox | Dowel tube grout used is as per project specification (PHOTO REQUIRED of the grout bag)
boolean | 2675b456-6c19-5ef3-96b9-1c0de43d4735 |  | tickbox | Grout mixed in line with manufacturers recommendations
boolean | 5c5aeb76-5858-5a1a-b1e9-1dc78d0a5711 |  | tickbox | Dowel tubes filled to top of tubes
checkpoint-status |  |  | checkpoint | Is there any transport or erection damage that needs to be fixed (PHOTO REQUIRED of damaged area)
label | 400c6786-eafa-5d39-b711-d41fedab13a1 |  | note | If there is damage, mark as FAIL. Once the damage is repaired, take another photo (PHOTO REQUIRED) and then change the status to PASS
checkpoint-status |  |  | checkpoint | Area has been cleaned from grout and rubbish (PHOTO REQUIRED of the area before leaving)
checkpoint-group |  |  | section | HOLD POINT - Confirmation that Props can be removed
checkpoint-status |  |  | checkpoint | Has the Builder given us written confirmation that props can be removed (UPLOAD copy of correspondence)
checkpoint-status |  |  | checkpoint | PHOTO REQUIRED of element after the props have been removed
checklist-flat |  |  | checklist | Variation Summary |  |  |  |  | Yes | Variation Summary | e0430a98-0ccc-4eba-958a-2a46732f8e98
checkpoint-status |  |  | checkpoint | Variation details entered below
text | ac616f1d-458c-5bac-9bc2-35bf5f53c172 |  | textbox | Project Name:
checkpoint-status |  |  | checkpoint | Site Instruction from Builder (upload copy)
text | f2dcba98-de3b-5822-9a46-ee97f57473f1 |  | textbox | Euro Precast Variation Number:
text | dd4fbfc8-825c-5c6a-9fa8-7b7008cfd528 |  | textbox | Description of site instruction/variation:
checklist-sectioned |  |  | checklist | Manufacturing Checklist |  |  |  |  | Yes | Manufacturing Checklist | 85d058ed-dea5-495a-bb59-3e159adc32b3
checkpoint-group |  |  | section | Manufacturing Documents
checkpoint-status |  |  | checkpoint | IFC Element Drawing
checkpoint-status |  |  | checkpoint | Euro Precast Primary Lifting and Propping Certification
checkpoint-status |  |  | checkpoint | Secondary Lifting Certification
checkpoint-group |  |  | section | Pre-Pour Checks
checkpoint-status |  |  | checkpoint | Mould check
boolean | 1c40e063-5e51-571a-9aba-108d4990a3fb |  | tickbox | Mould clean with release oil applied correctly
boolean | 5d151dc5-8944-5f12-85d2-4df84dc475d7 |  | tickbox | Primary & diagonal dimensions checked
boolean | e220f895-916a-54bf-91df-8efdd9cd16e5 |  | tickbox | Openings Checked and Correct
boolean | acfc4602-3da2-5749-b1b3-66e48b8b55c6 |  | tickbox | Rebates, Architectural Grooves Installed Correctly
boolean | fc8e7065-3d1f-5e4e-9ddf-cf6846636304 |  | tickbox | Formwork chamfers installed correctly where required
checkpoint-status |  |  | checkpoint | Reinforcing check
boolean | 4f64cd37-0c58-5932-a670-9a20df352430 |  | tickbox | Correct Size and Type
boolean | e1a8bf70-df93-5972-a70b-1038ca19a2e5 |  | tickbox | Laps and Splices correct
boolean | d2bd4cd1-f5e5-53d2-b8bf-825dcda6a740 |  | tickbox | Cover Checked
boolean | cd84c8d1-457b-5221-b2de-70fcbc3bc7ef |  | tickbox | Spacing Checked
checkpoint-status |  |  | checkpoint | Cast in items check
boolean | 17d421a5-44a2-5b59-89a7-93f2ef4f575f |  | tickbox | Ferrules/Inserts installed, checked and correct
boolean | 696087fa-5c2c-5df9-a436-d41932dd1173 |  | tickbox | Starter Bars inserted, checked and correct
boolean | 29cab84f-2031-5ec1-a116-0299afca2b18 |  | tickbox | Lifting anchors installed, checked and correct
checkpoint-status |  |  | checkpoint | Check Minimum Cover
checkpoint-status |  |  | checkpoint | ID Tag installed in non-visible face
checkpoint-status |  |  | checkpoint | Pre-Pour checks completed and approval given to pour Element
label | 2abbd363-3313-5311-9d4c-7269d9a99e52 |  | note | Upload sufficient number of photos of element
checkpoint-status |  |  | checkpoint | Upload photo of signed pre-pour check of shop drawing
checkpoint-group |  |  | section | Concrete Pour Checks
checkpoint-status |  |  | checkpoint | Concrete Strength correct as per design
boolean | db93ed56-0fad-5dd7-9d03-eb776661a5dc |  | tickbox | All Concrete Dockets Attached
text | 989257b9-9e07-5481-bf3b-21ee1f092588 |  | textbox | Date element was cast
checkpoint-group |  |  | section | Post-Pour / Pre Delivery Checks
checkpoint-status |  |  | checkpoint | Visual Check
boolean | 1bfd951c-2c10-5e18-b477-51ba985c6624 |  | tickbox | Does the finish meet class 2 as per AS3610
boolean | 1ff19a35-f210-5751-b3b4-5e5d73725cc9 |  | tickbox | Chamfers clean, neat and on all required edges
boolean | 039b8a8b-d6c0-5cc9-8a29-4eefd0ff27e7 |  | tickbox | Lifting anchors checked and approved
boolean | d9bcaa4f-4b40-5c46-853b-52dda1843432 |  | tickbox | Critical fitments / fixtures checked and approved
boolean | abd113ce-e195-531d-9481-0a1bc088fd8d |  | tickbox | Openings (formwork removed)
boolean | 7b03872b-9816-55ca-adb5-5426a52926d9 |  | tickbox | Nailplates / Recesses etc removed
checkpoint-status |  |  | checkpoint | Any Strongbacks Installed where required
checkpoint-status |  |  | checkpoint | Element free from defects that will impact structural integrity or durability?
label | c8f3c8ff-4c61-5634-b59c-be56028273a0 |  | note | If 'FLAG', raise NCR and notify EP Project Manager to discuss with builder
boolean | 4be4d717-d4a6-5d8c-ba22-2d40bd71b16b |  | tickbox | If NCR raised, take photo of completed approved works
checkpoint-status |  |  | checkpoint | All Post Pour Works complete - Element Checked, Approved and Ready for delivery
checkpoint-group |  |  | section | Concrete Test Results
checkpoint-status |  |  | checkpoint | Concrete Test Result attached
label | b1fbea8d-c7e9-5b1b-9ff1-a5e97a3dcb41 |  | note | Upload actual test result OR a test result of the same mix design from the same day
checklist-sectioned |  |  | checklist | Delivery / Installation Day Checklist |  |  |  |  | Yes | Delivery / Installation Day Checklist | ed233a0d-1134-471e-a8f2-5db17f4a6cf7
checkpoint-group |  |  | section | HOLD POINT - Confirmation of slab strength
checkpoint-status |  |  | checkpoint | Has the slab reached the minimum strength required (UPLOAD copy of concrete slab test result)
label | c9bbf854-3550-5dcf-b99e-2aa2642a158e |  | note | 12MPa for cast-in anchors and 20MPa for post installed anchors
checkpoint-group |  |  | section | Prestart / Start-up
checkpoint-status |  |  | checkpoint | Date of Installation
checkpoint-status |  |  | checkpoint | Installation team completing the install today
label | 2e9de6a9-8443-50b6-8719-3f96e702f0c9 |  | note | List names in comments
checkpoint-status |  |  | checkpoint | Exclusion Zone is set up (PHOTO REQUIRED of the exclusion zone)
checkpoint-status |  |  | checkpoint | Plant & Equipment prestart/logbooks filled out (PHOTO REQUIRED of logbooks)
checkpoint-status |  |  | checkpoint | Toolbox Talk / Pre-Start has been completed (PHOTO REQUIRED of talk)
checkpoint-group |  |  | section | Summary of the day
checkpoint-status |  |  | checkpoint | Hours worked
select | 78d03587-565c-5bab-926a-b4740dbf00a7 |  | dropdown | Time started on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 3c43c761-e0cc-5dda-a17e-e255c537b145 |  | dropdown | Time finished on site | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-status |  |  | checkpoint | Elements Installed today
label | 4d0b8069-eb4f-5b81-95fc-08e191d04ec9 |  | note | COMMENT below if number of elements installed doesn't match the Load Lists in the Safe Load Declarations
select | 2ada973d-8803-5f88-8f23-e67ec388aa3e |  | dropdown | How many elements were installed today? | 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 23, 24, 25, 26, 27, 28, 29, 30, 31, 32, 33, 34, 35, 36, 37, 38, 39, 40
checkpoint-status |  |  | checkpoint | Were there any delays?
label | 87faf9ba-5e3f-5b3d-aaee-0a556769d8b7 |  | note | COMMENT below in enough detail to explain the delay and what caused it. Add PHOTO if it helps record the delay.
select | d3140643-7f44-5203-8eb3-18b5642f0f44 |  | dropdown | How long was the delay? | N/A, 30mins, 1hr, 1.5hr, 2hr, 2.5hr, 3hr, 3.5hr, 4hr, 4.5hr, 5hr, 5.5hr, 6hr, 6.5hr, 7hr, 7.5hr, 8hr
select | 58046ee7-6a2f-55a4-9755-818c7abe3b68 |  | dropdown | How many installers were impacted by the delay/s? | 1, 2, 3, 4, 5, 6
select | ede201f0-4afc-511e-b34f-570146242cef |  | dropdown | How many trucks were impacted by the delay/s? | 1, 2, 3, 4, 5, 6
checkpoint-status |  |  | checkpoint | Builder sign-off
label | f4a9c5b1-6546-51e0-a12c-90fcd787c5e0 |  | note | By signing below you acknowledge the above summary as a true and accurate record of the day.
holdpoint |  |  | signoff | Builder Signature (must be authorised person)
checklist-sectioned |  |  | checklist | Variation works completed |  |  |  |  | Yes | Add New Variation | da3567ca-6a71-4701-80cf-44da3dd5c054
checkpoint-group |  |  | section | Works completed
checkpoint-status |  |  | checkpoint | Details entered below
text | c1876c5e-9363-593c-8eae-090e7e67aabe |  | textbox | Date:
text | e48c2ef2-7c9a-5f60-8588-3bb024bff947 |  | textbox | Name of people who completed the works:
select | b90eac2f-d675-5854-8254-d73c31208848 |  | dropdown | Time started at site: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | 9c1bc354-2aa7-5474-b55a-79c1d825e492 |  | dropdown | Time finished at site: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
text | 4a6b40d7-361f-5737-b1e5-ea343ebf6761 |  | textbox | Consumables used:
text | 89b4f543-41c5-5f1f-8493-03d9b87fa0e2 |  | textbox | Summary of works completed
checkpoint-group |  |  | section | Builder sign-off
checkpoint-status |  |  | checkpoint | Builder sign-off
label | 26b61b0b-0ae9-5937-9b1f-38d7a598bfd9 |  | note | By signing below you acknowledge the above summary as a true and accurate record of the day.
holdpoint |  |  | signoff | Builder Signature (must be authorised person)
checklist-flat |  |  | checklist | Daily Diary / Timesheet (Summary of the day) |  |  |  |  | Yes | Daily Diary / Timesheet (Summary of the day) | 827f66fa-6a54-462c-b0c9-0e3fc8922257
checkpoint-status |  |  | checkpoint | Details entered below
select | efeaabd7-bffc-59c9-8156-b95ee605a754 |  | dropdown | Time started today: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
select | a6c0ed93-39a6-5b90-a56a-6ecaaaf48a2b |  | dropdown | Time finished today: | 05:00AM, 05:30AM, 06:00AM, 06:30AM, 07:00AM, 07:30AM, 08:00AM, 08:30AM, 09:00AM, 09:30AM, 10:00AM, 10:30AM, 11:00AM, 11:30AM, 12:00PM, 12:30PM, 01:00PM, 01:30PM, 02:00PM, 02:30PM, 03:00PM, 03:30PM, 04:00PM, 04:30PM, 05:00PM, 05:30PM, 06:00PM, 06:30PM
checkpoint-status |  |  | checkpoint | Euro Precast Employee signoff
holdpoint |  |  | signoff | Add signature
checkpoint-status |  |  | checkpoint | Euro Precast Installation Manager signoff
holdpoint |  |  | signoff | Add signature
checkpoint-status |  |  | checkpoint | When complete please send timesheet as report to jane@europrecast.com
label | ff389c7d-4243-5788-8b87-fc01fe6dbd5c |  | note | Click the 3 vertical dots in the top right hand corner and select 'Send report'. Add Jane and click send.
checklist-flat |  |  | checklist | Grout Testing Checklist |  |  |  |  | Yes | Grout Testing Checklist | f68deb64-0d04-4ea8-bfd0-a40d1b78d035
checkpoint-status |  |  | checkpoint | To organise grout testing, call Construction Sciences. Primary contact is Michael Hardcastle on 0429 791 069. Secondary contact is Joshua Borg on 0429 790 444
text | f3cc1cc7-9b94-5c2d-a958-d7372e91101b |  | textbox | Date:
text | 8e373d23-5c4b-5793-8da9-df8d76bda450 |  | textbox | Project Name:
text | 55cece51-245a-5934-aae5-dfe106a73bc1 |  | textbox | Time of test:
text | 8d9f88bc-a126-5ded-a630-92e2e5304180 |  | textbox | Grouts tested:
checkpoint-status |  |  | checkpoint | Upload grout test results