## Table 1
[5 empty] | Inspection and Test Plan - Control and Supervision of the Works | [10 empty] | Doc ID: FH-DP1-PM-ITP009 Rev: 00
Client: Melbourne Airport (APAM) | [6 empty] | Contract No: CP1002 | [6 empty] | Prepared By: Brad Carroll
Project: MAPMP 2.0 – DP1 | [11 empty] | Reviewed By: Giuliano Follacchio | [5 empty] | Date: 10/07/2023
Construction Process: Topsoil and Grassing | [11 empty] | Approved By: Jordan Nicolaou | [5 empty] | Date: 10//07/2023
Specifications: Technical Specification – MAPMP 2.0 – DP1 ¦ No. 60692389-PS-01-AV-0001 ¦ Revision 1 – 27 March 2023
Structure / Component:
Lot No: |  | Lot Details: | [6 empty] | Lot size/Quantity: |  |  |  | Date:
Item No. | Task/Activity Description |  |  | Inspection/Test | [8 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  | Responsibility |  | Checked by:
|  |  |  | Frequency |  | Acceptance Criteria |  | Reference Documents | Inspection/ Test Method |  | Record of conformity | [5 empty] | AECOM |  | Fulton Hogan | Date
1 | Preliminary activities
1.1 | Check for correct documentation |  |  | Prior to commencing any activity |  | All employees and subcontractors are using the correct and complete set of drawings and all drawings are the latest revision. |  | AECOM Drawings | Visual inspection |  | This Signed ITP |  | HP* |  | FH Project Engineer
1.2 | Implementation of all measures and controls |  |  | Prior to commencing any activity |  | All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP, SWMS, WP and Weed Management Plan |  | PSP, WP, CEMP, TMP, SWMS, WMP | Inspect |  | This Signed ITP |  | HP* |  | FH Project Engineer
1.3 | Material Approval |  |  | Prior to placing |  | Topsoil used for the works is won from the site. |  | Tender Clarifications #44 | Verify |  | This Signed ITP |  | HP* |  | FH Project Engineer
2 | Topsoil
2.1 | Topsoil |  |  | Prior to topsoil placement |  | Topsoil shall be free from items including:  Clay lumps with a diameter greater than 50mm;  Contaminants;  Noxious pests and weeds;  Refuse;  Stones with a diameter greater than 50mm;  Subsoil; and  Tree and shrub roots. |  | MAS-CVL-001 Grassing (Airside) Clause 9.4.1 | Verify |  | This signed ITP |  | HP* |  | FH Project Engineer
[5 empty] | Inspection and Test Plan - Control and Supervision of the Works | [10 empty] | Doc ID: FH-DP1-PM-ITP009 Rev: 00
Client: Melbourne Airport (APAM) | [6 empty] | Contract No: CP1002 | [6 empty] | Prepared By: Brad Carroll
Project: MAPMP 2.0 – DP1 | [11 empty] | Reviewed By: Giuliano Follacchio | [5 empty] | Date: 10/07/2023
Construction Process: Topsoil and Grassing | [11 empty] | Approved By: Jordan Nicolaou | [5 empty] | Date: 10//07/2023
Specifications: Technical Specification – MAPMP 2.0 – DP1 ¦ No. 60692389-PS-01-AV-0001 ¦ Revision 1 – 27 March 2023
Structure / Component:
Item No. | Task/Activity Description |  |  | Inspection/Test | [8 empty] | HP/ WP/ AP/ IP/ TP/ SCP |  | Responsibility |  | Checked by:
|  |  |  | Frequency |  | Acceptance Criteria |  | Reference Documents | Inspection/ Test Method |  | Record of conformity | [5 empty] | AECOM |  | Fulton Hogan | Date
3 | Placement of Topsoil
3.1 | Topsoil placement |  |  | Each Lot |  | Filling of grassed areas will comply with Airport specification:  100mm thick topsoil  Smooth even profile  Free of ridges or water pockets |  | MAS-CVL-001 Grassing (Airside) Clause 9.5.2 Tender Clarifications #47 | Verify |  | This Signed ITP |  | HP* |  | FH Project Engineer
4 | Seeding
4.1 | Hydro Seeding |  |  | Each Lot |  | Application rates shall be in accordance with the Grassing Standard, but not less than six tonnes/ha Flexterra or alternative (Vital Bon / Hydro Mulch 1000) unless agreed otherwise. |  | MAS-CVL-001 Grassing (Airside) Clause 9.4.3 Tender Clarifications #45/46 | Visual Inspection |  | This signed ITP |  | HP* |  | FH Project Engineer
5 | Post Construction
5.1 | Watering |  |  | Each Lot |  | Following grassing works, and where access can be obtained without impacting Airfield operations, the area is to be watered to promote healthy grass growth. |  | MAS-CVL-001 Grassing (Airside) | Visual Inspection |  | This signed ITP |  | HP* |  | FH Project Engineer
5.2 | Maintenance |  |  | Each Lot |  | Maintenance of grassed areas until 90% of grass has achieved average height of 100mm. |  | This ITP | Verify |  | This ITP signed |  | HP* |  | FH Project Engineer
[5 empty] | Inspection and Test Plan - Control and Supervision of the Works | [10 empty] | Doc ID: FH-DP1-PM-ITP009 Rev: 00
Client: Melbourne Airport (APAM) | [6 empty] | Contract No: CP1002 | [6 empty] | Prepared By: Brad Carroll
Project: MAPMP 2.0 – DP1 | [11 empty] | Reviewed By: Giuliano Follacchio | [5 empty] | Date: 10/07/2023
Construction Process: Topsoil and Grassing | [11 empty] | Approved By: Jordan Nicolaou | [5 empty] | Date: 10//07/2023
Specifications: Technical Specification – MAPMP 2.0 – DP1 ¦ No. 60692389-PS-01-AV-0001 ¦ Revision 1 – 27 March 2023
Structure / Component:
Final Inspection On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract. Print Name: Position: Signature: Date: / /
Legend:
HP |  | Hold Point | Work shall not proceed past the HP until released by the Superintendent | [5 empty] | IP | Inspection point |  |  | Formal Inspection to be done and recorded
HP* |  | Fulton Hogan Hold Point | Work shall not proceed past the HP* until released by Fulton Hogan | [5 empty] | TP | Test Point |  |  | Product compliance test to be undertaken and recorded/reported
WP |  | Witness Point | An inspection which must be witnessed by the Superintendent | [5 empty] | SCP | Survey conformance point |  |  | A qualified surveyor to check product/section/structure and report
AP |  | Approval Point | Written or verbal approval given by the Superintendent
Notes