## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP009 – Topsoil and Grassing | itp |  |  |  | Yes | ITP009 – Topsoil and Grassing
section | 1. Preliminary activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All employees and subcontractors are using the correct and complete set of drawings and all drawings are the latest revision.
label | Reference Documents - AECOM Drawings
label | Inspection/ Test Method - Visual inspection
label | Record of conformity - This Signed ITP
label | HP*
label | Responsibility - FH Project Engineer
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP, SWMS, WP and Weed Management Plan
label | Reference Documents - PSP, WP, CEMP, TMP, SWMS, WMP
label | Inspection/ Test Method - Inspect
label | Record of conformity - This Signed ITP
label | HP*
label | Responsibility - FH Project Engineer
checkpoint | 1.3 - Material Approval
label | Frequency - Prior to placing
label | Acceptance Criteria - Topsoil used for the works is won from the site.
label | Reference Documents - Tender Clarifications #44
label | Inspection/ Test Method - Verify
label | Record of conformity - This Signed ITP
label | HP*
label | Responsibility - FH Project Engineer
section | 2. Topsoil
checkpoint | 2.1 - Topsoil
label | Frequency - Prior to topsoil placement
label | Acceptance Criteria - Topsoil shall be free from items including:
label | ○ Clay lumps with a diameter greater than 50mm;
label | ○ Contaminants;
label | ○ Noxious pests and weeds;
label | ○ Refuse;
label | ○ Stones with a diameter greater than 50mm;
label | ○ Subsoil; and
label | ○ Tree and shrub roots.
label | Reference Documents - MAS-CVL-001 Grassing (Airside) Clause 9.4.1
label | Inspection/ Test Method - Verify
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - FH Project Engineer
section | 3. Placement of Topsoil
checkpoint | 3.1 - Topsoil placement
label | Frequency - Each Lot
label | Acceptance Criteria - Filling of grassed areas will comply with Airport specification:
label | ○ 100mm thick topsoil
label | ○ Smooth even profile
label | ○ Free of ridges or water pockets
label | Reference Documents - MAS-CVL-001 Grassing (Airside) Clause 9.5.2 Tender Clarifications #47
label | Inspection/ Test Method - Verify
label | Record of conformity - This Signed ITP
label | HP*
label | Responsibility - FH Project Engineer
section | 4. Seeding
checkpoint | 4.1 - Hydro Seeding
label | Frequency - Each Lot
label | Acceptance Criteria - Application rates shall be in accordance with the Grassing Standard, but not less than six tonnes/ha Flexterra or alternative (Vital Bon / Hydro Mulch 1000) unless agreed otherwise.
label | Reference Documents - MAS-CVL-001 Grassing (Airside) Clause 9.4.3 Tender Clarifications #45/46
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - FH Project Engineer
section | 5. Post Construction
checkpoint | 5.1 - Watering
label | Frequency - Each Lot
label | Acceptance Criteria - Following grassing works, and where access can be obtained without impacting Airfield operations, the area is to be watered to promote healthy grass growth.
label | Reference Documents - MAS-CVL-001 Grassing (Airside)
label | Inspection/ Test Method - Visual Inspection
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - FH Project Engineer
checkpoint | 5.2 - Maintenance
label | Frequency - Each Lot
label | Acceptance Criteria - Maintenance of grassed areas until 90% of grass has achieved average height of 100mm.
label | Reference Documents - This ITP
label | Inspection/ Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - FH Project Engineer
checkpoint | Final Inspection
note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP