## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Project Deliverables |  |  |  |  | Yes | Project Deliverables | 35baa27c-f591-4ac6-9822-fff0df504d63
checkpoint-group |  |  | section | 1. Notated photos taken in perspective reflecting the following
checkpoint-status |  |  | checkpoint | The new site boundary valve assembly connection (Min two photos)
checkpoint-status |  |  | checkpoint | All underground water pipes complete with 'Denso' tape prior to covering up (Min three photos)
checkpoint-status |  |  | checkpoint | SVCA with cabinet door open and closed (Min two photos)
checkpoint-status |  |  | checkpoint | Sprinkler booster and remote alarm (Min two photos)
checkpoint-status |  |  | checkpoint | Annubar (One photo)
checkpoint-status |  |  | checkpoint | Sprinklers throughout residence, concealed spaces (ceiling areas) and covered ways (Min six photos)
checkpoint-group |  |  | section | 2. O & M Manuals in PDF format
checkpoint-status |  |  | checkpoint | O & M Manuals in PDF format
checkpoint-group |  |  | section | 3. Maintenance Log Book
checkpoint-status |  |  | checkpoint | Maintenance Log Book
checkpoint-group |  |  | section | 4. VBA Compliance Certificates
checkpoint-status |  |  | checkpoint | VBA Compliance Certificates e.g also a Certificate of Compliance from the plumber for all plumbing work
checkpoint-group |  |  | section | 5. Commissioning Results
checkpoint-status |  |  | checkpoint | Commissioning results including static pressure testing, actual flows and pressures achieved, compliance statements, AS2118.4 Completion Certificate, letter of compliance from for electrical installation etc.
checkpoint-group |  |  | section | 6. Completed and Signed Independent Third Party Certification (Sprinkler)
checkpoint-status |  |  | checkpoint | Completed and Signed Independent Third Party Certification from an FPA - FPAS Registered Certifier (Sprinkler Installation)
checkpoint-group |  |  | section | 7. Completed and Signed Independent Third Party Certification (Detection)
checkpoint-status |  |  | checkpoint | Completed and Signed Independent Third Party Certification from an FPA - FPAS Registered Certifier (Detection Installation)