## Ryman Healthcare NZ__Murray Hal
Step Id | Warnings | Rich Type | State | resource | type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4
c29fd09a-dc38-4953-b618-c63a17e730f9 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil
2bb1e8d3-a60f-45d3-ac19-273bae4bc847 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Civil 401
cb9a839b-24b5-424a-9887-5117f742073f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Civil 401 | Manholes & Pipelines
a3b73701-025b-45c1-b9ce-fb7b0ddbaf16 |  | checklist-flat | not-started | b0084461b3044fff40ddd573fd9971e2c1493e0e32c1196a5cb372d440a9a7a2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Civil 401 | Manholes & Pipelines | Drainage - Manhole & Pipeline Installation
c855f8ba-ce9c-4ed1-96d9-29c03125a491 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Civil 401 | Manholes & Pipelines | Ducting for NCS and Comms
c204fb5e-5463-56bf-bdca-13d1a0d095c2 |  | checklist-flat | work-in-progress | 8749770115955f289c9d34532d4aa7b3c7e59dc70eac6d8eec21cc5a1776be02 | checklist-flat | FALSE | FALSE | Site Works - Civil | Civil 401 | Manholes & Pipelines | Ducting for NCS and Comms | Manhole 1-1 and 1-2
08afaec0-9e0f-4779-961d-de365a25d375 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Civil 401 | Front Entrance Boundry Wall
ead2b5bb-c671-4982-8a77-8e2a2dd20671 |  | checklist-flat | work-in-progress | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Civil 401 | Front Entrance Boundry Wall | Retaining Walls - Front Entrance Commodore Drive Wall
9e3d14ee-acfc-4458-8b68-c0c7594a4c2f | Child Placement Method(18e3473c-0d66-4d64-a9df-e6e689f5251a) -- Placement methodology confirmed and necessary plant and equipment on site(87c0fe6c-c566-41e0-8b01-dc6e4dab472a): Data not allowed on signoff Raise remedial / Request Signoff(d0e0de6f-bc31-4e1f-b1fa-c33913643df1): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | work-in-progress | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Site Works - Civil | Civil 401 | Front Entrance Boundry Wall | Retaining Wall Near Commodore Drive Entrance, Adjacent to RW1-15
9044e413-fa58-4558-9f65-d39c9581daf6 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Civil 401 | Footpaths
e13ba3ba-a697-4814-a99b-dcb2284dcc21 | Child Placement Method(d7fc5ab3-6b5f-4490-b6c4-da17d9c3c616) -- Placement methodology confirmed and necessary plant and equipment on site(612bb1c0-ad5a-40f2-9d9e-0f6263e2b59a): Data not allowed on signoff Raise remedial / Request Signoff(b4c6cd6d-7192-499a-8c4a-fd9131eb4800): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | work-in-progress | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Site Works - Civil | Civil 401 | Footpaths | Footpaths adjacent to B01 & B03
033b7c66-a0ed-420b-86e9-06ef0920dcfb | Child Placement Method(36ad0c86-ca0a-4fb4-a4ef-fb0a466edb71) -- Placement methodology confirmed and necessary plant and equipment on site(7d3daa99-c156-4220-924f-67ccfebe3e08): Data not allowed on signoff Raise remedial / Request Signoff(d58649b1-57bc-49c6-a0a2-38a52a6bf6f9): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | work-in-progress | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Site Works - Civil | Civil 401 | Footpaths | Footpath Adjacent to B01
b0c1d682-cf7e-40f2-ab3f-68a63b53ca1a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Civil 401 | Services and Ducts for B01 to B04
94cf0c84-5811-5eba-82b2-77eceb89d66c |  | checklist-flat | work-in-progress | ecc41129594f66cd8ea3ddc6d8c4bfca2bfc28a62bc311f2a04fcec391b6d69d | checklist-flat | FALSE | FALSE | Site Works - Civil | Civil 401 | Services and Ducts for B01 to B04 | Underground Services Install
856a6fa4-51b3-4773-b74f-e88757a74b3c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 1
fd0ae60f-302f-4197-83ce-c57f55de7860 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 1 | Drainage
7562a81f-e235-49c9-85d1-013b68152cc8 |  | checklist-flat | work-in-progress | d9b2061d8ad175a0ee453e61d8519cd5edb37886e45136dc4d4186dc4f0a7c37 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Drainage | Drainage SWMH 8-6 to 8-5A
d1ada627-c002-4904-809d-0dfb49b71128 |  | checklist-flat | work-in-progress | b0084461b3044fff40ddd573fd9971e2c1493e0e32c1196a5cb372d440a9a7a2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Drainage | Drainage MH6-1 to MH8-6
c4f642a7-eed1-4379-9d94-df34c17fbb0c |  | checklist-flat | work-in-progress | d9b2061d8ad175a0ee453e61d8519cd5edb37886e45136dc4d4186dc4f0a7c37 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Drainage | Drainage - Tank/CP Install
97861429-8d7c-4aeb-ab3a-0eb6f1bc0278 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls
4d9c0ba2-0730-4ec5-aadb-a8415a5c50e1 |  | checklist-flat | work-in-progress | 149b94b7f9339c5d68887973126df5db6d81526087c3569b14bfaeac4ed93d7f | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Walls - RW 1-15
55966b5c-d276-4037-a836-7531463080ce |  | checklist-flat | work-in-progress | 149b94b7f9339c5d68887973126df5db6d81526087c3569b14bfaeac4ed93d7f | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Walls - RW 1-4
c73996bd-5f2d-4d3a-89ee-94fe11bc88c3 |  | checklist-flat | work-in-progress | 149b94b7f9339c5d68887973126df5db6d81526087c3569b14bfaeac4ed93d7f | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Walls - Dementia Wall
3a33c4b8-9a0b-4bc2-993a-071cd42ecdb6 |  | checklist-flat | work-in-progress | 149b94b7f9339c5d68887973126df5db6d81526087c3569b14bfaeac4ed93d7f | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Walls - 1-19
920be950-5b18-4eee-b320-a21ce1f890a7 |  | checklist-flat | work-in-progress | 149b94b7f9339c5d68887973126df5db6d81526087c3569b14bfaeac4ed93d7f | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Walls - 1-2
41347fb2-5183-4545-be06-11017a91a54e |  | checklist-flat | work-in-progress | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Walls - 1-16
7a477e04-7164-47de-bf5d-433b9115f54e |  | checklist-flat | not-started | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Walls - 1-17
ee47b43a-e356-4f39-a5f3-a061d8c54592 |  | checklist-flat | work-in-progress | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Walls - 1-18
e73d28ef-adcc-4ba5-891b-18919a374620 |  | checklist-flat | work-in-progress | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Walls - 1-1
d1bb94e3-acb4-4ae7-a9f3-a3347a1e2d74 |  | checklist-flat | work-in-progress | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Walls - 1-5
98daa60c-1840-4192-adfa-7ece80f9aab2 |  | checklist-flat | work-in-progress | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Walls - 1-8
d80e7a57-7473-4fcf-905a-9c60c9b25986 |  | checklist-flat | work-in-progress | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Wall 1-14
e6cc3f92-bcd7-4ef3-9140-b204f1f5b89a |  | checklist-flat | work-in-progress | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Walls - 1-3
2a32cc99-0bc3-4cc5-bb76-d65ce643acce |  | checklist-flat | work-in-progress | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Wall 1-9
3dc78cab-a82a-4733-a58c-e17f5014d528 |  | checklist-flat | work-in-progress | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Wall 1-6
4b7e6921-0f65-47b0-80ab-d6b75f4bcb36 |  | checklist-flat | work-in-progress | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Walls - B01B L4 Additionals
14cde712-2001-5649-8f3e-16b57cf9e29e |  | checklist-flat | work-in-progress | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 1 | Retaining Walls | Retaining Wall 1-12
45289cd2-8785-4042-a356-17960f6ebfc4 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3
83e9fa53-cbf0-4560-b536-4436a15b3855 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Drainage
9f1fd3d2-6b6f-4060-b4c9-28de3af52d97 |  | checklist-flat | work-in-progress | d9b2061d8ad175a0ee453e61d8519cd5edb37886e45136dc4d4186dc4f0a7c37 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Drainage | Drainage - Tank/CP Install
f275fd62-2c08-4fa5-9c06-32be78e40f1f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls
0c9490d0-2492-4149-90f0-f96b7a6c9f8c |  | checklist-flat | work-in-progress | 149b94b7f9339c5d68887973126df5db6d81526087c3569b14bfaeac4ed93d7f | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Walls - RW 3-9
f51ef22f-7f71-4bb3-8a47-353233038754 |  | checklist-flat | work-in-progress | 149b94b7f9339c5d68887973126df5db6d81526087c3569b14bfaeac4ed93d7f | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 3-6
271b97b1-d1ba-49fa-9835-10b0e8408dba |  | checklist-flat | work-in-progress | 149b94b7f9339c5d68887973126df5db6d81526087c3569b14bfaeac4ed93d7f | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 3-5
37c80812-ed73-4024-8a39-4a3dc5146549 |  | checklist-flat | work-in-progress | 149b94b7f9339c5d68887973126df5db6d81526087c3569b14bfaeac4ed93d7f | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 3-2
629a4258-8db5-45b3-ab86-2fbd19c7334a |  | checklist-flat | work-in-progress | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 3-1
4b9e2cff-5abc-4dc3-845f-7b233dd7f93d |  | checklist-flat | work-in-progress | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 3-3
1696fac7-9f90-49f2-9554-0ecbaf855267 |  | checklist-flat | pass | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - B08 Retaining Wall
a6818490-9556-4828-bcbe-24da424b186e |  | checklist-flat | not-started | 9efef5a28ee3b6e53aa6b1648b8a670db37adce45782b28a98339d964694a172 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 3-8
c8c97c6d-33c3-46dc-afb2-680c076db4cb |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2
7fcc4b2e-8313-41a0-ab15-bf6850dd354f |  | folder-normal | not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2 | Retaining Wall - RW 7-2
b9c2b635-c817-56de-925e-16d780cfe7ca |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2 | Retaining Wall - RW 7-2 | Blockwork
8fb533ac-8222-5189-bf60-0e0db101e0ed |  | checklist-flat | not-started | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2 | Inspection -
4fc56da8-7b3c-57b2-9aac-b881a6adcccd |  | checklist-flat | not-started | 8749770115955f289c9d34532d4aa7b3c7e59dc70eac6d8eec21cc5a1776be02 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2 | Backfill
8b1a1237-d13f-5181-ba70-14445149c8b0 |  | checklist-flat | not-started | 8749770115955f289c9d34532d4aa7b3c7e59dc70eac6d8eec21cc5a1776be02 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2 | Backfill
45628be2-f96e-5d84-a378-0253a47d65d0 |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2 | Blockwork
5e51e2ee-5849-5e32-8a97-8a964a585e56 | Child Pour Details(6863fb8a-6c6c-528c-80aa-199ced9e0815): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(07d76184-57a9-5901-b522-da79f8570085): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2 | Concrete Pour
68affd90-c187-5490-99d1-76aa4e4c8f30 |  | checklist-flat | work-in-progress | 1be12a3b70fb9738cf7dd16f282c84496270d5aa0bbb2ed877704dcafbfbc5dd | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2 | Falsework -
f6a41cb5-3edb-52b5-86b1-082fd56f8140 | Unsupported Children: checkpoint-no-status Pour Details(045aa3a1-cc91-5fc1-8891-8946fd060703) Child Pour Details(045aa3a1-cc91-5fc1-8891-8946fd060703): checkpoint-no-status must be display normal but was flat Child Concrete Supplier Specifics(39ef82df-dc00-5d70-9603-f8e05df1ab17): DataPoint Test blocks booked(47b5772f-e793-4a2f-8d9a-9dd51e6f749d) is missing 'button' values Child Concrete Supplier Specifics(39ef82df-dc00-5d70-9603-f8e05df1ab17): Data not allowed on checkpoint-group: Supplier Name:(65a56542-a1e1-4e32-970e-19d2d22eec2f), Specified concrete strength:(ce5ed86a-41fb-4acd-9b47-7c05c74e8d56), Concrete strength ordered:(63e9fd15-9292-4e1e-88ba-086727b230c5), Concrete quantity ordered:(4dec274f-21e9-4db1-9e6c-853fb3646910), Test blocks booked(47b5772f-e793-4a2f-8d9a-9dd51e6f749d) | checklist-sectioned | not-started | 6b09c5317d3c4fc26fa8cb356be170cb57db76645abad2bd78fe113c85f75d8a | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2 | Insitu Stitch Joints
737f38cf-a192-5cfa-897c-88f3c0d8090b |  | checklist-flat | not-started | c6822500abf06f86b9d564fa9c8e7b9e83a756cd7295deef986f9fd5b8f65ef3 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2 | Piling
5e385c8e-b8d0-5762-af42-938ebdde0ee9 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2 | Retaining Wall
09312671-f135-58da-bd82-7d66361f38ac |  | checklist-sectioned | not-started | c04b4b0b32475c101bb8f749b94a731d649584a81dca9a8cd39a85224a6fa307 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2 | Stair Install
c4e71359-4e29-50c0-b6d2-fb5e1a1e058d |  | checklist-flat | not-started | 984d2785309ec5231cb2a31b6097b9c8a03909e1aa2049ef6709cc4359907bca | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2 | Waterproofing
04a565fc-4faf-5b46-b615-b8af4b33643a |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-2 | Retaining Wall
ea0af837-7664-4c3d-b262-03beb8e795f9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-1
fa1c0ec3-2897-59df-9970-43817303a33e |  | checklist-flat | not-started | 984d2785309ec5231cb2a31b6097b9c8a03909e1aa2049ef6709cc4359907bca | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 7-1 | Waterproofing
302567e8-1e2e-467e-9f40-acc5255d4e94 |  | folder-normal | not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4
2efc761e-2d2a-5d7f-83df-9163616fb769 |  | checklist-flat | not-started | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4 | Inspection -
a62d3536-d148-5e2b-90c1-54b0d125ce6f |  | checklist-flat | not-started | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4 | Building Consent -
1cb4cd1e-447c-5f5a-93a2-39668d14a564 |  | checklist-flat | not-started | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4 | Council Inspection -
07584454-44ed-5986-8506-2ae73e400bef |  | checklist-flat | not-started | Add Observation Closeout Checklist | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4 | Observation -
57036cbe-6dae-5b4b-b2d0-fde172442d3d |  | checklist-flat | not-started | 8749770115955f289c9d34532d4aa7b3c7e59dc70eac6d8eec21cc5a1776be02 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4 | Backfill
fe1286de-b1ae-5dd2-9858-e892b1950152 |  | checklist-flat | not-started | 8749770115955f289c9d34532d4aa7b3c7e59dc70eac6d8eec21cc5a1776be02 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4 | Backfill
9060e94f-fd1e-5b5b-9389-7e0eb71e83c0 |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4 | Blockwork
8b41d40c-2e70-5626-9740-c3c8333e5c35 |  | checklist-flat | not-started | c6822500abf06f86b9d564fa9c8e7b9e83a756cd7295deef986f9fd5b8f65ef3 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4 | Piling
1be65dba-d7e7-5c4c-bcc3-dc1ef955c9a6 | Child Pour Details(59f406e0-c329-5710-859b-57d1721f4adf): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(99b220bf-3a86-59fd-b3a4-c816602689a8): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4 | Concrete Pour
690e60a5-814e-5d91-874c-c4f5142559a6 |  | checklist-flat | not-started | 1be12a3b70fb9738cf7dd16f282c84496270d5aa0bbb2ed877704dcafbfbc5dd | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4 | Falsework -
f7fee941-9935-56ed-a87b-cfe67ed3e9f1 | Unsupported Children: checkpoint-no-status Pour Details(5e07b5bd-a183-53e5-a2b2-69002d09f325) Child Pour Details(5e07b5bd-a183-53e5-a2b2-69002d09f325): checkpoint-no-status must be display normal but was flat Child Concrete Supplier Specifics(38126079-150c-5358-9d2a-d320c0f7a58c): DataPoint Test blocks booked(47b5772f-e793-4a2f-8d9a-9dd51e6f749d) is missing 'button' values Child Concrete Supplier Specifics(38126079-150c-5358-9d2a-d320c0f7a58c): Data not allowed on checkpoint-group: Supplier Name:(65a56542-a1e1-4e32-970e-19d2d22eec2f), Specified concrete strength:(ce5ed86a-41fb-4acd-9b47-7c05c74e8d56), Concrete strength ordered:(63e9fd15-9292-4e1e-88ba-086727b230c5), Concrete quantity ordered:(4dec274f-21e9-4db1-9e6c-853fb3646910), Test blocks booked(47b5772f-e793-4a2f-8d9a-9dd51e6f749d) | checklist-sectioned | not-started | 6b09c5317d3c4fc26fa8cb356be170cb57db76645abad2bd78fe113c85f75d8a | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4 | Insitu Stitch Joints
02e2ec63-2604-587a-9a31-8eaf588df474 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4 | Retaining Wall
0a0960df-aeda-5114-8442-6063ecc2404f |  | checklist-sectioned | not-started | c04b4b0b32475c101bb8f749b94a731d649584a81dca9a8cd39a85224a6fa307 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4 | Stair Install
3e328467-f11f-5f43-908e-5a3b9e2485b0 |  | checklist-flat | not-started | 984d2785309ec5231cb2a31b6097b9c8a03909e1aa2049ef6709cc4359907bca | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-4 | Waterproofing
6925e943-8060-4e78-ab31-30e1add78621 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 4-3
4194d6b4-d36b-4639-8851-51d67fb747bc |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-2
2658e1f1-6804-41d2-bf88-ac70eb2d77f3 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 4-4
64f16f36-4366-51b0-a29f-5c2eb277947b |  | checklist-flat | not-started | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 4-4 | Inspection -
ebb77fa1-cf12-5d56-800e-26399b44cfd7 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 4-4 | Council Inspection -
d1e556de-a6c1-58b4-afe4-02a8a0783d95 |  | checklist-flat | not-started | 8749770115955f289c9d34532d4aa7b3c7e59dc70eac6d8eec21cc5a1776be02 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 4-4 | Backfill
0c34f44d-40b8-548b-8b0c-bcd82a4986a3 |  | checklist-sectioned | work-in-progress | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 4-4 | Blockwork
5c261aec-5a85-59e2-99ee-9f55e34ee1d9 | Child Pour Details(d34c5731-aab0-5b72-96fd-2ce36cdc6f7d): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(88c75375-c75a-5269-9e8a-cea40604e32a): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 4-4 | Concrete Pour
691ecd83-2cf2-5970-b453-30987eb5ba4f |  | checklist-flat | not-started | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 4-4 | Retaining Wall Consent
b91fb286-639a-590f-9f1a-74415f3a62e3 |  | checklist-flat | not-started | 1be12a3b70fb9738cf7dd16f282c84496270d5aa0bbb2ed877704dcafbfbc5dd | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 4-4 | Falsework -
1eb3ddcc-c362-5c5c-b1b2-e3d0734ca5af |  | checklist-flat | not-started | c6822500abf06f86b9d564fa9c8e7b9e83a756cd7295deef986f9fd5b8f65ef3 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 4-4 | Piling
eb2077c5-6b67-5a3f-81cb-53790f7338dc |  | checklist-flat | not-started | 984d2785309ec5231cb2a31b6097b9c8a03909e1aa2049ef6709cc4359907bca | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 4-4 | Waterproofing
015d4f98-9105-52e4-852d-5e0f1a941acb |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 4-4 | Retaining Wall
9a8486dc-1eef-43ea-bf44-c9ee0b60b1ec |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 4-2
dadd3cf9-59c5-411e-aa73-0b35ae48e332 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 4-1
306816d8-c89d-40d8-ab42-b6a445318b83 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | BO8 Carpark
30420f48-20cc-40e6-b35d-3fbff576db1b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-7
86dc0f80-dfa6-4448-9e1a-17fdf4bc20f6 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-8
8c704fe5-6d64-48c4-bb2c-0d5736522b50 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | BO8 Building foudation Piles
26a49189-23e9-4c63-ad03-c2487198b748 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall - RW 8-1
ee872b2b-245b-471a-9f89-275d884d0cb4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall -RW 8-9
7d9dbc73-e2f5-4065-871b-d0567d5b24d8 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall -RW 8-10
3e612d9b-ed6d-42de-8455-d39051ccb058 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall -RW 8-11
724b9f6d-8193-4367-b4ac-014e0b9873d1 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall -RW 8-3
19d8dcc7-ba6a-40b5-ba51-d06fe0af3201 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Excavation - Bulk to levels BO8
3b6bd95b-1a5f-4741-9287-5b0fd0608cea |  | folder-normal | not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Pond Excavation
6cbe62d9-a886-5190-ad6e-af85b65c0042 |  | checklist-flat | not-started | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Pond Excavation | Council Inspection -
92be5ec4-e6d0-55ae-82ce-807a4c2f8166 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Retaining Wall
1d749237-6951-460c-bed1-f23555876275 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Transformer installed
c77863ef-2f98-4092-bb0b-c47aeee87fdb |  | folder-normal | pass |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Bush Cleared and mark out
389cfcc1-01cc-5263-b9ff-9ad289bae5bc |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 3 | Retaining Walls | Bush Cleared and mark out | Inspection -
95b30bdb-62f8-4539-bd86-680c145d3792 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8
c715ba12-2356-45fb-874c-22cba86ef66c |  | folder-normal | pass |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Excavation
bc0eb596-6eba-40a0-bac2-0d6b3cc7282e |  | checklist-flat | pass | 63698f41825fe2adccc8f338a7282f11a6e7ac2798e7812307fa7c88d5c92f02 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Excavation | Bulk Excavation
83d2f896-afb4-412f-a543-772143d76933 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Drainage
4a1f6d81-ca12-4e6a-9a34-0f9b674e3b06 |  | checklist-flat | work-in-progress | b0084461b3044fff40ddd573fd9971e2c1493e0e32c1196a5cb372d440a9a7a2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Drainage | Drainage - Manhole & Pipeline Installation
ca8e80da-3b6a-4531-8800-4a7cdd1c77f5 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls
8aba9b43-ef25-5daf-b29f-63c4c6f6d00b |  | checklist-flat | pass | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 1-7
6244ce88-44db-5bef-9f57-41022b016aa5 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 1-8
f34428b1-4c45-58a2-8950-24e75ef3ae4c |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 1-9
288d2e70-2eb7-5877-a24a-242de7aa67b3 |  | checklist-flat | pass | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 4-1
73af06d7-8f94-5887-b78e-ccff62ee541a |  | checklist-flat | pass | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 4-2
2b789959-058b-5c68-88a4-ae8e858cee57 |  | checklist-flat | pass | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 4-3
ca631956-f84d-586e-9350-d70517c714b5 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 4-4
87e7dd9f-1fc2-5d53-8eb1-67842b9c839d |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 7-1
82f5ea97-41b3-5486-89f1-4d8f7c839ea8 |  | checklist-flat | work-in-progress | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 7-2
95cd2973-899e-5984-97b6-cb5932b6772f |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 7-10
04000f8a-b50a-5e9f-a2db-cf10e75578a7 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 7-11
c66ba8a3-eefe-542f-bbb0-083328f1b0b1 |  | checklist-flat | work-in-progress | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 8-1
d4bd809f-51ea-5d07-9d8b-c8ac5cf01c96 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 8-2
9713410b-051a-5fa0-a764-dcecac2f2553 |  | checklist-flat | work-in-progress | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 8-3
b37d74c3-f610-526a-bf63-0e147df2cc0a |  | checklist-flat | work-in-progress | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 8-3A
d6105cab-3446-5184-b1b8-75b845a5e518 |  | checklist-flat | work-in-progress | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 8-4
7e11d9cf-ce2c-57d4-8e3e-5f141c58523c |  | checklist-flat | work-in-progress | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 8-5
a6db707a-bf0f-5fdd-981d-effc7be56f42 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 8-6
28730ba8-c787-5f19-b60f-6189890d9741 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 8-7
db9f9c59-6b2c-5cff-870d-d07831b449b4 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 8-8
9d53656a-08f3-52a3-a50a-b0a0e791fc71 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 8-9
8f0021b3-9a8d-5499-b11a-80c7e774d295 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 7-7
06e93ad5-b6f9-525f-8d2f-59d5c3ad83db |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 7-8
2a2ea05b-e0a0-5765-b3a8-e327926265d4 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 7-9
0ad317d1-b893-5aaa-bcfe-ac00d4e725e7 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 1-11
14411013-ea07-5368-8022-1fd011f8fe85 |  | checklist-flat | pass | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Walls | RW 4-5
3dc104ff-9d1f-57a5-be5f-599c8d3b5f96 |  | checklist-flat | work-in-progress | c6822500abf06f86b9d564fa9c8e7b9e83a756cd7295deef986f9fd5b8f65ef3 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Piling
3933ff2c-daf1-4d60-b5d3-5b20bfa644a1 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour
f14f482d-9e1d-59d3-8bdf-8c29891bff22 | Child Pour Details(66b1c0cb-3e39-5362-ae92-404f5ef81e85): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(ae86dc54-8582-5ae1-9622-c3ba3d21dab4): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 1-11
cdf7f0f4-924a-5764-8261-f1a758fd7cae | Child Pour Details(b6ae6632-ba05-5d82-8a48-ddd26c5ce862): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(421ee54b-c56f-575d-8029-9c6adbb659a8): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 1-7
82120b9c-c30b-568c-9985-163917a3e425 | Child Pour Details(33400107-71d5-54aa-8329-1581f0a8290f): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(781b4fda-bff1-57ff-9f32-249ffb42ab9a): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 1-8
adaa8817-eec8-5ee2-a1f0-c786db166928 | Child Pour Details(b9b12355-e4b7-58cc-af2e-10c6aac61e69): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(f8d343b6-5ee2-5070-8ce3-8115dfa430b2): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 1-9
d44f27cb-9ffd-5632-ae84-da2526abd757 | Child Pour Details(4186170f-36c3-529e-a4c7-4eeecddf7e8e): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(9add7b8a-d719-5aed-93e1-cf2e3799a679): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 4-1
fab17b35-f088-5674-b6ea-7e6d3c1abe09 | Child Pour Details(a7427e28-76fb-5dd7-a637-58ad5ec40676): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(c8256b7f-b9ed-501b-bceb-f9d3d4d7b626): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 4-2
eb75dfb4-7a54-5340-88a5-29c000dbf9f0 | Child Pour Details(2255dedf-4292-536e-bff5-3cafb8cfff43): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(f287d9e0-982d-5fc7-9282-f239e75433ed): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 4-3
20af38ab-735d-5702-bf9a-81098cb80ce4 | Child Pour Details(ef82859c-e0c7-5f83-9849-f4e6aeb0ceb6): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(9f56dcc2-44c2-5550-9153-7001b0c80656): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 4-4
e658c55a-383e-53f5-87ff-5e1a9dc28ed0 | Child Pour Details(196fc5f5-e04d-58f2-ac40-02ab05cdd22e): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(58b6aa2e-be19-5778-92e4-5bdf7030e09f): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 7-1
b2ed66b0-ade9-5229-b660-6a791cb486c6 | Child Pour Details(fba25d65-6a76-57a2-8eb7-bcc1282394d4): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(a6e305d6-065a-5965-918e-f3ec63174ac7): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | work-in-progress | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 7-2
21efa5c9-04e6-532e-b110-24dee68fe47b | Child Pour Details(4ecb6c3b-d8ee-50ec-858f-095d0c6a63f0): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(1648eb88-4bbe-5bf8-957e-c980b49432f3): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 7-7
63d7fd6e-1413-520f-b348-bdf6e3d25fca | Child Pour Details(f2b50a8a-cf8f-59ff-8a78-92b7bd09eb60): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(b010d846-ddfc-5b78-83dd-96d241e8364b): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 7-8
1871b5e5-4038-5483-bb14-7b7d8f6c07a1 | Child Pour Details(225e0f97-ab07-5c65-80a7-75a1e5e13d14): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(f19d05a1-2094-5ed6-97b5-09cd77b912d0): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 7-9
c991d1cc-c423-5496-a227-4918a3c4b9a5 | Child Pour Details(78ecaa9f-6be4-5f1a-917a-e83fd80307c1): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(05515c05-98e8-5c9f-9cdb-a4a62fe71686): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 7-10
f3cbeaf8-c580-5ae6-a0a2-cb50a4f72ba7 | Child Pour Details(e9d2b2d5-4058-53be-ac76-4578970fac88): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(c170d4fe-6bba-5ed7-ba03-bdf06334028f): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 7-11
c3e687d9-f9ec-592c-8c7a-3fdf93d77129 | Child Pour Details(193bf3b0-6415-557b-927d-9f253e6cff64): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(16d9f97f-540a-5e0a-b5b0-bd57b4a3d7f1): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 8-1
dfcb32d9-0183-57be-b7ac-5016b7944da1 | Child Pour Details(e000a050-0597-5023-b407-46efb11b1297): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(c2e482ec-20cd-54ac-a67d-a0e72deb2c01): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 8-2
a17898d0-0877-53d3-a837-dde6a07f6a4a | Child Pour Details(7f606b29-2061-5432-9cb3-8383bc66a62a): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(2748e684-1422-521a-b5ee-9ba73ce86263): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | work-in-progress | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 8-3
fa998d7b-6d5b-5782-b730-207737295317 | Child Pour Details(b2f01383-23de-5608-bf03-399a3ee50c79): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(643cd8a1-1100-551c-a3c7-233d9fbae4e3): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | work-in-progress | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 8-3A
933558ff-f1a4-54da-81e8-820c335eae7b | Child Pour Details(0fb38924-082b-59f6-bf35-d4ace2f5200d): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(522395fd-9240-5070-8a5b-5d0d87e4c7ae): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 8-3B
5b896d65-4ef0-5aea-9381-fdc3294d9bc2 | Child Pour Details(50f1d9f3-52fd-566a-a27f-189c116b33e5): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(7fc1642f-48da-550b-9e02-89ebd2abac8a): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 8-4
32201330-afa7-5507-820e-0807c7fe3902 | Child Pour Details(c1ce3c34-403b-59ea-bbfa-b898fd9854bd): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(9ee8d483-f725-520b-ad00-398f4799c6a7): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | work-in-progress | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 8-5
48a4672d-67e0-54ff-83a9-f8e7a07ee362 | Child Pour Details(ce27881f-1854-5557-b2fb-9ba7543b2ef3): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(ae8efa1e-2904-5fc4-8bc1-d3502b3b65b0): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 8-6
49787876-7174-5d4b-9c4f-2a0367a4ec16 | Child Pour Details(fdc8165d-c8d7-5096-adb7-7ba8dcfa70ff): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(da962731-9c71-5a02-b199-1ae2cc92e573): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 8-7
b38eff63-c0ee-5610-ae93-c3a82e657e33 | Child Pour Details(45e2aaa5-03c5-5025-a61f-727af8c76b96): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(893c8a1b-f501-5022-adb6-1556182ac433): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 8-8
0bf560e1-fb22-5161-9dff-39a47b36917b | Child Pour Details(15b885f3-906c-564d-bca0-4a8eea528627): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(d1524613-3bd1-543f-a399-0367305d2188): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | not-started | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 8-9
471d1073-7c3b-5085-9e26-7650e41c7160 | Child Pour Details(dceb5035-f1a5-550a-b7e6-5123d527e938): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(0fa0fa63-d5e5-592a-afc5-7ba29fe6f96a): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour | Concrete Pour RW 4-5
61210b94-4ae4-50c4-8d58-c913716ad62c |  | checklist-flat | pass | 8749770115955f289c9d34532d4aa7b3c7e59dc70eac6d8eec21cc5a1776be02 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Backfill
bd7fbf31-2978-5907-975b-1895d5a3e593 |  | checklist-flat | work-in-progress | ecc41129594f66cd8ea3ddc6d8c4bfca2bfc28a62bc311f2a04fcec391b6d69d | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Underground Services Install
21f08c20-679f-54df-9e32-8abedea0d724 |  | checklist-sectioned | work-in-progress | c04b4b0b32475c101bb8f749b94a731d649584a81dca9a8cd39a85224a6fa307 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Stair to Bowling green (beside RW 1-11)
70481b00-cf21-5997-ad66-2120e7b687aa |  | checklist-sectioned | pass | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Blockwork 1-7 and 1-7A
c51fd971-ab27-5289-82b2-16e6cd3517d4 |  | checklist-flat | pass | 984d2785309ec5231cb2a31b6097b9c8a03909e1aa2049ef6709cc4359907bca | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Waterproofing
56a2013f-a4f0-5b14-a1b7-8712713a062e | Unsupported Children: checkpoint-no-status Pour Details(59587ed8-b304-5fe0-b7bc-788dc9e1a429) Child Pour Details(59587ed8-b304-5fe0-b7bc-788dc9e1a429): checkpoint-no-status must be display normal but was flat Child Concrete Supplier Specifics(e23b221e-61f0-5d36-a442-388483dd513e): DataPoint Test blocks booked(47b5772f-e793-4a2f-8d9a-9dd51e6f749d) is missing 'button' values Child Concrete Supplier Specifics(e23b221e-61f0-5d36-a442-388483dd513e): Data not allowed on checkpoint-group: Supplier Name:(65a56542-a1e1-4e32-970e-19d2d22eec2f), Specified concrete strength:(ce5ed86a-41fb-4acd-9b47-7c05c74e8d56), Concrete strength ordered:(63e9fd15-9292-4e1e-88ba-086727b230c5), Concrete quantity ordered:(4dec274f-21e9-4db1-9e6c-853fb3646910), Test blocks booked(47b5772f-e793-4a2f-8d9a-9dd51e6f749d) | checklist-sectioned | pass | 6b09c5317d3c4fc26fa8cb356be170cb57db76645abad2bd78fe113c85f75d8a | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Insitu Wall at RW 4-1
d0c6ba48-5532-4f25-8640-f91d0b824b75 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work
b2f0cbed-d004-5ce1-ba13-fd8fcf9c1192 |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 1-8
2d5c738a-7895-5993-be92-77e63c1be238 |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 1-9
f005b6bf-c45d-54a7-a36a-aefb1bbb890c |  | checklist-sectioned | pass | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 4-1
875d75ea-1716-5337-b1c0-da05d751a185 |  | checklist-sectioned | pass | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 4-2
df938f09-fac7-5682-83cd-b67f120a2640 |  | checklist-sectioned | pass | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 4-3
81c2e501-5a8e-546d-9fa7-dc56b7c81861 |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 4-4
e811ab4a-0642-587c-b93c-03c3d28e83b1 |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 7-1
783d641c-0426-56ce-8543-1382871320d5 |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 7-2
b5fd00e9-522f-57fe-9d9c-08e6ee6ce00d |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 7-10
1cb1819d-59d7-531c-b2f6-7dae2f9dee3c |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 7-11
4eebd3e8-244d-5317-9140-9f2947b17c08 |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 8-2
60c0cac3-eb2f-5b28-ae6f-1c502002274d |  | checklist-sectioned | pass | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 8-3A
4af3fefd-8f0d-5d24-8156-fca254d4e7c8 |  | checklist-sectioned | pass | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 8-3
1391f2f3-8694-5dbc-bc21-6e6c2f30b240 |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 8-4
3ec41357-c2df-5c0e-a8df-30e520b30769 |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 8-5
f4af215d-492a-5cef-b09c-d90b070d84da |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 8-6
e2c47494-78d7-5d06-9893-f87a97be762b |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 8-7
36ef7e8a-01a2-5f52-9867-fb5e8975b924 |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 8-8
de2d80e8-761f-528b-86b1-3b4a950c8782 |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 8-9
bd579f23-7661-5424-b754-0ab34cc2400e |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 7-7
afaa648a-9bfe-57a1-8062-910ab82bd6cc |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 7-8
f56af126-865f-5f26-8b3d-be442182cf8f |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 7-9
53e60212-6404-5c70-8907-601958340f4b |  | checklist-sectioned | not-started | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork 1-11
0cd6a7aa-af72-5e78-babd-da22f0cb56b5 |  | checklist-sectioned | pass | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Block Work | Blockwork RW 4-5
a0969bea-12ad-48af-a5df-0d4f8c050f8b |  | folder-normal | pass |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Fire exit stair 1
ca9686cc-3487-5fa4-b565-e09b53cff999 |  | checklist-sectioned | pass | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Fire exit stair 1 | Blockwork
51367e4c-6ade-5fb5-9594-27075704a72f | Child Pour Details(397f26ad-0d2e-53f1-a643-08c553436720): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(c153732e-92f3-5b9b-b493-fd42663b7c82): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Fire exit stair 1 | Concrete Pour
cc2399ca-4d7a-40fa-a3d4-6b1bd21c146e |  | folder-normal | pass |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Stairs
a006ec20-115e-5f1c-9920-eabc0d06225a |  | checklist-sectioned | pass | c04b4b0b32475c101bb8f749b94a731d649584a81dca9a8cd39a85224a6fa307 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Stairs | Stair Install - Fire egress 1
6bb096ed-e212-50f7-a83f-aaaed9819683 |  | checklist-sectioned | pass | c04b4b0b32475c101bb8f749b94a731d649584a81dca9a8cd39a85224a6fa307 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Stairs | Stair Install - Fire egress 2
a92708e2-19c2-40ee-a6c3-503aafb65f7d |  | folder-normal | pass |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Mail box
ccb9f400-567f-5fa3-af2c-b7eab0739426 | Child Pour Details(d3cc5692-1fc4-5c1b-a6cc-cad821bbebe9): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(65415a32-24db-563d-9981-c1b85f290dc6): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Mail box | Concrete Pour
b43986bd-c91b-486a-8f5b-f2cb049e047e |  | folder-normal | pass |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Fire exit stair 2
bbf8960a-681d-5ecc-8880-bb246a0c56c4 | Child Pour Details(452168e8-dde6-56a3-a00d-65fa856a9f08): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(90ffde98-53f8-5d0d-8c39-e76f7085ea3c): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Fire exit stair 2 | Concrete Pour
acbd015a-5be6-59bc-aedd-4e21a1132162 |  | checklist-sectioned | pass | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Fire exit stair 2 | Blockwork
e904d40a-cb87-4cb1-8505-4443335283cc |  | folder-normal | pass |  | step | TRUE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | road and foot path
9aba1095-c138-566f-94a9-aee2b9cd3eec | Child Pour Details(33f0c68a-2195-51f1-ac47-fd839ee47aca): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(c8380de5-4191-5897-82c3-0fce7e4f1e65): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | road and foot path | Concrete Pour - RW 1-7 ramp to bowling green
6a8507c8-b920-5c7d-a159-2fdc3a58651f | Child Pour Details(6eccb4e7-0aaa-50af-b44c-4a84a7d13d05): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(56b04dd5-dcfb-5012-943a-f55e3e6b266e): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | road and foot path | Concrete Pour - B04 footpath and road work
0e83a9ab-4399-5b68-9699-9cf3669f6792 | Child Pour Details(5209b18b-f7c4-548a-9273-42a78399eb71): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(dfe8feb1-725c-5574-b078-843717f5cee9): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | road and foot path | Concrete Pour - Footpath along RW 1-7 to B04
bef07567-4813-5cc4-9c6e-1731d57529cc | Child Pour Details(1ebedaa4-1b2a-5ef9-84c8-99f9e7d9e963): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(18f388d4-1b07-5c4b-a66c-81e6828d2cbc): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | road and foot path | Concrete Pour - bollard lights and rain water garden
13699c02-575c-5894-8018-964f1db7c1ad | Unsupported Children: checkpoint-no-status Pour Details(3bed4c47-bd3e-5a46-a7b4-bd46923ecfa2) Child Pour Details(3bed4c47-bd3e-5a46-a7b4-bd46923ecfa2): checkpoint-no-status must be display normal but was flat Child Concrete Supplier Specifics(0e4b0036-0c62-5b9a-8d51-f56b186effb1): DataPoint Test blocks booked(47b5772f-e793-4a2f-8d9a-9dd51e6f749d) is missing 'button' values Child Concrete Supplier Specifics(0e4b0036-0c62-5b9a-8d51-f56b186effb1): Data not allowed on checkpoint-group: Supplier Name:(65a56542-a1e1-4e32-970e-19d2d22eec2f), Specified concrete strength:(ce5ed86a-41fb-4acd-9b47-7c05c74e8d56), Concrete strength ordered:(63e9fd15-9292-4e1e-88ba-086727b230c5), Concrete quantity ordered:(4dec274f-21e9-4db1-9e6c-853fb3646910), Test blocks booked(47b5772f-e793-4a2f-8d9a-9dd51e6f749d) | checklist-sectioned | pass | 6b09c5317d3c4fc26fa8cb356be170cb57db76645abad2bd78fe113c85f75d8a | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Insitu wall at RW 4-2
d1d8fb30-37c9-4194-be6f-b8c107e2ac5f | Unsupported Children: checkpoint-no-status Pour Details(5364593b-3afd-5b41-af52-a05e9e900fde) Child Pour Details(5364593b-3afd-5b41-af52-a05e9e900fde): checkpoint-no-status must be display normal but was flat Child Concrete Supplier Specifics(591da614-7663-5948-aa65-89a4f8044e03): DataPoint Test blocks booked(47b5772f-e793-4a2f-8d9a-9dd51e6f749d) is missing 'button' values Child Concrete Supplier Specifics(591da614-7663-5948-aa65-89a4f8044e03): Data not allowed on checkpoint-group: Supplier Name:(65a56542-a1e1-4e32-970e-19d2d22eec2f), Specified concrete strength:(ce5ed86a-41fb-4acd-9b47-7c05c74e8d56), Concrete strength ordered:(63e9fd15-9292-4e1e-88ba-086727b230c5), Concrete quantity ordered:(4dec274f-21e9-4db1-9e6c-853fb3646910), Test blocks booked(47b5772f-e793-4a2f-8d9a-9dd51e6f749d) | checklist-sectioned | work-in-progress | 6b09c5317d3c4fc26fa8cb356be170cb57db76645abad2bd78fe113c85f75d8a | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Insitu wall 8-1
a3d14d0d-cd7b-4917-9f1a-b9065d02ae4f | Child Pour Details(6fb24309-aa7d-58ba-9dbf-e518a4377873): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(6b80a2c1-99e6-5142-93cf-6e73caea49da): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | work-in-progress | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Concrete Pour - stair between RW 7-2 and 8-5
9fff30fc-d659-48ec-9dfc-24395350a611 |  | checklist-flat | not-started | e66ce6f3949b6504ef8d3004d3742f988a9f269c7dde5198db7fdd803da646d2 | checklist-flat | FALSE | FALSE | Site Works - Civil | Site Works - Stage 4 - 8 | Retaining Wall 8.2
5ddc63da-3191-41e0-a0ac-467a8c6f0129 |  | folder-normal | pass |  | step | TRUE | FALSE | Site Works - Civil | Sprinkler Valve Shed
728f5728-f196-53d2-95d7-b341d6b45988 |  | checklist-sectioned | pass | 5d47080a77bde57aebc5532e07ca717b3d440aeec11469c1b01ea89c2798896f | checklist | FALSE | FALSE | Site Works - Civil | Sprinkler Valve Shed | Blockwork
f85025e8-c219-52f7-b1dc-933bb7e9e953 | Child Pour Details(eae3c57c-8e46-5a04-8273-e5a0707e51d2): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(b478ac30-c00f-597e-a200-56459ff1c433): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | Sprinkler Valve Shed | Concrete Pour
91159dd8-bac9-468a-ac97-320ca35eb549 |  | folder-normal | pass |  | step | TRUE | FALSE | Site Works - Civil | old sales office
59da776e-aee8-5090-a16d-12567d7c102c | Child Pour Details(c5777182-e1f5-5530-a6f4-572f04e686e9): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(b739c132-2451-59c3-be20-ba931ab8c69f): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Site Works - Civil | old sales office | Concrete Pour
bf0a1f42-db9d-4c73-a40a-cced1c4cbf01 |  | folder-normal | fail |  | step | TRUE | FALSE | Building B04
36d25efb-3f6d-49a4-8110-5e3b0799f4d7 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services
e0adebe3-ed13-49f2-a0e7-f40169827490 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | B04 Piling
118643c2-dae3-4fc7-a621-3b48a778965c |  | checklist-sectioned | pass | 9aea508b758454e79852f31329e4e6385e8e29b9ef476ce139e1ea6d3b995b86 | checklist | FALSE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | B04 Piling | B04 Piling QA Pre / Post Checks
fccf9aa1-7075-4c9a-8e1b-2913629ae85c |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | B04 Tanking/Waterproofing - Subfloor/Foundations
9ead1720-e7ad-4027-9816-dc945ea88984 |  | checklist-flat | pass | 1f457e8f38efc5dcc7c7ded3e4b75269b1a35d89126c7b515ef0a5ea70be7710 | checklist-flat | FALSE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | B04 Tanking/Waterproofing - Subfloor/Foundations | Waterproofing
c11f86a2-8785-4c07-9c79-fec6e7896cb1 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | B04 Foundation Concrete - Pile Caps/Shell Beams
8e3fa40c-d5b0-4604-8a4e-3dbdfa107884 |  | checklist-flat | pass | 2a9d62d45b6e943ee26808113e89fca9e1373d6f0e0df18c4c8c24d3a8c91149 | checklist-flat | FALSE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | B04 Foundation Concrete - Pile Caps/Shell Beams | Shell Beams - Area A, Part 1
cd30111c-4408-4f30-afb3-db2dabb7f56e | Child Placement Method(2d0ca872-9c33-45c4-9fce-0b55ab12a92c) -- Placement methodology confirmed and necessary plant and equipment on site(df140d58-86bd-4e71-82a0-209444e94b18): Data not allowed on signoff Raise remedial / Request Signoff(90d3bb87-97f2-4579-8fb7-90ab5997a6ce): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | B04 Foundation Concrete - Pile Caps/Shell Beams | Concrete Pour - Shell Beams Area A, Part 1 (07.08.19)
5dfc575b-0eea-4dc3-8b6e-f443ce6d85bd |  | checklist-flat | pass | 2a9d62d45b6e943ee26808113e89fca9e1373d6f0e0df18c4c8c24d3a8c91149 | checklist-flat | FALSE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | B04 Foundation Concrete - Pile Caps/Shell Beams | Shell Beams - Area A, Part 2
e46527e4-61c2-4fc1-889f-f780efb7a53a | Child Placement Method(a9636c5e-3c0e-4ab8-8658-8b053fb70548) -- Placement methodology confirmed and necessary plant and equipment on site(9efc682c-f94c-4c89-8bf8-387999ddd3c7): Data not allowed on signoff Raise remedial / Request Signoff(37af1a54-3524-489f-a275-b24f120feb99): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | B04 Foundation Concrete - Pile Caps/Shell Beams | Concrete Pour - Shell Beams Area A, Part 2 (15.08.19)
4997e4a3-12c3-4a50-8acb-7760cb3263e3 |  | checklist-flat | pass | 2a9d62d45b6e943ee26808113e89fca9e1373d6f0e0df18c4c8c24d3a8c91149 | checklist-flat | FALSE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | B04 Foundation Concrete - Pile Caps/Shell Beams | Shell Beams - Area B
c87af456-2c28-4970-bed4-0bd3036a0f57 | Child Placement Method(8e2238be-2b6b-4bc9-9301-793078af7a25) -- Placement methodology confirmed and necessary plant and equipment on site(6ec613c5-d41f-4c59-b4d3-df298e905110): Data not allowed on signoff Raise remedial / Request Signoff(978938af-0668-4ae6-92a1-8c6615dc4fed): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | B04 Foundation Concrete - Pile Caps/Shell Beams | Concrete Pour - Shell Beams Area B
0d52abe9-c09b-4abd-85b2-dd82787fbb14 |  | checklist-flat | pass | 6f8b486c4839d012a6ff8bb4a35a2c50290dfb3547358a140d4165ad4240808b | checklist-flat | FALSE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | B04 Backfill
f1a993b8-94f6-4fd9-96c1-09015bbd4c1d | Child Placement Method(f4f215e7-7736-46c4-9d16-291880365fb9) -- Placement methodology confirmed and necessary plant and equipment on site(f0a297c1-6c88-4d16-9693-51cf19aa39c8): Data not allowed on signoff Raise remedial / Request Signoff(b30dbbf9-6075-491b-b346-b077e09aa212): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | Lift Pit 1
edb69578-5b93-44f5-9ee0-4d55c6c5e9fa | Child Placement Method(7dd52fb6-6159-4248-babf-495ed47b5775) -- Placement methodology confirmed and necessary plant and equipment on site(8c01f852-f096-4f88-8b71-103cf06cef1e): Data not allowed on signoff Raise remedial / Request Signoff(b6cd8088-e0f9-4429-93fc-ec4788f5e54f): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | Lift Pit 2
edd31154-2741-4abf-ae31-8711ddeafced |  | checklist-sectioned | pass | 9e8b1efda5377dabbf88314d6f87c0953b4a7ef48d37637c95016f7835b151dc | checklist | FALSE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | Crane Base
b5f85ab3-2c2a-45b2-9f1d-75c5796e6b75 | Child Placement Method(544f4157-58ec-41bd-bfdf-5c23f2644e3b) -- Placement methodology confirmed and necessary plant and equipment on site(9c48b2fd-20be-45ec-809d-f3709dc36838): Data not allowed on signoff Raise remedial / Request Signoff(0427f223-fe7c-46af-907d-757a2829b626): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Foundation/Tanking/Drainage & Sub-floor Services | Crane base no.2
39bf2b3a-1ec9-4493-82ea-b20055ece302 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof
b9e5869b-b42d-4218-a016-5f456d4787c7 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Basement (Level 0)
17c76edf-9f9e-4e71-af01-83e0e4fac8e0 | Child Placement Method(f500dc9a-6d7a-4cc3-8c6a-f92b0ae81d30) -- Placement methodology confirmed and necessary plant and equipment on site(e64b3d15-588a-4c6c-8ed5-7cb32ce7964d): Data not allowed on signoff Raise remedial / Request Signoff(db5eb864-5eb7-4f28-8352-48ab9f64c1b6): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Basement (Level 0) | Level 0 Columns
24a6aa33-6c38-4c1c-9e37-dd6a2299e7c5 | Child Placement Method(04eb76ff-c5d8-4cb8-a856-9861d052298b) -- Placement methodology confirmed and necessary plant and equipment on site(fd038564-dc2a-4ec9-9385-6e14e9e8f6f4): Data not allowed on signoff Raise remedial / Request Signoff(b09b273b-413e-4f36-b544-9b24a9b019f8): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Basement (Level 0) | Level 0 Stitches
993d0d86-d421-5089-9798-668fa3d2ddcf |  | checklist-flat | pass | 433e02032b39c9e639bb26764a365a2375b32c6577de1d1cd83a2fdef5dc8748 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Basement (Level 0) | Intumescent Painting -
198ef0c9-eead-49a9-9c0c-4415f75d20cb |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 1
ffa7a9a2-205f-4139-a0b7-b13930e94cf3 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Structural Steel Components
49c93aa6-8f0b-4765-83e4-fc392d12ffdc |  | checklist-flat | pass | 5d45cb25cce10fc2bec2bcccb69065573a7cd47f689f0eda30d01b7f22b0b3c3 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Structural Steel Components | Structural Steel Flooring elements (beams and angles) - Area A Part 1 Level 1
f79dd8eb-cbcd-4043-ac28-5cfced5d4d84 |  | checklist-flat | pass | bc2b1db8526e6c729e7d761ae488d818c90b35948b43de131194d4c8c5a7abf7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Structural Steel Components | Intumescent Painting -
c2a97046-0c26-4edb-9ba5-1dd3eeedea12 |  | checklist-flat | pass | 5d45cb25cce10fc2bec2bcccb69065573a7cd47f689f0eda30d01b7f22b0b3c3 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Structural Steel Components | Structural Steel Flooring elements (beams and angles) - Area A Part 2 Level 1
875efe2e-35c3-41c5-9bfb-8e8cee49b374 |  | checklist-flat | pass | 5d45cb25cce10fc2bec2bcccb69065573a7cd47f689f0eda30d01b7f22b0b3c3 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Structural Steel Components | Structural Steel Flooring elements (beams and angles) - Area B Part 3 Level 1
933c7272-05ce-43a2-8efc-c9504bec83fb |  | checklist-flat | pass | 5d45cb25cce10fc2bec2bcccb69065573a7cd47f689f0eda30d01b7f22b0b3c3 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Structural Steel Components | Structural Steel Flooring elements (beams and angles) - Area B Part 4 Level 1
d2012c6c-cce4-4ce4-8f3f-5ba811aadbb0 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Concrete Slab Pours
a8de76dd-cd3c-4763-a04d-7c037ba24a87 | Child Placement Method(fb93f7e6-9fa0-4b7c-a360-72bb1f38c7fc) -- Placement methodology confirmed and necessary plant and equipment on site(0593a83b-1b91-4926-a36c-dffc4de7ec8e): Data not allowed on signoff Raise remedial / Request Signoff(da03d3f8-3d19-4b1a-b7bb-943df89f73c7): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Concrete Slab Pours | Concrete Pour Checklist - Area A, Part 1
72f7b715-fb4e-4946-9a8a-a966b5989c51 | Child Placement Method(47e507d0-a8db-4a3a-b1d5-07834594d016) -- Placement methodology confirmed and necessary plant and equipment on site(9d9b7aa3-2af8-4171-805f-dc14f83b2107): Data not allowed on signoff Raise remedial / Request Signoff(92ad5a1a-3015-4d35-8082-bc33352f47dc): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Concrete Slab Pours | Concrete Pour Checklist - Area A, Part 2
7a1177e8-15e0-47d1-b2ad-d3eb90394946 | Child Placement Method(244bd6b2-a669-4baf-9928-58bd72fb0b6b) -- Placement methodology confirmed and necessary plant and equipment on site(2bbf1c5f-aff8-4df8-9821-4367a5a1716c): Data not allowed on signoff Raise remedial / Request Signoff(2ac46704-1263-4af0-951e-c1d91a23a766): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Concrete Slab Pours | Concrete Pour Checklist Area B
02234d39-c6dc-43ce-95db-95fa247eae07 | Child Placement Method(89214b60-ca36-4d9e-b676-c24147ff4e48) -- Placement methodology confirmed and necessary plant and equipment on site(cfadcff3-4892-4bf0-9d49-803e8e1c9fec): Data not allowed on signoff Raise remedial / Request Signoff(b1e15a92-3d60-4d8c-b84a-53189e1d21bc): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Concrete Slab Pours | Concrete Pour - Area A Part 2 Level 1
fac823e6-a6ad-4295-bf54-ea4c847b7f25 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams)
d7db96d2-ddbe-42a3-8fc3-d18ee095c68c |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Wall Panels
5f8f6438-857b-48d4-b306-917da9c85feb |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Wall Panels | Precast Wall Panel - Area A Part 1
21a9ac05-bb2a-4a91-bc1c-7146afda864d |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Wall Panels | Precast Wall Panel - Area A, Part 2
0d106477-36bf-42fb-af8f-70fa235c791e |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Wall Panels | Precast Wall Panel - Area B
630c89b2-e01b-4ce5-8bd8-9357c3e6e1da |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Spandrell Panels
f21c665e-3276-4e89-998c-58673811e5f3 |  | checklist-flat | pass | b69f2f615e1c62c2ac6579d73b8b490f45f8b2161f8bad49e286a6f489e1ac73 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Spandrell Panels | Precast Spandrells - Area A Part 1
3c3f1d0b-95c4-4b61-8ef2-8517bc30613f |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Spandrell Panels | Precast Spandrell - Area A Part 2
e8f4abab-51f2-496f-bf24-19f602395f62 |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Spandrell Panels | Precast Spandrell Panel - Area B Part 3
488f9e0b-6e20-4b88-a1a7-b1e6e130ea59 |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Spandrell Panels | Precast Spandrell Panel - Area B Part 4
838e3774-8636-4cc0-a073-b8a7b592b1e6 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Beams
c7f8cbd6-2022-4cc9-ad17-52f805662302 |  | checklist-flat | pass | a67b0f1a368052d70f282bdf1d7f1708de6608e0505ad8be4d957fd08e758884 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Beams | Precast Beams - 27/09/2019
1f053700-331c-44f2-9504-3f6bd7aa47e6 |  | checklist-flat | pass | 2a9d62d45b6e943ee26808113e89fca9e1373d6f0e0df18c4c8c24d3a8c91149 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Beams | Precast Beam - Area B Part 3 and 4
3b86861a-7096-4d91-a97b-62b9b75e1ac3 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Stairs
3d54d899-15f2-43ce-a39c-50d9ff6df484 |  | checklist-sectioned | pass | d5d42a973ea365557308febe2f52f10450abf9897317fe6b989933c92d40d4ed | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Stairs | Stair Install Area A
7884b6ab-f0a5-5ca8-9ddd-d18c9e20a308 |  | checklist-sectioned | pass | c04b4b0b32475c101bb8f749b94a731d649584a81dca9a8cd39a85224a6fa307 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/spandrell/edge beams) | Precast Stairs | Stair Install Area B
f8e0d4b6-0374-49a3-bd55-38c06d2b64cb |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Insitu Stitch Joints and columns
12b49537-3f9e-40a8-be66-7043e3f72a47 |  | checklist-sectioned | pass | 9e8b1efda5377dabbf88314d6f87c0953b4a7ef48d37637c95016f7835b151dc | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Insitu Stitch Joints and columns | Insitu Stitch Joints - Area A Part 1
adfb7e4d-8064-4605-b15e-40e4d34e3608 |  | checklist-sectioned | pass | 9e8b1efda5377dabbf88314d6f87c0953b4a7ef48d37637c95016f7835b151dc | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Insitu Stitch Joints and columns | Insitu Stitch Joints - Area B
edbfd08d-dcfb-448c-a437-26db7386b24f |  | checklist-sectioned | pass | 9e8b1efda5377dabbf88314d6f87c0953b4a7ef48d37637c95016f7835b151dc | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Insitu Stitch Joints and columns | Insitu Concrete Column - Area B
2f990d6f-772b-4f19-ae9b-5dcac2ab979b |  | checklist-sectioned | pass | 9e8b1efda5377dabbf88314d6f87c0953b4a7ef48d37637c95016f7835b151dc | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Insitu Stitch Joints and columns | Insitu Stitch Joints - Area A Part 2
5732e6b2-48e6-4c3e-b18f-52c9e529e346 |  | folder-normal | pass |  | step | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Shell Beam Pours
7a145afd-ff21-43fe-84f4-c289deffddb7 | Child Placement Method(b5b436d2-950a-41d9-8e48-804d7de1dddf) -- Placement methodology confirmed and necessary plant and equipment on site(ddf4046d-7d6f-40f8-a9b0-6db9c10838a8): Data not allowed on signoff Raise remedial / Request Signoff(925649d5-fbfe-4ff5-b9bc-4f5ee9f04a7b): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Shell Beam Pours | Shell Beams 8/10/2019
53b61812-827a-4ecd-819d-ec1ae816adc7 | Child Placement Method(ea3d2208-8194-4150-a0ad-47c50a5e71b7) -- Placement methodology confirmed and necessary plant and equipment on site(da90e4a2-52e3-4aae-8e05-f8fa8e8b2665): Data not allowed on signoff Raise remedial / Request Signoff(230618d0-551b-4a00-90e3-f1aa652ee3fe): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Shell Beam Pours | Shell Beams Area A Grids 12 and P
9502e2c9-4fc0-4786-b8b8-07d714cb91c0 | Child Placement Method(b995f4c6-0896-4869-bc71-0f1209ed3980) -- Placement methodology confirmed and necessary plant and equipment on site(edacba59-f849-449c-94b4-ef7ed5a06e85): Data not allowed on signoff Raise remedial / Request Signoff(c65689ba-567a-4181-9a31-bf60409cebfa): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Shell Beam Pours | Shell Beams A1 & A2 GL 13-19
c0831404-3d6b-41d3-b7d2-808cc95262ed |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Ramp
0c8521d3-9b12-44cc-8dfc-376f36f58e93 | Child Placement Method(a4c1b227-f963-4da3-b559-301bba5ac5fa) -- Placement methodology confirmed and necessary plant and equipment on site(4745b47d-376c-494a-aa23-63b663fdd573): Data not allowed on signoff Raise remedial / Request Signoff(65990d74-9b3f-4ea1-a561-e912aa5fdcae): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 1 | Ramp | Concrete Pour Checklist - Ramp
683d0593-bdb3-48bc-8040-555ca2b728b8 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2
5cdab44a-6745-43c0-a910-59d2df908363 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Structural Steel Components
6c2d533d-93aa-4e18-9f90-252aa84d2356 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Structural Steel Components | Structural Steel - Beams, Posts and Angles
5ec28486-b803-4aec-9d5c-5fb55ec915ff |  | checklist-flat | pass | 5d45cb25cce10fc2bec2bcccb69065573a7cd47f689f0eda30d01b7f22b0b3c3 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Structural Steel Components | Structural Steel - Beams, Posts and Angles | Structural Steel Flooring elements (beams and angles) - Area A Part 1
6fa429d8-4321-40e0-a205-b04c2eafbe5e |  | checklist-flat | pass | 5d45cb25cce10fc2bec2bcccb69065573a7cd47f689f0eda30d01b7f22b0b3c3 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Structural Steel Components | Structural Steel - Beams, Posts and Angles | Structural Steel Flooring elements (beams and angles) - Area A Part 2
daa76a7e-f093-49f6-9947-2f9a1a9b4b93 |  | checklist-flat | pass | 5d45cb25cce10fc2bec2bcccb69065573a7cd47f689f0eda30d01b7f22b0b3c3 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Structural Steel Components | Structural Steel - Beams, Posts and Angles | Structural Steel Flooring elements (beams and angles) - Area B Part 3
8a0de1b9-a696-4370-a274-7bd10b6f1e05 |  | checklist-flat | pass | 5d45cb25cce10fc2bec2bcccb69065573a7cd47f689f0eda30d01b7f22b0b3c3 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Structural Steel Components | Structural Steel - Beams, Posts and Angles | Structural Steel Flooring elements (beams and angles) - Area B Part 4
474d1ea6-6238-4b22-944d-2f4687f4b70f |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Structural Steel Components | Intumescent Painting
db06cab1-f0b7-4f2b-aba7-ad4a6b162ac7 |  | checklist-flat | pass | bc2b1db8526e6c729e7d761ae488d818c90b35948b43de131194d4c8c5a7abf7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Structural Steel Components | Intumescent Painting | Intumescent Painting - Level 2 Area A
5603d283-6b23-5ea7-89e2-d71bc7ec82c8 |  | checklist-flat | pass | 433e02032b39c9e639bb26764a365a2375b32c6577de1d1cd83a2fdef5dc8748 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Structural Steel Components | Intumescent Painting | Intumescent Painting - Level 2 Area B
00ee9fbb-0589-4693-b0f3-d5d3c1718b68 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Concrete pours
a91dc869-97fc-4b98-af45-bc62ef86ca70 | Child Placement Method(e50bc98a-a683-484b-b957-b3939e327d8d) -- Placement methodology confirmed and necessary plant and equipment on site(d3fcd8c5-c333-4304-b493-5dcd87dad401): Data not allowed on signoff Raise remedial / Request Signoff(51b6cb7b-ae07-4af1-b957-3dafc17926a1): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Concrete pours | Concrete Pour Checklist - Area A Part 1
8b30b6dc-1638-4e5b-a0db-0e230b2d4379 | Child Placement Method(8d4481d7-bc14-4e26-81c7-15074ad0f865) -- Placement methodology confirmed and necessary plant and equipment on site(966e991a-33de-4a28-afe2-b6df0c570aec): Data not allowed on signoff Raise remedial / Request Signoff(c7bf93ac-ca55-4edb-93f7-89197f52a4bb): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Concrete pours | Concrete Pour Checklist - Area A Part 2
8039725f-5a42-4e9f-89ba-abcd0fcd2b98 | Child Placement Method(a50dc95a-b6ca-4f01-ab84-e54fc762bec1) -- Placement methodology confirmed and necessary plant and equipment on site(3caef526-2148-45be-b44c-8b6cba9198f2): Data not allowed on signoff Raise remedial / Request Signoff(2af95a81-acef-4931-bd40-0d245035c6f4): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Concrete pours | Concrete Pour Checklist - Area B Part 3
3a991c31-f23b-488c-955c-a55c36a3b4b4 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Concrete pours | Area A2 pt2 level 3
e9d6ca7a-b389-4048-bf7e-08c43a04f941 | Child Placement Method(3af74a8b-6657-4b9a-9cb5-b5e2cbadd3d5) -- Placement methodology confirmed and necessary plant and equipment on site(9ac119ca-8305-4b2a-8e40-596d335b3c54): Data not allowed on signoff Raise remedial / Request Signoff(dfde212f-b0ed-405c-acbb-4ddc480f61a6): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Concrete pours | Area A2 pt2 level 3 | Concrete Pour Checklist
1efc40d5-a339-46a1-b682-454adbcb536b |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Concrete pours | 2Nd Pour For B
3e178ec7-e69a-4ea6-8fb1-b44fc0f71cc1 | Child Placement Method(69e46a2a-a1be-43b4-934e-623123b6993c) -- Placement methodology confirmed and necessary plant and equipment on site(bed021f3-a174-42e2-8742-87a9cde3a0ce): Data not allowed on signoff Raise remedial / Request Signoff(c79e1773-696c-4888-907f-b02c74df90d8): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Concrete pours | 2Nd Pour For B | Concrete Pour Checklist
4ff8b043-27c4-4d70-b3b6-2830bceb5520 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Concrete pours | A2 level 3 last part of pour
7c0e1b0b-0fb0-4a98-808e-4acffc8ce719 | Child Placement Method(27a81b97-e11e-4a68-a134-7454045653bc) -- Placement methodology confirmed and necessary plant and equipment on site(0b12bc6e-8e05-4f91-aeab-7eec4b221c1c): Data not allowed on signoff Raise remedial / Request Signoff(43c26b0f-27e0-4930-965b-bfb460dabcfc): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Concrete pours | A2 level 3 last part of pour | Concrete Pour Checklist
726e2ae5-8991-4896-964d-2547b853f9c7 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Flooring
861a3401-119b-4495-b6eb-8175cf6b2651 |  | checklist-sectioned | pass | cb015c0774f721e0622a965e160d42ad3879e0686d010f116ca47337341bf361 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Flooring | Rib & Infill - Area A Part 1
3daefe75-873f-460a-9802-5b2d7f954ffd |  | checklist-sectioned | pass | cb015c0774f721e0622a965e160d42ad3879e0686d010f116ca47337341bf361 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Flooring | Rib & Infill - Area B Part 3
3d9874b5-77ae-419a-8e94-8c1c225dc3fe |  | checklist-sectioned | pass | cb015c0774f721e0622a965e160d42ad3879e0686d010f116ca47337341bf361 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Flooring | Rib & Infill - Area A Part 2
e23b4e68-8105-4480-a4ad-d647a944f27f |  | checklist-sectioned | pass | cb015c0774f721e0622a965e160d42ad3879e0686d010f116ca47337341bf361 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Flooring | Rib & Infill - Area B Part 4
268fa7bd-36f5-564c-9c3f-11f6c767023f |  | checklist-sectioned | pass | cb015c0774f721e0622a965e160d42ad3879e0686d010f116ca47337341bf361 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Flooring | Area B level 2 New Checklist
d2752d13-2b60-5181-ac04-d280216cf174 |  | checklist-sectioned | pass | cb015c0774f721e0622a965e160d42ad3879e0686d010f116ca47337341bf361 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Flooring | Rib & Infill Area A level 2 new checklist
c374a161-b8bd-4e2a-a3c0-14bb77f7cf14 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Components (Walls/Stairs/Brackets/Spandrells/Edge Beams)
187ccff3-b819-4e60-a6c0-29fd57e1b305 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Components (Walls/Stairs/Brackets/Spandrells/Edge Beams) | Precast Wall Panels
0a4be2f6-19dd-4a21-84ba-4051b02c361d |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Components (Walls/Stairs/Brackets/Spandrells/Edge Beams) | Precast Wall Panels | Precast Wall Panel - Area A Part 1
077efadc-9286-4eee-8774-c8131a5675ed |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Components (Walls/Stairs/Brackets/Spandrells/Edge Beams) | Precast Wall Panels | Precast Wall Panel - Area A Part 2
724b9e87-c346-4487-9a35-e1964001716a |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Components (Walls/Stairs/Brackets/Spandrells/Edge Beams) | Precast Wall Panels | Precast Wall Panel - Area B Part 3 & 4
829f985b-3068-41e0-8f2a-4ce7fee0afe5 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Components (Walls/Stairs/Brackets/Spandrells/Edge Beams) | Precast Spandrell Panels
a9c36e84-4668-40ef-8a10-61c03797ede2 |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Components (Walls/Stairs/Brackets/Spandrells/Edge Beams) | Precast Spandrell Panels | Precast Spandrell Panel - Area A
a06b088b-0018-4510-8467-aee07dcaba2d |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Components (Walls/Stairs/Brackets/Spandrells/Edge Beams) | Precast Spandrell Panels | Precast Spadrell Panel - Area B
a5e56fdb-de95-4250-b081-a6fcb9839ca2 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Components (Walls/Stairs/Brackets/Spandrells/Edge Beams) | Precast Stairs
11c29304-ec44-459b-8010-4740ff639d39 |  | checklist-sectioned | pass | d5d42a973ea365557308febe2f52f10450abf9897317fe6b989933c92d40d4ed | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Components (Walls/Stairs/Brackets/Spandrells/Edge Beams) | Precast Stairs | Stair Install Area A
74aa7bf7-be13-57c5-9d9b-1e1cfd3ddb3d |  | checklist-sectioned | pass | c04b4b0b32475c101bb8f749b94a731d649584a81dca9a8cd39a85224a6fa307 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Components (Walls/Stairs/Brackets/Spandrells/Edge Beams) | Precast Stairs | Stair Install Area B
aaf5396c-21ae-4e74-8bbb-ccb0ff29dbc8 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Components (Walls/Stairs/Brackets/Spandrells/Edge Beams) | Precast Columns
1cc8a346-39f4-46ff-aeae-2f118b0cfb70 |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Components (Walls/Stairs/Brackets/Spandrells/Edge Beams) | Precast Columns | Precast Columns - Area A
c10fbe51-92a6-4c8e-8109-b9321a68cccb |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Precast Components (Walls/Stairs/Brackets/Spandrells/Edge Beams) | Precast Columns | Precast Columns - Area B
568efd37-2716-48f0-ae02-008bbfe10a78 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Insitu Stitch Joints
4c22741b-8fb2-40b4-ba54-35f17c2c3b73 |  | checklist-sectioned | pass | 9e8b1efda5377dabbf88314d6f87c0953b4a7ef48d37637c95016f7835b151dc | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Insitu Stitch Joints | Insitu Stitch Joints Checklist - Area A Part 1
0e70ed4d-702c-4da3-869d-31d28629d41f |  | checklist-sectioned | pass | 9e8b1efda5377dabbf88314d6f87c0953b4a7ef48d37637c95016f7835b151dc | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Insitu Stitch Joints | Insitu Stitch Joints Checklist - Area A Part 2
216a6a20-a9da-4918-8a6b-a592e5f4dc6c |  | checklist-sectioned | pass | 9e8b1efda5377dabbf88314d6f87c0953b4a7ef48d37637c95016f7835b151dc | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Insitu Stitch Joints | Insitu Stitch Joints Checklist - Area B Part 3
d8b432e2-6175-4b6d-ad21-49400736b735 |  | checklist-sectioned | pass | 9e8b1efda5377dabbf88314d6f87c0953b4a7ef48d37637c95016f7835b151dc | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Insitu Stitch Joints | Insitu Stitch Joints Checklist - Area B Part 4
3701310d-9a62-4584-a829-266146590a5b |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Transfer Beam
3a33e138-a5f0-4d0f-8120-313c1bc72c47 | Child Placement Method(3171cb0b-db52-4bf6-a663-9a428f8d1660) -- Placement methodology confirmed and necessary plant and equipment on site(456e69bd-9fe0-472a-8a91-03c5f33e5b72): Data not allowed on signoff Raise remedial / Request Signoff(c570adb8-b8fb-42ec-b9fe-64d15f311538): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 2 | Transfer Beam | Transfer Beam Pour - Area B
c642d5b5-292c-4aee-a507-1f2f8e4349e8 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 3
d6fd86dd-97e9-4a16-9f0a-1803d02beb67 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Precast Flooring
89e92cce-9a7c-4aca-94a3-30be8fdb5eca |  | checklist-sectioned | pass | cb015c0774f721e0622a965e160d42ad3879e0686d010f116ca47337341bf361 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Precast Flooring | Rib & Infill - Area A1 Level 3
c9495a42-abc9-4534-a59d-fd38491f98cb |  | checklist-sectioned | pass | cb015c0774f721e0622a965e160d42ad3879e0686d010f116ca47337341bf361 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Precast Flooring | Rib & Infill - Area A2 Level 3
f3bba19c-9dee-4bb6-bbf0-ca99cd360296 |  | checklist-sectioned | pass | cb015c0774f721e0622a965e160d42ad3879e0686d010f116ca47337341bf361 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Precast Flooring | Rib & Infill for level 4 Area A
1ace9c17-4524-5d91-a3d1-880096bd3d7a |  | checklist-sectioned | pass | cb015c0774f721e0622a965e160d42ad3879e0686d010f116ca47337341bf361 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Precast Flooring | Rib & Infill Area B for Level 4
1d10a057-d3f4-4f5d-bb50-754cc3d79a3c |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Structural Steel
f49a6380-b7d6-4031-8900-2f8726db02fa |  | checklist-flat | pass | 5d45cb25cce10fc2bec2bcccb69065573a7cd47f689f0eda30d01b7f22b0b3c3 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Structural Steel | Structural Steel
c4f20a0d-514d-4180-b924-4a8d49249187 |  | checklist-flat | pass | bc2b1db8526e6c729e7d761ae488d818c90b35948b43de131194d4c8c5a7abf7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Structural Steel | Intumescent Painting
91facd15-5bf0-5ab0-a44b-50dc36835fe0 |  | checklist-flat | pass | 54ea7daef64d6ad093ac7729c33f731524914ff7212604a6fec9d4e15031f2a1 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Structural Steel | Structural Steel Flooring elements (beams and angles) - Area B
089c0571-638a-5c1c-b85f-13c65095abbb |  | checklist-flat | pass | 433e02032b39c9e639bb26764a365a2375b32c6577de1d1cd83a2fdef5dc8748 | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Structural Steel | Intumescent Painting - Area B
06aee6d8-36bf-4fcb-9f60-9dc0324113eb |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Concrete Pours
1f88a1b2-27fd-4ef7-a4d5-6d1b0675ec3a | Child Placement Method(b52fbb04-1257-4f12-a8e9-f867dc603cfd) -- Placement methodology confirmed and necessary plant and equipment on site(da08e910-a943-46a0-9b26-1b8d35f796ad): Data not allowed on signoff Raise remedial / Request Signoff(4b9c0889-8391-4b9a-8ec6-9599d0101d58): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Concrete Pours | Area A1 LVL 3
08c81398-638e-44fc-ba94-c47a49680d4b | Child Placement Method(cf37dd02-9d32-457c-9067-f0c283989127) -- Placement methodology confirmed and necessary plant and equipment on site(43dcd12e-eeee-4da1-a8e1-b2cf2df00716): Data not allowed on signoff Raise remedial / Request Signoff(cd76c60c-06a5-454e-98ec-4227e6401142): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Concrete Pours | Area A LVL 3 GL M-N
7f86d0b2-d49d-542a-b976-2096e01bf2f3 | Child Pour Details(a60e808b-2100-51ae-be0c-820f2cc4e94d): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(6632ae85-0f45-5ef9-ac99-dd3b75ffa37c): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Concrete Pours | AREA B LEVEL 3 FLOOR GL-A-F
db2c1e9b-b3d6-4483-b2ab-9a218f65d177 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Precast Components
0406c41a-0f74-424e-83ea-cafc9d37b508 |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Precast Components | Precast Wall Panels Area A
081dd135-38e4-4c7f-b2ad-50e756ff4028 |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Precast Components | Precast Spandrell Panels
2d41f5ea-b5a7-4dfe-b952-1d60daea82d8 |  | checklist-flat | not-applicable | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Precast Components | Precast Beams
52e4c1e5-71ac-4cee-8631-bead69c021a8 |  | checklist-sectioned | pass | d5d42a973ea365557308febe2f52f10450abf9897317fe6b989933c92d40d4ed | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Precast Components | Precast Stair Area A
29d248e2-6913-467c-bd33-e657037bf70c |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Precast Components | Precast Columns
470345d7-17fe-5d14-bfcc-81f3ebc935d9 |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Precast Components | Precast Wall Panels Area B
147eda30-225f-5ee4-92af-19e9fed50120 |  | checklist-flat | pass | b60dad1c3d6035a7a83d42eea9413d7382a7ec38062ba50dac94f497c036b80c | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Precast Components | Precast Spandrell Panels Area B
468e193a-5e1d-57c2-bc69-5e8e751d88b0 |  | checklist-sectioned | pass | c04b4b0b32475c101bb8f749b94a731d649584a81dca9a8cd39a85224a6fa307 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Precast Components | Stair Install Area B
6554b402-fc16-47f0-bf06-350f7041ad06 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Insitu Stitch Joints
1a3e407f-4607-42b1-bfb6-b906a932c600 |  | checklist-sectioned | pass | 9e8b1efda5377dabbf88314d6f87c0953b4a7ef48d37637c95016f7835b151dc | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Insitu Stitch Joints | Insitu Stitch Joints & Level 2 Ramp - 21/03/2020
29779f9a-350b-5e70-8554-c6d2faf47257 | Child Concrete Supplier Specifics(dcbc63b5-b6ad-5ad6-a6c0-624485cd5201): DataPoint Test blocks booked(47b5772f-e793-4a2f-8d9a-9dd51e6f749d) is missing 'button' values Child Concrete Supplier Specifics(dcbc63b5-b6ad-5ad6-a6c0-624485cd5201): Data not allowed on checkpoint-group: Supplier Name:(65a56542-a1e1-4e32-970e-19d2d22eec2f), Specified concrete strength:(ce5ed86a-41fb-4acd-9b47-7c05c74e8d56), Concrete strength ordered:(63e9fd15-9292-4e1e-88ba-086727b230c5), Concrete quantity ordered:(4dec274f-21e9-4db1-9e6c-853fb3646910), Test blocks booked(47b5772f-e793-4a2f-8d9a-9dd51e6f749d) | checklist-sectioned | pass | a997c16a3c79527db6b527d00aab2b17b792c8e2aba27dcdb64bc9f3559551f3 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 3 | Insitu Stitch Joints | Area B level 3 Stitch
bd3b6d62-edc6-41c2-ba50-afbee307d9b7 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 4
39439b37-2dca-4181-a4d0-9c850a18b638 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Concrete Pours
545112ec-2b5e-403c-80bd-9f2e1ed6e38b | Child Placement Method(4fc8820b-a1de-4f5a-bde1-48019cf7825c) -- Placement methodology confirmed and necessary plant and equipment on site(3cb4b9e1-08c3-48a8-9ddb-2ffc6f2e1dac): Data not allowed on signoff Raise remedial / Request Signoff(1f428de2-1750-4f84-8f0d-cf08fce1b8f4): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Concrete Pours | ARE A_A1_GL 1 - 13- 28/05/2020
0faed58f-ee1f-4f96-a6f8-b97afd7a9f45 | Child Placement Method(ac2594bf-2f03-432b-8493-d5fd9506bbda) -- Placement methodology confirmed and necessary plant and equipment on site(4509d6a4-c644-49a5-a109-d62ed196b6e8): Data not allowed on signoff Raise remedial / Request Signoff(1bd693f5-637b-40f3-bfa7-0d451daf7d8b): Who is placing the concrete:(d7d65b81-2e53-4579-980c-8a1eebb15c0b) | checklist-sectioned | pass | 47b3c68906e011eab08e08af6b35a20547a50ad97786e6acce11302bf6fb69b2 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Concrete Pours | Area A_A 2 Level 4_GL N-X -13-21 08/06/2020
e6f04fa5-648f-59d6-baaa-29a2a0286a8c | Child Pour Details(2ed733cc-2daf-5c46-9060-9825362b778c): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(7846afe5-392a-5cc9-b823-4e44d7ab4aa0): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Concrete Pours | Concrete Pour Area B Level 4
322849fc-eb1f-4f8a-acfa-f3d9c5639575 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Precast Components
6285b25f-b6d4-44de-90b8-6f2b45a88969 |  | checklist-flat | pass | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Precast Components | Precast Wall Panels Area A
1941a8cb-5bdb-4b97-be26-02a01c6d35aa |  | checklist-flat | not-applicable | 041dcdf4ebc372e5bf7dab713778e16719b99d5bfdfc63254b14a13396527f8f | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Precast Components | Precast Spandrell Panels
78040b68-ff02-50d7-a2f3-cd3102a4c223 |  | checklist-flat | not-applicable | b60dad1c3d6035a7a83d42eea9413d7382a7ec38062ba50dac94f497c036b80c | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Precast Components | Precast Spandrell Panels
eab1d35e-f9ad-5382-8864-8d9f80f29e10 |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Precast Components | Precast Wall Panels Area B
6ce03cb1-85cd-5463-91bd-5478bba50836 |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Area A Roof 3
8ba4ac71-ceb3-53a0-b71f-b1e473726178 |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Area A Roof 1
ddc2252e-6b51-5dc6-8485-48242f04b1fa |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Area A Roof 4
b6fdcbdd-2442-57cf-918d-49488596d891 |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Area A roof 2
0075887c-7702-5c50-a66a-eaea9b92019d |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Area A roof 8
459806bc-e37f-5706-8293-e29c0e71e664 |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Roof 5
f7b88b91-ae67-5dd8-a93a-2299a40612b9 |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Roof 9
93ef81bc-4369-5eea-9321-831fefcaf995 |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Roof 10
9a1279e3-7283-50ed-bb42-c43d246efe54 |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Roof 11
961fd52f-3afd-5017-8fe1-6d6b85eb5436 |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Roof 12
804bd445-49c2-53c6-a17c-e31d11692971 |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Roof 6
45155260-658e-569e-958d-ec8f0ff378e4 |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Level 4 | Roof 7
60edda1b-0a14-5fd5-8631-2dcb6f762fc6 |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Roof GL L and M
358d2faa-1dc6-486b-bf2a-69bc6fa8762f |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Structure & Roof | Remedial Inspection
236be5e5-ebf1-5318-b497-5d17d5d842be |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Remedial Inspection | Inspection - Intumscent Paint
dd8cf811-8dd3-52c1-90d8-d1e40d2f0e92 |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Remedial Inspection | Inspection - Rib hangers
f256b563-46d4-5824-ae94-3d9d97596cae |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Remedial Inspection | Inspection -Penetration on steel beam
1d15b6f7-ddfc-506b-80e4-c9ad97ec016e |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Remedial Inspection | Inspection - cast in plates Area B Level 4
7f4d05cf-edc3-5076-a77e-0669fca2668a |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Remedial Inspection | Inspection - Ribs gap and exposed steel
3377d547-8ef5-570a-ac5d-e141babd22f0 |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Remedial Inspection | Inspection - Spandrel EA support
179e0b94-86b7-5b49-9f27-fb9428e57c9e | Child Pour Details(81e16e14-85d0-58f9-9d8b-9e408889b9d4): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(c157f561-799a-5559-8066-b30ff2723f95): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B04 | B04 Structure & Roof | Concrete Pour for Ali-Mak base
5b176800-feb0-555a-8532-fbec4aa0c238 |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Roof - B04 B Main Entrance
3ef31246-37da-569a-9500-5ecdc4181c53 |  | checklist-flat | pass | 8129df9400ed92f7e66445b23b370e2aae9861a17f352e221dc9cd514f3957ab | checklist-flat | FALSE | FALSE | Building B04 | B04 Structure & Roof | Roof - B04 A Main Entrance
4bfabe5f-211b-4899-a544-be5c7b4a0127 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B04 | B04 Facade
f04a6196-d5b3-46af-aac9-02996cabf03d |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Basement 1
6cc74cc2-bd81-427b-96ae-23e714c3aaac |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation
d2ea1efa-4457-492a-ae57-f33503f75ad2 |  | checklist-flat | not-applicable | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Exterior frame
1257fae3-ce07-4509-9bb3-9c92432e39d8 |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Concrete block/concrete panels
ed7f9a52-468b-42af-94e9-94a5ef937a07 |  | checklist-flat | not-applicable | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | RAB Board
0ddb3f46-7413-4d87-a8d1-e4be9578c29e |  | checklist-flat | not-applicable | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Tapes and vaproshield
eb1f9635-a4e1-408a-a49a-50e97dd83143 |  | checklist-flat | not-applicable | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Windows, sliders and sealants
0aab7557-1b9e-4283-a082-62947195a1fc |  | checklist-flat | not-applicable | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Flashing at windows and doors
87b8f881-ae36-4300-8f66-31565103c875 |  | checklist-flat | not-applicable | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Envelope penetrations
db2ea393-5641-4d77-94ab-75f2e385b07a |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Lintels
1b6f9f40-d24a-431e-84e0-9c99ea7d4b27 |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Brick works
a3efa699-4599-4cf7-b253-395bd2b9c8c5 |  | checklist-flat | not-applicable | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | STO cladding
071be340-7c2b-4664-80f8-6050bf65e01a |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Cladding sealant
0fc3e081-8830-4a79-b236-8d51f6275f19 |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Pergolas
4f9e03ac-acd0-4ce9-b23a-078ec3a67b3b |  | checklist-flat | not-applicable | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Balconies
e68c1fa3-f355-4303-924a-7c9a79b1de43 |  | checklist-flat | not-applicable | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Water test
cb31f7b0-846c-4de1-a9cb-3d394f3b3650 |  | checklist-flat | not-applicable | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Down pipes
63b57778-e51c-45c2-a09b-1f15f5204be1 |  | checklist-flat | not-applicable | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Balustrades
3aa87236-9841-400c-b6ec-5c75a7a0b44b |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | North Elevation | Passive fire
9785869b-25df-4bf2-9278-9519865eae79 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation
862b87d3-9f92-4351-8257-3b9e51da8cef |  | checklist-flat | not-applicable | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Exterior frame
757aac02-b532-4253-83de-ba9681fef1eb |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Concrete block/concrete panels
ba2bced2-901d-4043-8fa3-f704c9f9b786 |  | checklist-flat | not-applicable | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | RAB Board
d8e69089-add0-4917-8129-6728780a1b5c |  | checklist-flat | not-applicable | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Tapes and vaproshield
a76ea8b1-ca64-477b-846b-52e346f23cf3 |  | checklist-flat | not-applicable | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Windows, sliders and sealants
7320b230-222c-4394-852e-83a3b5062e8e |  | checklist-flat | not-applicable | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Flashing at windows and doors
bf780d33-b7e1-4977-9ce5-f6283e086f01 |  | checklist-flat | not-applicable | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Envelope penetrations
949b7bbe-9720-4db0-8356-fde3889eca87 |  | checklist-sectioned | not-applicable | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Lintels
ac751b78-4a24-4bea-8f90-0b12074e3beb |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Brick works
e9cbc674-0794-4902-87ce-0517528210a0 |  | checklist-flat | not-applicable | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | STO cladding
3d852f4c-b56c-4809-86e2-89660807163a |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Cladding sealant
c50833e2-eb0f-429e-a3b6-c263ce5c2ac3 |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Pergolas
545a7235-bb21-49b8-82af-03b12828b558 |  | checklist-flat | not-applicable | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Balconies
4844cbfd-ec5d-437f-ab5a-280b08b34e33 |  | checklist-flat | not-applicable | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Water test
e5cf167d-b757-4412-abd9-407fd0e00a7b |  | checklist-flat | not-applicable | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Down pipes
aa0d1161-7a1a-49ab-9e5c-145fda814329 |  | checklist-flat | not-applicable | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Balustrades
befa1423-f320-4892-a0c6-ce96dd71879f |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | East Elevation | Passive fire
e21e964e-55e8-40ad-8116-50531fa096c6 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation
08890e57-a54b-466c-97b7-3c015bf6594d |  | checklist-flat | not-applicable | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Exterior frame
c654f8c0-91e4-4f66-9eb3-e25576fa050e |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Concrete block/concrete panels
7cafbd72-f8aa-409c-b57e-4c346d8ee1ef |  | checklist-flat | not-applicable | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | RAB Board
82ff0584-9647-4cc7-83d8-bd32314d3be6 |  | checklist-flat | not-applicable | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Tapes and vaproshield
9003e4da-5556-4a37-a2be-361112be3240 |  | checklist-flat | not-applicable | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Windows, sliders and sealants
84b33800-3ce1-4852-ac1a-85d636dbe8bf |  | checklist-flat | not-applicable | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Flashing at windows and doors
1836bcea-8650-4ce4-ad4b-a36d5a595199 |  | checklist-flat | not-applicable | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Envelope penetrations
632f6457-b006-4c83-a5bd-6a5c86c9b801 |  | checklist-sectioned | not-applicable | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Lintels
b1104387-57a5-4949-b5f5-af5aba85b60f |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Brick works
525a5056-f1bf-4d4c-bd4a-a4e0f58639d4 |  | checklist-flat | not-applicable | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | STO cladding
128a26c9-dc01-4fda-a5de-104a5439d7b4 |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Cladding sealant
a2566b44-ef00-4a69-afd9-77cc3bbeaf68 |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Pergolas
6e62e444-36b3-4577-a92f-266294119df9 |  | checklist-flat | not-applicable | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Balconies
0d67378a-4445-4062-9320-0178b0d3f6ad |  | checklist-flat | not-applicable | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Water test
bfcb763f-d830-4192-94c5-38a19f80f006 |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Down pipes
9a0349c6-f5d8-498c-b021-e62b5b7d7a96 |  | checklist-flat | not-applicable | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Balustrades
74463829-d50b-444a-ae4d-3c6173c5281e |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | South Elevation | Passive fire
98df01f5-5579-4190-8902-1833fd31b790 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation
f7e7565a-0c94-4aed-8c57-b60d2ac26c79 |  | checklist-flat | not-applicable | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Exterior frame
b6966122-f4c1-42db-b94d-5c68571e2c2e |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Concrete block/concrete panels
105a3134-83a3-4c64-b019-b08b67e97d3a |  | checklist-flat | not-applicable | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | RAB Board
ab4b5e6e-f9f7-4fdd-950f-1947230cd21f |  | checklist-flat | not-applicable | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Tapes and vaproshield
f54f2689-65a3-48a9-9de1-1b0fa72dd982 |  | checklist-flat | not-applicable | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Windows, sliders and sealants
f121d2fd-03f4-4fc4-b05d-89b25717f154 |  | checklist-flat | not-applicable | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Flashing at windows and doors
b4f8cc70-5856-48c7-a1f6-0fe2d02f7519 |  | checklist-flat | not-applicable | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Envelope penetrations
892724cf-c90f-4e7c-9fb6-152a36d52e08 |  | checklist-sectioned | not-applicable | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Lintels
6ec3696c-9a8b-476f-80c2-fa58c6b2c9e2 |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Brick works
589daad6-f2ac-42d7-850a-b7ca9280b8a7 |  | checklist-flat | not-applicable | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | STO cladding
125ae9c0-fdb7-453e-b089-51199dc2b730 |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Cladding sealant
593174f0-b00c-4214-baff-3a676f98e684 |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Pergolas
67cbbdb4-c473-4a25-8e03-9e8b2af84098 |  | checklist-flat | not-applicable | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Balconies
bb23b0cd-33fe-4f6b-bb10-f4be7e201d22 |  | checklist-flat | not-applicable | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Water test
86998b61-272a-465c-91ca-597418beb600 |  | checklist-flat | not-applicable | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Down pipes
a7933da1-c8ea-4602-bf7b-a6f2ea4dc846 |  | checklist-flat | not-applicable | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Balustrades
06a1909a-8d66-4e44-aaad-ef9d0b833488 |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Basement 1 | West Elevation | Passive fire
3a84d71a-cf60-4f6f-804d-d6b33b7b7ec0 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 1
e8c2d91c-6bea-4ca5-8914-1f74abcf14f2 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation
0c78c64d-101a-405b-81bf-2009138f42ba |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Exterior frame
4885eb2c-1387-4782-a292-968caaac1f3f |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Concrete block/concrete panels
10a8071a-c8ea-4e23-8b23-c08b2f16d316 |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | RAB Board
44e9fc70-5686-48f0-830e-c354f3c23cac |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Tapes and vaproshield
7360801c-1b3d-4758-b1ea-2ad6a02e1735 |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Windows, sliders and sealants
9258e757-ce71-4f08-a692-64335f5cb99d |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Flashing at windows and doors
62b0b081-e752-40e9-833b-0b6d5d2f0621 |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Envelope penetrations
8fe99f45-f9f7-4dee-9dfa-1b00e6384a70 |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Lintels
f3e52bef-e44c-4066-9faa-0f1abc339858 |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Brick works
ecb7ab42-2973-416c-a79c-67ed1619ef4b |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | STO cladding
ca7fc3fe-5be4-4707-aa51-aa7af1476a33 |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Cladding sealant
faf42c48-3da5-4641-93aa-cb5f8d1e7d30 |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Pergolas
cb965412-bb72-4fc7-bbd4-064c00a59c39 |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Balconies
f1d643c9-82ae-4e4f-9b38-9a003713b7c7 |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Water test
4cd9cdea-eb33-4445-aeea-8f0705b1c55f |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Down pipes
55e2239d-ad46-4ed9-a98f-3ad9856a9ff8 |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Balustrades
5e90a4a6-19a5-4cb7-8650-0e14d7d73e57 |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | North Elevation | Passive fire
c93f51d8-746d-404e-a001-e6f2fd74ab78 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation
16c64175-944e-48eb-8114-af256a5bce93 |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Exterior frame
25637c8f-6170-4648-9ab3-5c3bafc84751 |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Concrete block/concrete panels
fb254bdd-041b-42f8-853d-28b7c363891c |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | RAB Board
aa186911-b731-4ec8-a82c-573826cc734b |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Tapes and vaproshield
977de971-3dfd-49cd-8e48-fc4514a15c50 |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Windows, sliders and sealants
b2a8e61c-5e07-4aff-9676-541cc07f8394 |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Flashing at windows and doors
9062d2d0-6652-436a-b1f7-21996a3cbb6b |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Envelope penetrations
03b2faaa-75f3-452b-a0a1-1e2a2fe50ea0 |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Lintels
7d976b09-2349-4b04-8cea-a099aa5f6741 |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Brick works
d066c21b-3365-4f99-b823-28cdcd745322 |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | STO cladding
3b01f2f5-a261-4fa5-bc55-959938c273f1 |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Cladding sealant
8a66a41f-37dd-4548-9f37-1a692348790f |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Pergolas
92e3895e-db5a-4c9d-a217-fc499322f17c |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Balconies
31b743d8-2c31-4ff1-bd3b-1dd2e289c9b4 |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Water test
921bce06-304f-4563-9ecf-04526a347aa4 |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Down pipes
6cf7f3d8-a0c2-41b7-9d6b-e4347b7ff6f7 |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Balustrades
8af14781-ae9c-46a3-b252-7bae68309513 |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | East Elevation | Passive fire
30d3ab5e-1097-4753-b176-a06826cbacf5 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation
22496a74-6875-49ae-966b-eeb0396c7665 |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Exterior frame
5258dcc4-8dc2-4f41-8e47-afe6d105e136 |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Concrete block/concrete panels
aaedbd41-dad3-44eb-9db5-f20bb25f6b93 |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | RAB Board
59980269-6bdd-428c-9de8-8550672f5899 |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Tapes and vaproshield
fa6b767b-603c-4e49-9fe3-ec5a147cf9a0 |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Windows, sliders and sealants
a9aca500-ba1e-4e58-9cf9-b9e5feebda22 |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Flashing at windows and doors
4e884ca3-bb3b-48cf-a549-ec6289c8304d |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Envelope penetrations
ed9c6b2e-960c-4b15-b634-d092c54c9fde |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Lintels
597cf40f-ea48-4c48-863d-43a4c3047d1b |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Brick works
7ce387ff-54ca-4809-9a82-8a690a4cb8c1 |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | STO cladding
b7968455-5c4a-4b18-8eb2-ef36dce734d7 |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Cladding sealant
d7d53410-16a1-43af-a691-978d0ba33e50 |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Pergolas
07e4882f-9708-49c0-8ce9-1d343fc22458 |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Balconies
eca1027b-1c1b-4062-80dd-e43c75c7cf24 |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Water test
6013263d-9a97-4874-8ea4-56a6053cc4cc |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Down pipes
547f64c8-eccd-497e-866a-57289deac9e0 |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Balustrades
48f266a3-748d-42f2-8fb4-a7bbc162757f |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | South Elevation | Passive fire
305e8c2d-6773-423a-bbc4-4caa8094b484 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation
d562707f-160b-4485-9522-897ad2603847 |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Exterior frame
792672b8-16c0-4808-817b-52f36d5a9e85 |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Concrete block/concrete panels
2fa0381d-d3a0-4fc6-ae86-148fb5349b5c |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | RAB Board
55173630-6f0b-4f89-90b7-1ba4ff18cd5e |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Tapes and vaproshield
a309dc30-d084-439b-af7e-8b7fa31f89bd |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Windows, sliders and sealants
bb8f0126-092e-47df-995a-b0a2d00d604a |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Flashing at windows and doors
a7c2deee-0ac9-4379-9db2-3d7ca77f1f64 |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Envelope penetrations
abeaef4b-c5ad-4eac-bc73-7c469809f503 |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Lintels
10682154-998a-426f-b79a-cf0a5677b357 |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Brick works
4a7a3e5c-f877-4f8e-b5d9-f64c5aea3b94 |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | STO cladding
07986b1a-f639-4f8e-810a-ec0805a9fba3 |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Cladding sealant
5e215b13-b242-477d-bd98-516fdd3cfe36 |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Pergolas
98368131-8012-4c62-8921-119a64092697 |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Balconies
d9c22b8f-4d13-4cf4-a92f-be0a4e43d77f |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Water test
12093a45-a4d2-41fa-a1e5-fab18566579e |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Down pipes
c4ffcaf9-4d2b-40c8-a361-90dfbabb44b0 |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Balustrades
79395f99-6f25-448f-b5c1-b57eb0d8f7e2 |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | West Elevation | Passive fire
8392b4d0-8a9b-51ac-8b3b-ce056555cc1f |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 1 | Inspection - Rainsheild
6fb8ed2a-686c-4329-8a57-5d9cf8b9d295 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 2
01566fe4-cfc8-4e70-9079-55295a1b2510 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation
d3bff96d-bc65-49bb-81d1-5363fad5ed82 |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Exterior frame
3510ed44-78c8-4767-9660-fcaf84639665 |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Concrete block/concrete panels
c42a75d3-f94e-491a-aa37-3450f8562c52 |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | RAB Board
1c2fa147-8625-4a43-903a-9325298cb94e |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Tapes and vaproshield
3045d390-e96b-4ebb-bed3-c948ecf54ee0 |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Windows, sliders and sealants
e7d9bedd-c065-4415-b93f-636bf5329266 |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Flashing at windows and doors
f9d9a2eb-2dcb-43db-9b77-689d32757378 |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Envelope penetrations
378c53c5-de50-45d2-b83f-1224ade7925d |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Lintels
7e35258f-b3b2-4c96-a0d5-672dbf350039 |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Brick works
aad1dc64-6744-4150-9764-7ecc809c0b45 |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | STO cladding
68f530a8-e261-4466-a6e3-81c06f863fad |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Cladding sealant
01fd5d7d-012b-4f36-89cc-626ea9e7f8c0 |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Pergolas
422cf03c-5399-4204-92e1-191fc0985dd0 |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Balconies
993e4f5b-a4ab-4244-8aeb-8642002ad782 |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Water test
182ba1c2-86f5-4a8a-b415-666201dc6884 |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Down pipes
f36582fb-aa98-4715-bdf7-941f8b147b94 |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Balustrades
bf133d3e-3f0f-4106-be1a-e8e5c305ba30 |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | North Elevation | Passive fire
d35dd71e-00bf-4df2-aa3b-704fa2661a0d |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation
4d1292e3-6c0e-42ac-ac2d-2a8775d598b2 |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Exterior frame
d69279d3-ab7c-440e-a010-125ac2ff0c44 |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Concrete block/concrete panels
425ca9ae-b476-4db7-a696-c6daab140416 |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | RAB Board
9be870b4-755a-4fe2-b54d-f706511fb2f7 |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Tapes and vaproshield
2e9c813f-5ad3-44a3-8422-7860d7fcc3f1 |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Windows, sliders and sealants
45a09775-19f8-4a5e-852c-b9811b62b323 |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Flashing at windows and doors
66971ae4-9b8c-4ddb-aee6-36608271317a |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Envelope penetrations
7fb3fe2c-ab36-42e8-a9c3-df1d98fa661b |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Lintels
ce837de9-2be4-4295-b8b3-4e29084ec167 |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Brick works
fafcedea-557d-4813-8261-b24dccfc0f63 |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | STO cladding
313e0ba3-fcdb-4d05-935e-4ec5a6e702c2 |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Cladding sealant
c60b3c6d-b949-4b2e-9a31-d973577209cf |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Pergolas
fffe663b-22f2-4a52-98d8-3949b5952331 |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Balconies
216011db-2349-4c74-9f83-3b90d9c83670 |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Water test
0cb4abe0-19b1-4048-9a67-9cecf6252706 |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Down pipes
4adfc1a6-6817-4d84-998e-87b344ae3d72 |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Balustrades
9f9cb304-1fb0-4993-81ce-aa05e8cb6129 |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | East Elevation | Passive fire
d2efaa3d-a4f0-472b-8f5c-4c54164f414e |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation
fac0cdc4-710c-475b-874d-a2007c4385ae |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Exterior frame
d2c709af-8585-4256-9918-55abc04cb1ed |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Concrete block/concrete panels
4011d29b-eb15-4aed-a511-eb9a9bd75efe |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | RAB Board
3b80c5b0-29a2-4493-946f-bca4b8b55cc5 |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Tapes and vaproshield
40cbbbfc-55b8-48e5-b885-9b12dd3fdab9 |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Windows, sliders and sealants
5af4fedb-1a0e-4f89-9d12-a520559bc34c |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Flashing at windows and doors
cb357e24-0a67-4b95-9617-e13713e08775 |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Envelope penetrations
8c90d7a1-a87a-4fa5-83e4-d4d5507b7775 |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Lintels
8178641a-f39a-4ca1-acf1-bf0bc517b196 |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Brick works
c84c8a2a-24dc-40ca-891b-bafe6f24a72a |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | STO cladding
af9ec533-fd2e-4d69-86d0-b22ec7d77305 |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Cladding sealant
6f4dce51-9191-4062-aabc-b81bfaeb1c57 |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Pergolas
f563334f-8974-4c39-bed8-82364f1e30d9 |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Balconies
769ae943-5958-4e5e-8328-3fab9ef308f9 |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Water test
fcb4c0ee-aef3-4e19-9766-3a1ebf2ba1de |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Down pipes
e7342e08-3a47-41cb-9aac-a9af089356cc |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Balustrades
0e92d902-5842-4135-a2f0-5d8c94eb9ffb |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | South Elevation | Passive fire
55d7348c-65fa-4a8b-a874-d9c44ca971ed |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation
d9b623ad-9475-41fe-9996-d78961e8dfcf |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Exterior frame
07af0d16-0338-4895-8581-b76412582af2 |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Concrete block/concrete panels
5596fc4c-4781-4fdf-b944-1b88513cb5c3 |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | RAB Board
25f2a4fb-53de-4d04-9a34-e39817c80870 |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Tapes and vaproshield
c5c03919-63af-429e-ac05-18d7c6947da3 |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Windows, sliders and sealants
52e2b5f8-49eb-4554-b14f-199ba7b4f754 |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Flashing at windows and doors
59f6f78b-d3dd-4eef-b37c-6bf1d334f99d |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Envelope penetrations
2583ea1b-0e0b-4db6-9deb-3765c6cafba1 |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Lintels
95352264-3f6f-469a-bcb1-3123fe82e3a7 |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Brick works
f7d8fc64-d720-480e-b076-a72b799105f7 |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | STO cladding
b113cd4e-819a-4d33-a75d-cb5088ab48b0 |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Cladding sealant
186edb2f-43c6-409e-a13a-953ce50d807d |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Pergolas
fd5e3f91-f06c-4622-a008-68e9b9c9575e |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Balconies
12b36571-2bbe-44e1-9f4f-e17094a6d71b |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Water test
77b4624e-ab63-4b5a-b71f-845e043e1d44 |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Down pipes
2173b9e3-23e5-4805-b167-e8deb7f5d317 |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Balustrades
c61eb9c0-4473-400e-b778-2a33d6901962 |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 2 | West Elevation | Passive fire
5d9757ec-47d1-4055-9007-c6f0dfcb6a82 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 3
6bee7507-4d0a-444c-967f-26eefecf3325 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation
41a377ac-e85f-4853-8bd8-7dc2662d7098 |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Exterior frame
54135b95-a66c-4838-9e96-aa381d2e8a28 |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Concrete block/concrete panels
265253ed-14b4-4e90-85da-55e7dde12bbf |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | RAB Board
bb711b43-48b7-4602-9b72-8ec983883ded |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Tapes and vaproshield
e29386ba-455f-4da7-989a-beb2191106ff |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Windows, sliders and sealants
b5af155f-4938-48b7-8f13-76af859943d4 |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Flashing at windows and doors
ca9f2bf7-7ebc-43f8-9f57-9ba1c619a5e2 |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Envelope penetrations
bc4535d5-8e98-4855-a9cc-23385592efc7 |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Lintels
fec66e4f-f7b6-4175-a22e-97658dff7d1f |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Brick works
e64ec9c2-e41a-4058-ad22-2928759930ef |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | STO cladding
3f10f59b-bc34-4e1b-9b8f-28bb0d191f0a |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Cladding sealant
c2e5c41a-0ef1-4a7a-a50f-16076a050000 |  | checklist-flat | pass | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Pergolas
782e5802-93d8-4c8e-9a89-f3c9ef988ad4 |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Balconies
ce1871ed-88c9-406a-b1d9-9b9d20b0fe34 |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Water test
b0be499a-f2e2-405c-aa05-521def6eb126 |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Down pipes
246411c9-e56b-4672-9201-7ab26bab5667 |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Balustrades
9aa38c46-1e71-48df-b08a-002061696d53 |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | North Elevation | Passive fire
f7cc4e24-64c3-4381-bd74-f0a0fe4b2853 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation
bd3bb186-6148-46bf-8d9d-d264fbc29af5 |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Exterior frame
163aaeb2-397a-454b-8f83-1ebf940fc78e |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Concrete block/concrete panels
5710e70a-2d4f-47df-b75d-7262b922d50d |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | RAB Board
c863f514-3e8b-494a-b045-aeb4379e485e |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Tapes and vaproshield
31341ecc-5ae5-4f63-8553-183f31fd0e00 |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Windows, sliders and sealants
ac5519ad-2f3b-49c3-ba39-66b89138a179 |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Flashing at windows and doors
a577ffef-1573-4f65-b8f5-707b52ea8a1a |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Envelope penetrations
be3a52ee-4f13-4c89-b3c8-c5d6efb94e02 |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Lintels
87a52394-bce7-448a-af1d-5f284594fb9e |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Brick works
47a82324-e455-4fdb-a731-97fc7ec5b5f9 |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | STO cladding
90d723ad-250c-4652-b229-48a61f5df7db |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Cladding sealant
d67aa301-c5df-4252-ac74-ab3f9744d5de |  | checklist-flat | pass | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Pergolas
6bdbf620-3d66-420d-a8a7-3ea7cec96864 |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Balconies
83059deb-265c-4e85-9ca1-f7b04d072ef4 |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Water test
0b641ace-6d1b-4e5e-b8c1-66d2dd65541b |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Down pipes
14f8d4cb-42ca-4540-807e-12c00ce2d2db |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Balustrades
58122b73-5172-4fa3-8681-0aa9456293ba |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | East Elevation | Passive fire
0ff82c14-729a-4992-90eb-df59d40e7983 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation
f7801a89-ea0c-4c4b-8cdd-4ac0a6e60c0e |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Exterior frame
57fd562e-e918-4603-b98c-3cacd22fe080 |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Concrete block/concrete panels
506570a1-10b7-4f18-a323-7ed4e6bcd35b |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | RAB Board
6815d2df-c6ef-4c7c-a57a-e234219d9ca5 |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Tapes and vaproshield
73adeb6b-6487-48f4-8b77-b5190a093237 |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Windows, sliders and sealants
7767cad0-0726-4360-99eb-73182088b291 |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Flashing at windows and doors
647b56ee-e980-4e84-8fe0-427702f1d52e |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Envelope penetrations
317cc9ac-7c75-4020-bc78-7d60fa3bf340 |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Lintels
809e4771-c6f7-48a0-9a83-6733a024095c |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Brick works
afa18a4a-8f85-45d2-9fcc-2990fd053e5b |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | STO cladding
e396ccd6-b712-4c2c-a893-b4dd44899c88 |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Cladding sealant
f6879a32-8ad7-402d-b489-fb6af9688403 |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Pergolas
c81f12c9-eca6-4c3b-b3cd-35bca4011278 |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Balconies
86fe7c71-59c0-402d-b906-656b865dd7de |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Water test
3d3bce96-40c6-44c1-9550-0813d4ad7ac0 |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Down pipes
27e82a2c-7329-4586-8d2c-762555289e47 |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Balustrades
129d76b1-3824-4421-b714-e22eba33974d |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | South Elevation | Passive fire
185a2fe7-0b1d-4a92-97aa-9b1714c0f0ab |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation
c236dd02-b4ed-4dfa-bb7f-f2b89046d3e9 |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Exterior frame
fbfa747f-7c85-4be1-ae42-6d05aee5c056 |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Concrete block/concrete panels
2fa5ac44-69c2-4000-b325-fa3ebc7119c6 |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | RAB Board
3ce22432-4ab1-4432-b47d-7af7bd5dc80e |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Tapes and vaproshield
2ef37194-2afa-4baf-83ef-b973a5b0b4e3 |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Windows, sliders and sealants
6a8556f6-6e21-4852-8183-e1e19f91effe |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Flashing at windows and doors
e5f8f0a4-1496-47a8-8780-bb14cc008821 |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Envelope penetrations
f4a1dd55-5b12-4514-bdad-7781c84d9e70 |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Lintels
f7d1a0ed-37ab-4319-87fc-523e33073195 |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Brick works
9b381c0f-5f4f-4920-bece-6f927f85f82d |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | STO cladding
3ebf4257-3d5b-4e88-a855-07e9b0dfa446 |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Cladding sealant
625276aa-403f-4d86-96b4-f3dd7e470ada |  | checklist-flat | pass | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Pergolas
0899f91c-c0c7-4701-9253-fe8978a10d5b |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Balconies
af482d7f-8ade-464f-8565-f7f629e82465 |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Water test
c652acde-ab0b-4dd3-ac31-ef66688d0f92 |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Down pipes
ca3d835b-100d-4b39-8261-62e381ef9875 |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Balustrades
a5e28124-21f5-45ac-b62d-044eee1ec6ff |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 3 | West Elevation | Passive fire
5a2801e3-96b9-4164-8ce0-e1d0297da46e |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 4
0930dc40-0350-497d-b542-cb514a1e4dc8 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation
d3151096-3ed1-42db-9ba1-f4ce2537b220 |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Exterior frame
07a67d21-a233-4fc3-943e-b60e3a4e9147 |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Concrete block/concrete panels
03db2c03-5017-4c5f-975b-147744934c72 |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | RAB Board
7384afa5-cca8-4c99-bcb8-95368075acbd |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Tapes and vaproshield
58a2a31a-2077-44d1-a558-3d3329c881cb |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Windows, sliders and sealants
5cf98c08-c0ca-4bf6-9301-991b12ee73c5 |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Flashing at windows and doors
28021354-3214-4ddb-991a-f1db2be45b64 |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Envelope penetrations
44778268-cc22-4a32-bfc2-f807109afd5d |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Lintels
2fdb46d3-17c0-4fbe-ac72-241ef88732a2 |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Brick works
4d9237f5-2e07-4c7d-ba0f-424239095f40 |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | STO cladding
bcbb62e2-49b5-4c30-ae80-573b6e3f1acc |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Cladding sealant
b1baba73-a29c-45a2-8534-654f7b528f5e |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Pergolas
dc3bb2ab-32da-4a82-85be-2d9d7a1214d8 |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Balconies
62473f17-975f-4b8c-8337-3ec6c0f77813 |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Water test
acc97237-e475-4721-b3ab-67fb37eec7d6 |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Down pipes
9feeeed1-9842-41f2-873a-adf5a0d54738 |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Balustrades
e18c4dc3-6aa9-41ef-ba65-ddd02bae690f |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | North Elevation | Passive fire
820949e3-e1ae-4ebd-8903-cc41856f7d63 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation
89c5bf29-9075-4330-8ec9-2bf9a1d8042d |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Exterior frame
8c9058c8-9038-4a63-97a4-3771c8df9ec3 |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Concrete block/concrete panels
106018d5-e06c-45c6-9ac5-5664b1fbb829 |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | RAB Board
b37aeb92-46e5-417d-b7cc-3f96ef8412b6 |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Tapes and vaproshield
bb3bc056-fdd5-4ac3-8942-538400b42cf0 |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Windows, sliders and sealants
b50171bb-fde8-4969-855a-e9f574f6bfeb |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Flashing at windows and doors
b6c52948-6bbb-4282-96ec-e645f0090e16 |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Envelope penetrations
c9e29ddd-1374-429d-99e5-91daaec84854 |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Lintels
07657521-b5f2-4053-95a1-ce2892ea4ed6 |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Brick works
8ee16905-5f9d-43f0-b160-18e132b7749c |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | STO cladding
95194312-7df1-4b05-b0fb-2e463d745d77 |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Cladding sealant
ccfd1c05-9b7b-4e92-a083-a215ac17c949 |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Pergolas
16d398c7-af3c-4f44-b78a-2a9e4172340e |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Balconies
d8a395de-db4b-4cf4-8712-7683e50b51b6 |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Water test
5a40c341-194f-4194-a256-f06e5795a67c |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Down pipes
795367ce-a395-4b3d-83d2-5534d4e6ffbe |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Balustrades
91fac238-ad2b-4ff7-b9bc-d33e69d208b2 |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | East Elevation | Passive fire
e7eab95b-63b3-428c-93c4-04dd8fcf9e39 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation
84a863ab-dc01-4f99-bc78-dea6a89c9bb7 |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Exterior frame
52c6f6c0-ca98-4a49-8ad3-637e7d2837ac |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Concrete block/concrete panels
7f43da18-0123-4327-958c-e984b4b0636c |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | RAB Board
f5157995-c727-4777-bbf8-b36341d2f67f |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Tapes and vaproshield
81831132-b497-4115-96cb-c0149d8cd2e3 |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Windows, sliders and sealants
a5a261ea-f90e-403a-80f3-642f9a797c45 |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Flashing at windows and doors
163e5212-2faa-4787-8ad1-ef0c867563a9 |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Envelope penetrations
22a4bbe8-31ef-4e27-8db9-2df4d1be9105 |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Lintels
b1473e98-a297-4f33-9662-3af0188ef38b |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Brick works
d0c63f14-4ef4-4d86-84a1-0666776993a3 |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | STO cladding
278d8340-0b8e-4a5e-8507-6da6ecdc8568 |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Cladding sealant
a0e2d7f2-467e-43ee-8b95-6e815defe1f7 |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Pergolas
77de020a-eb87-440a-bf69-b6facb4cd886 |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Balconies
8c81978d-61c1-4b99-b76f-3a9be44570e4 |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Water test
d4055135-ef01-4401-9601-9fd7f25197ff |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Down pipes
f7918b36-8af2-4b82-a800-952ce66528d9 |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Balustrades
aa8582de-3679-4706-ab77-eb136845d779 |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | South Elevation | Passive fire
1683702a-1d05-4c8c-bbaa-b764f8ac1dab |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation
b0a7c919-f667-4edf-b53a-f1ca7e0fa9c7 |  | checklist-flat | pass | 634820c44a1c16cc31dc9602f1dd724803a21f8cc2873c1e9777bf90c475c9c9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Exterior frame
666d8cfe-8413-44bc-bf83-0d0d1e6978cc |  | checklist-flat | pass | 57747e77a3897dd8e2a7ee4fc266d9d4630486f3e4aa878902f5ffea2ebed50e | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Concrete block/concrete panels
de1b01d2-a76c-4d75-a181-886c64badbb2 |  | checklist-flat | pass | f5ccb653471189071e85a6c3c384c89eabe7e5b2b0ebe1c5e480f48c98a7c5a7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | RAB Board
6ed457e1-84d5-4f66-8ffc-406a2fb2f09b |  | checklist-flat | pass | cfdf13cfc1ddb3f6edec07a64e408bca8ac2dedf71af34e57639c8e607547beb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Tapes and vaproshield
472ebda4-a08b-4bdc-98c4-95c0a0ed9679 |  | checklist-flat | pass | b389bafff13c9c3157f3cf9ad97ddd658df5d687dcc7149aca4de34e7df83309 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Windows, sliders and sealants
67b8b77a-c361-498f-8708-f06c22eb8e1a |  | checklist-flat | pass | 761639663cd2e0f261f9f015d47d6900cd9e0cbe4c37ec4a29c1a2b267c9f21f | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Flashing at windows and doors
2baab4dc-4f92-4001-b17c-6f3c25c550f2 |  | checklist-flat | pass | fa29df5af2649c7569188e02e9d1382615a9f60f1d3c86f80589c653dd1c8173 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Envelope penetrations
65559396-c287-4f61-9263-ebe0ee274fd6 |  | checklist-sectioned | pass | 4bac4edfa711790cf6c4cf8d69625e31ec5a960eef215c35cd150d9b34d90b6c | checklist | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Lintels
15dcc2b3-9b16-4520-af29-e8387108253f |  | checklist-flat | pass | d472675c4beed04cf93743a18bcd694452cf9050f0bee58840456110c076d6c5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Brick works
4018d411-276c-4d6b-8c37-aee496a0521f |  | checklist-flat | pass | 60c6b7211e6fd69cd1ccd72736f470501a3e6e5fe69a210416becd5025a3fa96 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | STO cladding
2edd9900-8a04-44d8-99d8-a1878bc21c67 |  | checklist-flat | pass | 502a73d7cf6d3f0c95da3539291728345899e5e6e5f05e5a369fff5ad8740aeb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Cladding sealant
e862e419-7ff4-41bc-9be6-68ca2b0fd78d |  | checklist-flat | not-applicable | dd4b5813c29237448faa8a09ab9948b5256c6623d5bf05c3c76ac2045b2ea5b4 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Pergolas
b66184c3-4880-4ab0-89c0-a3caebce79ce |  | checklist-flat | pass | 1c5117f2cd3d585d2bf5bdedf46c177b6bd526afaaffb73156d6ee1b2ab50fa0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Balconies
089ec786-7e41-4011-90fd-ff73fefac77d |  | checklist-flat | pass | 372786621e94570165c6c77e0a3dd090526dd650da87c383e36648e80adc85d7 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Water test
85dc3cc8-0ddb-45c3-9d45-fa76deb89df8 |  | checklist-flat | pass | 087f6848ba27fe7ad20f324cb51ef9977e7f2eef5768a773d11ea708c964d1eb | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Down pipes
529045d2-f971-4b8d-be07-76c0853c4a7d |  | checklist-flat | pass | 5e2457e820e1ed8eeb960ff93cdcfc70adf18a74e1ead0fe8f348c6b44f3bfce | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Balustrades
f785064b-c615-48b8-8b7d-e13dcb795652 |  | checklist-flat | pass | afef2fa3eb1a81a1fe2b68f06918943c193cd1858d1a39622890a370f146db56 | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Level 4 | West Elevation | Passive fire
e814fe28-d075-4be8-901e-cfa67a235632 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Facade | Roof
364ac6db-10fa-4b2c-a338-229ebbff6850 |  | checklist-sectioned | pass | 37f54201d2455095fd7a29eb3976e57c723e694c5a8c889d6b076bd976c32691 | checklist | TRUE | FALSE | Building B04 | B04 Facade | Roof | North Elevation
a64c8231-a647-4bba-aaf1-9a70d24dc776 |  | checklist-sectioned | pass | 37f54201d2455095fd7a29eb3976e57c723e694c5a8c889d6b076bd976c32691 | checklist | TRUE | FALSE | Building B04 | B04 Facade | Roof | East Elevation
32d2b095-a2a3-4864-9c43-9a5f070d660f |  | checklist-sectioned | pass | 37f54201d2455095fd7a29eb3976e57c723e694c5a8c889d6b076bd976c32691 | checklist | TRUE | FALSE | Building B04 | B04 Facade | Roof | South Elevation
ea2bfea7-3d5f-4e2b-a8de-ab6f6e70573e |  | checklist-sectioned | pass | 37f54201d2455095fd7a29eb3976e57c723e694c5a8c889d6b076bd976c32691 | checklist | TRUE | FALSE | Building B04 | B04 Facade | Roof | West Elevation
dc062e6f-cd04-5048-a840-34c06fb299bb |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Inspection - Remedial on timber fixing
9a2651d7-1dab-5329-bb51-12eab089999e |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Inspection - Remedial on fire collar at sofits
ca62e6af-c222-5e73-8513-2baea02875f4 |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B04 | B04 Facade | Inspection - Remedial on Short Lintel on Brick Veneer
1871c187-59d1-4dc7-b48d-bcf03063cf09 |  | folder-normal | fail |  | step | TRUE | FALSE | Building B04 | B04 Fitout
a69090f4-1ec4-4494-b9c0-864fe486df49 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level B1
90e453a0-024f-449b-8837-bd15320406ce |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas
f4c16b3b-0106-4ae3-a3bc-e0a94d1ecaeb |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby
e72a90e3-f95a-4ff7-8e06-4087e1d58339 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Preline
f6687755-ecbe-41ac-9fbe-2fb9fbe30ded |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Preline | Timber Framing
37337415-c7fb-4691-a453-e3e2344d6e14 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Preline | Internal Strapping and Framing
e79ea7e3-685b-4a61-ae05-51408442a81a |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Preline | Suspended Celing
609b0a11-f054-4613-a3a1-8e61ee272173 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Preline | Internal Doors
de18953d-e4ec-4206-ab5c-a22d9f875651 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Preline | First Fix Services
111d33bf-f414-48a8-b633-e719ce0a1830 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Preline | External doors and windows
3a7af26b-3b18-4acd-b5f9-f12f17ffb935 |  | checklist-flat | not-applicable | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Preline | Insulation
fa7f20ef-ad18-44ed-9137-b704cc39181d |  | checklist-flat | not-applicable | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Preline | Passive fire/Approval to line
b52f824f-e4ce-4822-86ef-db88e4031c6d |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Post-line
1e6b0157-da21-45af-8c79-b9d3724ffa41 |  | checklist-flat | not-applicable | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Post-line | Lining
6d1840e3-82d4-4893-8dde-6e22e2b1e2ab |  | checklist-flat | not-applicable | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Post-line | Stopping
90b4d21b-78fc-4822-8ca6-8a4e2fe5e6ac |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Post-line | Finishing lines
00cc4ca1-583c-4dc1-8bf1-b44fd9303633 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Post-line | Flooring
d322c2ed-4fe5-4d5d-85d2-77506eeebbd4 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Post-line | Painting
454644dc-1e6e-4782-9b70-40c9399f270e |  | checklist-sectioned | pass | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Post-line | Second Fix Services
eb1c89c2-8a3c-4437-8b56-830a58f78f6e |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Post-line | Fire Door
0b992032-16c7-4860-a1b7-823408b1bb3f |  | checklist-sectioned | not-applicable | efe9dd8861170a4f6c877309dd15ef71545349ef8eb7e2755d191ae9183ec15d | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level B1 | Common Areas | Lobby | Finishing
fc9677fc-d47f-4350-b71e-0d03afa54746 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas
0234fe0f-3a5b-4f7b-884d-6c4b7bb071b3 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB
956778f8-d898-4f9e-9733-d23ba2b87b80 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Preline
af9dd04d-0e2b-4c4b-8824-6526b090053c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Preline | Timber Framing
ca71dfc1-81ac-43b4-9362-b1fedc9844fd |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Preline | Internal Strapping and Framing
32fd2c7d-1f8d-457b-a24b-e2dde678faa5 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Preline | Suspended Celing
f9987a01-324f-488f-83ce-c6da3fba106c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Preline | Internal Doors
548891f2-bcb4-4663-a89e-7ea3fdb1b95d |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Preline | First Fix Services
c80b2922-bfe2-4020-9096-764507e24aa9 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Preline | External doors and windows
f64b5289-624c-4ace-aafa-e076f5f6a156 |  | checklist-flat | not-applicable | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Preline | Insulation
fb957bd8-4737-41b3-89ad-c8d73f011875 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Preline | Passive fire/Approval to line
f97b1cf3-f467-41a6-bc86-5bab77b8c753 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Post-line
551f7661-e6ac-47ec-8caf-914ab2470034 |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Post-line | Lining
60ce09e4-73a6-4556-b372-e2d51ec3c3de |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Post-line | Stopping
f3f506a4-7d9c-4fcf-8c34-9673d54f4650 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Post-line | Finishing lines
9b134b5c-1ef5-4b3f-8be8-101307267e74 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Post-line | Flooring
122ff524-b619-4ddb-a934-5fbad9afe1e9 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Post-line | Painting
22aa6469-ca60-40f7-a05f-e48e23503a7e |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Post-line | Second Fix Services
0fa57ff5-5b7b-461b-ac8f-24069707f262 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | MSB | Post-line | Fire Door
598057f1-ef0b-4ca7-b2ad-8eb952290533 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage
ef971dac-630e-4d70-84b1-391ec8ba3548 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Preline
e84ff9fc-a1a6-4cd9-bd73-6d1d146f5765 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Preline | Timber Framing
37431703-4d70-4422-8ad2-79554a835118 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Preline | Internal Strapping and Framing
e8a686fe-869d-4324-a535-210ed7c94b1e |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Preline | Suspended Celing
a9da736a-6bb4-4d34-ac3e-ab66895339a4 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Preline | Internal Doors
1888d371-55ba-4af4-9cc4-434b598f7f8e |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Preline | First Fix Services
66cd7919-5604-4111-b61f-ce29efa0f8c4 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Preline | External doors and windows
690d54f0-477b-40ab-8308-22be7579cca4 |  | checklist-flat | not-applicable | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Preline | Insulation
4e650069-019a-4b00-a247-a5d93e47a1f6 |  | checklist-flat | not-applicable | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Preline | Passive fire/Approval to line
aa0956c6-8343-4d2b-bf7c-640c6ff57a93 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Post-line
5b2def9e-3231-4516-934f-d2174a9cc33d |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Post-line | Lining
ebfca7d0-4c95-4359-af55-17c13aa2d175 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Post-line | Stopping
b0e60d0e-b11c-4bd2-9b67-7bf277df8267 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Post-line | Finishing lines
429bf9ee-032f-4429-ac7d-ca392878e332 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Post-line | Flooring
6d54ac12-1621-479a-8324-4dc1c045be69 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Post-line | Painting
70548422-ae5c-4219-a7fe-523e0eae5e3c |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Post-line | Second Fix Services
b94dfdd0-6e4f-4e9c-9e72-5096f1fd4133 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level B1 | Service Areas | Bin Storage | Post-line | Fire Door
a2bb9a2d-14ea-4ba2-b142-966c9b780ee5 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1
849698f1-69e3-4df5-9285-cdab149e2d5f |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas
51b17d93-81b9-4be2-a86c-dbb5fbafc052 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark
8949d79a-0b1b-4e1f-966b-0083c5cf2ced |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Preline
3c5f9eb0-9282-4788-a1eb-c6bf367ee407 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Preline | Timber Framing
c382cc79-a520-4a3b-8537-c4742c2a6da8 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Preline | Internal Strapping and Framing
f3969843-efb9-4620-8cda-ede39a53de2f |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Preline | Suspended Celing
dcaa2991-ecbd-4195-a6b0-50871c2cd33d |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Preline | Internal Doors
c44b84bc-da46-488a-a87d-5110b3215916 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Preline | First Fix Services
f0301bde-0c42-4677-a151-c4e8db452ff6 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Preline | External doors and windows
661cd0c6-a18d-48c7-abc2-e2a774ab1b93 |  | checklist-flat | not-applicable | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Preline | Insulation
7024f4cd-38dc-4d94-a454-af37a5172427 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Preline | Passive fire/Approval to line
3ed715ca-fbbf-4227-8532-49fc50f57712 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Post-line
d1445ef2-91de-431a-ac97-68cd7048a5e9 |  | checklist-flat | not-applicable | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Post-line | Lining
71c8d221-d445-458d-9e04-51452f6d767c |  | checklist-flat | not-applicable | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Post-line | Stopping
dbf43224-b184-4868-8a40-5998d9e0d09a |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Post-line | Finishing lines
f9b32209-7728-464b-ba50-2a550a06abe0 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Post-line | Flooring
9f3e6dae-0518-4c57-93cb-63ab65a3ab0a |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Post-line | Painting
ecbea0fd-e047-494c-820d-1bec5f27e0c4 |  | checklist-sectioned | pass | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Post-line | Second Fix Services
09081d04-c9e8-45e7-a9ed-5721c3c28690 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Carpark | Post-line | Fire Door
334659a6-42e8-4a7d-99b1-1c4eb3c3e352 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors
b5d71c7e-eabe-4dea-8de4-e4b58b2e84e0 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Preline
77ece2c6-f4b6-4687-9ec5-836c3ef57925 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Preline | Timber Framing
d1f59bd2-ec3d-4415-a783-47f51d5cd661 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Preline | Internal Strapping and Framing
36f38ec5-191c-4329-8bb6-6cc51e403c3c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Preline | Suspended Celing
cee88c2c-543c-4de1-bb69-460677c817dd |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Preline | Internal Doors
5c89093d-3437-4385-9e14-57bf20ff16c7 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Preline | First Fix Services
ab4141f2-a9de-4cb9-8130-cf412ddcb5df |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Preline | External doors and windows
c72c547e-3fe1-4dfe-b20c-9c97f71a4441 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Preline | Insulation
f91dc141-9fa6-43e8-9d60-39817f978e03 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Preline | Passive fire/Approval to line
490619f9-a4ee-4a2d-81aa-81f1ea8c5ab2 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Post-line
8a014b66-09d3-4b63-b9f0-e19f4978a4bd |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Post-line | Lining
9ff99110-0ad6-4c01-8b22-335e264ba67e |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Post-line | Stopping
437888bb-f103-4c20-8a2c-2ad43435dd3f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Post-line | Finishing lines
4414c4fb-9c2f-4c08-a40e-71eebfc4a408 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Post-line | Flooring
6fadeec5-0899-450b-9950-04b061833e25 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Post-line | Painting
d0244603-c3b0-4797-acc0-411b6a2d43ae |  | checklist-sectioned | pass | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Post-line | Second Fix Services
de11e16f-50e0-45e7-878f-600b2b7f25a8 |  | checklist-flat | work-in-progress | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Post-line | Fire Door
11baedfc-77b5-4f61-9f0a-33e5f87ca43f |  | checklist-sectioned | work-in-progress | efe9dd8861170a4f6c877309dd15ef71545349ef8eb7e2755d191ae9183ec15d | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Corridors | Finishing
314e1d2f-6b73-4be5-871c-1eddb43ce55b |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby
f8e3fa7a-6d81-4d13-9330-4f9257514800 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Preline
30dd7348-eb5f-4174-819f-93136cf7e0e0 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Preline | Timber Framing
35649bc2-89c6-43aa-bace-d2551e921ac0 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Preline | Internal Strapping and Framing
fd9b0fac-5d8a-4770-b181-eb39e02e9ec6 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Preline | Suspended Celing
fdd7247b-02bb-418e-9207-c82794040e40 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Preline | Internal Doors
5d46c5b9-5a0e-4797-9063-2bbae7574496 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Preline | First Fix Services
125e9e37-7068-43b1-acac-07e0dc3c9452 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Preline | External doors and windows
936b3957-3fa6-42df-8b48-8edeb27f532a |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Preline | Insulation
b15e5eb4-6b9f-4ed7-bad6-154a9dc2edc8 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Preline | Passive fire/Approval to line
4a3ae953-2924-4146-a4ca-972e4f5ec0a1 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Post-line
ad208309-5b3a-4365-bdc1-d7899cf7e8c5 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Post-line | Lining
3fb779e2-56bd-4208-8c83-006a2f9b1a32 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Post-line | Stopping
69e6a0e2-9f7a-4f98-8f88-26ed95b2970c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Post-line | Finishing lines
eb625efd-758b-466b-895f-ec3cc804e3db |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Post-line | Flooring
a44363bb-50c2-4f0a-a250-0cf046b66575 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Post-line | Painting
7a5e717e-9639-4de2-b216-953591a0521c |  | checklist-sectioned | pass | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Post-line | Second Fix Services
e4da8660-c302-4fc8-bc54-b6a3a532d81d |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Post-line | Fire Door
7251876a-7e1e-40dc-9fac-6dd294943d3c |  | checklist-sectioned | pass | efe9dd8861170a4f6c877309dd15ef71545349ef8eb7e2755d191ae9183ec15d | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Lobby | Finishing
c1df721a-f92b-4d90-b29b-23bdb568eeee |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell
e14b0326-c559-4a15-ba11-acff0593d253 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Preline
319561f4-53be-4b5b-9f3f-ee1ff7415844 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Preline | Timber Framing
b1657f56-daf6-4202-abd5-a6cde3fd040c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Preline | Internal Strapping and Framing
aa9e2e3f-abc3-419b-814b-353e47e22ccb |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Preline | Suspended Celing
506d7fe6-764f-4b7d-9a71-45750767d502 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Preline | Internal Doors
67369d01-a359-43c7-8cd6-296473b9ecbf |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Preline | First Fix Services
00f289c7-6a28-4fbd-93f9-2065863bc7ed |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Preline | External doors and windows
e637bcad-5352-485e-877a-69ac3e7822db |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Preline | Insulation
eb17b1ce-04c3-4f11-bb05-84bac58cd83b |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Preline | Passive fire/Approval to line
da38c04b-8810-448a-95dc-131e3032e911 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Post-line
de08f9f0-39ce-4dcc-a400-781045567d95 |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Post-line | Lining
528e162b-6fde-4a50-8641-e8a0686e3e25 |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Post-line | Stopping
dc64ccfa-1c29-4e25-a36a-90e0a79f6b09 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Post-line | Finishing lines
6928963b-17cf-4883-a129-57bf9575003d |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Post-line | Flooring
2a8b40ed-e117-4d71-8938-20a753025ccd |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Post-line | Painting
354a7733-2d82-4eda-8772-a1a0c259264e |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Post-line | Second Fix Services
045a7705-82bc-4407-9051-1ccde4bf0425 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Post-line | Fire Door
9d15d86f-97cb-46ac-acc0-407a1d5fb420 |  | checklist-sectioned | not-started | efe9dd8861170a4f6c877309dd15ef71545349ef8eb7e2755d191ae9183ec15d | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Common Areas | Stairwell | Finishing
8695fbf3-a8ce-40d6-906e-d45f492de190 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas
0de306d2-df81-4324-a633-48d6f51339e9 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical
aaa94d1f-ec0a-42b3-872a-1fa3843819ee |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Preline
571c8568-dc55-4745-b3bf-437134187eea |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Preline | Timber Framing
57b17e84-e847-4905-8b0e-571b2ce0246f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Preline | Internal Strapping and Framing
7e375189-eb33-488c-a867-60c6bb2625a7 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Preline | Suspended Celing
96256f2b-62d9-4df8-a456-4d8223169a79 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Preline | Internal Doors
79f6faf8-6885-484b-b84d-9df7c1c26ace |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Preline | First Fix Services
392c0cb3-1a5e-4357-a2a5-394f1ccf64dc |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Preline | External doors and windows
9243576c-afa6-4da2-8621-2b59a238e10b |  | checklist-flat | work-in-progress | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Preline | Insulation
1b1a9250-0875-4912-90a0-9bc479614305 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Preline | Passive fire/Approval to line
75062572-e1e6-4347-9263-c212d6054aca |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Post-line
1da0bfe0-3c36-419a-ad70-a55e15bcb94b |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Post-line | Lining
d9a2069f-8aba-421e-bf45-c4a35186d320 |  | checklist-flat | work-in-progress | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Post-line | Stopping
392b820f-2f65-47b8-9701-97fe53bde6b0 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Post-line | Finishing lines
b3d0a296-4d89-4e28-ae97-ed461a812b85 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Post-line | Flooring
581ce6c0-eb36-4945-91e4-27b4d8dd644d |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Post-line | Painting
4903d208-1dc2-4b92-b0ba-f4594a0bf771 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Post-line | Second Fix Services
9b582e1c-20a3-4b0f-9549-1a005ac65a9e |  | checklist-flat | work-in-progress | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Electrical | Post-line | Fire Door
7e64a4fd-37a4-4d29-820f-cd01aef5b9ed |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room
5b60de72-2137-4907-921b-a38ed1358a06 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Preline
a70269ea-c8ed-48b2-b3a0-330b2d043fc8 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Preline | Timber Framing
1979ea22-cad0-40d7-87ad-9be73f1e74ef |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Preline | Internal Strapping and Framing
5fbadae3-3c3d-4bef-9351-dd4104c204d6 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Preline | Suspended Celing
cedf161e-0be0-486c-8e75-d373b482e14a |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Preline | Internal Doors
f7115d7e-d4d1-491a-8709-603b037a21f3 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Preline | First Fix Services
ab7ab810-b921-4e57-b444-8c7fc487bd59 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Preline | External doors and windows
a3c826f4-aa26-4bca-8f82-7d863db16117 |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Preline | Insulation
184fbd22-6d43-4641-8d5e-6b51c05fb6f7 |  | checklist-flat | work-in-progress | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Preline | Passive fire/Approval to line
f56ebdb8-4acb-4d53-bdfd-9b783126dd68 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Post-line
74ba1574-8ba4-4423-b17d-4a1c752ea4b4 |  | checklist-flat | work-in-progress | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Post-line | Lining
b51d1dca-c563-4740-9dc6-b909438f13a1 |  | checklist-flat | work-in-progress | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Post-line | Stopping
6f436424-596e-4b93-9855-8e718aa2b4ba |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Post-line | Finishing lines
8596a623-de99-46d5-bee1-f8add27618fe |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Post-line | Flooring
754d2a10-74e7-4551-9368-a9251973dffe |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Post-line | Painting
64296c96-e3b2-42a6-a21d-a399810c16aa |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Post-line | Second Fix Services
4752d556-eb0f-4fe1-80fc-ab666b6fbe9a |  | checklist-flat | work-in-progress | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Data Room | Post-line | Fire Door
5c8e6f51-7ff4-43f8-b85d-a447e072b705 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room
cbca5ee6-36be-4493-a656-6ea87af68d33 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Preline
2e96fe4a-cee5-450f-bcaa-a4d08a1e4372 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Preline | Timber Framing
851185d3-04ad-4165-b1fc-8937c4ee9a5e |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Preline | Internal Strapping and Framing
4c49f87c-d648-4046-a3dc-4edb6684cfbc |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Preline | Suspended Celing
3708dcaa-83ec-484e-8a11-260ea8d5c3cb |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Preline | Internal Doors
83eb0d43-27b1-4abd-82b8-dc64de46a5bc |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Preline | First Fix Services
10022c1f-3f43-4a8d-8175-a04495a8b498 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Preline | External doors and windows
fd430d17-79ef-42f2-b593-7dc71d33fa0f |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Preline | Insulation
d2d4744f-6fe2-48d0-bad2-c8111f88e16e |  | checklist-flat | work-in-progress | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Preline | Passive fire/Approval to line
8ccd5000-659f-4500-b2b0-7b45ebe5a522 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Post-line
3e70b861-e084-41f2-93fe-ff6e788e6cbb |  | checklist-flat | work-in-progress | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Post-line | Lining
0467c5df-8047-4de4-b246-c48217ea0a2f |  | checklist-flat | work-in-progress | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Post-line | Stopping
6056aee7-2417-49c7-8a71-ae84877e4830 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Post-line | Finishing lines
45067f12-b1db-4ab1-8bcd-8a63af1d089b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Post-line | Flooring
311d5d4f-7cc0-4387-84ba-17099680b81b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Post-line | Painting
5d2ac876-535b-4b29-a96a-3267125517ff |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Post-line | Second Fix Services
535368fe-bead-4308-a72a-f7222c59f49d |  | checklist-flat | work-in-progress | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Mechanical Room | Post-line | Fire Door
86bc8069-c586-4e3f-8824-4171ce923a5c |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store
c801cbd3-9f11-4b7b-91d9-641afb419dc7 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Preline
00b6edb9-6ac6-4119-9099-442040d4d6dc |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Preline | Timber Framing
bc2b636f-157a-4fc9-805b-6dd503b93b95 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Preline | Internal Strapping and Framing
1c0c5b1a-f5ff-4655-9a50-9af150c84eb1 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Preline | Suspended Celing
78df93d7-ae71-4ecb-90cc-511bbd7c6675 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Preline | Internal Doors
02dd6b1c-a203-4dd7-8307-7620b2aed842 |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Preline | First Fix Services
00a842d1-e0b6-45e6-a691-365bc572167f |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Preline | External doors and windows
6f3a98f4-0261-4c8a-842d-4ac7f0a9dba8 |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Preline | Insulation
6bc64c67-64f6-427e-8594-7aa28f7baa7f |  | checklist-flat | work-in-progress | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Preline | Passive fire/Approval to line
cb5b46d4-19a7-4e16-ae9c-bb41f34c1a98 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Post-line
fffd37a6-500f-49af-bcce-09d9a2aa4a88 |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Post-line | Lining
375d4142-6927-4841-b20a-5edc06266894 |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Post-line | Stopping
682e72d1-c8ec-4a72-adc0-997a2f8a78e1 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Post-line | Finishing lines
f7135ce4-4425-41ec-8cc8-4ca0592503c7 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Post-line | Flooring
849d3550-ac25-43dd-b277-b5236d96a40b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Post-line | Painting
d7e9c4fc-c614-4060-9650-524fd46ec1b4 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Post-line | Second Fix Services
1f46edfd-2be8-427a-b8f5-d11b0ba14b29 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Store | Post-line | Fire Door
0ad7c4c7-0ff1-4883-8cbc-c236c3850c21 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage
bf4de7d7-d4f0-4faf-94ee-2b66b8c69e74 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Preline
4201b596-9f14-4784-8108-fd0c64257d38 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Preline | Timber Framing
d9bc1ba4-6c33-41d6-b350-c93429fff3c1 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Preline | Internal Strapping and Framing
4c3b93e8-2bcb-41e4-87e3-89042171b8d0 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Preline | Suspended Celing
2dee7421-d91d-40da-b5dc-aeba523afcb6 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Preline | Internal Doors
2d2e3653-02c5-4e27-9851-c2bf92a20ffa |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Preline | First Fix Services
8930359b-9258-45b1-9d04-7f9c53c383bb |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Preline | External doors and windows
32c1e89b-7aa7-454e-a6ff-74079fef4c67 |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Preline | Insulation
fb3fe96c-e6c2-4906-8b33-d351c4290974 |  | checklist-flat | work-in-progress | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Preline | Passive fire/Approval to line
ec4ddd67-3f4d-409c-acfb-af2b1d9235d9 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Post-line
927a6ad5-fe3d-44d9-840c-b601fb55055e |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Post-line | Lining
84c8af37-fc92-41d1-99a6-4be4ffd300f5 |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Post-line | Stopping
16d9f1f1-147e-4fde-b44a-02c8d92e17b4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Post-line | Finishing lines
cf988228-2f61-4310-8457-dc88b472b85d |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Post-line | Flooring
304532f3-feab-4ab6-9452-0cc1101fcb4a |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Post-line | Painting
a81d5fe5-5931-43e9-b167-41661ead0cb0 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Post-line | Second Fix Services
d5a6cc02-48e9-4426-aed0-9cfe89841590 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Service Areas | Bin Storage | Post-line | Fire Door
643863f9-4d27-4769-a4df-5b9ac66c31b4 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas
b8646a12-d6f9-4bfb-831d-c2ad9a0c9aee |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88
87074b23-5f20-4b9f-856b-0fa5b272b8de |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Preline
19c816da-66d1-4170-95f8-094e01ecb49a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Preline | Timber Framing
1f0abfeb-cf6f-45b0-993a-7c3d849d5638 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Preline | Internal Strapping and Framing
c4a549c7-2233-4d2a-a450-94e586c61e7c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Preline | Suspended Celing
679b25d7-22ad-4d7a-b04d-b1d7dde1f5b7 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Preline | Internal Doors
f5fd2daa-5d69-4dde-8422-03119f8f1a16 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Preline | First Fix Services
616a9f24-97ae-42ed-aedb-359688acb104 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Preline | External doors and windows
0bf5f006-272b-4e5f-bd03-40447fe3ff4e |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Preline | Insulation
0e179d1a-59e4-485a-b266-d8f725ffff94 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Preline | Passive fire/Approval to line
f0f2794f-b3b6-4021-b6b7-cedef37c2bf8 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Post-line
e85a0e12-d56e-40ac-bd22-7a2a36f20dbe |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Post-line | Lining
5aa2cd78-21a7-485b-8470-189d440fabf2 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Post-line | Stopping
affdca8f-4d1d-4b60-a631-4551f2b8a376 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Post-line | Finishing lines
7c507ca9-5111-46dd-bd4e-74d32d26cde4 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Post-line | Flooring
fc59e961-08ed-4f03-9a1c-289cfd5b2a1a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Post-line | Painting
79eb0504-0546-4a69-8b0f-6979755c3108 |  | checklist-sectioned | pass | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Post-line | Second Fix Services
48d4c3c5-04ad-4fbc-b307-bf0b390f6588 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Post-line | Fire Door
101713f8-6e66-41ba-842c-b73f235b6ae8 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Finishing
fe5f7900-76e3-4852-bf22-e5c922ffb481 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Finishing | Flooring
8f377900-ed07-406a-8718-6e118281a4a7 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Finishing | Exterior
cae83147-8486-4295-ba11-5a34fdf43dd0 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Finishing | Lounge/Dining Area
ea5f990b-0b9d-4b52-b94c-edf761030dad |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Finishing | Kitchen
a1599efd-a812-4684-9ffa-8e21c275e8a5 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Finishing | Bedroom
9d194086-599b-400b-9f14-efb75695321c |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Finishing | Bathroom
5474eb1e-4cc6-4ce4-821c-a982e0916fb5 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Finishing | Ensuite
0d4df9d7-1060-4520-b2d5-0621f18186ce |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Finishing | Laundry
acb70673-1cef-4080-9747-59a58f0a9c0e |  | checklist-flat | not-applicable | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Finishing | Hallway
1a977e4c-dd2f-4160-9dce-ac831a1acde1 |  | checklist-flat | not-applicable | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Finishing | Toilet / WC
b1992078-bb60-4751-815e-acd51032d3b9 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Finishing | Client extras
faeb2c6e-9dd7-4e75-95fe-e65b47fa9d0c |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A88 | Finishing | Final check before locking the door
3afd4071-0303-4964-8729-b8109fc87567 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89
80b7f740-da6c-4115-8eed-f25f55bf0986 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Preline
522e40e0-9b6a-4b8e-b53d-3c313201bbe1 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Preline | Timber Framing
801ee632-663a-47d2-a5c5-38824c828685 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Preline | Internal Strapping and Framing
4be290c2-c9fd-464c-98c5-d4669b570f7e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Preline | Suspended Celing
59f2b323-1c9f-44ad-843a-7bc9016a0506 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Preline | Internal Doors
bee7c5d3-fcdc-4872-b84f-2d884666288e |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Preline | First Fix Services
465cc4c4-ab54-4a73-8b3b-716eb2de9377 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Preline | External doors and windows
6688eeb7-9a38-44df-a52c-397eddaa64b4 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Preline | Insulation
3bea6b29-dadf-44a4-a8bc-aed3127aa782 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Preline | Passive fire/Approval to line
047a08b5-e222-48fe-b186-3e01fbba51c7 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Post-line
073f3ce8-25a6-499c-9804-1688cf8345a1 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Post-line | Lining
bf01cf05-073c-482a-8953-522071127500 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Post-line | Stopping
f537b3ce-c7a1-4532-a093-cb200aae3547 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Post-line | Finishing lines
c7bca60e-1c2e-4006-b7ef-741f7cb2b9a1 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Post-line | Flooring
7a7782eb-41d9-44d6-b401-077e729da872 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Post-line | Painting
c6e74401-fea1-47b6-bce7-007c64e26800 |  | checklist-sectioned | pass | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Post-line | Second Fix Services
f21f4874-9c4a-4b1f-a193-7c41259393b0 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Post-line | Fire Door
cdd926f2-f063-4258-9628-b40c31260fd1 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Finishing
b12580f7-1f00-4377-bff4-987a54193eda |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Finishing | Flooring
1e3b40ff-93ad-47ba-94ae-d119f2297947 |  | checklist-flat | not-applicable | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Finishing | Exterior
e0049f46-34b5-4640-9971-2bc093c92cf8 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Finishing | Lounge/Dining Area
5ff6e502-4e28-49ea-8e0b-d2c82d016fbe |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Finishing | Kitchen
9f96f949-8561-4324-8dfc-6d57a51086ff |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Finishing | Bedroom
0e72a25d-66b1-4dab-8095-6ac044c59818 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Finishing | Bathroom
e33b03f1-f999-428a-bca7-69b062c5f80f |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Finishing | Ensuite
31925fd1-2c15-4630-a194-c80ab5ecc432 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Finishing | Laundry
75133787-6428-413d-a4ee-0dcd95fe3313 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Finishing | Hallway
8ac07ddc-bc93-4db8-a772-cce35f116a67 |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Finishing | Toilet / WC
acdf9d8a-7eca-46ba-bb5f-93ee7bcf6993 |  | checklist-flat | not-applicable | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Finishing | Client extras
65838750-198e-4cc2-a1f9-91eb000fa590 |  | checklist-flat | pass | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A89 | Finishing | Final check before locking the door
aae8be5d-ad7c-46cc-ada4-19acd29e6b4e |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90
678043e4-b7cd-4885-9201-d410df587689 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Preline
91500fe1-081c-427f-afcd-2b130d70e823 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Preline | Timber Framing
3f755d66-bfa5-400b-a237-cf1f87940067 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Preline | Internal Strapping and Framing
fa0f72c4-8d09-4d5d-86b6-022c010692ff |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Preline | Suspended Celing
625c0de2-4143-4860-ac43-160b05cd4b34 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Preline | Internal Doors
6e862fce-0c79-4bcc-af73-0cf8fd86ac08 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Preline | First Fix Services
4ea12997-388c-49d3-abb3-a23f3e803c93 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Preline | External doors and windows
39030994-1f2b-4d15-8280-46b3f0762d8e |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Preline | Insulation
a260d7fd-b6ec-4fc2-ab97-2e73e7612e4f |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Preline | Passive fire/Approval to line
88b9cf91-5c04-42f5-aca9-f7812015af63 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Post-line
4b04ea81-4833-4252-9ac2-fe1f1f90ada6 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Post-line | Lining
f0c98660-6110-4892-9492-d3aee7e94ec6 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Post-line | Stopping
67158415-3af5-44e5-99ab-d3baca8e104a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Post-line | Finishing lines
bd2bed1a-d88a-41ba-a5ce-e8ecc5254b6e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Post-line | Flooring
c86bd8e9-66cf-4510-bdda-f503d7383e25 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Post-line | Painting
825730a9-5ee8-4ad6-9738-5599d47d6855 |  | checklist-sectioned | pass | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Post-line | Second Fix Services
41a9ab4e-92b5-4b6c-a021-2e1d924a05c1 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Post-line | Fire Door
6deac43b-85fe-4216-98ce-53c6e1bb7b06 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Finishing
a21a852f-4704-4173-b6fb-6142e2cd3372 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Finishing | Flooring
db4fc07d-65c1-4b71-9625-dd6dac0e0a2c |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Finishing | Exterior
86dffeb4-bc4d-474d-888e-06135630c30d |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Finishing | Lounge/Dining Area
285fe33b-f26c-4f57-83aa-20a336cf70a1 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Finishing | Kitchen
73506971-c490-4bcc-b9b5-08f4b7126836 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Finishing | Bedroom
58586a45-ac3f-4f49-b88b-1f6dfb758165 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Finishing | Bathroom
d195d22e-81de-4a13-994e-8e6f1e0a11a7 |  | checklist-flat | pass | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Finishing | Ensuite
3bfad200-8f19-4692-9ba0-2639ca36a9de |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Finishing | Laundry
ceda8ffc-31c5-4ce1-873c-050e505ed61d |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Finishing | Hallway
199b4ee6-ddac-4015-aa4f-0b0f84fe86b8 |  | checklist-flat | not-applicable | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Finishing | Toilet / WC
f40d82bf-0475-4a6a-85bc-ccc5963e0fe9 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Finishing | Client extras
63e165a7-3625-44a0-be31-28cd97d38647 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A90 | Finishing | Final check before locking the door
64ff0b9a-c4cb-41f4-9c21-579b7247b9f8 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91
d88a39c7-0bfa-4f93-9cbb-8189470934a4 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Preline
9fc6834f-49dd-4543-865f-64c4659697f8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Preline | Timber Framing
242c0e72-36ab-4ae9-8894-3e481d9b7c37 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Preline | Internal Strapping and Framing
68de19ad-1180-4391-a76a-6f3ca90f64dd |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Preline | Suspended Celing
6431e5e7-8c6c-4c4e-b692-e488cb5b4b4a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Preline | Internal Doors
da75c6db-538d-448f-9c33-6799b0d07712 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Preline | First Fix Services
3c9e36fb-d20e-40c6-af54-6c979d43327b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Preline | External doors and windows
9175336e-ae89-4a04-a4b1-48427ab3869b |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Preline | Insulation
2e16418f-c75f-4507-8b87-b68fd516f015 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Preline | Passive fire/Approval to line
3eb97874-7e5e-433d-83eb-d32c0a02d820 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Post-line
0a555cdf-6b25-48b3-9fba-8be46044e1cf |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Post-line | Lining
ecf702cd-602d-498f-bfb2-fa011cb4b548 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Post-line | Stopping
436f777f-2fef-488c-bd11-1cf7f2ae2179 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Post-line | Finishing lines
9b919d52-2053-4187-a646-ffa956f7f873 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Post-line | Flooring
0de2aaf3-0c02-4095-bc98-39fd9e34bb94 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Post-line | Painting
5d8df91c-5959-458c-8b03-6f3552be8611 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Post-line | Second Fix Services
7f0424ed-ba75-42bb-969e-7abd88c007de |  | checklist-flat | not-started | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Post-line | Fire Door
a1422037-64dc-426c-ba76-5400c532eaf3 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Finishing
1f3f415a-2d86-42df-ad08-f011f2021452 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Finishing | Flooring
a9fe8943-9103-4090-b0bd-939708e12849 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Finishing | Exterior
266ccd52-451b-4096-87c9-759b1c30255f |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Finishing | Lounge/Dining Area
6e38839c-f928-461f-9e1e-f666034e7a8a |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Finishing | Kitchen
5ed098fb-91a5-4c9c-9b04-425e0ef1c11b |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Finishing | Bedroom
3ea44353-51c7-4ceb-bd9e-a05a2d374a94 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Finishing | Bathroom
722e9976-5dfc-4e37-aabc-33e097037eca |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Finishing | Ensuite
adec5f73-d1ce-4660-8d54-fb832e0c32c6 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Finishing | Laundry
7d60d2cd-fed7-40e1-93ce-b60ab59bb1f4 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Finishing | Hallway
66b499b3-2edc-4934-a354-a38718dacf59 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Finishing | Toilet / WC
8b1b5573-3cc2-4381-b860-12103f80970c |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Finishing | Client extras
c039d732-7e0b-48fe-8e4f-373e27c5fe33 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A91 | Finishing | Final check before locking the door
907f392c-8de9-40fd-8be9-7ec5d5a17892 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92
2bad3abd-2d97-4713-8908-8b38dc2bf95a |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Preline
55d38872-0c49-4759-9093-5c23ab2f32c9 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Preline | Timber Framing
b7c95772-99b5-40a3-90de-e7130168b4d3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Preline | Internal Strapping and Framing
ff397765-f5af-48aa-ae88-425f356f57fa |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Preline | Suspended Celing
93b494d8-f16e-43f2-9a71-2b2b1c5b6b86 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Preline | Internal Doors
659a1703-1b7c-48fe-8449-cda7675e1032 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Preline | First Fix Services
4ca55b87-61f5-42cc-b850-7bebbf4cdd2d |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Preline | External doors and windows
31167fef-5d69-4fa6-bd7e-734801e36367 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Preline | Insulation
47cff7b6-2e2d-496b-8a2e-0fae68556829 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Preline | Passive fire/Approval to line
454e15ea-cc9e-4fd0-a540-63b7945f3bbe |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Post-line
524cc6d7-bb95-4fda-9ab5-ec3825b7930b |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Post-line | Lining
30a3bbec-ff31-4381-9287-d8a2d4ee71b7 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Post-line | Stopping
bf8de1d2-1a08-4362-b2c7-cb5389c49318 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Post-line | Finishing lines
abbac265-e0af-4ede-92c9-94aa54a0cc5e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Post-line | Flooring
9dc6b050-9fd6-4765-88f0-6d7f46a18ed0 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Post-line | Painting
27d837ba-e609-47f0-a4bb-40fdc29148f4 |  | checklist-sectioned | pass | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Post-line | Second Fix Services
6bf11983-bbf9-440b-b45a-e1492de6c3f1 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Post-line | Fire Door
f0704366-fe0a-4000-a3d7-7ee5e1521e53 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Finishing
64454ccf-dd0d-4aa0-8304-bd02fa30359a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Finishing | Flooring
0ed44baa-b9a6-4940-8c28-314070dad98a |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Finishing | Exterior
b751f850-5f50-42c5-a4c0-e476922e4c12 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Finishing | Lounge/Dining Area
35e9d06d-2dc5-4baa-ad92-0da7413b57b6 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Finishing | Kitchen
acd38ffe-819c-4824-91c0-f17cdad19833 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Finishing | Bedroom
19f20ab1-d3c2-4387-b211-50c76bcccfd4 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Finishing | Bathroom
e2ce1c64-10de-43cc-b940-2cd649db8e21 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Finishing | Ensuite
9278eeff-9ece-4c6b-8981-8474f339a94e |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Finishing | Laundry
7e58aaae-fdd1-4f80-8367-b60d59508d7e |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Finishing | Hallway
c0440ceb-d63a-42e2-86b4-c83062031eb1 |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Finishing | Toilet / WC
47f159bb-b6d7-46f7-a4ed-4e0a4b2e8c29 |  | checklist-flat | not-applicable | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Finishing | Client extras
b26b3d6a-b8c4-434d-91a2-d450c57927ee |  | checklist-flat | work-in-progress | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A92 | Finishing | Final check before locking the door
701d4f5f-a60a-4094-94e7-575391942e34 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93
ff010517-1c4b-4f07-a4c6-bb32b9c5d4b8 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Preline
5290aa7f-22ec-4b49-a779-8d49f2f0d4ab |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Preline | Timber Framing
826ac982-1e04-4504-92dd-c5aff4f375d1 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Preline | Internal Strapping and Framing
3ec8c6b1-cb0e-4cb4-88cf-499bbcf2e04e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Preline | Suspended Celing
20bed72f-d9f2-487d-8588-d7c719eaa4ed |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Preline | Internal Doors
92255d1a-8d97-45eb-98f8-78191ef6023d |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Preline | First Fix Services
b27065a7-5757-4de2-8ea0-d18f517afb1f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Preline | External doors and windows
8ac87bad-4dd4-4fdb-a91a-36f5fe3a3db4 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Preline | Insulation
7ae6ed4c-422c-4d83-a25a-4217ac026116 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Preline | Passive fire/Approval to line
75171a2e-697c-4d69-bc21-c72f31e85787 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Post-line
23ace1b8-5943-4442-aa6e-f84bf56ddff0 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Post-line | Lining
fa7fc9fb-4c05-4107-99d4-917e51af2dcf |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Post-line | Stopping
7959b63b-91e9-4983-8800-41df2d1f2a83 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Post-line | Finishing lines
d8c39ef9-d807-45a4-ad81-25f6472b5232 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Post-line | Flooring
9ff6ccfd-2f9e-4c87-b8e6-f7394ec52708 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Post-line | Painting
7dafa600-bcff-443f-8d5c-68612b0195ce |  | checklist-sectioned | pass | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Post-line | Second Fix Services
ae2ba7d5-aec0-4b53-b920-7794538e44d4 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Post-line | Fire Door
f624fc82-8bfd-4a30-97f1-2de5a14f7330 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Finishing
5c5178a2-f844-4284-a4ff-645970e5f09c |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Finishing | Flooring
073a8d5c-1d6c-44de-bf1f-d766be6af275 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Finishing | Exterior
a228eecb-b5b5-46ee-943b-12c4720315e4 |  | checklist-flat | fail | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Finishing | Lounge/Dining Area
c2d4ffaa-fad8-42ec-a637-195cb9c596e4 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Finishing | Kitchen
5e5bb4e5-f9a3-4047-b2e5-cf507b182357 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Finishing | Bedroom
581f90dd-7bdc-41de-90b9-aa64da1a360b |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Finishing | Bathroom
c3e05274-3e19-4d92-b07b-8c8bd1a9ec1a |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Finishing | Ensuite
43915139-a71e-4883-930e-b90082b38f8c |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Finishing | Laundry
08813856-836e-47b5-84e0-15dbc7a158e6 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Finishing | Hallway
41dd593c-0af7-46e7-b23e-41d6d0b11edf |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Finishing | Toilet / WC
1ddf510f-cc32-41c3-b72c-090395befdd1 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Finishing | Client extras
fae8fc9a-53b1-4ebc-a037-1abbedc6cbb7 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A93 | Finishing | Final check before locking the door
d381d47a-4e74-427b-a0c0-20879f7907f9 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94
312aa211-4d21-42ed-9f35-c1ae1a3c6dad |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Preline
49e6a487-e6ac-49ad-b998-02f601d7d709 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Preline | Timber Framing
4eab20ac-f24c-40c3-8eb2-391ba0112386 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Preline | Internal Strapping and Framing
f2d7899b-b2d2-4901-931b-3ddad15f785e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Preline | Suspended Celing
4ee38446-8dd2-47db-8667-37920489fe1c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Preline | Internal Doors
394d061a-702f-48be-af64-0d31a84683d3 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Preline | First Fix Services
0103fd64-bd58-4942-bf69-0e28b5c1717e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Preline | External doors and windows
134a601f-0a1c-4f5b-87d3-baefffffe668 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Preline | Insulation
99ad7e0a-a3dc-49b4-98e5-aacbffc58bff |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Preline | Passive fire/Approval to line
5a999631-bb9c-4a89-adfa-adf05ca5f0b8 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Post-line
70ae630e-69fe-410a-8db0-983d305bef5f |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Post-line | Lining
e5fec572-1e8b-436c-a0ee-77b4bb3e90be |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Post-line | Stopping
1e67df57-1f09-4778-a27e-3aa919bc7963 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Post-line | Finishing lines
0f6faec5-a7f1-466d-97ef-87c73c14fc4b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Post-line | Flooring
6c26059b-3556-4ec3-aed9-9c3966d9e442 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Post-line | Painting
0c729b68-7767-47fa-8a57-5716f6ade9f2 |  | checklist-sectioned | pass | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Post-line | Second Fix Services
67a5f5b0-4abd-4836-8a0d-d7597b6728e3 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Post-line | Fire Door
4b4408fe-76e3-45f1-af48-682d7734d2de |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Finishing
3bbed7cd-b119-4273-8870-9be36be4255f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Finishing | Flooring
4593c072-2039-4151-b0dd-1a31b34b57d7 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Finishing | Exterior
1592ac40-0ce2-4f9c-92ae-72991a1193ec |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Finishing | Lounge/Dining Area
5f034899-995f-4c68-aee0-7437cd229b44 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Finishing | Kitchen
29e20103-a460-4989-a9fd-1a34ccc4a3ae |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Finishing | Bedroom
b698d848-3e27-4e07-9d4a-55ee91ec8420 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Finishing | Bathroom
800873f8-75e6-4b2f-8b8c-e2cd9e87fc24 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Finishing | Ensuite
12ccd622-64e5-4ee9-bf70-c5d107b9f5b1 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Finishing | Laundry
2ca35212-544d-4dee-adcf-3cced95ced51 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Finishing | Hallway
902f28c2-3d6f-4862-b6e5-c23bbbdef4ab |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Finishing | Toilet / WC
075da502-5dba-4156-a575-e4dc235cf990 |  | checklist-flat | pass | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Finishing | Client extras
e0ea45f8-4d7a-4e43-8f49-9d1e37f8463b |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A94 | Finishing | Final check before locking the door
a4ff5b28-d261-4c67-9f41-a3abeb3934c6 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95
ba5f398a-fdb3-4709-b617-edcc3701e0be |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Preline
72fc2bdf-eada-41ff-82ab-5e635b8ace57 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Preline | Timber Framing
c4b169c9-71fa-4264-9f12-b933eff69a18 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Preline | Internal Strapping and Framing
3a10bb06-f6ee-40c0-b5a1-909a2b06d9ea |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Preline | Suspended Celing
2dd1c0b6-b3ae-4461-9aff-fde2f6e0707b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Preline | Internal Doors
6f952a9d-ffe0-4e26-816f-c7b9587be736 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Preline | First Fix Services
8b48319b-0341-4a35-94de-0930345bcbbb |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Preline | External doors and windows
dbafb216-f1da-4a84-a8c0-1a9c39114eee |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Preline | Insulation
d39111a3-db3d-48e3-af18-d0e1d43587f8 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Preline | Passive fire/Approval to line
f30a90d8-b7f7-4cdb-8806-d3256857d9ed |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Post-line
0c3e1d94-1e03-4c68-9237-ede927f284f9 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Post-line | Lining
ffcfef82-ac5b-4dfb-8f10-9ab0ec29ffc0 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Post-line | Stopping
7343f0e4-b311-4f44-985c-10b6f0f5705a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Post-line | Finishing lines
e7841b2d-950e-4403-8dea-d7263b2ead36 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Post-line | Flooring
c04cc99b-b394-474a-91ce-c5b7075799d3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Post-line | Painting
3b11c0d9-a440-4182-95eb-3fd6a8446c6c |  | checklist-sectioned | pass | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Post-line | Second Fix Services
42af755f-6a45-4126-b861-3bd98c809d1d |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Post-line | Fire Door
1a2eda33-5f9e-4ac0-8a20-230f3d67999a |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Finishing
f75904d2-60e3-4908-9f00-44318f67bd73 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Finishing | Flooring
52550e89-04ee-4043-ba39-ffe6a46addd2 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Finishing | Exterior
c1c7ee2b-fa57-4d6b-99f8-6aeea4a770c5 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Finishing | Lounge/Dining Area
74cd4910-2b28-4808-9d34-c5768a5d1373 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Finishing | Kitchen
8995305d-c916-457d-8564-fd21c0c2b464 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Finishing | Bedroom
0472663c-3910-4c24-a1c5-f10dbc06390f |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Finishing | Bathroom
dfd53671-dbd9-45c6-8929-395f8c10fafa |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Finishing | Ensuite
ca534672-88ae-4fd6-89ec-7f236fbd62fb |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Finishing | Laundry
c8445a88-5ce3-41d8-be05-9603a1b7f900 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Finishing | Hallway
91988a41-e089-42c6-bb97-1cc9e82620af |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Finishing | Toilet / WC
06ceb4d7-6e2b-4bf6-ba44-726a2f3468fe |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Finishing | Client extras
3a7bd433-5940-44e0-8bc8-b34921aca9f8 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A95 | Finishing | Final check before locking the door
1b1c0a68-63d5-43c0-aff2-f06967d74315 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96
cf450851-85dc-4974-a81a-4cd175346660 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Preline
c05ee799-b163-4174-982e-738dcd76e8f5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Preline | Timber Framing
de6efd3a-4ef7-4dd3-b88b-7d2049d32e0f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Preline | Internal Strapping and Framing
dba85ae1-30a6-41b7-93cf-59822729ed1f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Preline | Suspended Celing
0158fd9f-c688-46a2-8bb8-a2d473e631c5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Preline | Internal Doors
7759efb0-936f-4867-93bc-f6b1e1fc0833 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Preline | First Fix Services
14bf7323-1626-46ff-8977-b6864094f6ac |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Preline | External doors and windows
73c6dd66-fb44-4950-bf12-8c535e16d619 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Preline | Insulation
bfc44051-0439-490a-9465-48e758fd632e |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Preline | Passive fire/Approval to line
06b5346b-57a7-42a2-9578-927ae3748409 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Post-line
b5a828d8-9081-47ad-9eb6-83673a265b23 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Post-line | Lining
1c9e6375-bcda-4556-80e5-eb3032bb784f |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Post-line | Stopping
c9caec2a-ba3e-4a1d-a8f6-fa2a94983f60 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Post-line | Finishing lines
ee94057b-ee7c-4421-a2b8-be53290fe1cc |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Post-line | Flooring
ba2bf1fe-cea6-4fe4-839b-926e8ad2882e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Post-line | Painting
c4257c61-8478-4d68-bd21-e65154397383 |  | checklist-sectioned | fail | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Post-line | Second Fix Services
8827f349-e033-47ce-b49f-ba3e3faf23e1 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Post-line | Fire Door
18cdb6e1-445c-4bc4-afc8-49a84c3ea688 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Finishing
23d58ff8-eca8-4e09-9e69-cf6638dfcfe9 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Finishing | Flooring
abf810a6-50fb-4a49-a61f-15895b1a8553 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Finishing | Exterior
7b0291b0-b416-41f5-b658-d3547f9a6084 |  | checklist-flat | work-in-progress | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Finishing | Lounge/Dining Area
00474f65-b7b9-42a7-853a-521ecb715dd3 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Finishing | Kitchen
194ddea4-054f-41b0-a73c-6e99cd7d59ba |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Finishing | Bedroom
3623b47a-1ec0-4f52-a692-9a5f704b6098 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Finishing | Bathroom
d2fbe6f1-4df3-4b5b-8b6e-321f60278093 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Finishing | Ensuite
55a07d5e-b101-4876-baab-ed0c25e6f6ca |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Finishing | Laundry
59ed2d08-1489-47bd-b0f8-a1247592132e |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Finishing | Hallway
98330f33-dd9a-4bd8-8ec7-7f0726759358 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Finishing | Toilet / WC
d72bb9c3-ecb0-42b6-9473-c047115b16a8 |  | checklist-flat | pass | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Finishing | Client extras
aee3ed2f-14d1-45de-b5a5-d1837c15bd84 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A96 | Finishing | Final check before locking the door
272a3e38-c9f8-4814-a517-11f0d6ecf468 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97
0807b6ff-0f66-432c-9768-26eb4e64bca8 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Preline
19c1b303-9ba8-4c9e-83fa-755bf3e66578 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Preline | Timber Framing
21038ab7-dc69-4716-95b9-2cd72dc39209 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Preline | Internal Strapping and Framing
82a71b42-ba91-4b11-be59-c6af0ec5c62d |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Preline | Suspended Celing
03760ef0-3839-4324-92ea-19fb5ad16c5b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Preline | Internal Doors
f70b1501-b75a-43f2-aa1f-1f45b40a1c7b |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Preline | First Fix Services
d8d9261b-07e8-4f39-b807-e4247ba43240 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Preline | External doors and windows
fe8d6df4-b56e-4d36-a019-778790889ccf |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Preline | Insulation
329cf046-ed0e-4e51-bba0-19aeecf22b62 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Preline | Passive fire/Approval to line
4a87752c-ce18-4789-9ab6-a6f8a30f5ae2 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Post-line
bd07cdea-f151-4fef-bb25-49c9764ec0ad |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Post-line | Lining
4a60fb5c-6d40-44c9-9709-adb5893765fb |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Post-line | Stopping
30efd943-4448-440f-b5f9-f7bf64701b96 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Post-line | Finishing lines
f5db4720-d289-4aa7-a69f-d228c18461d3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Post-line | Flooring
b8b77864-df59-44b1-9d07-58571c4355b8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Post-line | Painting
2c9b18a7-5608-4a9f-a2af-bbca4370e196 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Post-line | Second Fix Services
4e2fede1-72be-4393-9b86-eddbb38291b4 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Post-line | Fire Door
b205b954-a745-449c-b8cf-82525d8ca2db |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Finishing
9a9f1e24-b8f8-4a80-861d-ff565b4aa135 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Finishing | Flooring
dc32fde8-bcb5-46db-b4d6-8acc6f11d624 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Finishing | Exterior
63feef80-bbe7-4d5b-bd3c-ce3367d4d003 |  | checklist-flat | work-in-progress | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Finishing | Lounge/Dining Area
21b58009-fa30-49d0-b961-ab259fb16f85 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Finishing | Kitchen
35f58306-a050-402d-a469-46cf80456c79 |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Finishing | Bedroom
3eeae768-9a08-4661-bcd2-fd74e518b1f9 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Finishing | Bathroom
9f86ddca-8c5d-4604-af50-8aa18fb27eca |  | checklist-flat | work-in-progress | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Finishing | Ensuite
189a2f74-ae49-4929-98f7-e5047848efca |  | checklist-flat | work-in-progress | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Finishing | Laundry
6b75c451-f97a-42d2-9aee-a56b71549bcf |  | checklist-flat | work-in-progress | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Finishing | Hallway
93c98c21-f0ea-4f67-b805-e3b017454664 |  | checklist-flat | not-applicable | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Finishing | Toilet / WC
84d2300f-836c-46bb-be69-f35502c5c23c |  | checklist-flat | pass | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Finishing | Client extras
0b096c43-c144-4c7c-b631-191ae8e8f74f |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A97 | Finishing | Final check before locking the door
0436d111-9ad4-496f-b0de-704850a5607b |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98
8693a4da-0600-45e1-973c-8d90fe253729 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Preline
7f88edec-9dcb-40f8-8f00-f46574930ce8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Preline | Timber Framing
bf076d72-0d0b-4371-879d-db4116f043f0 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Preline | Internal Strapping and Framing
857f5c79-33b5-4cab-b43a-13d8a6a97332 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Preline | Suspended Celing
d25f591e-a4a5-4326-975a-58dcc8216787 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Preline | Internal Doors
35c8bc38-07e1-4233-a5e9-94f73f5c4bb3 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Preline | First Fix Services
322da775-ee55-475f-8a9d-e41e6c688673 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Preline | External doors and windows
88668f0a-b5da-492d-a21b-14bbdea593f2 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Preline | Insulation
2317ee0a-ac7a-4c59-abf5-91dcbda9f0e8 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Preline | Passive fire/Approval to line
3f9187e3-c3da-4512-b8e6-ee55e4c96947 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Post-line
b706e5e1-bf8d-4b9f-af63-b55ae65a23b0 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Post-line | Lining
87cadbba-7289-476c-9cba-f530ed5f9c23 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Post-line | Stopping
8955d583-135a-4cc8-8123-1be0383352cb |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Post-line | Finishing lines
6881a333-0cbe-415d-b45c-0b346ea2d2cd |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Post-line | Flooring
92c61877-5c36-4301-b584-9146f5bddd95 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Post-line | Painting
99184b5f-b72c-424a-9652-8c27b98ed04b |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Post-line | Second Fix Services
1b765ef1-8ac1-4d22-b247-fe9b94cd3167 |  | checklist-flat | not-started | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Post-line | Fire Door
223c5b5f-d19f-48fb-be22-b959fabc4e0e |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Finishing
8f3497cb-ce3a-40bb-9d8a-52683c8313a1 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Finishing | Flooring
5a472c48-b12c-47e1-8fa1-7fbe93d5f5ed |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Finishing | Exterior
5c279218-2b0d-4a78-9de4-5532b2920fbe |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Finishing | Lounge/Dining Area
5ad32745-2c7c-48c5-b3ca-45e075bebb21 |  | checklist-flat | fail | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Finishing | Kitchen
664cdf8e-c561-440b-ad15-2f78145372b9 |  | checklist-sectioned | fail | 6cb5cee186d30ff5793335efeab489867317380d59424063c0448e8a3c0c9f2d | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Finishing | Bedroom
58703ae0-b8e0-4437-a9b9-cda03035d6ac |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Finishing | Bathroom
423f0acd-4d97-4574-926f-f4d6ae3b3e11 |  | checklist-flat | pass | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Finishing | Ensuite
ad3aa009-b519-47ec-938b-3f2bb7626f5f |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Finishing | Laundry
9bfdc373-74a1-4bb8-988a-6c34b25fa98c |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Finishing | Hallway
918b82bf-a702-41dc-a61b-5c28e1480f69 |  | checklist-flat | not-applicable | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Finishing | Client extras
7faa6361-0437-4fe7-aaf8-9eafbd92d755 |  | checklist-flat | work-in-progress | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A98 | Finishing | Final check before locking the door
bbb82311-fe65-4e81-8377-be5d189f8c46 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99
9191ee81-7dc0-4243-9c4c-3e02bb47eb10 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Preline
1a414c60-48fd-4609-abea-b14cf49ecd0f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Preline | Timber Framing
7b2e4445-e19a-4ea2-b222-e6891e8efc65 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Preline | Internal Strapping and Framing
9b4943be-c313-45b6-9163-e3da96329c35 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Preline | Suspended Celing
2df5c92b-bc93-446e-86b4-d9d8189e106a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Preline | Internal Doors
74218de9-a106-48a2-87c5-fcdf88907970 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Preline | First Fix Services
6532e3ae-bb01-4446-b8db-377ab1fe3c11 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Preline | External doors and windows
03cdd8f8-4c16-48b2-bb95-2490c2c4dc71 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Preline | Insulation
1c30c676-6df8-4e01-b62b-6a97caf94434 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Preline | Passive fire/Approval to line
dd58e6d7-6852-459c-b3cb-c9d1ce6ec6b3 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Post-line
a989af7a-4c70-436d-b833-3d1e7d142a14 |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Post-line | Lining
65be81c0-e5e8-43e7-aa77-0f893e8e392f |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Post-line | Stopping
9c84cfbd-86e3-48c3-844c-85e205060652 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Post-line | Finishing lines
468b2627-9856-4b85-a9c3-3a7fffccf258 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Post-line | Flooring
86accf2c-244d-430b-91f1-2384cf533441 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Post-line | Painting
7f70657b-f014-4bde-9acf-154f89087710 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Post-line | Second Fix Services
86cdd61b-b8d5-4046-b946-4800b42abb81 |  | checklist-flat | not-started | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Post-line | Fire Door
9ea87a1c-d887-4f3c-9a36-a04e3fe93abf |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Finishing
20bdee0a-a394-4224-9b75-784181f20e49 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Finishing | Flooring
1e69e850-47d5-46fe-af21-a927cf73ebda |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Finishing | Exterior
7832fe7e-9ead-41f8-8f6d-f86d9693b955 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Finishing | Lounge/Dining Area
8f0435e3-0219-40ee-897a-0363502bc3ba |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Finishing | Kitchen
01acc3f0-fcbe-4e89-b584-9f7aefb699c3 |  | checklist-sectioned | fail | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Finishing | Bedroom
4efac9f9-1668-4030-a008-2144551697d6 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Finishing | Bathroom
a8196c69-afc6-4b23-b5eb-40fcb7ed96b7 |  | checklist-flat | fail | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Finishing | Ensuite
38d8f0cd-4257-4bd6-9993-9fbe4c3b17c3 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Finishing | Laundry
bc8a2eec-9e09-42a9-901f-cf8604c5d799 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Finishing | Hallway
91f32d58-7aed-476e-b722-1b547538c983 |  | checklist-flat | not-applicable | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Finishing | Toilet / WC
a03d6d21-68c1-4807-b3d6-e36bc064ba86 |  | checklist-flat | not-applicable | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Finishing | Client extras
19cf2b16-6464-41fd-8c32-7a48bb11e3aa |  | checklist-flat | work-in-progress | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A99 | Finishing | Final check before locking the door
7becf702-dfac-4a8b-ac4b-274ccfd154d4 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100
f4864c51-62e8-4376-a5f3-1b85c31b46c6 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Preline
9fbe88b3-8825-4257-92cc-d3125c92ecee |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Preline | Timber Framing
0336bc0c-83c1-4f0a-a5a1-6c53550d5389 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Preline | Internal Strapping and Framing
e70a5fd0-dc2f-47ba-9915-474eaa3dca33 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Preline | Suspended Celing
b193f956-4569-4344-af4c-624c5693467b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Preline | Internal Doors
acbb6941-4a4b-4a8c-a7f2-fc68f8d420bf |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Preline | First Fix Services
8805311c-9632-4e2a-9791-3aa6d8361782 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Preline | External doors and windows
32c5d802-aaa2-4a72-aa71-8736604b7b16 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Preline | Insulation
272a90d2-e9cb-424c-bb4c-6b9f1b13bd2d |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Preline | Passive fire/Approval to line
3dfcef30-d50a-41c9-84ad-4bf9b4c33986 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Post-line
743936af-23a9-41dd-ad45-057340b543fa |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Post-line | Lining
3684778d-d8b8-4fab-9e49-b38b6c3fceda |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Post-line | Stopping
c767951a-3dad-433e-a95d-798cfe475da5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Post-line | Finishing lines
3e4b3fad-584b-4559-be1f-a2d5b979d9aa |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Post-line | Flooring
076028f7-aafc-4913-93de-308491e1b2e6 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Post-line | Painting
706d0e48-8595-41c4-a2a9-f6896705c4aa |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Post-line | Second Fix Services
0f713c01-4c0b-4e81-82b1-2a82804296fe |  | checklist-flat | not-started | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Post-line | Fire Door
6a48896e-29fc-4f8c-ac20-d13013634e31 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Finishing
2dbb79af-3a4e-4b41-abdb-64cea12d3f9b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Finishing | Flooring
7b289040-292f-48cf-bf49-2e040893ffa8 |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Finishing | Exterior
861e3f08-8d7e-45c0-92f0-11daf22cad56 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Finishing | Lounge/Dining Area
b0190932-e341-4bd5-946d-3323adc9d9b8 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Finishing | Kitchen
f2762b5a-9e2b-4900-b0f3-a7fbc484697b |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Finishing | Bedroom
a887fc45-40d2-4bf5-bda3-b92f3476799f |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Finishing | Bathroom
0d9269c3-e339-49ee-8460-b52d956113a4 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Finishing | Ensuite
26af1d44-3b06-4d6f-9b61-a193f7951c22 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Finishing | Laundry
d5e59a29-d9c2-42bb-811b-1d2260a0a2eb |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Finishing | Hallway
2bfa6a22-3045-474e-a6a6-a151fe56a0e0 |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Finishing | Toilet / WC
81a502ab-da89-467a-b282-340c8b2b9a01 |  | checklist-flat | pass | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Finishing | Client extras
02fb5928-7708-47fa-8358-6ae96a46bd8c |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 1 | Residential Areas | Apartment A100 | Finishing | Final check before locking the door
10360b55-91e0-443a-ba9d-b581a0081ca7 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2
7003f952-cf79-47d8-99f0-d51cd97701c7 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas
8c724395-3e92-4a1e-a61a-d0254c6d5c45 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors
16afee5b-764a-45a9-8846-8bb474a8f7f4 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Preline
79500389-7f39-44a0-890c-aec37370909a |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Preline | Timber Framing
cced6e87-d646-4713-a324-f8476e3a3b9a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Preline | Internal Strapping and Framing
c7472f91-527d-490a-9635-49ea418ed9f2 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Preline | Suspended Celing
d72fd73e-bc18-41cc-bb84-2dedc1f3be9f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Preline | Internal Doors
5f11a30b-56bf-4912-97e4-72bdc1b6b230 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Preline | First Fix Services
a873b6e2-2e9c-45ac-afe0-d170e4a5cc49 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Preline | External doors and windows
545ec2d9-77b1-4ac5-a0c7-d32c9aad4b96 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Preline | Insulation
7e67729c-2485-47d7-90b0-cb2faef5715c |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Preline | Passive fire/Approval to line
96c6151c-f57a-4f6b-965e-aa730c9645e0 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Post-line
ebe2cfce-251d-43a4-8e40-a143c3f84631 |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Post-line | Lining
6125f304-c2c6-4ef2-8fc7-6fbfd571b36e |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Post-line | Stopping
0d6d80d7-4fee-4b37-8eda-4537608b0575 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Post-line | Finishing lines
ad5d955a-d179-48c9-a2e6-489f6afc6148 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Post-line | Flooring
f2c0179a-a791-4647-983d-107b21d23627 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Post-line | Painting
a465758e-03d8-47f2-bfe1-83185a8b8791 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Post-line | Second Fix Services
37c28cac-cdf5-4a46-bd86-72d45853d32d |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Post-line | Fire Door
836ea448-f031-4178-a75d-d2877db9c3d2 |  | checklist-sectioned | not-started | efe9dd8861170a4f6c877309dd15ef71545349ef8eb7e2755d191ae9183ec15d | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Corridors | Finishing
06c01681-4e0c-46ae-8dc7-9603d8955506 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby
f504e294-27be-4a1c-946a-6cbe762c6064 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Preline
1f7368b7-7a59-4a40-bad0-3321b1344c29 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Preline | Timber Framing
4887c7d6-cb24-4168-bf4a-ba255d6ca7fe |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Preline | Internal Strapping and Framing
37572fc1-5235-4f2b-9a82-02566e3e30e3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Preline | Suspended Celing
fee3152d-9e0f-4527-b85b-cf7d67add01b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Preline | Internal Doors
7b7a3f01-2e62-4a77-9bd7-e50ad9bbc35e |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Preline | First Fix Services
28f86614-58cc-4594-bb8d-c1544b2ceaa4 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Preline | External doors and windows
4291b502-8e58-4ff1-bf0f-29527f1992ad |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Preline | Insulation
98b36522-58bf-4ddd-a074-e9c0684d7fe5 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Preline | Passive fire/Approval to line
c243b0e8-3d2c-45f7-950b-2f2ecf35759b |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Post-line
ff06768c-dbb8-4a28-b42a-35c1cbdf5612 |  | checklist-flat | work-in-progress | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Post-line | Lining
13cbdd06-4476-4049-a9f1-4c6dc044ece2 |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Post-line | Stopping
c69f0148-9d53-485d-b604-22fb8d70e10a |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Post-line | Finishing lines
39808a61-75a1-4d99-854d-73d4b2957164 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Post-line | Flooring
7ba645c6-5d8e-4d19-aac2-4e75f8395dc8 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Post-line | Painting
296a3ebb-3363-468b-b997-22680611a0b8 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Post-line | Second Fix Services
c09c8b47-df3e-4d12-8d47-5b5781061aad |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Post-line | Fire Door
469dd7ad-ad9a-4424-b186-7e3581d0ed58 |  | checklist-sectioned | not-started | efe9dd8861170a4f6c877309dd15ef71545349ef8eb7e2755d191ae9183ec15d | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Common Areas | Lobby | Finishing
bffb0256-5789-4556-8775-7d5597045b47 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas
4118c7b7-c2d1-42cd-ab61-f2f9922094ca |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B
ab9577c2-f073-4a28-b5cc-278aebac713f |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Preline
df616ed3-5de5-47ab-8103-f5998a748832 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Preline | Timber Framing
c3c56965-f299-4dd4-a3d5-b84e4fbf790d |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Preline | Internal Strapping and Framing
825e36ac-1fdf-4ec4-91b0-3f96131492bf |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Preline | Suspended Celing
1360a7b2-41e4-4438-bf02-270e6e32d9d1 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Preline | Internal Doors
0175734a-a616-4a80-b74c-0668242e5de8 |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Preline | First Fix Services
699e83a9-d837-4c30-863c-1166fb409667 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Preline | External doors and windows
ff05a9ee-4f43-453c-881a-065a2d846e34 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Preline | Insulation
97e2c04d-11fb-4100-9378-a568e21477f8 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Preline | Passive fire/Approval to line
ab0f6439-9acf-43e0-bbaa-a394c6763306 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Post-line
ad400768-8eb9-4364-922b-81887ef5d3ee |  | checklist-flat | work-in-progress | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Post-line | Lining
fd0b2f02-53ff-42db-9906-ce3d80dec98c |  | checklist-flat | work-in-progress | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Post-line | Stopping
8a66e963-421a-4491-b89b-c90905acec47 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Post-line | Finishing lines
20e7508c-4f96-4bad-bf9a-43194a1e1391 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Post-line | Flooring
1dc883a0-47d0-4c9a-9492-d608287c9afc |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Post-line | Painting
a42b3bc7-820b-4c41-9639-f17df8712277 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Post-line | Second Fix Services
7c14ca2d-4bec-4db1-a037-59617b59f216 |  | checklist-flat | work-in-progress | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical Area B | Post-line | Fire Door
422fc29f-b239-4dbc-90cd-277bc75e2457 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A
37cdde4a-5c56-4885-9a55-c002d572a18c |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Preline
f2a28bd2-920b-4dfd-a9d2-9a0f3c959d82 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Preline | Timber Framing
7baf7f2e-6997-40e2-926f-3094554c3d49 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Preline | Internal Strapping and Framing
af6d9025-b02e-4105-8c29-8df7e322e209 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Preline | Suspended Celing
413f8a71-c47d-43b3-a24c-2acc92157254 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Preline | Internal Doors
cadfae4b-a36b-4705-be03-4cc61c7e1df4 |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Preline | First Fix Services
c074b292-7c47-4d18-a2c2-f6b0fdfebf5f |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Preline | External doors and windows
7d2195a4-c279-4ae9-83f6-c01c28b5ef80 |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Preline | Insulation
457250ae-75b3-4927-8eba-87247d2d56fc |  | checklist-flat | work-in-progress | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Preline | Passive fire/Approval to line
f236360e-886f-4cab-a009-13936409a904 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Post-line
0001c354-323a-4391-974f-bce4ed3a5295 |  | checklist-flat | work-in-progress | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Post-line | Lining
c38e822b-68a4-4b7f-93b3-8e86046864cd |  | checklist-flat | work-in-progress | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Post-line | Stopping
2050dfb9-945d-4d77-b9b0-a13f3acd5ed4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Post-line | Finishing lines
75269263-47ec-4cfb-943c-eb40c5823d54 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Post-line | Flooring
dac3fba0-b542-4e6b-be6d-5e6793c3ef1c |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Post-line | Painting
a6b7e3b1-2040-41ab-850f-502c5114cf6e |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Post-line | Second Fix Services
0f4a85fa-1840-4b2d-aec2-a36e921b370f |  | checklist-flat | work-in-progress | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Electrical 2 Area A | Post-line | Fire Door
64341370-e64c-4265-89ce-704d634fd7bc |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B
488b6831-a618-4b3f-9a0c-0d7a415056c4 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Preline
c3739732-63b3-4bd9-8020-a10b8619b32a |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Preline | Timber Framing
8264b7cb-49b5-420f-a044-a88a8bd2997b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Preline | Internal Strapping and Framing
6ced272b-7d23-46e0-bdad-44f192cee77a |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Preline | Suspended Celing
7594388d-6e50-478a-961f-191abaf0afcc |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Preline | Internal Doors
4ec3ec7a-0731-4d0c-bc2e-ac9bd11e27ac |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Preline | First Fix Services
3b10aa6e-c426-41f8-b2bd-287752f5c3c6 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Preline | External doors and windows
7a711874-76c0-4189-b140-d7ee71e7ec5e |  | checklist-flat | work-in-progress | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Preline | Insulation
745ae59e-ebde-462e-8bb1-27750823bd77 |  | checklist-flat | not-started | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Preline | Passive fire/Approval to line
cd19a765-a917-4420-a2cf-afd89cac1622 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Post-line
bc23bb63-9d04-4c12-b119-974fa93163e4 |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Post-line | Lining
1a3963f9-f65d-43d2-a4bb-89ec624ea9ae |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Post-line | Stopping
7904a577-925c-46d7-ab88-c005cdff6af0 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Post-line | Finishing lines
e8c20b16-feeb-4c54-b748-954eca803a75 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Post-line | Flooring
2b9cbfa0-8a98-4eeb-992e-a6e426cf61b7 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Post-line | Painting
e25529ab-7b49-4f53-b77b-36f9d3514890 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Post-line | Second Fix Services
27c811d7-4c48-4eb8-a63d-44f5509f37a7 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services Area B | Post-line | Fire Door
e9df6a86-b1be-4024-af82-6846ff7ac668 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2
d9f80a78-6e87-4298-b4cf-6d1067f01626 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Preline
8c54bb81-8cc3-433c-a133-e0a054fbad96 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Preline | Timber Framing
2a4b522c-f128-490e-a91f-9c48ebece1e1 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Preline | Internal Strapping and Framing
b5fc878d-d725-440e-90d0-6a9912cc0e99 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Preline | Suspended Celing
cba6abc3-cbc4-4bb0-8be0-8016550564ac |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Preline | Internal Doors
a26d6b5f-96c3-4c52-a1ae-5c88242b7272 |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Preline | First Fix Services
cf4b619e-7728-42f3-a4de-038484221806 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Preline | External doors and windows
f25809bc-a79e-421e-ab95-c273979c9e7c |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Preline | Insulation
77838d5f-42ed-49ce-b078-7e57547c51b8 |  | checklist-flat | work-in-progress | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Preline | Passive fire/Approval to line
a546370d-3230-4404-94f5-dcb67290e7f6 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Post-line
650cbcec-16b9-46d7-926f-dd6766622d67 |  | checklist-flat | work-in-progress | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Post-line | Lining
75a89810-1ca5-4817-b04c-d7eed20505fd |  | checklist-flat | work-in-progress | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Post-line | Stopping
a1c80c0d-5969-4081-85c6-dcd9aeaee2ff |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Post-line | Finishing lines
bf8819d2-04ab-47cf-84a0-5fcc76071b66 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Post-line | Flooring
2cf7e1dd-406f-46c3-8634-0f8846821a69 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Post-line | Painting
2dcc7a3d-e374-4636-8f58-e8c785299326 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Post-line | Second Fix Services
cfddce18-c27b-4a03-ae69-1336b434538f |  | checklist-flat | work-in-progress | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 2 | Post-line | Fire Door
77eb0b15-70aa-4ab4-97d6-df035f27c9d6 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3
1d205bb6-da01-4215-9750-94c66952771d |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Preline
30b09d36-61e8-4a53-9a73-b5f028d7f1e8 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Preline | Timber Framing
4bfa4ff2-4129-47f7-8c0d-40742c82d003 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Preline | Internal Strapping and Framing
0b04d2ad-dd44-4c2c-95d0-1ffb747529c4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Preline | Suspended Celing
9f931401-77fd-49af-8992-5f1e024aa9c8 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Preline | Internal Doors
5ae32188-f9b0-47f6-91b8-4bb95b5c322a |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Preline | First Fix Services
24eb2324-b52b-408e-ae60-dfbe257215d3 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Preline | External doors and windows
4133acf3-6fc3-4b8c-9b86-278d61ca4940 |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Preline | Insulation
a46c0e69-ba5f-4fd5-b6f1-61c130f1b562 |  | checklist-flat | not-started | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Preline | Passive fire/Approval to line
c6eccb37-a4d5-4d21-81a2-ab30fde031e2 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Post-line
db0d83bc-f103-4b79-a17b-42da659486a9 |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Post-line | Lining
8047ed4d-5f05-47ff-a275-d82fa89350fc |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Post-line | Stopping
4cd1e0a3-f3da-4091-af88-485c5daf6257 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Post-line | Finishing lines
a2243bfd-b86d-4df5-9521-9a7f146416a6 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Post-line | Flooring
e04b9497-4ba0-4ed1-aff2-2bb5a88f2cbe |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Post-line | Painting
30bd4c72-90da-47a4-a970-11a33a99b996 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Post-line | Second Fix Services
d72abc80-aff7-471e-bd39-01ac49917b2c |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Service Areas | Services 3 | Post-line | Fire Door
d7e4ea33-e9d9-44a6-8bed-a27866ba49d5 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas
791cf0e7-1c90-4859-9b59-2c9a8bb17635 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88
f5540f56-8afd-4b66-be1d-5c31db587c6c |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Preline
04a89c2e-0d83-4105-b243-b1c349458621 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Preline | Timber Framing
a6e7dd4d-fbd1-4517-b9fe-ff141e68a703 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Preline | Internal Strapping and Framing
59ae44d0-1904-4ccf-bc80-9c57b2390a05 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Preline | Suspended Celing
d2f56318-bfad-46ff-ae15-690d82d263a7 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Preline | Internal Doors
6d600873-0222-430c-bd21-8e3db3be3ba0 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Preline | First Fix Services
81e312d6-0958-498b-b01d-8d40393ab1e3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Preline | External doors and windows
8a6d2516-eaa4-47e8-a60b-203e99da91fc |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Preline | Insulation
5e05d16a-d65b-4a80-96da-8ffa88669adc |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Preline | Passive fire/Approval to line
26d1690f-a9ad-40ed-9f6e-a5e0533c2670 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Post-line
cc87e94f-a00b-4804-a7ab-0362d6f50461 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Post-line | Lining
124ebf4d-97ca-48a3-8af7-38e7cc3c4354 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Post-line | Stopping
53ebb19c-bb6f-451e-a9c3-85011a5ddb5f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Post-line | Finishing lines
e11dbed1-7e37-4d0f-abf4-85a4e3260bc7 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Post-line | Flooring
2e6fa2dd-36a6-410c-8eb9-ae360f2353e0 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Post-line | Painting
d4372d24-4bc8-4726-8c90-d91dd2b88041 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Post-line | Second Fix Services
23f43daa-efa1-4109-b8be-b48f96956133 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Post-line | Fire Door
8264c7bf-591f-49f9-9ca3-3bb208894dc3 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Finishing
9f24609a-80aa-415f-b3a4-e075127db92f |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Finishing | Flooring
ff3ddd40-0494-4da4-9900-8588ea2de597 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Finishing | Exterior
9b600090-c5ac-4e43-a01e-6908feba8674 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Finishing | Lounge/Dining Area
44fdf131-0df6-4e00-8bb7-d8c2d26c3b85 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Finishing | Kitchen
bd7964a2-fab1-405c-bfcd-07706c6436ea |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Finishing | Bedroom
9b3dad34-c783-4c73-9008-4026ca253531 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Finishing | Bathroom
107dfb42-f3f8-4c93-85f3-de15d7ace168 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Finishing | Ensuite
1c5ecfcd-5edc-4f7a-b107-e71dbff584ad |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Finishing | Laundry
431a34e8-cfb7-4f72-9061-faac4ada1ac4 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Finishing | Hallway
c1af68e0-13be-45fd-9cd0-b49f50fee452 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Finishing | Toilet / WC
a926ebbb-90cd-4079-ad03-425cc16bd6a4 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Finishing | Client extras
73c590cd-583d-4e46-a4a2-3d05d5f18353 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B88 | Finishing | Final check before locking the door
a92fe3c4-1eb9-49f5-aeb7-f63bacb1f2d5 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89
698f49ee-23c7-4e26-a385-6b64b9960371 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Preline
3d7eafa3-2a5c-4c37-b998-794a7683930c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Preline | Timber Framing
57d8d962-a8da-4f55-b2f9-06767b2493fd |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Preline | Internal Strapping and Framing
ea6e93de-a156-4b13-9f26-5fc556017df1 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Preline | Suspended Celing
f2c57c1e-1cfc-4e2e-9c70-9a05c8a7126d |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Preline | Internal Doors
e630aad2-bc14-4a54-88a6-f330e5a0e1f9 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Preline | First Fix Services
d880c92b-f4a3-4073-846b-0b88f209b3e8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Preline | External doors and windows
0a46aa97-6432-491f-8ae9-db8fd7265198 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Preline | Insulation
5ffdf530-8c30-46f8-8085-be32afb8a01b |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Preline | Passive fire/Approval to line
c434eca4-8d61-4ee9-a1d7-31f7bbf9cf0a |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Post-line
b39c127d-4b66-4978-9ba4-9cb519586e2a |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Post-line | Lining
154de5db-a53f-4bd9-aec7-d15ae8844da9 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Post-line | Stopping
33eefafe-4916-4522-9240-fe1f34065782 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Post-line | Finishing lines
e9c293ae-605d-4cac-8cdc-2689515258cf |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Post-line | Flooring
e37af17c-839b-4036-a882-cf64caeb067d |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Post-line | Painting
91cb51ae-6cf2-491b-a833-d1c0c9643e47 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Post-line | Second Fix Services
d8b22e65-5e5e-4ef7-80be-5db5bb4e0327 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Post-line | Fire Door
dbf80c68-deb7-4de0-add3-f31e7a575de4 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Finishing
81be4d38-9fae-47cc-bdbb-752e31429895 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Finishing | Flooring
36aabff2-883c-4d14-a6a2-cef184efb122 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Finishing | Exterior
981c4b56-1364-4fec-8360-a673138aa494 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Finishing | Lounge/Dining Area
f4ad6a93-c77c-4401-996c-fefd3e0cbd6f |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Finishing | Kitchen
6e04332c-5a18-45fa-a101-97d10157302a |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Finishing | Bedroom
bc265f48-25d3-46fa-9cad-4d3d5706e684 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Finishing | Bathroom
e74b09f1-e42b-454e-a561-06a59eb238e9 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Finishing | Ensuite
35ea38dc-64ea-4a6c-9e59-96a233e0c9a1 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Finishing | Laundry
b4ecafc7-c128-4f7f-8fb1-2893aa52108b |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Finishing | Hallway
efde5877-a874-4f1c-a900-155bb358addb |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Finishing | Toilet / WC
21822f9e-cc5a-464a-ae8b-cd9c7b700f2a |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Finishing | Client extras
409197a9-9904-4f51-af72-6af409ec4178 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B89 | Finishing | Final check before locking the door
ff6014f8-7d50-4f3b-ab7e-ad5171c45d5d |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90
565df801-af55-4271-a431-042d1e5ada97 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Preline
12b4d94b-ee16-47c8-b9a6-6518b94df4ea |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Preline | Timber Framing
412c5f92-6f61-43e7-ad28-3eecf2e917f5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Preline | Internal Strapping and Framing
deac6ceb-f2fb-44fd-a6e4-f616324de065 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Preline | Suspended Celing
3e1356e2-d166-4732-ba62-d97c81280b6c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Preline | Internal Doors
9d11533d-4702-4881-992a-ba4f32e4d8d3 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Preline | First Fix Services
010a2804-4edb-4724-a621-f72594303ce1 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Preline | External doors and windows
c1ed6fce-89d8-42c5-b2e7-066a0abf6a55 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Preline | Insulation
c6c64fb2-2728-4983-a20d-1a0ce8dc8d5a |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Preline | Passive fire/Approval to line
2c54483a-e074-479d-9426-1e93b88801fe |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Post-line
6814a7d1-5c7e-405e-8ad1-8ebe37d48087 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Post-line | Lining
add0520c-f95c-429e-8dc0-0fd85ae43d31 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Post-line | Stopping
d9a6683e-0ff0-4f53-9525-f242c3bc90bc |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Post-line | Finishing lines
147d300b-be38-4679-9410-6b964060ab2b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Post-line | Flooring
32bff4cb-b20d-400f-82de-ff7293a92c97 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Post-line | Painting
7d2d6bd2-9305-4060-a11e-9d19c06bba86 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Post-line | Second Fix Services
cb890c91-5cda-421e-9c04-9788270f4d26 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Post-line | Fire Door
8c39c97a-9483-4947-a58f-bf09d7c19c45 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Finishing
aff4c500-2826-4ae1-ae0c-e8364f21a6ed |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Finishing | Flooring
165ee744-4b17-4052-a339-3ec7494758de |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Finishing | Exterior
177b034d-b55a-4c4c-a0a2-6991371a5bbe |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Finishing | Lounge/Dining Area
8a2168a2-8fa0-4fc1-8da7-4d9a6e89404e |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Finishing | Kitchen
c5495156-6418-473e-a6f9-2344c832f5ae |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Finishing | Bedroom
b77fd4c8-e3e3-454c-b9d1-5d0bc03bf379 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Finishing | Bathroom
80c9aa2e-b7e5-482b-9cda-16c013aea29e |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Finishing | Ensuite
5a4263f2-c2b1-4afb-964d-f48f674c7058 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Finishing | Laundry
f23929a7-67b3-4d8b-bb6e-16421128c9f5 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Finishing | Hallway
b73af52d-8c51-4fbc-a29d-541d58832136 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Finishing | Toilet / WC
3ce689d2-cca4-43ee-881d-6b010adb8f3e |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Finishing | Client extras
9fd3dba5-1fdc-4207-bdfc-45dc694434cf |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B90 | Finishing | Final check before locking the door
d90ae20c-ef53-4707-b5f9-4eefd3b93005 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91
b92703df-3fb4-4ca7-803d-fee858b45164 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Preline
efd4f9f3-370d-47d5-b6c1-ad2659358b9f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Preline | Timber Framing
d14cd2b5-02f2-4402-8ee6-1b785434c8d9 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Preline | Internal Strapping and Framing
5cadb8b8-0af7-4f5e-a0db-53a535c65690 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Preline | Suspended Celing
a44643be-2773-4e8e-891f-f4c3ec7eb682 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Preline | Internal Doors
67bd667e-271b-4de0-ae74-c150a71c558f |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Preline | First Fix Services
604237d7-cd1d-4caa-b2ed-9b9b5d710117 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Preline | External doors and windows
d064473d-860d-46d1-bdb2-c85d9b4cf3d0 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Preline | Insulation
1d2579d7-b641-4281-9cd0-ac48997f6f88 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Preline | Passive fire/Approval to line
f79c8198-775c-4111-9ae5-3c5cae6a8349 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Post-line
5efc70c7-621e-4df3-a7c3-f5126b5f97b3 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Post-line | Lining
214c8a1d-d40e-4488-860e-5dd2f1af8171 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Post-line | Stopping
d9cf77a0-5428-429e-9b79-48d26e66671a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Post-line | Finishing lines
c06baf51-b6f5-46a8-af25-f16497387335 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Post-line | Flooring
26fb38d9-e0ca-4def-828a-23c175faf185 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Post-line | Painting
3238bd88-1b8b-473e-9717-590625a6326d |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Post-line | Second Fix Services
5d9fa199-9200-4add-88f5-0b38ebd6b88f |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Post-line | Fire Door
de0c7e89-5385-473f-9e27-94a977a06b88 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Finishing
b2e638b5-9498-46f7-8888-a94c6c3258de |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Finishing | Flooring
90a9a290-a262-411e-9112-e5b4603583cc |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Finishing | Exterior
36c25ecd-c038-4ddb-90c3-beecf1178ab0 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Finishing | Lounge/Dining Area
69883b85-7a38-4e43-8af3-2ab0c804d2a3 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Finishing | Kitchen
7d75c520-57d1-4522-b237-ac2d5a7d4e72 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Finishing | Bedroom
0472ff5f-c2be-4b82-af79-b37c365df3ca |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Finishing | Bathroom
fdb35b08-8fdd-44dc-a0a5-8fae8abcdada |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Finishing | Ensuite
18e33941-3403-4d93-9941-8d7de7463262 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Finishing | Laundry
9cb40656-06df-4b6b-a170-f4497ce15111 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Finishing | Hallway
d3b88581-94da-42f3-8de1-d55b6d238a75 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Finishing | Toilet / WC
e6c2e668-0cd7-4c86-a580-16fab8952a5e |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Finishing | Client extras
ecfafb29-2003-4634-ae0e-352f62ecba5a |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B91 | Finishing | Final check before locking the door
93d118fa-6c9f-4412-8c49-7de9c7d9161f |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92
23baada6-9521-4360-b00f-1d860717fbfb |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Preline
726ee484-c3d4-4c7d-82e4-b22ed0b05df2 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Preline | Timber Framing
98a4e636-9ddd-468f-89e9-c0c816b60a74 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Preline | Internal Strapping and Framing
b5888f7a-d0c2-418d-b2c8-3f405c4a1584 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Preline | Suspended Celing
3bb2c129-e614-45ab-96c5-40b186f260f2 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Preline | Internal Doors
06ee57dc-1db8-4f39-ab2c-fdb26d71b319 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Preline | First Fix Services
a51825e2-595e-426b-ac95-099db17a2a71 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Preline | External doors and windows
a4621dfb-3fac-4210-95f1-5e6ea03d5e2d |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Preline | Insulation
e390ece6-b075-4187-a8d1-fd1282d60ed1 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Preline | Passive fire/Approval to line
0925f15a-eff3-4b26-a514-753e24d0272c |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Post-line
56b53946-8b83-4dfe-8755-c0160c65630d |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Post-line | Lining
85f69375-742f-4157-bc43-71e12cc7d8d2 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Post-line | Stopping
67c07705-5394-4bac-b616-1cdfa4d58140 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Post-line | Finishing lines
3aeeb09a-ca9f-41cb-a32b-d497a9bfcc5a |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Post-line | Flooring
d64569bf-9252-4f69-9618-860b8adfb0af |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Post-line | Painting
0a40674f-dffd-4a2a-b4b7-13d18ede1fe7 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Post-line | Second Fix Services
1ea7a186-14e7-4dea-983a-66abbd7b4d5c |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Post-line | Fire Door
2a4aaada-4f68-4767-b474-99b0d4ac9830 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Finishing
48792461-4dfc-456a-bb39-0bac4ab2b582 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Finishing | Flooring
67e89791-3201-4c99-b04b-2e2cfa84d9a5 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Finishing | Exterior
5426d589-00a2-46c7-b0d9-4adf9c1b2b69 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Finishing | Lounge/Dining Area
fb76bc97-58ae-4360-abf4-7502df95e005 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Finishing | Kitchen
3a3c8bc8-1baf-47a9-9662-05b7872568fb |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Finishing | Bedroom
34ba5a3a-e8a4-47b1-8725-1c389550759a |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Finishing | Bathroom
14cdc28b-96fd-4304-b59d-e830ba37ecc3 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Finishing | Ensuite
d46bb479-b04f-4275-b90f-dc82981fbda2 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Finishing | Laundry
9c5d424e-8b4b-4307-9922-fe725d4af7ac |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Finishing | Hallway
0c208c94-20ae-4bfe-893f-12ae9399bff9 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Finishing | Toilet / WC
adf02290-2a68-42ea-b81c-5cee71876055 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Finishing | Client extras
9442ad28-b079-4cf4-a9cd-408213e4f25b |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B92 | Finishing | Final check before locking the door
c3355e14-008a-4b30-a7ca-003678fdda2e |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93
c8b02603-1c75-4be9-911c-aab153173025 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Preline
99994ebd-b2b4-4ef8-9114-615a5f81d6de |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Preline | Timber Framing
e361c0d4-3c92-4167-a3b5-4f64ab3f3f7f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Preline | Internal Strapping and Framing
4c1e5a25-1a86-453d-8629-5708bad20c75 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Preline | Suspended Celing
e630ac57-08a3-4fb4-af89-df92185cb787 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Preline | Internal Doors
35e13459-c1c3-4119-b240-7babb9a0541c |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Preline | First Fix Services
6ff1b259-c480-437b-8c30-903221ab2db5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Preline | External doors and windows
8ff2fc5e-93df-4b04-89aa-afe27f298239 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Preline | Insulation
6d40e3d4-74f6-4f9a-882b-f8ba98f51632 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Preline | Passive fire/Approval to line
81faaa09-08d1-4ecb-9072-a7f006a74871 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Post-line
ca8039ae-e998-48b2-a29e-f01dc0f929f7 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Post-line | Lining
c04014a0-46ac-438c-93f0-fc4c465f1c02 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Post-line | Stopping
a709c912-ad39-409b-911c-498630d8b153 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Post-line | Finishing lines
6968ecdc-cef3-4f88-a521-b072fc72c84e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Post-line | Flooring
b86dec50-28d2-4234-8c40-60cbc55086c3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Post-line | Painting
bf969ac2-41b7-4b51-a20f-f5143a59a720 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Post-line | Second Fix Services
2df24e8f-24d2-48d1-a600-d9666f546f5c |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Post-line | Fire Door
0f3c5aa5-20ee-4de4-8418-266b1ed94f44 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Finishing
41aa0395-a83a-4318-901d-3906bddb7465 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Finishing | Flooring
906fbb0e-0710-4f37-b847-8a72c3d502ba |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Finishing | Exterior
8bedc713-8d51-415b-b431-7342953c93e2 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Finishing | Lounge/Dining Area
8869a936-101d-4545-bd60-5630412de659 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Finishing | Kitchen
13b45cea-06a7-4a47-9e3d-f3d5978264ea |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Finishing | Bedroom
9aacb72b-231e-46ae-9dd0-6c71ea68d54e |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Finishing | Bathroom
4cd84106-6ed7-411c-863c-30d6b0756df0 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Finishing | Ensuite
609618cb-2861-447d-8192-f5aa0cb202fd |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Finishing | Laundry
d1914105-dc13-40ab-8b85-070f18036085 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Finishing | Hallway
62827a19-af97-40f4-9f87-fc1f46a3a59e |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Finishing | Toilet / WC
02e662c3-c30a-4323-b745-b09a4fd6b1d0 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Finishing | Client extras
1f815af8-b17e-4aea-8684-bd43de60e896 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B93 | Finishing | Final check before locking the door
67705975-af39-4859-9246-7b4e3ded67b2 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94
cf2a599a-ba6f-4d59-9e99-ef86c22a5961 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Preline
e3487230-f37a-42af-9d8b-ecfd821fa110 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Preline | Timber Framing
ccf81755-be8d-404f-a312-cd66909bdba4 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Preline | Internal Strapping and Framing
4f444c33-df89-466d-a8af-85d9451c9e6a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Preline | Suspended Celing
af9afa33-1270-4e1f-9d85-b865236a32b6 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Preline | Internal Doors
f3f29edd-a8a9-4198-9b21-942edc9d7d1a |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Preline | First Fix Services
315f01c5-22c6-43a7-8e0f-9b32590e34f4 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Preline | External doors and windows
e5c073b4-b963-4d8b-be23-69b74a9883db |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Preline | Insulation
dd58d53e-be88-4d80-aba8-5a92f93d412e |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Preline | Passive fire/Approval to line
9d9ff1ef-8441-481d-a994-36b74cdb7dea |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Post-line
5cba0f84-f1f8-46f8-9e73-d793bd1d900a |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Post-line | Lining
4dddf1d3-ad08-4049-8c34-a4d743bf1aa6 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Post-line | Stopping
c717810b-3b11-4b4e-a0e3-e6dc484c9f53 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Post-line | Finishing lines
1a14ad5e-a781-4020-83a7-ff47dc53b230 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Post-line | Flooring
6a04d450-9ea2-44bc-8337-95c8977ad658 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Post-line | Painting
45876fc1-50b9-4225-be88-930f8e1f67a9 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Post-line | Second Fix Services
6fa1f214-a344-4b6f-9dfd-566e9a411c7c |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Post-line | Fire Door
8972185c-4841-4e67-a072-a3dd2387f3e1 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Finishing
1b417235-2674-485a-85ab-68ee29c2998b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Finishing | Flooring
b30db6e3-595c-407e-b6f1-9b4aa9d79041 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Finishing | Exterior
ed42d45b-167c-4037-b5e1-5ecf26390d82 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Finishing | Lounge/Dining Area
5f817b0e-467f-42dd-bcc7-7e460925670b |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Finishing | Kitchen
263a398e-fa2b-4fe9-8402-0c5e8568e99d |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Finishing | Bedroom
f8266d72-547f-4fa9-8d9b-f7707b139cac |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Finishing | Bathroom
bd5e09d5-84b1-4391-9a1a-2d42aa703055 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Finishing | Ensuite
9bbe6198-764a-4281-8c1b-7cd789eae85a |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Finishing | Laundry
35f6b120-13d7-4eb1-ac5b-4c823e067fdf |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Finishing | Hallway
a9205708-e4d3-4a71-b643-7d28cf38d479 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Finishing | Toilet / WC
17e7a320-ea34-4cbd-b002-acf7990962c9 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Finishing | Client extras
b92c3730-47f9-4110-927a-035da34c4c7f |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B94 | Finishing | Final check before locking the door
a2122b4d-2673-4c4b-8e33-7da20fde73ae |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95
cb3b7f4a-3f92-42b7-bf9e-04cec1655b53 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Preline
d8423ab9-e345-47b9-88fa-fdc9f45da83f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Preline | Timber Framing
682b7fb2-f924-458e-9d86-c4138ea89b26 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Preline | Internal Strapping and Framing
0f8d44b1-c7f6-4626-8f23-e0f5c0d8f2a3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Preline | Suspended Celing
f3890b9e-baed-493c-ac25-88f676f49ee3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Preline | Internal Doors
de0153ea-0856-4593-8ff9-5d5f59609d30 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Preline | First Fix Services
b9cda16d-cf65-4923-8f04-9c7829f175a1 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Preline | External doors and windows
758fb6ed-dae3-4993-a7e2-9d03da4bb4ed |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Preline | Insulation
cb78f6c7-37b2-46b3-b14d-2e762b13dcc7 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Preline | Passive fire/Approval to line
9a1151c5-c01f-4f51-a361-e04f7b614012 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Post-line
b6bc60e2-251b-473d-843d-54c0db226b7b |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Post-line | Lining
50fe8c5e-46de-45fd-8e1a-3090f68f3530 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Post-line | Stopping
f5d3b5c6-13fa-461f-8d89-a18ab5fecbd4 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Post-line | Finishing lines
8b554d3a-0ed0-4124-85ba-238542cd72a4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Post-line | Flooring
bc856ae0-5819-4a65-b742-8e6ab7f4019b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Post-line | Painting
11fc3ee9-2f5c-4c1e-b2ce-9a87c6cdd7eb |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Post-line | Second Fix Services
9d46b834-5148-4089-a76c-2a808bb35db1 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Post-line | Fire Door
4491a711-ad52-477b-ba9d-32984a8466a5 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Finishing
4332938d-2bc3-4937-9864-aed51049acba |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Finishing | Flooring
9b8eab46-47f7-43fc-9e5c-b5957c637afe |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Finishing | Exterior
fb6527dc-40ba-45bd-af3f-82a1961dd195 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Finishing | Lounge/Dining Area
8ab6f7df-5e66-4ac9-8ffa-4f85d52829e3 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Finishing | Kitchen
b9db5ca4-81dc-49a5-8382-8fcc126728aa |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Finishing | Bedroom
14452c9e-ef47-4e31-985d-803fa447fbbd |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Finishing | Bathroom
d100bee2-f9a9-4bb0-9a56-f56c64dad64a |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Finishing | Ensuite
d2b5ed4c-ff1e-4eb6-bf40-098e11784b63 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Finishing | Laundry
77b069f1-1978-45c7-bf7e-ee9620bc0353 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Finishing | Hallway
6e89b541-7258-4025-ad24-23a4a9b5b71e |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Finishing | Toilet / WC
0dfd1a8b-b31c-4621-9f81-923014f13833 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Finishing | Client extras
e5f64f45-e3ad-4aaf-b660-0952844c0611 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B95 | Finishing | Final check before locking the door
1c26edc9-5b23-42af-97bb-348d11e0afe6 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96
4df2d34b-e8bf-4ce4-87b7-c19c7079ea42 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Preline
453fc743-df8a-478f-a3e1-a58c307d1fa1 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Preline | Timber Framing
30c1d5a7-b495-43e7-8938-64687c96d718 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Preline | Internal Strapping and Framing
b18cb65a-0851-4598-bdfd-051134ad811c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Preline | Suspended Celing
013ff21f-0a30-40bb-bd2c-e71788e0b35a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Preline | Internal Doors
98fec7cb-e57d-4e64-8325-845af82cd3f0 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Preline | First Fix Services
7cedd9d2-d857-4907-bc6d-da1a4b01f8d7 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Preline | External doors and windows
55b81945-eb82-4f6e-8544-6db58e1faeb3 |  | checklist-flat | work-in-progress | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Preline | Insulation
4370e50c-65e9-4148-98f7-088b0433fddf |  | checklist-flat | not-started | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Preline | Passive fire/Approval to line
3c8b7517-31d5-4209-b8aa-a0601c35fd83 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Post-line
d0de1f17-c4de-4d73-bc1a-919e43685005 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Post-line | Lining
a5b97763-e606-458a-b4f7-f81283cdeb1b |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Post-line | Stopping
4ea89b83-0a4a-488e-a936-965de06ef753 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Post-line | Finishing lines
5f8a6523-8a0e-41a0-bad8-a5ea5715c08b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Post-line | Flooring
e3024835-9246-4fa8-9360-a4914dfa4e59 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Post-line | Painting
5ecdca9a-fdb7-499b-ab8a-53b7ae5f5fc7 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Post-line | Second Fix Services
92df5cc4-77b3-4fa7-a1ef-50ce52371c96 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Post-line | Fire Door
5b3b04d5-910b-4b6a-a77e-25df399a74f0 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Finishing
beb46b1b-41ed-47b6-ab74-3ec14a82e1e5 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Finishing | Flooring
4c0958ae-3c77-4a8a-8e09-cd3edf8cd1a5 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Finishing | Exterior
0e812fbf-c5f0-4b09-9761-d3bb545ed68b |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Finishing | Lounge/Dining Area
4dc178c3-7745-4e3f-b614-f4b6c607a3fc |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Finishing | Kitchen
adaa331b-9b9b-423b-9505-8709e72b4752 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Finishing | Bedroom
efce2962-e488-4462-8277-25fa947fd464 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Finishing | Bathroom
cdc75469-6e0a-4d6c-9212-cdeb89274271 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Finishing | Ensuite
166e4799-c696-4eee-9d79-fa45f3808f96 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Finishing | Laundry
ae6e15fa-4559-4582-a818-f452b364ac3a |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Finishing | Hallway
695b458d-4e39-4361-83ca-93aca1915bc3 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Finishing | Toilet / WC
016cfa53-0de6-4935-abfd-14bb4604ecd9 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Finishing | Client extras
a531c7f7-6f3e-4c00-bd45-db51c1b4a6d4 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B96 | Finishing | Final check before locking the door
766bde2c-ddf8-4d1f-8f01-f2aa1b6bdf00 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97
81734ae5-bf8c-486b-bc39-ac8a897acf1b |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Preline
e614f5ac-3eb8-4854-8c72-0784c1652dce |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Preline | Timber Framing
581f0567-b62e-43a1-8b50-8fb062126807 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Preline | Internal Strapping and Framing
65e33129-52f6-4781-bfd8-fade1165f9d2 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Preline | Suspended Celing
6754aa24-5079-40f9-93cb-5d1f174e035e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Preline | Internal Doors
132a640c-2764-42f8-86d5-3894263a4302 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Preline | First Fix Services
b742195e-f8af-474a-9e56-80458f27ba9d |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Preline | External doors and windows
771d4c98-0bce-4297-a527-5b2031f74858 |  | checklist-flat | work-in-progress | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Preline | Insulation
f5fa7fea-62c8-4eee-b354-c4548eb151bb |  | checklist-flat | not-started | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Preline | Passive fire/Approval to line
c4b8c4df-dab1-44f1-b0a2-37ef1df60737 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Post-line
cd14ec2b-d84d-4e68-8f53-bb432dfeb9ec |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Post-line | Lining
8d87389d-84e2-42eb-a52c-f3a4c0abffba |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Post-line | Stopping
54eadffc-1847-497f-a459-136632482739 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Post-line | Finishing lines
c3fa1327-d1d0-4635-b49f-f529488532fd |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Post-line | Flooring
5cc4955e-3f38-407d-9af9-5ced4d40473b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Post-line | Painting
a13ee7f3-2d3c-4f5e-86c2-2e8177bae1cc |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Post-line | Second Fix Services
f2c75355-81a9-48ba-92df-1973fae7ff1d |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Post-line | Fire Door
36af6e3b-306a-4cc0-bfb6-16386b0e4f4c |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Finishing
9d0e5d64-0a1d-43cf-8021-23efbfdb5486 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Finishing | Flooring
cecd514f-a53f-4fa2-9eb7-3ee1a80ee1b8 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Finishing | Exterior
d10ccc24-042c-4015-a28f-6b9c95febc9e |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Finishing | Lounge/Dining Area
36fb5306-34ca-47d5-a58d-97f24bcdeec6 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Finishing | Kitchen
7eb5bf24-cd66-44c0-9359-68347de2fb28 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Finishing | Bedroom
bb079d59-c556-4e56-b3de-a9f8cd14bf5d |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Finishing | Bathroom
f5b62500-8400-4186-b711-925ca8e63cc6 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Finishing | Ensuite
b42e067c-439f-47b5-8bbd-d5e9837727bc |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Finishing | Laundry
86b093e9-c829-473b-9dba-e5d0cfcc2b5d |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Finishing | Hallway
2daf664c-914c-42cb-b461-ee013176aaf4 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Finishing | Toilet / WC
d285cea1-f42b-40f1-8e0b-a890aa6578bf |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Finishing | Client extras
9f8599d5-9a33-4856-b28e-21a921e98352 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B97 | Finishing | Final check before locking the door
6f76d48f-cf03-4a59-ba9a-51037f004c59 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98
900daa65-b45a-439e-b346-26c806b96be3 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Preline
83595c26-923d-4789-9895-c1418cda9b66 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Preline | Timber Framing
6ab2dac8-382c-4ae3-bacf-bb3845c08cb1 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Preline | Internal Strapping and Framing
6e940299-3fa9-4a94-bfc9-e39f11b36054 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Preline | Suspended Celing
db67dafd-318c-4188-b5d3-e3e7ae9a5ebc |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Preline | Internal Doors
c76a2087-86a9-47dd-ba7b-65c47ea35594 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Preline | First Fix Services
a940dae7-7a99-4f7a-bbbe-a8890227a3e5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Preline | External doors and windows
a98ecf63-9e3d-4156-8fe4-78905dc412a3 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Preline | Insulation
52b4665e-b910-4b7d-b5c7-ddb099e3fb12 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Preline | Passive fire/Approval to line
ffa5a227-a443-42f4-9cbe-9ee0221a542d |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Post-line
b809e170-34df-4dc5-9b53-b957b5aae6d5 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Post-line | Lining
19552670-b687-4846-a4e7-037427f31861 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Post-line | Stopping
8b5269b2-f023-48a9-a38e-5f27ef0d0443 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Post-line | Finishing lines
d1aaf017-5277-476e-826d-0d873d132300 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Post-line | Flooring
f6965580-04d4-431b-94c6-5f9ecb0ff304 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Post-line | Painting
501ae4b0-306d-47b1-b22f-2d9c2faf7037 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Post-line | Second Fix Services
e41a026a-4ab3-4d45-9125-38496b7e499d |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Post-line | Fire Door
51c9a7bf-ddbc-4539-a3d1-7b681de17252 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Finishing
bd12ffcc-b4dd-474a-a2a3-459112731760 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Finishing | Flooring
32134f2b-0869-478a-b3cf-4997ede1828a |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Finishing | Exterior
72aa26dc-6fc4-4df0-967e-6a559b72e7cf |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Finishing | Lounge/Dining Area
bcb49864-c1e2-42f8-97d7-720b1a07cfb4 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Finishing | Kitchen
220a7559-3ed1-477a-9a06-9a724e38021a |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Finishing | Bedroom
f9524444-594c-4c42-9650-bd48aab9d741 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Finishing | Bathroom
fa377711-abe3-4aa3-881a-91b89da0329e |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Finishing | Ensuite
5b033c66-956a-47a8-aa22-b7390ce8186d |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Finishing | Laundry
206b77a6-5146-4ae3-973f-177067728169 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Finishing | Hallway
568050d2-9cdc-495f-ab72-a52b0dfb5519 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Finishing | Toilet / WC
b1dd0f6f-dfd7-47da-90e7-1240a57127c9 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Finishing | Client extras
8a4adb87-2085-4dc0-b879-cfac920cfc28 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B98 | Finishing | Final check before locking the door
2e6d94c2-d545-400c-8808-12b80923ff09 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99
d8922cb3-5c22-46be-a3e7-5dcc3b78fded |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Preline
9ec343e3-d806-4df1-a316-788243c4196e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Preline | Timber Framing
15060dc1-3544-414d-8bd7-7f13f39319c2 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Preline | Internal Strapping and Framing
593d5e13-1054-4ae5-b3cb-7a210d9a2e29 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Preline | Suspended Celing
e30abe8e-bdf6-4eca-ac5a-2010be86aecb |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Preline | Internal Doors
182364ae-d835-4333-9386-7cf73eec9d27 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Preline | First Fix Services
b89aeab4-2d5a-43b8-8e35-a30462d2cd37 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Preline | External doors and windows
390eba50-3f9d-4868-972a-e473f72aac4a |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Preline | Insulation
2b4c2d90-e78f-4d00-bda3-a8767ba9fe2a |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Preline | Passive fire/Approval to line
0b811c40-55ef-4c7e-b2c2-d929f1352c4a |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Post-line
3edb8db7-eaf9-4e5e-8f41-c533577984c9 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Post-line | Lining
b87097c1-b3d1-4abe-b56f-a69c9105c08e |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Post-line | Stopping
e7854633-8592-4b0e-9b30-e98df6ffffcb |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Post-line | Finishing lines
ac8af975-d6f2-4c28-8d3b-49d7b7181060 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Post-line | Flooring
5704cbee-b9b5-437f-823e-7820bfbe5ca4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Post-line | Painting
de74fb44-782b-45a2-9d56-c32211bc7c94 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Post-line | Second Fix Services
7bf1f57c-0d6e-4ca0-8d49-13b0ff06384d |  | checklist-flat | not-started | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Post-line | Fire Door
d6a4add8-0031-4442-bc6c-65c1aaa771c8 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Finishing
f3b95974-5600-4db3-ba06-d176a9109e41 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Finishing | Flooring
2a5d9d75-541f-42a6-8277-2927ada490ac |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Finishing | Exterior
d812e7bf-3045-413f-b493-924d98f2d3a5 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Finishing | Lounge/Dining Area
1b5acedf-32ef-4bf9-8e1f-a20c5c62dbcc |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Finishing | Kitchen
91fb80ee-7909-4d21-b0b8-91961d1bab70 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Finishing | Bedroom
13fa544b-bf2a-4374-82d9-7fb54470a0f0 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Finishing | Bathroom
edbde984-51e8-4efd-abb2-89f497e09a48 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Finishing | Ensuite
b493bc3b-e215-4410-98f5-f04a1c270821 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Finishing | Laundry
5c5640cd-e663-4e80-b4dd-9761a402aaea |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Finishing | Hallway
f8dbbc12-61bc-4126-a357-41d3c4897915 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Finishing | Toilet / WC
99cd6bdf-f14e-461f-9c3f-da5593fcad3c |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Finishing | Client extras
e4664fc4-307f-47f8-9764-37c765ec7d44 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B99 | Finishing | Final check before locking the door
ae745637-951d-40dc-b464-e811f4f52292 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100
cc7a37e3-c573-42d7-b4fd-f10dd38df718 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Preline
c7a2aa8a-fc4a-43f1-b8cc-e028564386c2 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Preline | Timber Framing
01fdecc7-7cc1-4352-9185-6f18391c49b1 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Preline | Internal Strapping and Framing
f6f5161e-d286-4fa7-9eac-e6454b2f65e3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Preline | Suspended Celing
0d326e9d-f1f6-45aa-8c46-080b17629f45 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Preline | Internal Doors
c55f2253-91ce-47ea-b533-429dcad5eb45 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Preline | First Fix Services
b78d47ae-517f-4305-b757-f370d0f16e0f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Preline | External doors and windows
1703b160-be3a-407e-9e26-0ee074069885 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Preline | Insulation
e61f00f3-1a90-4928-a299-3398f4211d20 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Preline | Passive fire/Approval to line
58465c7c-382d-4eed-af21-caaa22596086 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Post-line
10d6b206-6911-49ba-87aa-fb6fb92cbed6 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Post-line | Lining
7341be71-d639-469e-b792-61b7550d0bb0 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Post-line | Stopping
a0f2f125-b122-4ff4-8c46-9afa265a6901 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Post-line | Finishing lines
521ee0dd-1989-47ae-a6e5-e2e4509f285d |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Post-line | Flooring
23de1398-e946-429f-9033-61bc6e5184cc |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Post-line | Painting
5f00fc2d-e878-43f5-a813-43e363aad5f8 |  | checklist-sectioned | pass | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Post-line | Second Fix Services
3be163cc-e16b-48ac-99eb-e2799ba18bf0 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Post-line | Fire Door
1a735628-994d-4e42-9b36-dc73c6fffcd9 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Finishing
68f0059a-119d-486f-b99f-3e4e285b29f2 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Finishing | Flooring
bab168b3-ac37-4c72-8aeb-fd58d385404c |  | checklist-flat | not-applicable | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Finishing | Exterior
3968c0c7-6c0f-4124-a725-8060b6b8b725 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Finishing | Lounge/Dining Area
2552dbc9-4701-4fd1-b425-7fa467d523d1 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Finishing | Kitchen
468d196c-e664-4792-a5ce-c9cc77f2d527 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Finishing | Bedroom
c2331f71-350b-4f31-b7a9-40508bce5a3e |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Finishing | Bathroom
23fbf80a-358c-4fd0-b289-b36d52685e33 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Finishing | Ensuite
cd98f10a-b9da-4572-8ee0-f7609a7ef2a6 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Finishing | Laundry
63378fb7-8c41-4392-b77e-f1f807ed241a |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Finishing | Hallway
d46c41ef-d105-43ae-bb1c-cd5dd7b4815c |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Finishing | Toilet / WC
405914f8-750c-423e-a554-e3aa3c63eabb |  | checklist-flat | not-applicable | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Finishing | Client extras
9a2ea0cc-7299-42ff-8902-bd0a1f02ce3f |  | checklist-flat | pass | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B100 | Finishing | Final check before locking the door
3b77adfb-8dd2-4d89-a372-cdc58958494b |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101
63e8aa0f-aa97-46ba-bba7-85d654b37a46 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Preline
bc501b03-22db-4f8b-b08c-7f3922f79512 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Preline | Timber Framing
465b0693-e285-4a22-9de1-4064a09f74a9 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Preline | Internal Strapping and Framing
3cac307a-ba99-4180-a50f-83057b303328 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Preline | Suspended Celing
0813210f-7af0-4f42-98d4-6191588ca467 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Preline | Internal Doors
3ef9789e-8218-4eae-8c77-5db3a34832d4 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Preline | First Fix Services
e6cb7113-df3c-4c4d-8181-7655af13a163 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Preline | External doors and windows
4aef0ac7-a349-4e68-b92b-5267e2fdfa1b |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Preline | Insulation
b54e0b3c-a1a9-4ee9-93f5-96436f3cfb04 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Preline | Passive fire/Approval to line
5b743f37-d34a-427c-9f7e-2bcac76aa636 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Post-line
f5158456-4257-4e0d-88c6-5f686503849b |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Post-line | Lining
a0547ed5-e186-4827-9b4e-bc2dc4998d43 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Post-line | Stopping
569c762e-ad0c-4283-8194-151fd28d5520 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Post-line | Finishing lines
7d5bfda0-4fc5-4da5-ac02-273e80b1f3e0 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Post-line | Flooring
b7258845-d908-4832-b76c-798063b6ea4b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Post-line | Painting
9d5c0bd0-8f31-49e9-985b-bedfaff95602 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Post-line | Second Fix Services
0124fe49-4097-4d60-913e-85c85e50c2c0 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Post-line | Fire Door
3e05efa5-0733-4e8f-9902-96b52d8c126d |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Finishing
817cb148-cc53-4de3-94d6-c1033d0322c2 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Finishing | Flooring
8c06357b-0e44-4935-935c-8f7d357b884f |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Finishing | Exterior
14d64c0c-9724-48ae-b2ae-104822df42a7 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Finishing | Lounge/Dining Area
553c12a0-ccc1-40b4-b269-1ae8ab2008fd |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Finishing | Kitchen
ac7b5cf3-a65c-4cb4-b1d8-e54b156e6507 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Finishing | Bedroom
0bcf8d7a-5dbe-4ff6-981d-71910efa530c |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Finishing | Bathroom
3a3d0df8-241a-4be1-b5f6-1a94f8255df6 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Finishing | Ensuite
32f7e470-c7c7-4e84-bbac-482e0af9e748 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Finishing | Laundry
f36a01be-f66f-4d92-b325-8fb811289c69 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Finishing | Hallway
014a0b37-ce9c-4e3d-a5d1-82ef01fb828e |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Finishing | Toilet / WC
6564e5b0-ce31-413e-8aec-38eb92251597 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Finishing | Client extras
dac7ff35-0501-441b-aea0-bd703c60f911 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B101 | Finishing | Final check before locking the door
20c01665-5355-4d8c-9c26-38b22285df84 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102
58953bb4-847a-4a81-85f6-a01a14843ca1 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Preline
7edf3052-1ad5-4e50-bab2-6d6246bbcc16 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Preline | Timber Framing
88602c0b-668f-4d7e-99dc-fecedcdd1aa0 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Preline | Internal Strapping and Framing
b20c75bd-f68e-48c3-8540-25a6da466332 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Preline | Suspended Celing
54964b2d-15fa-4af5-919a-9b559c3a82ca |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Preline | Internal Doors
bd2132e1-18a3-46c7-8787-07bbe9671043 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Preline | First Fix Services
1554840f-b11e-42f5-b889-bc58fcab709a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Preline | External doors and windows
5b4a508f-dfc1-4d16-bfb9-047751080efa |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Preline | Insulation
720e7a78-d68b-42aa-9433-55b027e93d96 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Preline | Passive fire/Approval to line
1569e07d-6a18-40a3-879c-38004d9ff143 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Post-line
e08068ff-3f90-473f-a2a6-88fa5348ae0b |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Post-line | Lining
2dba28e2-1afe-4fa1-886b-6664ea3e3f36 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Post-line | Stopping
eec2703b-170d-4a78-ab1d-20050f2fa0ec |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Post-line | Finishing lines
0bd7f704-12c8-48ee-8d98-3b529c045660 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Post-line | Flooring
939e3458-b4d9-4be4-915e-6c909dbc7bd5 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Post-line | Painting
8fbee065-fdc2-4b83-ab30-1c56cb048b49 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Post-line | Second Fix Services
91f92c15-1c61-4f08-a35c-ad6ba115849f |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Post-line | Fire Door
bc0434af-4e86-4f6d-bd0b-e20c6e7050b0 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Finishing
f6fbb436-4840-4fa5-92b9-9769279a4272 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Finishing | Flooring
927a6ede-9d36-4095-bc64-696efb6da6a5 |  | checklist-flat | fail | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Finishing | Exterior
8c6f64b6-f4a2-4f72-b0cf-4075d98381e6 |  | checklist-flat | fail | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Finishing | Lounge/Dining Area
40a7ad6d-7fa7-425a-b362-33a11d7a6d09 |  | checklist-flat | fail | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Finishing | Kitchen
63c4535b-856b-404d-add4-6fafc829683b |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Finishing | Bedroom
f396632c-1f99-4ec0-9a04-1a7bffd7a0b5 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Finishing | Bathroom
1682912e-83ab-45f7-a91d-03f3a3668101 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Finishing | Ensuite
27c295ed-8158-4850-bba8-a6bf51101a71 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Finishing | Laundry
f9c22861-e46c-4a32-919c-0e3dadb308af |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Finishing | Hallway
fbe93d19-8de7-4d47-b4c8-6eb5fd6813b3 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Finishing | Toilet / WC
5d509c3a-3cdc-4ff5-a81a-ac92e31ea964 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Finishing | Client extras
3968d14f-dfe7-4b25-ba4c-408c0dbeb1f2 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B102 | Finishing | Final check before locking the door
87de0cc2-303d-4993-ab5a-417edfc1111b |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103
10280ab3-ef5e-4c14-b257-80a59cc4b7c3 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Preline
1f65ec5d-3d0b-4131-be8c-99bdedb71237 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Preline | Timber Framing
29bec7a4-65f4-43b2-920f-f754fd29dfd2 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Preline | Internal Strapping and Framing
54e6eaa5-7a7a-4b6f-bcb1-22e00b9758df |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Preline | Suspended Celing
06b755c6-cae6-4c33-ba53-78cf2c5e73fe |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Preline | Internal Doors
95c1247e-512d-43f8-a35d-132738ccd44a |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Preline | First Fix Services
76949d41-0a0a-4285-8189-40fcf80360cd |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Preline | External doors and windows
34b0b4b4-56a2-49d8-9b74-5fd02455b397 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Preline | Insulation
dc7a3e00-5232-4984-9312-d714d432a07d |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Preline | Passive fire/Approval to line
791eb561-d75a-44ee-a8d9-51846d38dec4 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Post-line
4f0ddc6d-7a3b-449c-a96c-b3c08b0f5445 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Post-line | Lining
0206c4b5-7f49-49a5-8c7c-c72fa19a6446 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Post-line | Stopping
9b904726-0d8e-4e5d-aef9-9f9181e5d32b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Post-line | Finishing lines
3cf909a0-fe42-4611-a02a-acf53907f039 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Post-line | Flooring
f1f1d8fa-5fbf-402e-becc-55525ee701f5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Post-line | Painting
12a6e956-54bf-4bcb-a22d-ec71defc8744 |  | checklist-sectioned | pass | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Post-line | Second Fix Services
c8acb620-4f04-4b53-bbcd-d0d00b45f7ad |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Post-line | Fire Door
d43e3b12-19f6-4c63-9bc2-76cbb8360aa7 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Finishing
26cf9289-d7dd-44c1-9819-5747060eedfb |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Finishing | Flooring
8e3e4080-5a9d-4abe-b9d2-075ed2f27731 |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Finishing | Exterior
201ff988-5277-4bc5-a54b-c680214c3ce0 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Finishing | Lounge/Dining Area
964c2c0a-6ccb-4cdd-b016-0ac3409fd611 |  | checklist-flat | work-in-progress | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Finishing | Kitchen
6e04bcc7-af87-4148-b4a7-8bf023be9ab3 |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Finishing | Bedroom
7e95cea8-d029-4adc-9e5f-663f8359ebd2 |  | checklist-flat | work-in-progress | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Finishing | Bathroom
6cbf4ff6-6e1f-4fd7-a74d-bb3941756787 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Finishing | Ensuite
8c3f8bff-dc0b-4ff2-9c12-a2b2d3411c47 |  | checklist-flat | work-in-progress | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Finishing | Laundry
cfbd9eef-9973-4afa-a80a-824344d05dab |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Finishing | Hallway
6a6fde9e-d274-40cc-a7b7-2785bd0949c3 |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Finishing | Toilet / WC
b5b0d65d-1daa-4915-9c3b-a01e25f4a4d1 |  | checklist-flat | not-applicable | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Finishing | Client extras
9a3fd8ad-ed84-435e-9987-a6d27dbcf5e0 |  | checklist-flat | work-in-progress | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B103 | Finishing | Final check before locking the door
db98dc57-8509-44b1-b02a-1d6bb8850d4f |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104
9a617c4b-e4d9-4eda-b8f9-c61fbfa82424 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Preline
0aaf7d27-884e-4f8a-af56-b958a557df27 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Preline | Timber Framing
4a3e77e2-3129-4cc0-8fd5-04a6e0464f54 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Preline | Internal Strapping and Framing
57fe0511-86c9-487f-a00e-9b194c351c5f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Preline | Suspended Celing
26d30661-7da2-42fd-bdb7-d841dc826a53 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Preline | Internal Doors
3473a7fb-dfda-4136-9d32-6f46c0946e71 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Preline | First Fix Services
ea896d7d-7b32-4ebb-81fa-154b91f9f71e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Preline | External doors and windows
804234e4-cec7-46d6-9dfe-7ff9f3f068c5 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Preline | Insulation
7c5b2acb-6d53-45d0-9661-6aa55538f20b |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Preline | Passive fire/Approval to line
bec0f511-da2b-43f5-8c82-c382a30e8cad |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Post-line
2757e96f-f566-42d8-ab01-6189d8031150 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Post-line | Lining
ffa2cb60-38dd-4da0-be87-2a85eb2d5d42 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Post-line | Stopping
d4055080-d0f7-4ff5-bfeb-f71d007461ef |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Post-line | Finishing lines
0203eabb-2251-4bac-930a-10b69b50d88a |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Post-line | Flooring
eec41898-4c82-4431-9385-0ac2a8f17349 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Post-line | Painting
aeda6055-647c-4f51-b7b3-f81c06c1e385 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Post-line | Second Fix Services
b9927a7e-d2d5-44b1-86d5-44e86dad94c6 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Post-line | Fire Door
33986a66-679b-482c-8a61-403e1a3bf7b8 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Finishing
e05cf335-f66d-4523-b848-6a619107b530 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Finishing | Flooring
2ef011e0-1c06-452a-8ead-1e7fb78ca0b3 |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Finishing | Exterior
b3f5a23e-42ab-4a78-82e3-28e3a3f1b40d |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Finishing | Lounge/Dining Area
8daa5c20-13d6-4cd7-bdb2-7e2e34227f34 |  | checklist-flat | work-in-progress | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Finishing | Kitchen
4084527a-18ec-4918-a152-fb6b6908abce |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Finishing | Bedroom
8a5d04cb-d156-45f8-954d-e82867513269 |  | checklist-flat | work-in-progress | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Finishing | Ensiute
80284e60-b679-4490-9018-89fef658a3d2 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Finishing | Toilet/WC
a617d27e-9c1f-4c2d-a229-3a332ed8375e |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Finishing | Laundry
d3d12e0c-267b-4d9a-ada0-2b2153a3b0db |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Finishing | Hallway
8f3d3a57-0c3c-4267-ac10-bd29fd75b01e |  | checklist-flat | work-in-progress | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Finishing | Bathroom
401b935d-0338-4446-8dfe-3a8b07ed6b22 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Finishing | Client extras
8df892e4-2881-4ceb-acb0-ed8300b8f8c4 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B104 | Finishing | Final check before locking the door
c88d15f6-f0d3-4092-91c6-1a9b7748a70b |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105
19d8e9ef-201d-4c76-9c41-c008a9085036 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Preline
1a4da0b7-9325-47c1-8c63-fdf694059567 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Preline | Timber Framing
cd87b4f1-a8f1-411d-bfdf-7be8852a9207 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Preline | Internal Strapping and Framing
e35bd80b-dd9f-4a8c-97f1-cd18156a76aa |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Preline | Suspended Celing
ce889d85-e890-4a68-8554-096789301dd8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Preline | Internal Doors
685b9adb-f42f-41c4-ad15-4bb5cd5a5481 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Preline | First Fix Services
0672e441-b233-47f2-9e32-7ca1f4cd3e5f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Preline | External doors and windows
57b58476-946d-4537-ad7d-e1bfa030d56c |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Preline | Insulation
20a14a2b-6793-44fb-b32c-097c45fce548 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Preline | Passive fire/Approval to line
25b0f4a0-965d-4797-a6f3-e51960ec307e |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Post-line
5d6d1d55-20c2-44aa-aa04-1ee48926141e |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Post-line | Lining
264d96a8-6a93-40dc-95b8-0491bdfc2fa1 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Post-line | Stopping
777972bd-df0e-4e19-b2ac-565e48b69aaa |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Post-line | Finishing lines
f3cca18c-0c75-4a84-b33b-c8c8029df6a3 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Post-line | Flooring
09f4d9f8-f25e-4773-b078-44bdd4434ed4 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Post-line | Painting
4f8331c2-8552-4876-bd63-70c535b67c1f |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Post-line | Second Fix Services
a1a11078-36c3-4249-b469-b20329f5d650 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Post-line | Fire Door
d4ddd598-c848-43e7-9b97-26620ef6552a |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Finishing
082176d4-17ef-4baf-ab56-4e0df6bf6b61 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Finishing | Flooring
ca8b83da-0b12-46ef-80fc-717cd2535425 |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Finishing | Exterior
74129939-659c-44ea-a897-2f8ecdc0d6c3 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Finishing | Lounge/Dining Area
eff0c3e3-f6eb-4226-8db0-90c72afb6d88 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Finishing | Kitchen
b38b00f4-0d86-4daa-91c6-a36a222dbdfb |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Finishing | Bedroom
bae0e388-6cf2-4a4d-b7a1-eb7a29cedbf4 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Finishing | Bathroom
15a794fb-3e47-4ba0-81ba-fc9c22312908 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Finishing | Ensuite
8124a86e-73d0-4f5e-a8af-c0177f8c71f9 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Finishing | Laundry
d4f84dbb-a294-41ca-af9e-7e135c2112b0 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Finishing | Hallway
ef01fdaf-d16c-4e8d-8dcb-4e9aabc87cd2 |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Finishing | Toilet / WC
bee20dec-14d1-4fb5-aa46-8c789599d770 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Finishing | Client extras
1834f1f9-a6d7-46f1-a02b-2597bd80a357 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B105 | Finishing | Final check before locking the door
76931a91-2004-44a2-a163-2d8b9488ca77 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106
fcfcde50-8d91-4b00-a98a-a8fcfe24def2 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Preline
42932f7e-1cdb-4e50-b2c9-28cc31b90bd5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Preline | Timber Framing
03508465-59ed-4f70-9c4b-0ca4d02f3c4e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Preline | Internal Strapping and Framing
6323d76e-9819-4490-bd4a-d6433f8e1be8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Preline | Suspended Celing
7a07897f-35f5-485c-a460-15e9048c33c0 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Preline | Internal Doors
53d8d67a-340d-40f9-8f3f-66324e782d72 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Preline | First Fix Services
75d0fc3a-9fc2-41f5-9748-bc26e6dea323 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Preline | External doors and windows
76a874ec-81c1-4a8b-aeb6-9e8079911ad6 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Preline | Insulation
9ac063f4-659c-42f1-a63b-2a0e825e4394 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Preline | Passive fire/Approval to line
5a01429d-3a92-4018-b395-1589fc1e98bc |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Post-line
ddd36a1f-0e03-43f8-99eb-80740574ea00 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Post-line | Lining
b1f5854d-5fd4-4276-be72-6c0388dd53bb |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Post-line | Stopping
849fce94-1cc4-4f9b-83be-41e5932b0a87 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Post-line | Finishing lines
937724ac-1882-42fa-a980-cb21216cfacb |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Post-line | Flooring
98b74ae9-48d4-4169-a664-08c02213991c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Post-line | Painting
8435286e-537d-4ffe-ac62-3242a339a7d2 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Post-line | Second Fix Services
2f9798ad-caaf-4e6e-8399-2cf4dedd0b20 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Post-line | Fire Door
537b2d7f-4537-4ec3-a885-a4c02fdd1959 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Finishing
764ca6d9-44b8-499a-b7a0-0125335be74a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Finishing | Flooring
2a3e358b-7728-4ebe-a6db-6e4c755d7f75 |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Finishing | Exterior
b0fc6943-a218-4a3b-872d-c1be705501cf |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Finishing | Lounge/Dining Area
e2b7777d-86f6-4ff2-91fe-92e0137889b9 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Finishing | Kitchen
f811742f-7907-4239-a42f-db5292f41896 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Finishing | Bedroom
622aab93-21c8-472b-bd74-e056194ed8d9 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Finishing | Bathroom
7e81f49c-d8d5-4446-8773-460fe23bcf5e |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Finishing | Ensuite
b0676fea-213f-4d73-b299-f09e81aa7f32 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Finishing | Laundry
ba8fbd5b-c90e-4b18-a227-d79dce6d6fc3 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Finishing | Hallway
620ae8d4-a20f-43c7-8315-0e9469269920 |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Finishing | Toilet / WC
0ab3eabd-3ac4-4ff1-b2c7-9a23e3cdecd6 |  | checklist-flat | not-applicable | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Finishing | Client extras
db5b117b-4a06-4b5c-939d-6743c25b8dab |  | checklist-flat | work-in-progress | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B106 | Finishing | Final check before locking the door
8fb42299-aed5-4029-ba4c-02a905fbb48b |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107
ba0e0e34-fdde-409d-9093-b6b9f18c8600 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Preline
b16ca413-29a1-4198-b0c8-8e7c78a49ada |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Preline | Timber Framing
fd04ee53-416e-4d9f-b1c5-9f7322370854 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Preline | Internal Strapping and Framing
13fba240-f647-4b23-a195-b68ebc31bf40 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Preline | Suspended Celing
9a780b40-53b5-4ee9-8bb1-eec7407dec70 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Preline | Internal Doors
e5fa8f51-76f4-4441-923d-d9274f5b3246 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Preline | First Fix Services
ab67803f-fc7f-44ba-a822-fd0fb234ad8b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Preline | External doors and windows
af811431-5b91-4bc5-91cb-71ad0114966e |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Preline | Insulation
b3ac136b-f088-4bda-8cce-24ff8fe5e799 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Preline | Passive fire/Approval to line
4e5b01ef-6615-42c5-bab9-2e07115553d3 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Post-line
c1632d39-e098-44ed-a9d5-1879953a96d1 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Post-line | Lining
317ca7bc-5d36-443a-8819-e2178ff579c7 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Post-line | Stopping
9dc2b0e6-5a44-4dd4-af1f-c73feea9ddef |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Post-line | Finishing lines
292c53b5-e14e-4391-9f7a-3fdcd7fe8f79 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Post-line | Flooring
c88d78ff-1bbc-4e22-9f3b-68c7148c0124 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Post-line | Painting
be46cba4-e133-45e2-81a0-2e7cafd05ec6 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Post-line | Second Fix Services
7b8b30e0-029a-400c-8877-92e5a1463c5f |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Post-line | Fire Door
ebda9b1e-7962-4a99-b74d-f6321f1e3e33 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Finishing
1a8a6393-8437-44d2-9f74-bbb2c6a38aa2 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Finishing | Flooring
90caa330-e09e-487d-8e70-88aecdff7b54 |  | checklist-flat | fail | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Finishing | Exterior
5b8d31e7-2846-4e00-93c0-4c7ededd8832 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Finishing | Lounge/Dining Area
7a03a5f2-b730-4308-9c78-60c745233ac9 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Finishing | Kitchen
03c38e41-4dbc-4690-91c8-7372d421ff1b |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Finishing | Bedroom
1bac3749-ad8d-46ee-9ca6-5fa51a5dee24 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Finishing | Bathroom
687663a1-aef8-4c76-9103-4786252ff3ff |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Finishing | Ensuite
d0bbc4d4-621e-4620-a300-3486f1176ccb |  | checklist-flat | work-in-progress | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Finishing | Laundry
a7bfdf84-1041-480e-88e8-573d2610f167 |  | checklist-flat | work-in-progress | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Finishing | Hallway
825d055c-33e6-4b8e-925c-a6905ed33c21 |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Finishing | Toilet / WC
d94d534f-570e-4929-af3b-b01aaf223d92 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Finishing | Client extras
d2ff637c-2eb1-4215-a937-8646f2ca286a |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B107 | Finishing | Final check before locking the door
bb54643a-f21c-434e-90ee-d0e4875868d3 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108
e34dc3db-735c-4a52-898d-9c9f444b9b28 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Preline
d70a394a-a1cb-40cf-9e83-bfbaaeb7df85 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Preline | Timber Framing
e82c3fb0-762d-40d7-8b66-934dab4fd17c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Preline | Internal Strapping and Framing
4d751414-ed06-4544-89c9-144a76d0a324 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Preline | Suspended Celing
c6d09c05-632c-4aaa-bc45-b4d390732fb2 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Preline | Internal Doors
5e119b91-b0fe-4bc4-93b9-efebd0d71550 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Preline | First Fix Services
a75f40f6-4c06-493f-a372-426d463e0b68 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Preline | External doors and windows
d9324cbf-e558-400d-afca-e0968cc3e080 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Preline | Insulation
3792ca54-28b5-4454-8e81-2233c94aa136 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Preline | Passive fire/Approval to line
3359cd98-63a7-49f4-8023-070af68f7112 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Post-line
2de4d502-4fb4-41fa-a2d5-a4db9be336f1 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Post-line | Lining
b03d4e12-e993-4909-a144-c227458657df |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Post-line | Stopping
83249854-7a39-443e-9b2c-e83e27dad6a0 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Post-line | Finishing lines
ebb53ba5-8448-4776-b2c2-082d992ec57b |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Post-line | Flooring
2aedc83f-cefb-4a9e-b4b8-b88b5ad399ba |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Post-line | Painting
600af041-9437-4a94-87fc-e5dce9b95391 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Post-line | Second Fix Services
56f202d2-7811-42d6-94cd-ae54fc13a2ef |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Post-line | Fire Door
449e9146-8b58-4373-8b61-3ac147aa9e1f |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Finishing
03216219-bcf8-4213-9ed7-d08888643d53 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Finishing | Flooring
180cd615-dbdf-4417-977b-829af76d1204 |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Finishing | Exterior
16c2748c-5374-477a-9416-70ed5520b196 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Finishing | Lounge/Dining Area
82d86804-8bf5-49d1-a3a9-3a58e3ac2387 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Finishing | Kitchen
dce93e3e-a7c0-459f-af3d-9b2c363b1dc8 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Finishing | Bedroom
700e8810-4d30-4b09-8242-4bfcdd339853 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Finishing | Ensuite
e1fc43a3-197d-4a48-a32d-bd2c9102dd27 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Finishing | Toilet / WC
3356d535-1a2c-4338-8230-450443580a02 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Finishing | Laundry
eb4054f7-fe71-4d6a-8b54-0c19b06a6041 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Finishing | Hallway
19c45d6c-c6de-40e4-b67c-fcffe5d215b2 |  | checklist-flat | work-in-progress | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Finishing | Bathroom
e49880e0-25d4-49a5-afbf-7a5b2ef9f43b |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Finishing | Client extras
81f96a0b-0b67-4a3a-9ac4-2a65ab525007 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B108 | Finishing | Final check before locking the door
9aabfee2-8079-45f6-ab9a-2b3b9a9e8b3e |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109
52223113-3f77-4555-b63e-064889efd600 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Preline
088bccb2-9a75-4172-abbf-e6db114dbc6e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Preline | Timber Framing
4ec0399c-072a-4c9a-a98b-52c1ede75d4f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Preline | Internal Strapping and Framing
822c5f25-756f-42a8-9667-e4e3cedee784 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Preline | Suspended Celing
37587bf1-c037-494d-837c-6ad573eb00fb |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Preline | Internal Doors
d3126c2a-f299-43fe-8068-50fc09ba7c0c |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Preline | First Fix Services
dccdc116-5001-43a8-92c7-4232a56b0d34 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Preline | External doors and windows
27f75775-5bbb-4ff2-9bdf-1a8c1137ae48 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Preline | Insulation
2fa0be4c-d159-4bfa-8931-864af84519f0 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Preline | Passive fire/Approval to line
f16b8ef3-a0b3-4384-8a6b-d861735614eb |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Post-line
ae619225-c945-44eb-8f5d-c49a1b348f83 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Post-line | Lining
68f4dd04-7c0a-487c-9bba-f10cddea1e3e |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Post-line | Stopping
0e69fc65-814a-460a-9a79-f622137feac3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Post-line | Finishing lines
430bf3e0-ed35-4b7a-9b3f-4a2a5a8e53cb |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Post-line | Flooring
a96c9480-f07b-43d6-9197-16dfd5cbac22 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Post-line | Painting
f44c567a-891d-4ead-b91e-86f34f1c1164 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Post-line | Second Fix Services
87d4ac23-9d58-499b-b441-b66e73462ba5 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Post-line | Fire Door
6ff71705-a45a-47fd-8f98-95d0a13cb23f |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Finishing
55b5208e-7730-4e26-88a9-4a2c6ae3fa79 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Finishing | Flooring
2d3fa3b4-297d-4fad-b0ea-0f6eb2f4d4f4 |  | checklist-flat | fail | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Finishing | Exterior
fc962667-345c-431f-90b6-6652638cf857 |  | checklist-flat | work-in-progress | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Finishing | Lounge/Dining Area
2f4e5b56-efbf-4f71-84af-b3756d4f64f2 |  | checklist-flat | fail | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Finishing | Kitchen
22a180f2-5d2e-45e0-ade8-cc6dfbeffde4 |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Finishing | Bedroom
eeddf3e8-24f8-49a3-af2d-4c691b69ca29 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Finishing | Bathroom
2ac44420-b1af-4d60-a32b-7d121720228c |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Finishing | Ensuite
05eaa693-9dea-47da-90e3-bb8f45f3709f |  | checklist-flat | work-in-progress | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Finishing | Laundry
4703205c-42cd-42d5-811e-1006fb3c076c |  | checklist-flat | work-in-progress | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Finishing | Hallway
a1367a63-3848-41e3-a00d-e20cda0d780e |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Finishing | Toilet / WC
85a617bb-17db-4967-b8fa-e6d342f3ab33 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Finishing | Client extras
d3d15970-bf90-4676-aecb-b4f297530d9e |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B109 | Finishing | Final check before locking the door
0747d9db-2775-4b59-9311-8f6d25c95846 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110
fc96a23b-763b-40a1-aaae-dce39f07fe6e |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Preline
5073581c-d07b-4ffe-97e9-afa25b96c738 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Preline | Timber Framing
2ecc1ee7-9463-47be-a183-66c7a3b7730a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Preline | Internal Strapping and Framing
88d1fddf-2d51-4e1a-8fa7-9da1b2e4ca27 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Preline | Suspended Celing
3595519b-2322-40ff-acd8-826f2cedeac9 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Preline | Internal Doors
29f2931f-63fa-4bb8-b258-d7b62f9bfd62 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Preline | First Fix Services
027fbb70-61c0-43e3-b378-871131056854 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Preline | External doors and windows
8b737f8c-95c2-42e0-a4b1-9f9d0ed6d78a |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Preline | Insulation
36847c71-9b02-4a3b-8daa-d051ede148dc |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Preline | Passive fire/Approval to line
d348da6d-3a2c-4154-8e62-9dc31919c9a5 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Post-line
cd93ef41-5193-4efb-a814-1b7b4f86ab91 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Post-line | Lining
d70aa3d4-3650-4308-9274-eadc0587d0c3 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Post-line | Stopping
b346e5a5-ea64-48c0-8915-276f53803ac3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Post-line | Finishing lines
c7a44b01-5a86-406f-8f6b-f60e117c2f75 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Post-line | Flooring
53cd93df-1a5c-4463-980b-cf562c3755a1 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Post-line | Painting
0a1729b1-f377-40a2-87a3-f90f05cec7d3 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Post-line | Second Fix Services
b3a6ca2d-7ed2-42dd-8053-e3ef9bdf5398 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Post-line | Fire Door
37d6b5d7-460a-4ec0-bc1e-a570695c2e56 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Finishing
52c29ec2-c627-4034-8c33-13fd5cef2529 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Finishing | Flooring
6a32abc1-6d17-4b27-844b-a4f01d55d799 |  | checklist-flat | work-in-progress | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Finishing | Exterior
e8c498f5-4c51-4f7d-8330-b9335d06737b |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Finishing | Lounge/Dining Area
a85be425-01bd-4d66-be05-c3395f65c88d |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Finishing | Kitchen
fc369c9e-a245-4561-be19-4f760e18b00c |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Finishing | Bedroom
c9ce7dd5-a9d8-4e23-8b3c-c4ff5a30d77e |  | checklist-flat | work-in-progress | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Finishing | Bathroom
a52cf410-ad73-4822-bc48-7b76d4c35d8b |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Finishing | Ensuite
6ce9f45e-c07c-4bdb-a4d1-4742f4546be4 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Finishing | Laundry
3599241d-5e49-4e05-81d2-ae38d120301f |  | checklist-flat | work-in-progress | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Finishing | Hallway
8ba613ec-1120-444c-82ec-911377c53f1f |  | checklist-flat | work-in-progress | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Finishing | Toilet / WC
d27ac1c9-773e-4a5a-aee8-66aa26dc0fd5 |  | checklist-flat | pass | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Finishing | Client extras
3eabc498-6f6d-424c-b219-136b4efd7e93 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B110 | Finishing | Final check before locking the door
ecef2826-af87-43f9-b8c5-9d94e0e14617 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111
911b9ec9-d3de-422a-b877-8ee49012f779 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Preline
83da02a1-7ecb-46a9-8249-4ed7f08126ad |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Preline | Timber Framing
d24e65c0-b63f-4b83-9532-419519acef2f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Preline | Internal Strapping and Framing
cb1926fd-fdb7-484a-926e-197b64f51d5a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Preline | Suspended Celing
c8970882-8068-46a5-ac9e-6c4fcc6ea3f4 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Preline | Internal Doors
1c0cb228-ccbf-4fbf-8794-e062178002c3 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Preline | First Fix Services
98214f4d-494c-4f95-99dc-c5ae182b34dd |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Preline | External doors and windows
4ed9814b-aeeb-4c8a-af00-b110d9f142d6 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Preline | Insulation
78fefd35-30cf-4c1e-8159-72c230f0dc8a |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Preline | Passive fire/Approval to line
f96f4105-6e38-492b-b780-dfe1ab42087f |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Post-line
f4276fa8-103f-48e4-bda2-981dd40a36b1 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Post-line | Lining
6aaa7baf-03e2-48cd-86c4-5e17e08e2e3a |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Post-line | Stopping
e6238c59-2e91-4979-8673-765a771f6ad9 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Post-line | Finishing lines
e617961c-221e-41b4-af53-e29c6b17237d |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Post-line | Flooring
1252fd15-d618-4f3a-b652-08e497791d15 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Post-line | Painting
95f683db-91fe-48e3-a897-7847a198b262 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Post-line | Second Fix Services
4920c294-90c6-4640-ab82-5f188c01e86c |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Post-line | Fire Door
a39aa9ee-1624-4268-b4c9-9ba5ae24b25b |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Finishing
275d0ee1-126f-42bc-9e57-f179b9fc50e9 |  | checklist-flat | fail | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Finishing | Flooring
194961ad-fa5a-48dc-9514-a6dc904e6f02 |  | checklist-flat | fail | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Finishing | Exterior
d1f4f005-0699-4b21-908f-5f16c4b5639e |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Finishing | Lounge/Dining Area
59ea7a5c-b488-4d0f-8c94-c81805735ef3 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Finishing | Kitchen
98164935-4346-4ea7-983e-6ae531744a08 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Finishing | Bedroom
e3e4bc36-dcea-4786-a2b4-1a5409ddf126 |  | checklist-flat | fail | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Finishing | Bathroom
86617e8e-14bb-48ce-9f25-95f6edd6fd48 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Finishing | Ensuite
437f194d-2136-4e0c-b6a2-9e0e311e3b69 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Finishing | Laundry
cf8323df-c621-4b6d-82f0-d26b79e31ea7 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Finishing | Hallway
5dce50aa-495f-4bcb-b387-187d40abddc1 |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Finishing | Toilet / WC
c634a5c3-c540-4f36-b10c-c58387330835 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Finishing | Client extras
40c5b261-6f99-49c5-90aa-4bb4174dacfc |  | checklist-flat | fail | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 2 | Residential Areas | Apartment B111 | Finishing | Final check before locking the door
90726b6f-fdb7-4b4c-b607-6df7adf112dc |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3
556fb3e0-b729-4bc2-ae9b-52ba69e262a9 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas
1ea02333-11cc-458c-9fb4-8af299045ea5 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors
21b1c3c2-e2fe-451a-94ba-6150df15b1b8 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Preline
dad8b2ab-5ef2-40ec-81d5-b776860cbd31 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Preline | Timber Framing
2cddd6ab-7e6d-4568-b75d-79ed1b9fcc25 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Preline | Internal Strapping and Framing
5fccb0f1-2efa-471f-bd2d-97426119b331 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Preline | Suspended Celing
00967b68-3bf8-45e6-b0b1-ae8c50a147a3 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Preline | Internal Doors
46580acc-e05e-4c8f-ab4b-0763e2a92147 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Preline | First Fix Services
9829f36b-3ad3-4eb2-9c71-2977f5662453 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Preline | External doors and windows
8fe0c53b-9ceb-411d-b00b-3d9d2d45745a |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Preline | Insulation
8b9ae23a-66c5-4797-ba79-310a05d2bb56 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Preline | Passive fire/Approval to line
6d3de206-12c8-4699-aa4f-7ca210ff72ba |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Post-line
d279efbd-fce7-464f-8da8-d55b5caec75a |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Post-line | Lining
d64188da-861c-4dbf-893c-7b0e1c3bbb5b |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Post-line | Stopping
cac53fc8-ed04-47c5-b14a-34a65dfa0fa4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Post-line | Finishing lines
c0d41612-96c5-40dc-8901-e58c931d32b7 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Post-line | Flooring
f72d27b5-ed83-4f4e-8523-9d97bba3f6da |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Post-line | Painting
c6e5d6d4-1e24-4ab7-9575-1e2d20a255f9 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Post-line | Second Fix Services
0a88963d-880e-4d7b-9be1-c412c216fc75 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Post-line | Fire Door
f9ee5ff9-fb44-4cbb-846e-15e4c24b6f02 |  | checklist-sectioned | not-started | efe9dd8861170a4f6c877309dd15ef71545349ef8eb7e2755d191ae9183ec15d | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Corridors | Finishing
b7a195be-80ee-4a98-92e6-b45bae8e97b0 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby
0bf6600e-df7c-4644-b2ec-c71fa2b5c8b3 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Preline
24336168-fbc1-43a5-b10c-abf2ee6785d3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Preline | Timber Framing
ee1fabe7-90bb-47a2-8b54-563f285e90ea |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Preline | Internal Strapping and Framing
4a39e91a-d207-492d-906c-043e7b392003 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Preline | Suspended Celing
16b3f117-0118-4926-91eb-e85ffa4a1ff4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Preline | Internal Doors
fadb8a3a-e040-4149-9489-449b02412b21 |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Preline | First Fix Services
2bbb723a-6bfe-4dc5-82fc-1bd0d88fdc44 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Preline | External doors and windows
07a67b6f-ed10-4634-acd3-bf95e3902c22 |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Preline | Insulation
ca3e52b0-421b-4900-8dda-8735411eb2c6 |  | checklist-flat | not-started | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Preline | Passive fire/Approval to line
7a25f65d-bb63-4cc7-9aba-745b83ae3dd9 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Post-line
3b4b715b-a805-4059-b3d4-6c95aa5327e7 |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Post-line | Lining
6ab9d875-cc2c-4f74-ade9-8981a49fe989 |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Post-line | Stopping
0d59b04a-7cca-4ed1-8a27-2e2fa566bb35 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Post-line | Finishing lines
3e4a4413-5548-4a53-a439-fac48a180599 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Post-line | Flooring
bf45f958-c4a0-4b35-aaaf-f48678ee7db3 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Post-line | Painting
620b28cc-be5a-4726-a936-8874ac8cfb32 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Post-line | Second Fix Services
c18d68a8-482a-4780-9474-fb92faae6842 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Post-line | Fire Door
92b811a8-7d95-40d8-9d0a-d5b9c606c751 |  | checklist-sectioned | not-started | efe9dd8861170a4f6c877309dd15ef71545349ef8eb7e2755d191ae9183ec15d | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Common Areas | Lobby | Finishing
cdf541e4-666d-4199-9cf1-60c8c756d7cc |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas
68142a17-5ee7-438a-832a-743d22e510c5 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A
d83edf21-8ec3-44bd-87b2-771dac68b846 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Preline
6d19fa08-de1a-4ae4-94b9-1cbf0cff5a60 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Preline | Timber Framing
09693afb-2d17-47fa-9c7e-33d95faa055b |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Preline | Internal Strapping and Framing
f60b8af3-a72c-48f4-948f-f1170691ff42 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Preline | Suspended Celing
7b186fc0-6200-470c-8c3e-0b7a6980c5aa |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Preline | Internal Doors
07c1128c-d050-4ac4-aff1-0035a11d8613 |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Preline | First Fix Services
d1b82022-4ed8-41ba-9e1b-5092b788dcbb |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Preline | External doors and windows
5c29c016-12ac-4420-99a4-2a0d13169e14 |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Preline | Insulation
f78a059c-2b41-476a-9188-c0da082c24d4 |  | checklist-flat | work-in-progress | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Preline | Passive fire/Approval to line
e290b2a1-616a-42df-a7a7-e85593ba040d |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Post-line
bda9da01-565f-4212-ba8c-5aafc6ae24b1 |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Post-line | Lining
e8bd72ee-b441-474e-b912-e37bb18000d0 |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Post-line | Stopping
861523f2-c0d6-4086-b9da-12c33afd4c29 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Post-line | Finishing lines
e24722a1-5de4-41ce-8a1e-ce9a68c22fac |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Post-line | Flooring
d9856553-8b61-4d0a-9cb3-ce91717155a3 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Post-line | Painting
82f76249-9c1e-48f0-976c-8ed9d6eee838 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Post-line | Second Fix Services
8a26372e-a58b-46de-82de-bf6b4ee92fb4 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 1 area A | Post-line | Fire Door
11e13eb3-2a2e-4f30-8e1e-ee7b75c6f455 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B
2ffd10f9-c279-40c4-ae9c-0361f593ad40 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Preline
4b2a321e-e129-4d1c-9d5c-f8119e585dd3 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Preline | Timber Framing
55e8d7d6-2035-4ca6-9f98-9c0e568bf13b |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Preline | Internal Strapping and Framing
fe8221ae-4b36-49e7-aa33-bf8c0ec0cc55 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Preline | Suspended Celing
85280e5d-1fa2-4f69-8303-9531e2f11773 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Preline | Internal Doors
44d4b8a9-9690-4e96-837c-ea1cf4b1d1d5 |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Preline | First Fix Services
bb6dd5d8-7ca2-4b4b-9b00-7827058e48f4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Preline | External doors and windows
ab64e9f2-74ff-4691-9f5e-4c2dc1515aee |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Preline | Insulation
e9ff80a7-99f4-47a2-9e40-b8b99ff6de54 |  | checklist-flat | not-started | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Preline | Passive fire/Approval to line
ddc4bca0-2f8b-4212-ac21-7a404b5a64f7 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Post-line
e684da9b-70be-4730-8869-ba1919308abe |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Post-line | Lining
1289dbdf-3eb2-4f27-80be-169fe0d6bd4a |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Post-line | Stopping
e0dcf34a-ed89-4eb9-b188-d1e3aa6561dc |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Post-line | Finishing lines
7914efe5-e34f-408f-91a1-f92b16386cfc |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Post-line | Flooring
4f9a9fec-22f9-44b6-904a-be0e95b81642 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Post-line | Painting
6ef13cba-f86f-407a-98ec-9fab618a0044 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Post-line | Second Fix Services
f5a5b14c-aa79-4901-9231-525bb4a14733 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Electrical 2 area B | Post-line | Fire Door
a092a9da-ec6b-42df-bd93-e6fda5d50f7b |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A
538ca657-3b44-43a4-ab78-50581b99fc4f |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Preline
e03b5abd-4a85-4998-b552-843252f8440a |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Preline | Timber Framing
c38baf59-9e3d-4e76-9323-c69c85551b27 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Preline | Internal Strapping and Framing
58cccff9-6c03-4df9-8d48-08f59e6f2da1 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Preline | Suspended Celing
a2919aa3-7b5d-4919-895a-96abfc409c87 |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Preline | Internal Doors
bce608ed-613f-4b85-ae39-f58c6b96e2a6 |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Preline | First Fix Services
edb57230-6679-4841-ae2c-07321f0ca0be |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Preline | External doors and windows
96dcc283-ccdb-41e4-a26f-b665a1f779d9 |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Preline | Insulation
39035bc3-432d-47e4-8fbb-d7f5c3f766b4 |  | checklist-flat | not-started | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Preline | Passive fire/Approval to line
64571c5e-93fd-4b46-a13d-4767e2ba79f2 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Post-line
13b252aa-5252-46a7-aebe-519a5c3066d6 |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Post-line | Lining
79d11457-d4a0-4754-9e12-ac5fc5e317a3 |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Post-line | Stopping
97d9bcce-f078-4b00-a145-23845502e730 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Post-line | Finishing lines
1e19606a-e2a9-4860-ae2a-49d611a7131f |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Post-line | Flooring
27e83e68-4253-4733-a827-cdd4a63dc7e8 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Post-line | Painting
0516d6f5-70f8-4b15-8fb3-f579cf23bb6e |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Post-line | Second Fix Services
2a475736-8edd-47e8-96e3-513ec9f9946a |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 1 area A | Post-line | Fire Door
b6ce7641-f760-4392-9f8f-afc4ecf81572 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A
98afbb52-dfe3-4af3-8416-48d7d779fd65 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Preline
167796d1-6c35-41ae-b837-d903082e4547 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Preline | Timber Framing
de8e428a-3ebe-4da1-a52e-34c4b2c28bb8 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Preline | Internal Strapping and Framing
5b33170b-a885-46a2-afb6-ecfa3dee3406 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Preline | Suspended Celing
0f7b7de3-f125-4329-8225-e727c79be961 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Preline | Internal Doors
bed5712c-8e96-48bb-8fc8-012d6fd6cfb0 |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Preline | First Fix Services
3ce04a59-d294-4774-b18c-1ed5339abe60 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Preline | External doors and windows
16717660-abea-4430-86fd-7c434b00e32e |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Preline | Insulation
f98b2272-4008-4685-aeee-100b7294b6d8 |  | checklist-flat | not-started | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Preline | Passive fire/Approval to line
c779a6dc-38c1-4df3-b110-7bb32f3c7e87 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Post-line
668062ba-ebc6-412a-ba91-afe20de167b3 |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Post-line | Lining
5f46ed1a-a678-4090-893f-f1599353b6ea |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Post-line | Stopping
58c4679f-a260-4ee4-85da-ac1d2bb7fe2f |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Post-line | Finishing lines
8d7273f9-bd6d-493d-ba9e-fd5eff48942a |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Post-line | Flooring
d63fa24d-b691-4277-9b00-98c4e639223e |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Post-line | Painting
82c6856d-777f-40b6-bc58-c2c8f07479d2 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Post-line | Second Fix Services
ff4ab7a5-76b5-4e3d-bdf6-f861fb813508 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 2 area A | Post-line | Fire Door
62e16a8a-4237-406e-b83f-b6ca2e968b5b |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B
22c25c12-a8c2-43a7-950b-c636fc24ebc0 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Preline
44588756-283b-4f23-b797-5d60af721876 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Preline | Timber Framing
601a21e3-fda9-4773-ab31-658a25e7d040 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Preline | Internal Strapping and Framing
1ab70cdf-b724-483f-913f-12e411f18b94 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Preline | Suspended Celing
b2767923-a2d8-4746-9542-656810c89368 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Preline | Internal Doors
42cf1a28-89e5-4a1c-92d9-b5d3c73d84f6 |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Preline | First Fix Services
15106ae9-0f43-4e0b-82ca-6121b18e1337 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Preline | External doors and windows
0b273609-af6d-4578-bde7-8eebec3c557a |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Preline | Insulation
c0e0996b-6857-4744-8301-35ff441abd5a |  | checklist-flat | not-started | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Preline | Passive fire/Approval to line
1b954c52-a2bb-45c5-9e96-06bf943a2759 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Post-line
521b3eab-d122-4fea-a6ef-cc8258c95089 |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Post-line | Lining
2cda53ba-277d-4150-8c6b-d79232186f7a |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Post-line | Stopping
7aaf1f0e-3df3-46aa-9fb4-7ab7752436a2 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Post-line | Finishing lines
d3a0a41c-9f63-4fbf-8918-7a900fe005f1 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Post-line | Flooring
ae40d933-b415-4c56-a3a3-ddc0b487f5e1 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Post-line | Painting
ce5ca846-d6c2-4100-a2bc-7bbaa738602c |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Post-line | Second Fix Services
9f819872-6fc1-415a-915b-398cbde76e27 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Service Areas | Services 3 area B | Post-line | Fire Door
cfcd254d-23a7-4ac0-b63a-955635d7ea8b |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas
466d4fa3-c4fe-443b-ae76-d7bc6f96d2f6 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88
67719003-acd6-42a9-9850-13d8c7b4ff72 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Preline
071025b6-7bec-43aa-b84e-3a7a7a5eea1a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Preline | Timber Framing
22fc9c58-d099-4ad0-9521-fa49c11d271e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Preline | Internal Strapping and Framing
4e760273-786e-444a-95ca-8f924d1f7cd0 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Preline | Suspended Celing
554734e8-ea40-4c2a-9b68-dcb006d28c70 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Preline | Internal Doors
0bcac7f4-3898-4a87-ade8-d0a5fdbf0e69 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Preline | First Fix Services
a41582fe-4a66-4c59-be9e-b52b5ce27207 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Preline | External doors and windows
df4222e2-99f3-41e6-983a-069c334b1bb1 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Preline | Insulation
d1ffc4c7-7d4d-4e75-81e7-0cff87ce9418 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Preline | Passive fire/Approval to line
1bcf4965-5461-41dd-807d-21ab09ca8d9f |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Post-line
9dcdfbfe-0c9e-431f-9d96-23592c6ddaa7 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Post-line | Lining
166275cf-a95e-4ddb-98e5-d83e679878d7 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Post-line | Stopping
df19091b-9811-4d50-b317-cdcc6433dc8c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Post-line | Finishing lines
8d10f1b6-1a8f-475b-8ef9-0c7eb76b6a24 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Post-line | Flooring
9b02ce2f-b3ef-46b7-a1bb-4b8f2bb4a09f |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Post-line | Painting
2a13b350-b1e7-4439-bc7b-9994d5e911c1 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Post-line | Second Fix Services
b7aae055-14c1-40d9-99e0-aaccb0fbbc4e |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Post-line | Fire Door
27aa5401-767c-490f-b575-90d534957720 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Finishing
e0c7b7b7-82fb-43c9-9729-65695049c7a4 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Finishing | Flooring
28e98c29-e80e-4fe5-8df5-7de42ec52eed |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Finishing | Exterior
15125de6-8408-41e9-9eb7-6316cd06b39d |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Finishing | Lounge/Dining Area
67603d29-66f6-446b-90be-87bb3ed6452d |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Finishing | Kitchen
b509a4ee-78b7-4dd5-9321-0137f58d6ddf |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Finishing | Bedroom
a9edd058-79d2-43e8-aba2-9304c54741b9 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Finishing | Bathroom
47734fb9-1312-4ed9-b80e-5d65c2de7f4a |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Finishing | Ensuite
6a14925d-2a26-43f1-bb5c-d4951c3e45bb |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Finishing | Laundry
c4b03f0e-9b1d-429d-9681-81a49aa3d6bd |  | checklist-flat | not-applicable | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Finishing | Hallway
163feb80-92f1-4e0f-893d-8db6f9fec50d |  | checklist-flat | not-applicable | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Finishing | Toilet / WC
523e4344-ac82-4d87-b313-a42b0d4fffd3 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Finishing | Client extras
5b558667-f3d6-4deb-bc83-e3f517ee567c |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C88 | Finishing | Final check before locking the door
bd92bdc2-141b-4561-9a6f-1f2f45cc9299 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89
06177822-1bb8-436a-9280-c30e678189eb |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Preline
f3636503-9a81-4925-b545-8eabe2d0cfcb |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Preline | Timber Framing
61044d39-f63e-49b4-871b-948ec15fadea |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Preline | Internal Strapping and Framing
c66bfe03-1880-43af-b00b-798951c89fec |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Preline | Suspended Celing
3b4d29c7-8c7c-495a-ab9d-d30cb81cfce4 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Preline | Internal Doors
cf52d9d7-2955-4ada-9b74-209989ba8201 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Preline | First Fix Services
2a0a2f23-df92-41ba-a65d-060f640cc780 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Preline | External doors and windows
b6f49785-b967-49ae-890f-dd4bea9bac29 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Preline | Insulation
c22b3279-8166-46f9-8944-5d69ae3f0fae |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Preline | Passive fire/Approval to line
df8f2f44-17e8-49a4-a416-95a6fc38648f |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Post-line
cf2692db-4b65-45fe-a6f3-342216717a94 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Post-line | Lining
a05c3289-b3f7-4e4a-9d5a-1dddbc1a2ddc |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Post-line | Stopping
6dabd847-9504-4f06-9a38-a8fcb3afa64e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Post-line | Finishing lines
b7676f7f-de36-4e7e-b0f9-5694e08faa98 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Post-line | Flooring
a414eb64-df0f-43f5-a366-d6712ca5453d |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Post-line | Painting
2da41fb1-70ef-4ff9-a192-bd9b6f885f26 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Post-line | Second Fix Services
65bc213d-19bd-4d45-a1d1-a46702742273 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Post-line | Fire Door
86100946-01af-412d-9ab7-f73c50a7cc85 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Finishing
9ec49361-e079-4cbc-95c2-1997d14aa371 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Finishing | Flooring
03e9dd87-e818-4746-aad9-9fd7382c32b5 |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Finishing | Exterior
b2da8ce1-0899-4492-80e7-960a67b07425 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Finishing | Lounge/Dining Area
134fd127-20bb-40c0-863d-18d8e1b054b3 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Finishing | Kitchen
78944453-e9ff-42b6-a71f-399a2817da25 |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Finishing | Bedroom
f1d2beb3-5f1b-4a0e-b066-e559f62c4336 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Finishing | Bathroom
6371077d-839a-4984-a9fa-f075b7eafc33 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Finishing | Ensuite
2c1c67cf-1db5-4327-88f9-b8f717c33528 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Finishing | Laundry
65c17629-65c3-4400-991c-d132c40078b7 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Finishing | Hallway
b8e2b283-3a77-4e1e-893d-52ee89fc7105 |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Finishing | Toilet / WC
8b3721bc-4cbe-497d-aeb7-0b57b61fd312 |  | checklist-flat | not-applicable | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Finishing | Client extras
c4f1ae1e-f33b-461f-9cba-85c2269543af |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C89 | Finishing | Final check before locking the door
c0dc31c7-010c-46d4-99d8-158435fd4aeb |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90
89ef377d-8171-4b1f-bc85-2c419adf3d28 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Preline
9b13b13a-2047-408d-a1f2-0ceeeacb9836 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Preline | Timber Framing
981ec13c-6c29-4538-802a-844fb4737b4c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Preline | Internal Strapping and Framing
04590244-09e4-43b7-8863-fa6f2b9631fd |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Preline | Suspended Celing
37b2223c-fa4e-4b3d-8789-f7d18173305b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Preline | Internal Doors
0a68fbfb-89ac-4cff-aa22-a2e1ac2adaea |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Preline | First Fix Services
5459a585-557a-4ba6-9645-95ae81324e4a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Preline | External doors and windows
49269ea8-5337-419e-bbe1-52b73fef3787 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Preline | Insulation
d5ce5a5e-51d5-49f5-a66f-b87cf343000d |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Preline | Passive fire/Approval to line
11701452-39c1-4a75-a9b7-c60433e32014 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Post-line
ecad0f10-898e-4ebc-b8c3-303a5327dc67 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Post-line | Lining
960ffd1d-16a3-4fde-bef8-f6e074047a4a |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Post-line | Stopping
3df8e930-282e-4d1e-af51-c3da45409575 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Post-line | Finishing lines
1a24600e-20f4-4c64-82c8-2618d837fe39 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Post-line | Flooring
a285e1ef-7fbd-454c-83b1-8691c8945409 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Post-line | Painting
c8655d66-b72c-4fa8-ba34-d65b39796eb2 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Post-line | Second Fix Services
e12bdf23-eac9-46f1-ad10-770a746e9794 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Post-line | Fire Door
966d91ee-6977-48c6-a903-fb18c6b380d7 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Finishing
3878067b-0704-4e76-9581-fa90aa86b9f4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Finishing | Flooring
87972edf-aa85-430f-a115-fe56b786cb13 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Finishing | Exterior
c760c413-937b-46c9-a9c1-37b278b37b53 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Finishing | Lounge/Dining Area
64d20ef0-60cc-4af8-b0e5-afd6d708a759 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Finishing | Kitchen
16a2123f-d0c5-4af5-849b-75f7f50c4532 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Finishing | Bedroom
038fd6cc-2941-494d-a9a9-6849564a4ad5 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Finishing | Bathroom
d2ff8d43-56ee-4746-989c-55f6c46ae519 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Finishing | Ensuite
4b033063-47fe-46b6-b7d9-fee40a12aaba |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Finishing | Laundry
3071a323-6956-4b94-9150-74efbbd6670e |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Finishing | Hallway
c79b2ea2-ebf3-4026-9092-7424e29f03e2 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Finishing | Toilet / WC
105927c7-9eb8-46b1-82e2-b610d381ae0f |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Finishing | Client extras
67ea0047-01c1-49c6-88a4-7c879cb20b1b |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C90 | Finishing | Final check before locking the door
1c5557a8-c751-44a3-893d-87556740cf10 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91
332806a0-0afb-4d1e-a03c-831669f680b4 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Preline
8a54631f-4c9c-40b8-95ca-2be29e5b9ca5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Preline | Timber Framing
7b4fe208-2a5b-472e-b11a-a59341ce43e1 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Preline | Internal Strapping and Framing
d4225fef-51d1-40b3-8369-a9c05e32563a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Preline | Suspended Celing
0d0c9f60-c620-4a8f-af43-cdf7d6e15e7e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Preline | Internal Doors
cdcde455-84ed-4707-86c5-5fc9bf95d8a7 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Preline | First Fix Services
6623d2c1-ff03-4907-b889-875cea991ec4 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Preline | External doors and windows
714aa2b6-febf-486a-9eb6-10dfc95f1ac4 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Preline | Insulation
7e356fcd-0b6c-4cde-8a02-10f5bcd8d6c0 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Preline | Passive fire/Approval to line
19c1bf50-ee2e-40a7-bba9-b7d8bb812e97 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Post-line
354b375a-22d8-4aea-a455-e09c2aab135b |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Post-line | Lining
213d9088-bfa3-4811-bf8f-6ec4f008c73e |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Post-line | Stopping
7c44d530-8f76-4310-a257-912c2339be88 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Post-line | Finishing lines
f3f9f9c0-18f7-4e54-9c01-9e29fb277974 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Post-line | Flooring
08cddf20-e464-4f90-a1e8-e28eea0c1a26 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Post-line | Painting
e84b9dcc-4d88-46bc-a703-0b4a6bb26a24 |  | checklist-sectioned | pass | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Post-line | Second Fix Services
b8f94e6a-9fd4-4ca0-83ac-e87446035dc4 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Post-line | Fire Door
1dd95834-197c-4823-bfe3-ddd9ee563b8f |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Finishing
7a8c736a-beff-44e6-9e8a-e616f5011ea6 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Finishing | Flooring
0bf628a5-cfe5-41d3-bf21-d4e2532c0ea8 |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Finishing | Exterior
b97d540e-0656-4397-8a90-cf05c0cdaf8d |  | checklist-flat | work-in-progress | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Finishing | Lounge/Dining Area
bfb2e961-2204-4f00-9401-3d882aa4265c |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Finishing | Kitchen
493d240d-2b37-454a-8185-91be7e061bb6 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Finishing | Bedroom
8f7850c6-abac-454f-a436-248349efebdc |  | checklist-flat | work-in-progress | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Finishing | Bathroom
a0f8722b-7897-4413-a614-83a7129e6bf0 |  | checklist-flat | pass | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Finishing | Ensuite
26806106-208c-4aed-8221-1e314cd879c3 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Finishing | Laundry
f03cfc97-b379-4975-acdc-70e0965ffa07 |  | checklist-flat | work-in-progress | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Finishing | Hallway
d510cd7d-294b-4e21-ba68-c8e58fbf8699 |  | checklist-flat | not-applicable | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Finishing | Toilet / WC
076fe366-30b6-4e92-9d1f-9a1c6dba558a |  | checklist-flat | pass | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Finishing | Client extras
3e699139-4807-48d2-88ca-b67aab1549c3 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C91 | Finishing | Final check before locking the door
8f865ad9-d6d1-485b-8faa-4a7e5d0e8841 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92
7e50bf76-662f-403a-a260-132015e984cf |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Preline
2bd1b870-155c-4f7a-8563-655cc113189e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Preline | Timber Framing
2bde691d-2184-43f2-a777-630b1449234a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Preline | Internal Strapping and Framing
6771e72a-207d-4653-9a64-8d73e15ef7e8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Preline | Suspended Celing
b1b5fdcb-e482-4ddb-8075-8637b357cbf5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Preline | Internal Doors
f09200f3-12ca-4553-b449-6bfaff39dc4c |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Preline | First Fix Services
91d4d887-3d7a-4a20-8197-740005686081 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Preline | External doors and windows
d209113d-0b01-432f-abd5-453572b02861 |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Preline | Insulation
71fdd0b4-1d9c-4db5-9e63-9de864e60c15 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Preline | Passive fire/Approval to line
77d01f9d-4961-4714-8faf-d627ea3e44f7 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Post-line
dc14d889-e44b-4726-b5e2-29ab1fcd7286 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Post-line | Lining
43de4516-67ed-4279-9ae5-2e36b4b39dca |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Post-line | Stopping
74f94ab0-490c-4c72-9da8-653f3e7860ce |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Post-line | Finishing lines
c20284a4-c945-4546-959c-baf548f9243b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Post-line | Flooring
5e9bd5f5-d3ba-429f-97ed-2f719f2c1f6b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Post-line | Painting
12782e11-808a-4bc2-bb5f-b1826a409508 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Post-line | Second Fix Services
6be2cf67-3a55-47a1-8a12-35c66a815049 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Post-line | Fire Door
f29cd06b-b755-4e2b-9cf1-1e3ba8b3fe1e |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Finishing
47524fec-e435-4b4e-8c6d-7748480b5cbe |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Finishing | Flooring
26f56c54-b2b2-4315-9583-c05b33d6a3e9 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Finishing | Exterior
30866872-1b66-4ed5-816c-9f88a51cb0dc |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Finishing | Lounge/Dining Area
3bf37c61-e23f-45a3-b860-aedb45422ce8 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Finishing | Kitchen
c875d225-d7a4-4d26-b610-90bf03c022bb |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Finishing | Bedroom
46ff4684-c421-4e75-ba55-dedc4bcf290a |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Finishing | Bathroom
913d0578-c764-4f2b-bd21-bad4b15858be |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Finishing | Ensuite
a3c353af-3114-4591-8ce1-076e70b281c9 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Finishing | Laundry
75bacd40-7eb2-4c4f-8509-7efd300aba3e |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Finishing | Hallway
89167b98-aa7b-4cc9-a729-64c1f16681e8 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Finishing | Toilet / WC
ec33470c-b964-441a-9aee-4c6f84a37702 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Finishing | Client extras
4665ed4e-b8f3-416d-ab77-eaa68d572ec6 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C92 | Finishing | Final check before locking the door
ce6d897a-b001-4a65-9b30-547b24dbfc20 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93
5cc8d0a9-d696-4090-8faa-7f0a985f85b1 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Preline
8273b6d8-8be8-4606-b6cf-4122c31f558e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Preline | Timber Framing
c55f7254-8671-41f2-96fc-b6afbd789c32 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Preline | Internal Strapping and Framing
11b220bf-ba22-4d7b-9249-d51cc5ffab30 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Preline | Suspended Celing
a5419288-dead-4c27-8939-0cd1e35a4edf |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Preline | Internal Doors
6eafa6c0-b284-4850-a459-2c9e64c284ff |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Preline | First Fix Services
b880a072-8b1f-4742-9ede-6231436542bc |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Preline | External doors and windows
c82de23a-3e2b-43f7-a3c1-2ff1221dc970 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Preline | Insulation
b00843aa-516b-4ca5-ad15-f450ffcd8903 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Preline | Passive fire/Approval to line
15ea9ce4-e012-411e-b7b9-fc6c4dc52e78 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Post-line
f55d989c-efd5-45d5-81cf-b011465eaa5e |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Post-line | Lining
0b932d9e-df77-4137-95bc-6b0d4f38bf46 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Post-line | Stopping
f1eb9255-d72e-43ac-a523-fed1f05ff4e5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Post-line | Finishing lines
be04cfe9-94f1-4ee9-86fa-75e56c3a3f56 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Post-line | Flooring
ba760b2a-2d4b-4e47-827b-3cf5fa9e19e6 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Post-line | Painting
eda0d033-2261-4533-9bf0-82bfb24f6452 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Post-line | Second Fix Services
f589cd21-9e06-4fc8-ac2b-0558ecfd5ba6 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Post-line | Fire Door
e814d774-6116-45d1-822f-9d8dc95d5d67 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Finishing
45d4cb83-b299-45f7-a52c-4059f6358f7c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Finishing | Flooring
9d912dbc-450a-4516-b827-c5b561ab0237 |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Finishing | Exterior
5faca8f6-7a75-45a7-8fe2-5cd4ce6d914d |  | checklist-flat | work-in-progress | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Finishing | Lounge/Dining Area
d95a5b63-cfef-4f99-a638-4161f8378a41 |  | checklist-flat | work-in-progress | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Finishing | Kitchen
684af01d-665b-4766-ac29-6dbdd9649d29 |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Finishing | Bedroom
9703ef2c-9329-40c7-b815-8ae7cf3fc54f |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Finishing | Bathroom
4c210ba1-15e0-43a1-8a4e-f5f9cb42d889 |  | checklist-flat | work-in-progress | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Finishing | Ensuite
0d72aa1f-3340-415f-9794-0ed009f87834 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Finishing | Laundry
89710456-b518-4acc-8164-d8d7cead7883 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Finishing | Hallway
fcfbf3f1-d102-4b7a-aa4c-683fe308606c |  | checklist-flat | not-applicable | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Finishing | Toilet / WC
41d7e94d-7d68-471e-a120-c7d62b9ca412 |  | checklist-flat | pass | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Finishing | Client extras
437cde8b-ef77-4e5e-9da6-3d38a9fffd6a |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C93 | Finishing | Final check before locking the door
26370c3e-ec41-4b8b-8438-7480f28b240c |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94
bab36042-4c11-46e1-b873-edf617c3d257 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Preline
8b8a8de9-cfc3-4204-8255-db15dfd4c983 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Preline | Timber Framing
70ff663d-4245-4de8-a3d8-a672b7f95223 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Preline | Internal Strapping and Framing
43810d6a-b05b-494d-aeda-27a0d6723f64 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Preline | Suspended Celing
326b27c9-c316-4c23-9c40-48e9cf302589 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Preline | Internal Doors
70e3eb03-30a2-474c-a198-98dfb08d8e49 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Preline | First Fix Services
857c1c8a-7260-48f3-9c88-9d1bb363a584 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Preline | External doors and windows
9695afa9-92c2-4d7f-a13d-6ca7c1274e90 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Preline | Insulation
91b6433b-a5c3-4d3d-86c2-7b30beee94c7 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Preline | Passive fire/Approval to line
3ba48227-e88d-44c7-a6dd-35ede5132235 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Post-line
6c33398d-fa29-42d4-88fa-6694da2990e2 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Post-line | Lining
b20e801e-2c07-4ba7-bd44-88f6c4384924 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Post-line | Stopping
4e790ffc-47ed-410c-9c01-4c96a17df308 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Post-line | Finishing lines
84dfdf3d-92c4-48d2-bfb8-69a49cd670d4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Post-line | Flooring
9015f976-fbef-4e6b-9c1c-f9f513089350 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Post-line | Painting
f2489657-4cdc-49db-b0ee-d5c7591dac29 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Post-line | Second Fix Services
364935ea-1595-4ebf-a2c7-646c1da7662b |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Post-line | Fire Door
e7cfaafd-4795-49b4-bef3-fa29b7f410df |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Finishing
fac1f84d-9d37-4c3e-bdb2-04af8391005f |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Finishing | Flooring
97b58df0-dc2c-46c3-822b-efe617648b77 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Finishing | Exterior
3e3ca01f-efb3-4c7e-844d-c9b0dbc79219 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Finishing | Lounge/Dining Area
01fff90e-6e04-4d24-88e7-58c31547f874 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Finishing | Kitchen
c8a2a407-f42d-4016-b1f6-bd0aa5cd694b |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Finishing | Bedroom
b07f7259-bccd-4c39-84b8-7769b327582a |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Finishing | Bathroom
a54ceb90-8bc9-42f7-ac22-761b5a69bc04 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Finishing | Ensuite
58fe3b0d-ffa0-4912-8310-bc6884b7a921 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Finishing | Laundry
3463cb3c-a15f-47d9-b153-30228f763c28 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Finishing | Hallway
edcad276-aea6-4d29-bbfb-f774e61173dd |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Finishing | Toilet / WC
54a43d75-1fd3-4509-82ee-09c29a9e539f |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Finishing | Client extras
ac27b620-ddf3-468f-85c8-b90e440c70cd |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C94 | Finishing | Final check before locking the door
2d72cd6d-bf53-4589-a3a4-d0d8d095900d |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95
7db27919-15f5-4365-b7e6-19f591c6df5d |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Preline
e635231d-a7f0-4437-8469-cf4719a9c0ee |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Preline | Timber Framing
494fd7b0-1343-4bd5-8445-8d0ce03317e0 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Preline | Internal Strapping and Framing
5c66b83d-daeb-4500-b12e-e51a39c66aa1 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Preline | Suspended Celing
632f2aac-b89f-4672-8568-10db730a75ea |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Preline | Internal Doors
c5f9e624-a69d-4aeb-bd49-76dc42247bef |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Preline | First Fix Services
6e01d40f-b404-41cd-818f-bc6e26e90541 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Preline | External doors and windows
6ee1fa32-a6c3-4656-a97b-c3c7e9c14cd5 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Preline | Insulation
a68e0eb1-3f81-4102-895c-a07e0d72782c |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Preline | Passive fire/Approval to line
64b2dec9-274f-4202-bb87-eb3c524b4397 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Post-line
46de94d0-20eb-4d3a-9669-832fd53e10a9 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Post-line | Lining
ebb87b51-61b6-4731-bb83-97837130b1f7 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Post-line | Stopping
86df529d-613a-4d19-accf-fead77199d16 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Post-line | Finishing lines
82aaa84d-9249-4576-8e96-6e7cbe9e84b6 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Post-line | Flooring
52388035-b76a-4136-8135-673e07125fea |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Post-line | Painting
2413f9c7-2bf7-4c41-96d3-9f88c5259cb0 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Post-line | Second Fix Services
c02a2622-55c7-435c-ade4-050a93ceda30 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Post-line | Fire Door
51bd657a-a504-4839-b303-3e5964329126 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Finishing
362814a2-7b04-4cde-a966-a5c5e98802d0 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Finishing | Flooring
d415cf98-dff9-4163-8a1c-9fc148f9475c |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Finishing | Exterior
5892c50b-f9a0-4e76-b42e-73d741bc1c25 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Finishing | Lounge/Dining Area
7f4d7fac-95c8-4c4a-9c68-89d0658cf003 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Finishing | Kitchen
13c1cfd0-9597-47eb-af3b-3a4c533e4ac5 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Finishing | Bedroom
b716c1f4-b0f9-498c-8b8f-6938fb5ac27a |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Finishing | Bathroom
66f5e6ec-145c-4fc9-a967-4d1729921219 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Finishing | Ensuite
e7a377e6-717c-4689-8577-256d3b3ffc00 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Finishing | Laundry
76eb6512-b0d8-4826-99dd-ee5f16371f08 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Finishing | Hallway
ea1e334c-605c-4abc-9b7f-55e7db6a6df4 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Finishing | Toilet / WC
559a603a-d0fb-4701-ac24-4fea6630b04e |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Finishing | Client extras
3d7f35ac-da07-4020-a4c3-6b58f2e53e16 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C95 | Finishing | Final check before locking the door
6171d2db-b4d9-40ce-951b-dd35959bb6c7 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96
5ffdc7ae-c7ee-40fd-91f5-7a566387dbd9 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Preline
57b79209-6b6f-4180-ac83-d4ad758acc25 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Preline | Timber Framing
b4b162f9-5e8f-4229-9a0a-a3d58bb73b68 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Preline | Internal Strapping and Framing
767fed4d-a9e6-45a8-a56e-01f47686200e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Preline | Suspended Celing
361cfe47-3bf5-48f2-a307-336eeeaa7ecf |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Preline | Internal Doors
5bb05c27-9c72-4734-8639-a9dc2c9a6afe |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Preline | First Fix Services
1a1af59c-263c-4774-8a8f-a3d8e28c9f4f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Preline | External doors and windows
77afaced-2e09-4db0-9e01-e934df1f4fe3 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Preline | Insulation
ff1ce09f-ff6f-4939-8463-cd6d6c4c3e83 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Preline | Passive fire/Approval to line
c605d859-aa6b-4968-ada3-95d8346c69b4 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Post-line
6d3e2989-a8db-4c01-8761-81b031338207 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Post-line | Lining
a4c74b79-d889-4f35-8076-8f9e8f1583c6 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Post-line | Stopping
ca4965ed-7035-44a5-9ffd-e678c140044b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Post-line | Finishing lines
7d2e617d-2928-47a8-adbc-d058c14d7fa3 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Post-line | Flooring
2f4d44e2-be59-43a2-9274-612b566e462f |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Post-line | Painting
d37797b6-f616-479c-976b-31125302cce6 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Post-line | Second Fix Services
4ce0c083-9c3f-4afe-b363-4eb3f25229d1 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Post-line | Fire Door
ae91a1dd-0084-495a-bbc0-95cf7cbf73c6 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Finishing
117c8351-a193-4507-bc52-3bae4fe7bde9 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Finishing | Flooring
e9ff0bd0-c934-44e2-9d77-3037b2eff5de |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Finishing | Exterior
60826017-65b7-488e-8ad6-e4d43dd9e2a7 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Finishing | Lounge/Dining Area
affc499c-614e-499a-b971-fc79e55462c8 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Finishing | Kitchen
dc99852c-6aab-4d67-8914-513eb6e44cfb |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Finishing | Bedroom
8316565f-b660-4300-8712-6379a4ca2cf8 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Finishing | Bathroom
26438a5d-df1e-4dfc-b87a-36aab2655b1a |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Finishing | Ensuite
a03fd80e-f805-497d-b627-5326461f2f16 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Finishing | Laundry
645837db-2d34-468f-9d8b-b5b305e70ec1 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Finishing | Hallway
8f614f94-4a94-479a-a06a-a58295be2a72 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Finishing | Toilet / WC
abf2dc42-a2e2-40f6-a6b2-5fbfa6d14fc1 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Finishing | Client extras
b6ffa4e5-343e-4d4f-bce9-93abd5bb015a |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C96 | Finishing | Final check before locking the door
51f4a036-baad-47b3-9948-5da3c6b2a6d0 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97
90789b2e-5029-4c0f-8856-0c5374c9ffc0 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Preline
79938f51-f7c7-4aaa-86a3-7251b1d37a18 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Preline | Timber Framing
e7aac7b9-3cb4-4f59-b013-84f3f643c698 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Preline | Internal Strapping and Framing
5e2b63dd-58d1-4a0c-97c3-b7382dd1b5a7 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Preline | Suspended Celing
846d26ae-05d0-4ed9-971c-e1c340523182 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Preline | Internal Doors
1fa289fc-ae5c-49f3-89a1-c66b44ebf937 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Preline | First Fix Services
a783ec7f-e64d-4b8f-aee0-26c0d7c937ac |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Preline | External doors and windows
484848e7-9609-4153-b74a-eb16bbbf9a42 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Preline | Insulation
e867bcec-c0cc-43a1-bfab-f0bc6c3c0d96 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Preline | Passive fire/Approval to line
92649035-a891-4393-b04b-a7975658111d |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Post-line
54532473-6b97-4e80-902c-1422467a99cc |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Post-line | Lining
8214004c-3433-4358-8bbb-1692b516299c |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Post-line | Stopping
03f57b7a-1a93-4dd2-828d-f87aaeb2c21e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Post-line | Finishing lines
07ff10a4-f48d-4d2f-9378-4792554a2a87 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Post-line | Flooring
fe95652f-5e0b-4374-b5ba-ef5759d8a8c4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Post-line | Painting
592ca63b-f004-4aab-859b-068aaab0a9f1 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Post-line | Second Fix Services
1543dd5a-6759-437c-a9e5-728422b89f53 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Post-line | Fire Door
cb07dcc4-d229-407a-9148-e12210365a4b |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Finishing
32a70364-a645-4906-9fb8-9f5b35b214b8 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Finishing | Flooring
a0fb25d8-76d6-45a3-bd61-e2a05a6c2925 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Finishing | Exterior
aa25648a-f79a-475a-a2ac-61599a69ba88 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Finishing | Lounge/Dining Area
b27a40ab-e690-4a3d-9292-83dd9111d1a4 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Finishing | Kitchen
2172344c-c15b-45e7-a711-db2c7a4e542a |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Finishing | Bedroom
adbcf6d1-775a-4edd-aaca-7e96ac5c79b3 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Finishing | Bathroom
97a79f03-466a-4417-9226-f7171eadb46c |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Finishing | Ensuite
10abec0a-7949-4f47-aa54-3b575589690f |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Finishing | Laundry
f4778746-a9f6-4a42-a9f7-37f024c869ec |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Finishing | Hallway
147d823c-b03c-4140-a5ef-e6a951e9b4c3 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Finishing | Toilet / WC
c5bdd122-56d3-4ba3-9c4f-cc80d0abae9b |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Finishing | Client extras
e2165ffe-43a8-4dad-b6ca-36026d698183 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C97 | Finishing | Final check before locking the door
b99c0645-9daa-4bf8-a621-d81d61b7dd43 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98
cc406eba-6961-4742-aa74-cdcb3bb7667d |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Preline
a2161bc4-28c3-4d16-bffc-6f33381f9bc5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Preline | Timber Framing
91aca12e-dbee-473f-bc06-ddbcf175cdae |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Preline | Internal Strapping and Framing
155efdee-9ee6-4290-846c-4b80bfa50d45 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Preline | Suspended Celing
4d0f48f6-37b1-4f14-a8be-26e41efe8c77 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Preline | Internal Doors
e66c92c8-4992-4d2c-9141-ff0f4120559d |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Preline | First Fix Services
39e6b886-cb0c-43a7-aaf5-69b5fcbbd09c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Preline | External doors and windows
f30539a0-afa6-4581-9c64-92fce0c1f791 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Preline | Insulation
a0994851-142b-4347-8c29-c56228d93dca |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Preline | Passive fire/Approval to line
e5d7bf38-f87a-4358-9f47-d35d545a6deb |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Post-line
930e21d7-c1f3-48ec-8125-b5efd803b69b |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Post-line | Lining
b5ec132f-512e-4813-82f4-61a78bc04c04 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Post-line | Stopping
82416c3c-c187-4c1e-abbe-481aa06035ea |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Post-line | Finishing lines
ef497b21-f356-4500-811d-9dd439f35e0c |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Post-line | Flooring
80919ec2-a935-4ca3-ba7b-aa71188c2d10 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Post-line | Painting
f1a02d18-95e6-417e-97ad-c2035de7fdda |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Post-line | Second Fix Services
5b7fe96f-3ff0-4387-bb50-d11c864ec3f4 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Post-line | Fire Door
3ff675a1-1411-4c7f-98d2-4235ba4c2bdf |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Finishing
2127c1be-16f6-4c91-b3e5-ba292e5d5f51 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Finishing | Flooring
9efb46e4-5c99-430f-8dae-63ff8b5c78b8 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Finishing | Exterior
c36e94c0-8b8e-4f68-bcb3-23650ff84bc3 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Finishing | Lounge/Dining Area
c9a7127a-139e-4171-9bd7-c4aa3e689cb3 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Finishing | Kitchen
a7660076-5bf8-4dfd-9821-c36ba92b0764 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Finishing | Bedroom
8be96d43-5988-4a9d-aaf1-cccf5249a8e2 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Finishing | Bathroom
94726d97-b4e8-45e6-b7d8-76e2ad74b93d |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Finishing | Ensuite
5995cabe-75e5-4f12-be27-18b8084bb1d0 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Finishing | Laundry
be41edb1-e960-470b-9a71-f00e2f85c86d |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Finishing | Hallway
29851f8b-a05c-46a5-9d60-1ee65d151acf |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Finishing | Toilet / WC
45cf11ed-2f33-40aa-b53f-f36073c42dff |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Finishing | Client extras
904109fc-0ab1-4d8f-8e2f-017cfcd26715 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C98 | Finishing | Final check before locking the door
673c49a3-3683-4ef4-8547-8fce8945116d |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99
ecf28064-8a8f-482e-a09d-b2a449e0e328 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Preline
43476097-5282-4a4c-9aa1-4d839020b8a2 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Preline | Timber Framing
22d55fd2-e971-4e30-a18e-30a87b14f419 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Preline | Internal Strapping and Framing
a39afdc7-ad79-4455-b7f2-a63d91d0394f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Preline | Suspended Celing
a4c10394-dd93-4ba2-999b-3db06ae3aed8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Preline | Internal Doors
de9c9598-07fc-4112-9b46-bd58e9e57f66 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Preline | First Fix Services
06a19599-74d2-4fa6-a863-72eae900cc1e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Preline | External doors and windows
d9ec3106-0c7a-4467-88f3-994d00be8ebf |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Preline | Insulation
2593254d-b7cc-4e30-9a5a-3764b656a8ac |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Preline | Passive fire/Approval to line
47ff976b-2440-472a-890f-9c321ca7ea91 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Post-line
09526e04-dc4f-457f-852f-8fd136873238 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Post-line | Lining
1fa34b55-d47c-422f-92be-8c4614d27d77 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Post-line | Stopping
c59e5f9f-7dae-4832-9f46-cd31d4855772 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Post-line | Finishing lines
1f505e70-cd0e-4915-90c5-d2486fd43269 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Post-line | Flooring
12463399-b9e6-4939-a78f-03b5d22ef990 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Post-line | Painting
9426f72b-d319-455c-9855-227da14930c7 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Post-line | Second Fix Services
41dc9458-358f-43cd-983c-16c2ab3f5851 |  | checklist-flat | not-started | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Post-line | Fire Door
3d3a1fb3-19d2-4037-b84d-8595b474be22 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Finishing
03d7d8a8-8435-4f08-a0c8-9c397e6000c9 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Finishing | Flooring
91d4d7d6-0c9b-4f7b-8a7d-bc4dfdd13033 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Finishing | Exterior
a6188b60-ed42-4445-adaf-f25c04ee614f |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Finishing | Lounge/Dining Area
282be408-6b3a-4aa3-a6da-660741a07060 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Finishing | Kitchen
8b2af239-31db-4686-a4a0-fbd4c471a3e7 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Finishing | Bedroom
47cb1e87-4ae8-4c50-a8d5-9a944b76aa45 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Finishing | Bathroom
07e7ca2d-e483-4be5-b58a-3acb472a9e57 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Finishing | Ensuite
2c392c47-a669-421d-afb0-d3be2c0c9f33 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Finishing | Laundry
12eb6212-01e6-45ec-af62-7439b43ab055 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Finishing | Hallway
fafe79b9-0851-4c95-b0f5-081c499fdb72 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Finishing | Toilet / WC
b4050b5e-0792-4b63-9d1f-20225b16e464 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Finishing | Client extras
55327fef-3cc5-4682-a5c8-721b7f83026b |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C99 | Finishing | Final check before locking the door
c66f42a3-9611-4dd5-8016-37de55c6b3b2 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101
8defd280-17c5-4b02-a008-b46691674400 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Preline
6192559c-179d-4fe5-a492-26102d28e696 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Preline | Timber Framing
f0de08a8-5289-44a3-b2ba-e5480d586815 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Preline | Internal Strapping and Framing
127145b1-9bfc-4c89-8369-72efc162bee7 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Preline | Suspended Celing
204e2703-ef55-49dd-b1d8-48b4a561633d |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Preline | Internal Doors
2a13e4b8-e9bc-4785-9d5d-635c39461662 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Preline | First Fix Services
3af9f5c5-9a82-4736-abca-db069f51b0bf |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Preline | External doors and windows
c5ff6b72-abfa-4991-bb6d-747f56d1479c |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Preline | Insulation
9c894137-6929-45bc-bfae-5d8134dafe74 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Preline | Passive fire/Approval to line
5a485a7e-7626-4792-9f5e-3eaf34bed9aa |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Post-line
c270da72-7b4e-4522-a049-a7da5518b103 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Post-line | Lining
369425a7-4c1c-4017-9e53-a870c6afefa7 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Post-line | Stopping
6c4c9857-035c-4e36-ab28-d407e158cb27 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Post-line | Finishing lines
55ae248c-e333-41fd-b85d-0b568d05cb80 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Post-line | Flooring
a6274811-5518-41bc-9bef-b2dc88c8b033 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Post-line | Painting
35bf71ab-6196-4bd4-861a-cd1148fba951 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Post-line | Second Fix Services
ec4fa15c-255a-4055-a6fa-e94f17e13a2f |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Post-line | Fire Door
41040bf8-e428-4d21-864d-1fe047b67a3c |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Finishing
0968433c-e0d2-4759-aaea-742fcaa493c6 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Finishing | Flooring
42dfd725-d60a-4759-b790-356050e3e368 |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Finishing | Exterior
5f469231-ebe6-4bb9-8638-bc9aaffbabdd |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Finishing | Lounge/Dining Area
7fba3015-efe8-4b3a-9a56-8257927d71f2 |  | checklist-flat | work-in-progress | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Finishing | Kitchen
e8d007c5-b35f-499d-99ec-54bfefdc76a6 |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Finishing | Bedroom
941edf5b-280c-4cd3-b84a-c66e105a1627 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Finishing | Bathroom
baa28499-323b-499c-88c0-b709015c9a86 |  | checklist-flat | pass | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Finishing | Ensuite
f8ef0b10-f66f-41dc-8dbf-db92a6801a3d |  | checklist-flat | work-in-progress | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Finishing | Laundry
afdc5603-dcc9-43a1-9685-c67b9aebdcb8 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Finishing | Hallway
61ba3672-7efc-41ca-812d-89400ae394b3 |  | checklist-flat | not-applicable | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Finishing | Toilet / WC
ef278c6a-fe51-4e24-96b3-026cf9b7840c |  | checklist-flat | pass | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Finishing | Client extras
3eb5923b-17cc-49d2-ad04-0c40f16009fb |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C101 | Finishing | Final check before locking the door
4e69d89d-aa55-4d7b-afb0-9bb817d2e6b7 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100
94f1baf4-03af-4af8-9334-041a7dea4c3d |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Preline
294aa5b2-368d-4cee-8d04-71e0c3acb4c7 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Preline | Timber Framing
9167723f-c76f-471f-9925-356bafab80fc |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Preline | Internal Strapping and Framing
c11fd21d-7b59-4243-80f3-628c730c0933 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Preline | Suspended Celing
cd45474e-d9b5-4e30-8bf2-449d7deacb2e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Preline | Internal Doors
d4e399aa-82ea-4b34-8257-5fa153565aa1 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Preline | First Fix Services
dd9daf78-3335-4483-95e5-ef9cba3816d9 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Preline | External doors and windows
80615fab-b41e-4467-8f4c-2cc846a8e9bd |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Preline | Insulation
7a824855-1ca7-4b88-a972-16482f2ea617 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Preline | Passive fire/Approval to line
5b3ecdf1-08b6-4db2-8aa5-d2a8a743db2c |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Post-line
fdfe3640-a247-4d27-8ce8-2d94beea37b8 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Post-line | Lining
48b67627-0270-42cc-bd6b-58e71e3f90d8 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Post-line | Stopping
1a66fbbd-00b8-4a5a-b25a-f2a694d09eaa |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Post-line | Finishing lines
23995725-6497-4619-a80b-db0212fc6aa0 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Post-line | Flooring
e3f106cf-95ef-46e0-b685-ff6492989f20 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Post-line | Painting
309d61b1-f5fa-4bc4-908e-1a8ba880fb72 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Post-line | Second Fix Services
210e515d-0e8d-47de-8ac9-2492a0384b87 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Post-line | Fire Door
1e9099d2-0797-4836-a15b-bc85fa31d229 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Finishing
f19ca478-2bbd-465a-b32f-9b2f42dc1e55 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Finishing | Flooring
3f5b1faa-b826-4ced-9f86-a69d9cf635bb |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Finishing | Exterior
0375a5b0-cf70-4952-8518-0bde2fe0f7cb |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Finishing | Lounge/Dining Area
a4bb4a8c-a517-4b96-a93c-a812d9215008 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Finishing | Kitchen
2a337143-2df4-4a72-ac5a-fd32250b8af9 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Finishing | Bedroom
9053bcb5-e8ce-412e-b0e8-c407f8dcd20d |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Finishing | Bathroom
7ac3fcc9-5e99-4b98-b6fb-c394580cecb3 |  | checklist-flat | work-in-progress | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Finishing | Ensuite
99d8912b-8ad2-4323-80a5-aa9826f1ddf0 |  | checklist-flat | work-in-progress | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Finishing | Laundry
9b543734-da56-4681-9a61-a2c4276b4339 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Finishing | Hallway
1e7bd116-ef50-4680-948f-382a1ea2b533 |  | checklist-flat | not-applicable | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Finishing | Toilet / WC
83b9de15-afed-4b73-91f5-46e879e0d1de |  | checklist-flat | not-applicable | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Finishing | Client extras
2d3ff890-c2b9-4921-a291-2bdddf64bce9 |  | checklist-flat | pass | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C100 | Finishing | Final check before locking the door
666a1a1f-415c-4cd9-8509-810648474d1e |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102
df7e04ef-2c90-48f0-ba0c-982e49c5ecc6 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Preline
3368905f-52bf-4f27-9d50-0142264a51d2 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Preline | Timber Framing
776594b2-c931-48b8-a558-855f75622b76 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Preline | Internal Strapping and Framing
551f459a-69e3-4f65-bb64-463bb43d3095 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Preline | Suspended Celing
3d8a8bb0-4294-4bc8-99f3-5ced7605f255 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Preline | Internal Doors
13464278-21b0-47d4-8ed0-8990ecba0658 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Preline | First Fix Services
0c34015e-1723-4655-9e88-03b5271b0160 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Preline | External doors and windows
1deb4e20-4e7c-4079-b1ca-8d53b636d1c5 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Preline | Insulation
55fd95a6-6748-4e42-99d3-78cbf080885f |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Preline | Passive fire/Approval to line
9fda9bb7-b0c1-424e-8015-373729aedf9c |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Post-line
447ca84f-a61f-486b-8caa-c5135bcc6e62 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Post-line | Lining
9e09cd1c-d0a4-489b-af7d-bdf36efba42d |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Post-line | Stopping
0254917b-2b13-4a67-9b8e-467147d2224e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Post-line | Finishing lines
7a2edb5e-9437-4c80-b687-234c493d7e6b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Post-line | Flooring
835c1bee-9e2c-492a-a3ef-d2f762057c38 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Post-line | Painting
9185ce1d-0b47-4d04-aab0-a8fda6a50da4 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Post-line | Second Fix Services
746241e8-6d19-4dac-b9f2-696ecd25a4aa |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Post-line | Fire Door
1b0f45b8-7d75-4155-8540-660d8f20664c |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Finishing
1e25d48b-0fff-460e-bdbc-83fa35815674 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Finishing | Flooring
83c92a63-f91a-4376-b600-07f384806aef |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Finishing | Exterior
3fc45661-51e7-466f-95c2-9a3a63969a4d |  | checklist-flat | fail | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Finishing | Lounge/Dining Area
f6c060aa-d36d-4796-9d35-5af0cf728406 |  | checklist-flat | work-in-progress | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Finishing | Kitchen
9c315a79-2a13-4263-b300-8771112e35e7 |  | checklist-sectioned | fail | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Finishing | Bedroom
f42f35f1-ad5d-4871-92c4-1a91b58edca5 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Finishing | Bathroom
6595ad9e-bf10-4093-af74-c0a75e4e2751 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Finishing | Ensuite
9f4b3bfc-1391-4a38-ba1e-197fa80b7365 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Finishing | Laundry
b8ee7c37-b444-426f-98d6-87b8185bd67b |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Finishing | Hallway
31487274-c7bf-476c-8c7c-7bf36ca1e32a |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Finishing | Toilet / WC
0c5cc732-1e2c-47c6-92e7-e5a3fff06e20 |  | checklist-flat | not-applicable | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Finishing | Client extras
8426e4ee-c375-4ebf-b4ab-810194b88d6a |  | checklist-flat | work-in-progress | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C102 | Finishing | Final check before locking the door
afae4c22-5abf-40d4-8206-415e6a0d3c4b |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103
d895c9bf-570d-479d-b5a5-45bddf2bb610 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Preline
759e1074-4b7e-4a0c-96d9-71e9a5cfbbb0 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Preline | Timber Framing
05f2d946-e3c5-41d4-959a-e232f0349289 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Preline | Internal Strapping and Framing
a95f6064-180e-4f0e-b1af-33b3374a788c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Preline | Suspended Celing
09688d64-6ce8-4b4d-b69f-b3a99a0532e3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Preline | Internal Doors
1e2b5482-9934-4d79-a355-5cb636d0b1d8 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Preline | First Fix Services
612d9157-2620-4652-94b8-ca0963c63f0d |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Preline | External doors and windows
528c93cf-88cf-495d-ae30-5c9244d4b36d |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Preline | Insulation
bf6bda6f-d3e5-4001-918a-ef7b3f3214b0 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Preline | Passive fire/Approval to line
654124b0-24b8-472f-84dc-6a8b55f7e6d9 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Post-line
59363ad8-cccb-447e-9453-8dabac9312d0 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Post-line | Lining
a35452ee-d3bc-4855-b067-b6c24d744f79 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Post-line | Stopping
014acef9-8736-47cc-9f53-cd70c8364d97 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Post-line | Finishing lines
1aaea308-aa4c-431c-9bf3-39afe5532d10 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Post-line | Flooring
a044bc8c-5148-4598-8f35-578c393f5979 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Post-line | Painting
32ecb838-92df-4516-ad66-54d392db38e2 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Post-line | Second Fix Services
4fbd3f94-aca8-407e-98df-09d5b8432519 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Post-line | Fire Door
6c195cb5-e80b-4075-b497-0636fd49dff6 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Finishing
e3e6d87d-365e-4145-829b-d18f761eb75a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Finishing | Flooring
83ac7e6e-09b3-4448-b78c-0787b6b864b7 |  | checklist-flat | fail | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Finishing | Exterior
004826e1-f727-43e6-8506-7a24ca144097 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Finishing | Lounge/Dining Area
34264c8f-691a-4dfa-a748-a99c762d5f04 |  | checklist-flat | fail | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Finishing | Kitchen
2eedb1d8-181b-4e18-8264-a22de0df3508 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Finishing | Bedroom
aff425b5-41e9-4b41-9ea8-6d23aeca4a6b |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Finishing | Bathroom
8196e2dc-3cb1-48bb-becc-b774b20847be |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Finishing | Ensuite
78a01100-c172-470a-8833-afa2e5ecad64 |  | checklist-flat | fail | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Finishing | Laundry
8303a188-8c82-4145-9744-3da0dcea35be |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Finishing | Hallway
89b48b6d-bd99-41a4-abde-457926513253 |  | checklist-flat | not-applicable | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Finishing | Toilet / WC
d51282ba-6d36-4cd6-a5f2-f05b8e1f920d |  | checklist-flat | not-applicable | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Finishing | Client extras
ad3d6a50-9907-4f9e-a8b9-0c9ecf593a1a |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C103 | Finishing | Final check before locking the door
1dc93c9e-2e45-4b4a-bc6b-7a1d110bec06 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104
26db7bdc-ad69-40e2-95fc-7e54d3772ed1 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Preline
371d9c11-9de6-4beb-81c0-8d75bdc8053b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Preline | Timber Framing
3ebe3967-e8a1-4709-9a48-252f760f015c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Preline | Internal Strapping and Framing
f0877e8b-d7a3-4efd-a076-ab7d60835d52 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Preline | Suspended Celing
2bd71248-f036-4ed2-8b5b-fbd155b35b71 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Preline | Internal Doors
0a1bcc3e-0cc5-4c7b-b192-be19af1e3355 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Preline | First Fix Services
607afbed-7b9b-4b04-b0eb-02ab76a65c4b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Preline | External doors and windows
abd67702-11ae-4eec-b93c-9f0d99fb99c1 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Preline | Insulation
5935f317-2c77-44e9-a9f8-40b5a06ba2be |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Preline | Passive fire/Approval to line
3e3728e1-87a5-4b89-981c-884db018fd08 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Post-line
1255dcd8-fe3d-431d-bddf-40497a64c316 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Post-line | Lining
ffa365fd-e304-439e-bbee-b2a93dc371f1 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Post-line | Stopping
838880ea-5039-4ae3-9491-682b1b14eb02 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Post-line | Finishing lines
10491650-8515-4012-af99-fa355278d134 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Post-line | Flooring
d2093872-6513-42ac-9393-2089323cc374 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Post-line | Painting
157adde9-158a-4036-9f94-962dd5cf8ffb |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Post-line | Second Fix Services
b9ca3eda-86e1-48fe-b7f3-dc845c725272 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Post-line | Fire Door
9c8ee87b-a4ce-4718-b26a-f0b77288fc73 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Finishing
7c57d68b-9e72-40d3-b3e3-99453079ef3d |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Finishing | Flooring
cdac32a4-f204-426e-a3bf-2c7a58ae68ad |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Finishing | Exterior
e6dd1ec5-af1a-4a09-af66-c6292b662f3a |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Finishing | Lounge/Dining Area
cc12991a-3a0a-4668-85ac-9b1ea0c99363 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Finishing | Kitchen
758b6c82-9cad-4dac-a01a-9ad77fb79697 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Finishing | Bedroom
1390ea3f-985e-4a5b-b7d3-fd4db2ba7326 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Finishing | Bathroom
a6b71ae4-1647-4eab-b42a-d0b66b12b631 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Finishing | Ensuite
8f7ee38e-f02b-484a-93b5-ff0425ad9753 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Finishing | Laundry
1a89deef-de90-49b9-90cd-c0ff1ba5402e |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Finishing | Hallway
f73e1cf3-6d5b-4724-a5bb-3501746e7165 |  | checklist-flat | work-in-progress | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Finishing | Toilet / WC
0b347959-54df-4fad-b066-e0a1e4f662f9 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Finishing | Client extras
4b9b9a38-8acf-4383-b079-ce2d1a97cc6f |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C104 | Finishing | Final check before locking the door
2f4ba4d1-ec63-49d6-908e-b6d1f28d77e0 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105
6a9a0ec6-a1e2-4dba-9c85-b800f0b46e90 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Preline
062663ff-ab96-4f64-b99e-c8f1a7f8f6c9 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Preline | Timber Framing
922309af-276d-49f8-8053-c3317df6e99d |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Preline | Internal Strapping and Framing
4f0f7827-4149-49c7-9c9c-d7b5174998b2 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Preline | Suspended Celing
d01a6cab-8172-47f9-8a8f-20d982e8fdb5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Preline | Internal Doors
c5c86ea3-64be-4937-b754-c1ffb4958aaa |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Preline | First Fix Services
e251f389-9bba-4094-8b7a-38ec9da27d34 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Preline | External doors and windows
529bcfcc-5f6b-4adc-b149-db170629cc37 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Preline | Insulation
dd5c7927-d5e9-445d-aeea-75edaafeacbe |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Preline | Passive fire/Approval to line
3e5a7bfb-c901-470e-a64f-a0663a2547ac |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Post-line
0da579c5-65e1-45e0-8654-5b975cb47ecc |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Post-line | Lining
fcc53512-b3fa-4a28-b909-bff84fa75dc1 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Post-line | Stopping
5a5e063c-2745-4c99-90a3-710421acf957 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Post-line | Finishing lines
ed2ef357-12de-4b0a-b034-10d73b3959f5 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Post-line | Flooring
d1a6318f-06f0-49e1-93eb-00a8c5cb8ab4 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Post-line | Painting
86e0c105-a4ab-471d-b5b2-8be846cb7ce0 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Post-line | Second Fix Services
86005194-b31f-4f01-83be-723b1829e54d |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Post-line | Fire Door
02b561b0-d130-4356-ac3c-c4a173ac52cc |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Finishing
8edfdd7a-dd70-4970-b7bb-15400b9cba07 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Finishing | Flooring
dd95f504-b2e3-4332-bfde-5e7e84cc470f |  | checklist-flat | fail | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Finishing | Exterior
d6f022c4-055a-4b56-ae0e-58413df0f0e5 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Finishing | Lounge/Dining Area
8df0f49f-4395-41d0-b973-458ce0678b5d |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Finishing | Kitchen
29dbbe5a-52b9-479f-a01e-b0f75fe3be5c |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Finishing | Bedroom
7a9dffcc-9d8d-4442-94c9-0a8bb7185c4a |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Finishing | Bathroom
1ea40177-030b-4b40-91da-5474fbf015ba |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Finishing | Ensuite
261913b2-5824-4a96-b037-50d811bdafeb |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Finishing | Laundry
4e0bf760-27e1-4a5e-9072-248ea1564b39 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Finishing | Hallway
9094cf24-f3f3-4088-bab6-4b52fe3ca0c8 |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Finishing | Toilet / WC
b3c408d2-acdf-401f-bb2a-ee40052fc2b3 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Finishing | Client extras
974ef0b3-451a-4468-8cf8-13a0aa2a1d60 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C105 | Finishing | Final check before locking the door
bd038000-b60d-473a-8889-a8d1f68e9bf2 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106
62af7cf7-f2c8-4315-8397-a21df4dec579 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Preline
a3ca9f57-a9c5-4ae6-8453-9f1096f27f98 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Preline | Timber Framing
63151bca-a93f-416e-8969-f15d40feaaf9 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Preline | Internal Strapping and Framing
5c9fc59f-6135-418c-8050-9ad40761392b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Preline | Suspended Celing
f8c025a6-c588-4bc4-8758-f498dd520f83 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Preline | Internal Doors
4fc54337-406c-485d-b997-06ebc8943a0e |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Preline | First Fix Services
6372ec8f-4e46-440f-a19d-c9f2708dfd44 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Preline | External doors and windows
093663f0-c8f2-400f-a30b-2e5a3fca1612 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Preline | Insulation
baded6a6-cc10-4a70-a335-c2bb000416b4 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Preline | Passive fire/Approval to line
258b0011-cec9-40d2-bed0-15ff271221f8 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Post-line
1b742ab1-d43c-42b6-95b1-b1c7fbf51e18 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Post-line | Lining
c92e90c0-2071-4645-b8cd-8b0ede9947b7 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Post-line | Stopping
457bb9d1-7142-4442-b9b7-d3a085b70f63 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Post-line | Finishing lines
14c2d9d0-b62f-4e48-864f-349d2874ce2f |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Post-line | Flooring
33a3eaaf-0219-47b3-8dde-e0b97a088934 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Post-line | Painting
cdc35f26-0bb8-4d73-944a-e4480881dea6 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Post-line | Second Fix Services
5a6f3f48-e11e-4200-9a3f-c85f2eaafefb |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Post-line | Fire Door
69355eaf-8adc-4d8f-a3ad-ed7a6cd0af80 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Finishing
61afd7bc-4341-4769-8b3f-1c6bb19fe6fc |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Finishing | Flooring
b6f199ef-ea0a-4f4c-a612-ab134cd5d4a6 |  | checklist-flat | work-in-progress | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Finishing | Exterior
589cccaf-f1fb-4991-b554-ab37f7216358 |  | checklist-flat | work-in-progress | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Finishing | Lounge/Dining Area
82591272-efc5-4bd5-a670-5906aafc3d38 |  | checklist-flat | work-in-progress | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Finishing | Kitchen
53091243-fcc8-4dac-8f57-c5bae93204e1 |  | checklist-sectioned | fail | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Finishing | Bedroom
b2a25131-fb80-4100-8d9e-6cd326239031 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Finishing | Bathroom
1ed54a80-3a98-4f11-b3ee-d01a97aef0a0 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Finishing | Ensuite
3588bab0-14a2-4812-b541-fd691e220824 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Finishing | Laundry
75bf1462-ce9e-43c8-987f-efc0a998147f |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Finishing | Hallway
c17e5f73-ea69-4996-9265-ac54fc03b9d6 |  | checklist-flat | fail | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Finishing | Toilet / WC
47090202-6e8c-446c-90b4-01e771f5547d |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Finishing | Client extras
b0089702-c199-4be1-9d9c-18d3bb735122 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C106 | Finishing | Final check before locking the door
6b8a6c6b-a1e9-4ce2-bb69-0cd43c42c6a8 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107
faf60314-a9e9-4b2d-adfc-99ba2e589fdb |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Preline
01b59d18-6c6d-4635-968c-c7cd322cdb03 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Preline | Timber Framing
820db080-54c8-4299-91ca-fe03a63d457b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Preline | Internal Strapping and Framing
7844d78a-8626-45a9-9d36-c5bfa62438e7 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Preline | Suspended Celing
735af77f-a285-4474-8625-cf9d8d9ba6c4 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Preline | Internal Doors
180f0579-0e4a-4713-91fd-ff86a43e291a |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Preline | First Fix Services
89029b71-38d6-4f9f-898d-2df9e2bef0f1 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Preline | External doors and windows
3610b094-c6e9-4b41-a203-876016eaa1de |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Preline | Insulation
7ef66612-0a09-4f84-a45b-4832b1856b2d |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Preline | Passive fire/Approval to line
93f18b4e-f3b1-4479-8652-eb01f532ad27 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Post-line
c233f6c4-3665-4ba3-af0a-be36fa18e65c |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Post-line | Lining
04949180-dc66-4844-ae30-a21211436f50 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Post-line | Stopping
bf6a937f-c433-4d42-bce2-58e1876df8bc |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Post-line | Finishing lines
e949d845-49a7-4ffe-af09-f912f4425911 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Post-line | Flooring
0df48bb3-1f29-4442-abff-b727841ea124 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Post-line | Painting
10298711-426a-4fe5-819d-9c89761e5649 |  | checklist-sectioned | work-in-progress | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Post-line | Second Fix Services
fd2184dc-f785-47aa-a87c-89998c36032f |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Post-line | Fire Door
0ed0687f-4344-4180-b5cf-5b7ab077688a |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Finishing
76e129b5-fff9-4096-acd4-ccc7ebfa83c3 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Finishing | Flooring
5c7d5018-0163-4c98-9677-584d9c625d92 |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Finishing | Exterior
4e7307d6-b63c-4741-9f80-8f153766e4d7 |  | checklist-flat | work-in-progress | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Finishing | Lounge/Dining Area
309cd2eb-d2bf-4d41-beab-f8cb8ea0b5fa |  | checklist-flat | fail | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Finishing | Kitchen
c62c1c5f-e781-45d2-81c2-02ca8cc11ec7 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Finishing | Bedroom
b3d95ad8-beee-433c-b97e-eb853988ad13 |  | checklist-flat | work-in-progress | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Finishing | Bathroom
4a870a0f-f755-49de-8405-0b7bc1683f51 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Finishing | Ensuite
b77d783b-739f-469b-943f-422c1bb5a0e7 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Finishing | Laundry
c6ef8145-733e-4754-9714-2a035df08807 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Finishing | Hallway
62a91cf3-767b-4303-8a45-c8e2783ab34f |  | checklist-flat | fail | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Finishing | Toilet / WC
35920260-3aff-42db-b965-31db9500d246 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Finishing | Client extras
9bc8ae2c-5829-488a-b481-5d610dbb5b0d |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 3 | Residential Areas | Apartment C107 | Finishing | Final check before locking the door
8db91d4e-55d0-4a0a-8555-109934c6812d |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4
b0d7e8bc-e28b-4f7a-9e04-a515e883f1d3 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas
c019c4d0-6fa6-4b9e-ba46-23afb6bcd38e |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor
4c9fd1e8-54fe-452b-9e8f-ff55e8de7db0 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Preline
46fa48ae-a4d1-41fe-bb34-7fc3e8659f85 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Preline | Timber Framing
6f7316f5-9bc6-4992-b51e-3d57dadf317e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Preline | Internal Strapping and Framing
5cc0cfaf-87d4-40af-9147-b3461c731540 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Preline | Suspended Celing
5b8f1951-5d99-4492-9548-7ca6e939090e |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Preline | Internal Doors
58550be4-5105-44db-80b3-065806205f6a |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Preline | First Fix Services
c9102ea7-f09c-48e7-bf6c-dc455eedfdaf |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Preline | External doors and windows
109b49b3-4eeb-4c5a-a316-a4fc74e5b22b |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Preline | Insulation
54a5426b-58c6-4a52-a469-f100521f20ee |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Preline | Passive fire/Approval to line
f3d2ca0e-478a-41e6-8c3b-5deffd51cbe1 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Post-line
75ccba3d-e725-4886-aa66-3484277d6063 |  | checklist-flat | work-in-progress | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Post-line | Lining
779cfcfc-8f58-49b7-b92b-9b0148159e51 |  | checklist-flat | work-in-progress | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Post-line | Stopping
42fd786f-6260-4d22-b42f-8a41c934853f |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Post-line | Finishing lines
ac46a777-0473-480b-86d1-38fc13a57431 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Post-line | Flooring
20995228-79b6-4cd0-ad08-6cabe57ef5cc |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Post-line | Painting
4a1f068b-4d3e-4149-968e-d0cf48585a57 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Post-line | Second Fix Services
f33873f8-2f74-4209-879f-9201bc7af15d |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Post-line | Fire Door
b896d242-b5ba-41f4-9583-c0d9007a3c1f |  | checklist-sectioned | not-started | efe9dd8861170a4f6c877309dd15ef71545349ef8eb7e2755d191ae9183ec15d | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Common Areas | Corridor | Finishing
7f4d7b98-c8b0-4b92-8e80-c85d20fec281 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas
6a395808-e13f-4ec1-85d3-f15a70f57199 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A
d1fb9805-62aa-4a85-bcf1-6f73f03b82b9 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Preline
24832970-a022-4182-b1e9-0244c9235755 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Preline | Timber Framing
72aff71c-65f4-4686-a4ce-0a00e96bbe9f |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Preline | Internal Strapping and Framing
ae6ab84a-0f21-4a8d-a9f5-0311af70194b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Preline | Suspended Celing
88e5e6b9-3985-49a2-91e7-6f6ed6b2366d |  | checklist-flat | not-applicable | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Preline | Internal Doors
db2457a9-9b54-4c9c-aaf5-3f1f04507c87 |  | checklist-sectioned | work-in-progress | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Preline | First Fix Services
e9923b2f-aa6e-49a8-a9ad-ab2ff9765260 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Preline | External doors and windows
0c2d9825-2dfb-4327-8186-3193d5aeca3c |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Preline | Insulation
2a09f1f1-93ec-41e2-8349-506ffbc1fbda |  | checklist-flat | not-started | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Preline | Passive fire/Approval to line
fa3a9a56-6687-4492-8385-b64652265e45 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Post-line
67540f29-6f8c-4d93-98cb-d290155d99e2 |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Post-line | Lining
8b187771-f0a2-4c78-b27e-e564f1cf8240 |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Post-line | Stopping
bfe8e5aa-4284-4a12-866d-0c2c672c94b9 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Post-line | Finishing lines
fdac8f9c-820a-4ecf-a726-fbb3e199ab98 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Post-line | Flooring
5cee9183-c190-46d7-bb78-af0fa4616c2d |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Post-line | Painting
7980bf2d-be5d-40ff-84ba-9a345e9cbb42 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Post-line | Second Fix Services
8ccaf58d-c8fa-4ce0-a6a6-8e7f230aec2d |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 1 area A | Post-line | Fire Door
3120ce17-b205-4107-8f7c-2fc8162d26af |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B
7319958d-c826-450b-8a98-51b7837fd773 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Preline
a1349328-67d0-4b0c-b949-a4eb9e86909b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Preline | Timber Framing
cfa916bf-a0ce-4a24-83a6-449160016be8 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Preline | Internal Strapping and Framing
4d5f83a7-9b59-42d1-9744-458094513b25 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Preline | Suspended Celing
0f63f02a-9f61-4e45-a104-90bd8dfd242e |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Preline | Internal Doors
ba3fcd67-8633-4281-b9b9-c2ab7692913d |  | checklist-sectioned | not-started | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Preline | First Fix Services
c185e3fc-f5a5-4ab9-b119-02222204d870 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Preline | External doors and windows
36f18169-6ff4-405e-9b65-ba937f7f06bc |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Preline | Insulation
7e88b1d4-4a76-4d94-b063-ebc8a511ed79 |  | checklist-flat | not-started | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Preline | Passive fire/Approval to line
7643aa11-91b7-41e0-a96e-b94fab00b469 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Post-line
6f1ed119-a99d-4d9a-85ee-4f4067ef3c9e |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Post-line | Lining
3d2bcfc6-4f78-4805-9b82-a16fa9e9b68d |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Post-line | Stopping
5a1b3c9e-abc3-4958-bf04-788017f4ab4b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Post-line | Finishing lines
6b4a1bf2-7930-4a82-a998-a51b059a2032 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Post-line | Flooring
5ec77b41-1726-4a7e-8349-9c1d57713cb0 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Post-line | Painting
a9ba1e00-c375-4ce8-b14a-8697a5aa8a15 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Post-line | Second Fix Services
e841b0f9-8851-46b4-8e05-929a47147c45 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Electrical 2 area B | Post-line | Fire Door
b715fe09-b302-4d1f-9dec-e77ac31b1e4a |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A
6021734b-e613-4ec4-a4e1-c0d06edf7047 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Preline
3e2aad7a-dc41-4c53-99a8-2f4fe934ee34 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Preline | Timber Framing
5b245a80-1c7d-43f2-98ac-0bd8deac4528 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Preline | Internal Strapping and Framing
8f3e346c-477c-4b7d-85ac-0cd3f3e30032 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Preline | Suspended Celing
339474f6-6330-4420-a706-34cc99b56352 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Preline | Internal Doors
b695961f-2b3c-454e-82b3-1f4a34ae370f |  | checklist-sectioned | not-started | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Preline | First Fix Services
63e72a4a-4a6b-415b-b363-7643d0dab603 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Preline | External doors and windows
79d40e84-cd8b-49da-8953-f3b3808210c1 |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Preline | Insulation
46fd7a93-093f-4919-8525-462c1d66ad0b |  | checklist-flat | not-started | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Preline | Passive fire/Approval to line
a6adc6ae-e415-47f1-9d6f-89efccca136c |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Post-line
8804b6f5-c17d-4591-a8da-ad9b9bacfbca |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Post-line | Lining
607c5726-a57e-4109-9e9a-19933f15aa20 |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Post-line | Stopping
efaac114-3c10-41c4-8e6d-df6b8d7be8f7 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Post-line | Finishing lines
69140329-296d-4a88-885c-c72d084fd1f5 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Post-line | Flooring
09488447-8510-46d4-b6dc-0af5b425fc9d |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Post-line | Painting
3b87bee7-ba36-4cbd-8e16-0b7ab48b04a0 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Post-line | Second Fix Services
8181f99b-59d8-4461-bff4-b0fb23b3bc5e |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 1 area A | Post-line | Fire Door
63341d6e-0bd1-4f39-8762-76a077c38110 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A
10367916-caf6-489e-8fed-eb152f63c867 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Preline
2238db53-5c36-4bac-95d3-5d86ce18d7cf |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Preline | Timber Framing
33ea3d8d-5cc2-4f5f-a248-07ac8050ed61 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Preline | Internal Strapping and Framing
512a5e40-c2ac-43ad-a363-83bc8daf05d4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Preline | Suspended Celing
52674d79-4437-43bd-a799-de29ed8b258c |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Preline | Internal Doors
0cc148d4-5637-441b-a1b1-beba8829960f |  | checklist-sectioned | not-started | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Preline | First Fix Services
fceb82a2-a1c9-43f1-8838-f6e7f80f0abe |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Preline | External doors and windows
fd9b3055-05e7-4116-8b52-08259e9f4508 |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Preline | Insulation
75328c2c-127c-4316-9394-0e07bf98864e |  | checklist-flat | not-started | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Preline | Passive fire/Approval to line
a010f48c-d026-46cb-8a52-edb46e022deb |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Post-line
259b2679-3464-4ea8-839d-44ff20da8e9e |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Post-line | Lining
d029e57e-e30e-4059-9971-4162c91180d9 |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Post-line | Stopping
c3514cf9-3ec2-474f-b0fd-9899df9460a2 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Post-line | Finishing lines
fb611a0c-557c-4b8c-96ed-618d124ba6d3 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Post-line | Flooring
ced5ef6a-42c4-4a24-8973-acd81db2edf4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Post-line | Painting
8ca62b0d-8946-42a7-acb0-063660bbfee2 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Post-line | Second Fix Services
c569f6e7-a86c-4375-a837-ecf6310c3ec5 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 2 area A | Post-line | Fire Door
3e9ed453-1c50-4440-a296-4a4504235e82 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B
7f2fefcc-e054-435c-9c12-4db78743769a |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Preline
3a3e7bdb-34ec-4fc5-8c36-e58d5046be6d |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Preline | Timber Framing
2d84af38-fb95-43a9-b43c-209d1709edb4 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Preline | Internal Strapping and Framing
8e716042-1870-47b8-ba8d-3dddbf1661e2 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Preline | Suspended Celing
04676866-7c74-4693-b908-fb42e79bfd59 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Preline | Internal Doors
50cb1a1e-b579-43ac-a85e-80b8ed1eecfe |  | checklist-sectioned | not-started | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Preline | First Fix Services
bea2c53a-1426-47a3-a1f1-ec6f2faa1f3c |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Preline | External doors and windows
d363a0d5-784c-49cf-a82c-33c90e344216 |  | checklist-flat | not-started | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Preline | Insulation
4b411aa4-026f-4b73-a291-070f654e3308 |  | checklist-flat | not-started | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Preline | Passive fire/Approval to line
9c6e7acd-d632-4a86-a9ff-f6eaf31f8ba8 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Post-line
e769caf6-e106-4a9f-88a9-71a06b4d1bfd |  | checklist-flat | not-started | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Post-line | Lining
69c9f140-254e-4260-b8db-8ff87d3e3afe |  | checklist-flat | not-started | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Post-line | Stopping
e02273ee-de98-4f1f-8592-85cceed70f0b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Post-line | Finishing lines
166ef4c2-9174-49da-8105-187f97f9d1b6 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Post-line | Flooring
79bad5d0-d4a4-4a05-8340-3bee4e091a58 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Post-line | Painting
d3136bec-3ec6-4bc0-9f38-c0408c782ca1 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Post-line | Second Fix Services
3172a206-e2b6-46cf-bda5-78d7d63a12f4 |  | checklist-flat | not-started | a91a4a5e49fffbc21c836e8f3401a8f586105e32d97cc8c7464dc0051f61d698 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Service Areas | Services 3 area B | Post-line | Fire Door
819fd96a-2950-415a-860f-ac0a315f8fc2 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas
889389d1-9c72-478e-b8ca-597b156a1d90 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88
88750845-48ba-42c7-bbc0-368261b2df00 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Preline
349c52c9-5599-4155-99a4-5e5fcced83ab |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Preline | Timber Framing
f64da9f0-db11-41ae-873e-64b329f66626 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Preline | Internal Strapping and Framing
aa5dc01f-8baf-4e00-acb6-a4197b09fd7b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Preline | Suspended Celing
ab4bb5bb-79d5-490c-a43d-75bf3ea5eb90 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Preline | Internal Doors
29dd91fb-96eb-46b4-a034-db7cf7e7ce34 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Preline | First Fix Services
2d0d6b6a-e0b0-459e-a294-f56f080d1ae8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Preline | External doors and windows
4e1627b5-2d89-4417-8a10-58fb5e219797 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Preline | Insulation
d51e9e65-f734-40f9-822e-5626d612ac41 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Preline | Passive fire/Approval to line
413babdf-8c9f-46b0-92a7-c9ef76573fda |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Post-line
f94f2f15-5745-47dc-b3d8-3c08d89a1a0f |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Post-line | Lining
e779c33d-476d-429f-9d72-136f32b184b1 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Post-line | Stopping
694de2bb-707e-43e6-87b3-7b9661ceb33b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Post-line | Finishing lines
c1bf69db-462d-441a-a7ca-a1e021cf7c3c |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Post-line | Flooring
83b6d4b5-95cd-4b80-82b2-02cc8353d3f9 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Post-line | Painting
9bc77d65-5d6a-451f-b3bc-89621f56ea50 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Post-line | Second Fix Services
a7c16987-faff-406e-bc4d-8e57c2fca03c |  | checklist-flat | not-started | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Post-line | Fire Door
ba7e93ad-ad46-404d-8c05-6325fb845cc2 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Finishing
c3111f27-82d5-429f-8fef-7564f3622b21 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Finishing | Flooring
0c057c72-823e-4877-a7c9-bf40e0123ca5 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Finishing | Exterior
53d47d0a-effe-4cb6-b66b-ab9d1854253d |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Finishing | Lounge/Dining Area
915536ce-fc37-4c61-b37c-aea58a8819f4 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Finishing | Kitchen
39ede516-63f3-48ad-b06b-8364d059f77e |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Finishing | Bedroom
a83878f7-8aaf-4488-b1fa-7010f9e573ee |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Finishing | Bathroom
2991cf52-ad9b-45ea-87f5-8f123a1f54e5 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Finishing | Ensuite
cbddd194-c05a-47df-adb4-9c901190622d |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Finishing | Laundry
cf6d809e-c0ac-41eb-927c-a1e8bfddeca6 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Finishing | Hallway
826fae00-a068-47a4-9efd-8b1ff83b838b |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Finishing | Toilet / WC
180cb1b5-70fc-4db8-a087-2037e84889f7 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Finishing | Client extras
9a98a276-30ba-4f17-a5c4-5105c135e9dc |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D88 | Finishing | Final check before locking the door
7ec4709a-e2fb-443f-9859-0b7b10b43dd6 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89
a7c18727-3875-4d0d-b495-69b5077c769a |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Preline
e066efbb-3503-49d5-9ea3-214fc344b9bf |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Preline | Timber Framing
0bab5678-49a9-4034-837c-54a859c91d25 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Preline | Internal Strapping and Framing
95cc6cba-c907-4293-aba3-4d9cbac3f9ff |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Preline | Suspended Celing
bab2cff4-29b8-4fca-b5d9-8d88034149aa |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Preline | Internal Doors
8ba06d30-83ea-4f43-a765-1fe85bcb5236 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Preline | First Fix Services
8fc63514-24a8-48b4-80a8-bf5cda6ba5e8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Preline | External doors and windows
cc6c512c-e25e-4ff1-b534-4de772792d15 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Preline | Insulation
1972246f-a673-4ddb-9a91-ff13650db795 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Preline | Passive fire/Approval to line
12275c94-620e-4482-b4f1-9f59b0ba695b |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Post-line
cf101fc3-bfd0-4520-8dba-80bda588e54f |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Post-line | Lining
0364cb3d-ec33-4ad8-803b-1d16796ec4df |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Post-line | Stopping
11c1c708-853e-4d95-b9f5-4ae1e5e54b4d |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Post-line | Finishing lines
588b49a2-eec6-4eab-b7d4-9c640ba61ace |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Post-line | Flooring
e737269c-a876-41a4-954f-ecfc0bfe17db |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Post-line | Painting
d26998f1-dcb9-41ab-9757-8e7a29e040df |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Post-line | Second Fix Services
03cd6e1f-9e1b-4351-b058-89c6337f4ee1 |  | checklist-flat | not-started | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Post-line | Fire Door
272bc364-9023-4e79-a363-22daaa9f4cb2 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Finishing
80c17a8b-6e65-44f4-b16e-5140b55daaf5 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Finishing | Flooring
0455f014-4154-4103-a9c1-0c5ce0419d07 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Finishing | Exterior
b84ab47c-ce0b-4d20-8815-39b1ca109758 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Finishing | Lounge/Dining Area
17181b40-f301-41bd-bb30-ff86d7c5bf3d |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Finishing | Kitchen
f4b07dea-d836-418e-946d-e0847683c286 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Finishing | Bedroom
42d9022b-c3a1-4688-8df0-6785b2d0d57f |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Finishing | Bathroom
381a6985-dbb1-430f-b057-92633ff9072c |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Finishing | Ensuite
9d824354-6aa6-4ac2-a6d9-ff1f187db2f1 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Finishing | Laundry
6bee32c3-6348-4fd9-941e-3687a26fcba6 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Finishing | Hallway
5d2863bd-1c59-449b-a98d-7e35d20bcb24 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Finishing | Toilet / WC
10400c95-9edf-4f8c-b138-6250085d5509 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Finishing | Client extras
dd1d355d-192f-48ca-ad71-295e22bfa209 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D89 | Finishing | Final check before locking the door
eb63716c-af6c-4a12-8c70-45c08b107ff2 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90
011215a1-ebf3-4863-8b98-175a4c33b35e |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Preline
a3f60762-4b0b-405b-a798-47a3ba4791c7 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Preline | Timber Framing
27d043da-6b37-4deb-8060-8a996f1371f8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Preline | Internal Strapping and Framing
782a50e6-77be-432c-b241-29b3596a34d5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Preline | Suspended Celing
7621056f-8d2d-49ab-a43b-068f4b21dd21 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Preline | Internal Doors
cfa42b7b-b64a-49fa-874b-63f1ee4a24c2 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Preline | First Fix Services
309041d8-aa1f-4385-842c-2631d442706f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Preline | External doors and windows
d0d7b018-0b13-4695-88c8-6c431cc0b239 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Preline | Insulation
11f29e12-df5e-4bf6-b3a1-5d98d0a90401 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Preline | Passive fire/Approval to line
f84d5f1a-253f-48ea-84f1-ecce352cecbc |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Post-line
a73d4c17-4944-4691-82f9-f60e8eb748fe |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Post-line | Lining
56ecc205-60ab-4267-befa-be767047de38 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Post-line | Stopping
90e7a1d0-304e-4713-a11f-e230289c564c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Post-line | Finishing lines
9951ac27-1158-4178-bc73-1cdf9f3282bb |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Post-line | Flooring
01fc9304-0144-4586-8339-074a55329918 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Post-line | Painting
e8a665f4-c989-4415-8b00-3266f69e5f20 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Post-line | Second Fix Services
1a5bfebf-4dea-4d9e-9c15-6cee8bafa7c4 |  | checklist-flat | not-started | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Post-line | Fire Door
a628788e-5eb6-4065-9e91-ed11ddc500c0 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Finishing
81270f17-669e-4073-af8f-c3cd8a47ee92 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Finishing | Flooring
cc30d451-77fa-40e9-b29b-f4a7e3354cec |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Finishing | Exterior
1dfd23ce-9a1f-4286-93c3-da9e94318b5a |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Finishing | Lounge/Dining Area
20900658-1acf-4b96-b227-024a0eda4e74 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Finishing | Kitchen
a30d54cb-0111-434d-b134-6f0a82cdb86f |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Finishing | Bedroom
f33749aa-f35b-4eb5-83ff-891a955c4884 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Finishing | Bathroom
040c05c4-b5d0-46a5-8a48-17f8257f3627 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Finishing | Ensuite
600309bf-96f1-4e9a-a7c5-f23344233e99 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Finishing | Laundry
2edc5c22-8e1b-4a4d-81fe-427beb77259e |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Finishing | Hallway
ceb6e502-1e49-479f-a6bf-8b0f9342063a |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Finishing | Toilet / WC
af401b18-29ba-4518-98af-faead3537610 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Finishing | Client extras
b6ef798e-4c89-4004-a915-0dda3bdfd64f |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D90 | Finishing | Final check before locking the door
95e352ae-147d-41be-900f-aee5e83f726c |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91
15ae882c-e70d-4cb1-910f-7a98c019e77a |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Preline
bce6a67d-56f5-4131-8dc6-7ed4b1501c78 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Preline | Timber Framing
2f82a7da-5cf1-45e1-85d5-37d8582581cf |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Preline | Internal Strapping and Framing
b73f289a-b9b1-4ab3-95a4-aa6b99d3c65d |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Preline | Suspended Celing
cb4d6375-d30d-460e-850d-2430e7c3c138 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Preline | Internal Doors
b16b8186-cf3a-4902-bf1b-4b51df1fb99f |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Preline | First Fix Services
6673b61b-6c12-417e-9c69-5437765c1f01 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Preline | External doors and windows
1a8834cd-6061-414c-8c07-5b1a0a431868 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Preline | Insulation
697e3282-7d07-4932-8700-48ab4f7ce58f |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Preline | Passive fire/Approval to line
ded67c47-04fb-4db8-9049-511cc5b87f04 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Post-line
761fa11f-592e-4c2b-82ca-3cdb57d6bf6d |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Post-line | Lining
92516967-f9ba-405a-894c-df76b6ed568e |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Post-line | Stopping
9ecb9d5f-55ee-4ebc-a158-f5735cb52ffa |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Post-line | Finishing lines
af900706-62ec-4b47-8423-e28bf6753a65 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Post-line | Flooring
57b4ee6c-30fa-4a97-b2c3-28588038f97c |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Post-line | Painting
00a80c3f-7cd1-4ac3-bf87-3d0abdd07948 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Post-line | Second Fix Services
a1c1b3f5-b47f-4f64-8197-9c5f6f75e99b |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Post-line | Fire Door
f29678c1-06b8-47d5-a277-3c4dda2ae3f8 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Finishing
c9280e2e-41e2-47d4-a313-7be49b74aa68 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Finishing | Flooring
bbebb7b9-5a55-47e0-92d0-ef81119773db |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Finishing | Exterior
9a80bf21-5391-4f80-87ba-c2b6e6195b00 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Finishing | Lounge/Dining Area
2b6b5027-db29-4d06-bd1d-481e6afb7a04 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Finishing | Kitchen
4126e9d5-a6e9-4329-9937-4e0324c72b5d |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Finishing | Bedroom
9668e600-65df-414b-a1e2-3fd3cc7c5598 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Finishing | Bathroom
8286d4a5-b71c-4b46-901a-f8e2b7a32ac6 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Finishing | Ensuite
af86a78b-f402-492b-8338-7416f34503f6 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Finishing | Laundry
241a7b74-8cc9-4487-8a86-bbb4b9dede9c |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Finishing | Hallway
fdebc7ee-963f-4791-8976-ac916ab54c93 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Finishing | Toilet / WC
bfbae3cf-e737-44a3-b9a3-087e0ac8c341 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Finishing | Client extras
df1f6380-57cc-4358-8f62-2339e1184f5d |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D91 | Finishing | Final check before locking the door
3dd4d525-cfec-4782-84cc-3c420460bed4 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92
9d492223-ed09-4fa8-b6d1-760fd37ece9a |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Preline
e1cb09cf-cad6-4446-9585-01436c7182d6 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Preline | Timber Framing
04ee4055-6a12-423d-ba8e-cf1f4a8a262a |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Preline | Internal Strapping and Framing
99c2e372-e9e1-4703-a900-2e541fe8ea5c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Preline | Suspended Celing
a80d3301-5b80-4ced-b15e-7f2a7ca3a3ec |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Preline | Internal Doors
3ca51345-25b7-49c7-835b-f9ff6bf66a6e |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Preline | First Fix Services
6bedb9f9-f6dc-4102-830e-79000697df34 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Preline | External doors and windows
06ea88e5-336f-4232-930c-9f432671941c |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Preline | Insulation
10c1e3b5-4303-4e26-84bf-5c64be681193 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Preline | Passive fire/Approval to line
634b37b5-6750-47e0-934d-a08c8178e00d |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Post-line
4884caf5-07a9-4a6a-bfaa-8e062fb2ed4a |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Post-line | Lining
fa97d68e-fe9b-4be3-9582-95354b7c8a06 |  | checklist-flat | work-in-progress | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Post-line | Stopping
3765d5da-ffb7-439c-8653-7dbea847443e |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Post-line | Finishing lines
2a82df3b-c018-4109-9068-c01570e3c577 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Post-line | Flooring
53022c06-aec7-475f-9cbe-c1a0efe8e7f5 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Post-line | Painting
c7ac4d57-10fd-4883-8591-c19621e7de69 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Post-line | Second Fix Services
f9ad0ce2-5d55-4627-b26c-6d2bd568291d |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Post-line | Fire Door
424eb6eb-827b-4c5b-b5f3-9888613de951 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Finishing
1a58223f-9720-4de0-a16e-799b9b5c5102 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Finishing | Flooring
8a46f374-1be0-4b1a-a18b-95e81d9e1f55 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Finishing | Exterior
451c5e51-3fe0-468d-a061-1552bf763faa |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Finishing | Lounge/Dining Area
ddf990ba-fceb-4b82-b028-066456b8353a |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Finishing | Kitchen
4972ecda-967d-4834-b052-5cd0b406e8ac |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Finishing | Bedroom
55331e3a-2215-4fe8-9374-4a6680d7632d |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Finishing | Bathroom
b8bf2240-acb4-4ae6-84be-76aac29d7bb0 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Finishing | Ensuite
0a1b7a71-7a66-43a0-a209-6d8eb77839fc |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Finishing | Laundry
abcd89e3-03d0-4374-94de-892c6783c15e |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Finishing | Hallway
5f65eace-d366-457d-a54f-105f67ab0cfb |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Finishing | Toilet / WC
de9d6256-1895-4d56-844c-6375d9d854f4 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Finishing | Client extras
3368feef-6395-46b6-b5c6-44ad3e292900 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D92 | Finishing | Final check before locking the door
bc0c132c-7713-486b-b0fe-e4fd654e3b19 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93
4f2f3770-5fa7-4fe6-bc34-8a6df2f43dc7 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Preline
49461a91-cde1-4733-aa1c-2589fd10002f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Preline | Timber Framing
3a1f810d-218f-439e-b01b-ce5a3e14bcc9 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Preline | Internal Strapping and Framing
f35adece-60f7-4203-bb78-fa60a88df567 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Preline | Suspended Celing
8547a91d-ade3-40c5-96b7-c53de0ced779 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Preline | Internal Doors
ee6c1459-79d3-42d2-9f7e-1adb94133440 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Preline | First Fix Services
6a90a213-728b-48c0-8188-3183a00b1953 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Preline | External doors and windows
6575c126-ea73-403e-8bae-d6e885e6cf03 |  | checklist-flat | work-in-progress | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Preline | Insulation
7040a95f-7cea-4819-abe6-a14440d9be7d |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Preline | Passive fire/Approval to line
0dcb8c1b-ae58-4dd4-ad86-4b969bc137ad |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Post-line
815fe7cf-cff9-4a32-8416-41fabf048b4b |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Post-line | Lining
377dac03-99c7-4e54-a2b8-563f97753521 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Post-line | Stopping
e61bb09e-d76e-44ef-9ea9-e9e9614c2e45 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Post-line | Finishing lines
8f4678d5-3ba2-4a81-9ff8-f701a3a47cba |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Post-line | Flooring
cddcfec9-13aa-40c5-82e5-e97cb9940df4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Post-line | Painting
307915ef-96c2-4199-85ca-1e2f0f9c20ec |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Post-line | Second Fix Services
74704fdd-100c-4ef7-91fb-a39fa837dc68 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Post-line | Fire Door
d146964d-de51-4ba0-87ae-714bdc540b73 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Finishing
9a7f6e4f-d48a-4797-ae24-e6cbf85c7ab1 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Finishing | Flooring
0bf3c4bf-7495-4231-b685-5cf7d9e5c7fa |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Finishing | Exterior
67ebc628-70f9-4c40-8ad1-9ede4a104013 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Finishing | Lounge/Dining Area
7337ebda-f4d1-44d9-9648-bf952e066bba |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Finishing | Kitchen
d83556f0-75a8-490a-a636-4addcb55aca4 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Finishing | Bedroom
dbc87f4b-515b-4d5e-84fb-a4229619c787 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Finishing | Bathroom
44041ee0-100c-4329-be81-ad69a85b7426 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Finishing | Ensuite
639d8ad9-44b1-4bfa-a5fb-9c0a1872c540 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Finishing | Laundry
cdf68695-e579-402f-8ae6-42a47053f06f |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Finishing | Hallway
3dad1e9a-7434-47fc-b7ce-22426c0aad0f |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Finishing | Toilet / WC
049eb775-f292-4bf1-ba17-6f4d450f7deb |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Finishing | Client extras
06e247de-73c5-4a94-a4a6-2c10eb91a969 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D93 | Finishing | Final check before locking the door
e42066d9-7891-4a12-8c53-e8b644a8a7d5 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94
152a5511-2fc0-4aeb-b5a7-73cc66501e85 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Preline
ddb61f4f-4e81-4375-af46-b3536d0c028b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Preline | Timber Framing
b69249bd-f3cb-4071-9402-b30e4a857fab |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Preline | Internal Strapping and Framing
7de4e916-b77a-4cfc-a0f7-3259b2688d2e |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Preline | Suspended Celing
21af68c9-e622-4be7-af1d-c14295385752 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Preline | Internal Doors
82e21c01-3743-45ad-9829-a156c3cb0bb1 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Preline | First Fix Services
bae537d3-82b3-4fee-9559-7e16cda63df2 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Preline | External doors and windows
35ed0111-b824-4d47-b60d-6f988fb13b4d |  | checklist-flat | work-in-progress | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Preline | Insulation
98aa59a7-c32c-4c01-ba3c-b1908ec90a3d |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Preline | Passive fire/Approval to line
c4ca5ba5-e2c3-41f7-bfa4-eb0fb6107490 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Post-line
48cd4e72-160a-4d31-9275-db6c525eaa66 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Post-line | Lining
66ebe6fa-8452-41cd-8608-6a045a3cd33f |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Post-line | Stopping
017dd729-2841-4a69-b547-8edede091ec3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Post-line | Finishing lines
2b3e001d-75a6-48b9-85c1-d97b60205f5e |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Post-line | Flooring
9ef178f5-faf6-42cf-97c6-477f2863b015 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Post-line | Painting
589765e9-6ee4-43dc-bfbc-9734432f0870 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Post-line | Second Fix Services
0408a45c-413c-4ac7-9f9d-cc9160496e74 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Post-line | Fire Door
40c06940-774f-4bdd-800b-635dc7816bad |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Finishing
b4942e03-e3f0-4d39-a5dd-a15c2f45278a |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Finishing | Flooring
3a574e98-9ce3-4e05-8275-22a0d7197583 |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Finishing | Exterior
007d7629-aee9-445e-adcc-a23e9757d60a |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Finishing | Lounge/Dining Area
dc3253c2-d64d-462d-9d8c-a3eafc8b6540 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Finishing | Kitchen
4b036413-2ea0-45e0-acdb-ba969fa54aeb |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Finishing | Bedroom
622e880c-712d-4736-8910-f90d51b1ac6f |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Finishing | Bathroom
ef0cd33f-52a4-49f2-a274-a0039678fa76 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Finishing | Ensuite
e10c6828-72a1-42ff-99b8-87400f5702d3 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Finishing | Laundry
0d212e91-229a-4370-b5ea-17c0aa031aa7 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Finishing | Hallway
a8e23cb1-6f4a-4ea6-8ad6-d8c31194d893 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Finishing | Toilet / WC
e9145002-4b94-4695-ba87-bc2fb725cbeb |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Finishing | Client extras
26c3590a-9318-4357-917e-2337b2debe01 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D94 | Finishing | Final check before locking the door
b7378f0a-aecb-4440-8b9f-1d2d2595fd01 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95
79652d5c-6e09-4bdc-a82f-942659e47faf |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Preline
7520ffcb-4183-4a2a-ab90-52d9058b03a8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Preline | Timber Framing
a940efcd-3cd5-47e3-b1c8-9f851e4230bf |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Preline | Internal Strapping and Framing
ab9ab587-9342-43fa-bb0e-47af10a90b1b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Preline | Suspended Celing
08c436cf-3b4e-4235-9233-219b41111d44 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Preline | Internal Doors
6223f394-bfd8-45be-a165-1045e4eacd4a |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Preline | First Fix Services
9f037792-0bc8-450a-ae23-a01c7a9a71cb |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Preline | External doors and windows
49e73d2a-fc66-4a20-8035-1ed1d2306ea9 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Preline | Insulation
37118f66-1859-4a41-9914-776ad424d082 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Preline | Passive fire/Approval to line
101f45f5-3f10-47fe-95e8-7dba7c99fb4c |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Post-line
ff92b177-4509-4913-baaa-a5e8602a0132 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Post-line | Lining
ed48d9b2-cc4d-4841-9339-d6935da474cf |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Post-line | Stopping
ab7ad458-d07d-486c-9545-4a7748bcac24 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Post-line | Finishing lines
4cde67a4-2489-4d81-8971-901e5302d8a7 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Post-line | Flooring
5b483e12-ca0f-4407-ab61-2ac1a0c5e983 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Post-line | Painting
57a30dbd-4d02-4d17-9bfc-88ae038af553 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Post-line | Second Fix Services
5632fa34-87e5-4b25-988f-fb38abf9b4bb |  | checklist-flat | not-started | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Post-line | Fire Door
eb084c56-c722-4ecb-b4c4-733a1a2e974a |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Finishing
c86eb5a1-238e-438d-9457-bf12e4cec272 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Finishing | Flooring
06eedbf8-62a8-47b1-8fee-83727839a0ca |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Finishing | Exterior
8b9eb393-4a5d-4c00-8fdd-e4265af9ce0b |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Finishing | Lounge/Dining Area
7cc77341-8d6d-4cfc-872c-cf97be7f12cd |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Finishing | Kitchen
e1a6ec8a-2268-462b-ba5f-430421bdbb31 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Finishing | Bedroom
a41631b3-a827-474a-b847-d879a977e520 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Finishing | Bathroom
215f84d7-be2d-400a-8026-2ab438e85a27 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Finishing | Ensuite
51ad9ec7-af0b-406b-9c5b-a7c3d87e49b4 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Finishing | Laundry
930c80b5-82c1-4d28-8b0c-5a5a611537c3 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Finishing | Hallway
d231e98a-32c3-4d24-9575-e0872020468b |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Finishing | Toilet / WC
ff13a95b-f8e7-434f-8980-adfa3dfa5d4e |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Finishing | Client extras
0a502a5b-4bf2-41bb-8b90-fc84bff1b9c8 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D95 | Finishing | Final check before locking the door
1ae81c1a-f316-499e-a15d-4e7ffc8ef92c |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96
a3de4e55-1b4c-4a27-b1d9-6aab10a32754 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Preline
c2e29330-3626-4249-9ca9-3e82d7d3df40 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Preline | Timber Framing
a4dd62fb-7728-4ce9-849c-2cc28a73353b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Preline | Internal Strapping and Framing
70a52781-1188-4ff1-a7c9-735c382b1dbc |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Preline | Suspended Celing
bebffa3a-7e7f-4e22-a3b4-72b219c29808 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Preline | Internal Doors
5f255b49-c3a6-4652-addd-400cf869526f |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Preline | First Fix Services
ab841faa-1c93-4253-9dca-9d50458f05ca |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Preline | External doors and windows
e9a4c66e-72e5-4f83-925b-86949c0ebf7f |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Preline | Insulation
3c3eca09-e754-467d-89ab-03ec2d6017fc |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Preline | Passive fire/Approval to line
03021139-192b-4400-a686-5def90e9da40 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Post-line
d6f3c93e-696b-43b0-a2c0-887ef299cfb1 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Post-line | Lining
835264ee-b71d-4ab7-89ae-124b69dd662f |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Post-line | Stopping
a8fca078-f1b3-4b20-a488-5ffab1b70cc6 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Post-line | Finishing lines
10bc01bf-faf5-4b20-a241-644f01472813 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Post-line | Flooring
dac8c354-ced2-4f15-b209-8befc7b6c5d8 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Post-line | Painting
ebac46f1-5156-44d9-817f-fd202e45bbbf |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Post-line | Second Fix Services
6e780bd9-0368-4bba-b4bb-6c411abefd4e |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Post-line | Fire Door
775a5649-16bd-4ca8-bb3a-231932cbbbcf |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Finishing
bff31921-3fb2-4881-bd02-de1044147694 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Finishing | Flooring
b74d0c36-d8da-4740-bd86-fa39d1e3d36e |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Finishing | Exterior
7d9a8ae2-e5d6-44bc-92bb-b38f8d6ccd41 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Finishing | Lounge/Dining Area
e255a922-2c64-4eab-b3cf-1fb7e0917681 |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Finishing | Kitchen
58226019-ccfc-482f-b29a-07875f35237e |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Finishing | Bedroom
1c92c951-9422-4a04-b93d-4c9abe434b5d |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Finishing | Bathroom
5188231a-936b-4d96-873e-fc950763be4f |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Finishing | Ensuite
c2ffa5cd-0bf7-4970-8be2-3dcccf9085b8 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Finishing | Laundry
3a19d571-cc21-422c-a0ad-400143c9dbd9 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Finishing | Hallway
48e73c7c-15a1-419d-bb49-219870a64521 |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Finishing | Toilet / WC
619e803a-4511-422d-bcd4-24930f29b900 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Finishing | Client extras
9db5c493-a022-41ed-8df9-0054fcd2d80b |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D96 | Finishing | Final check before locking the door
80d127ed-02e6-475a-b899-f8f024728159 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97
8a4073e4-5a7e-4f94-b48d-4d8156bf11b7 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Preline
ef2be391-c0e9-4166-af2b-0a438d1fc0d5 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Preline | Timber Framing
72ac3614-c8b4-4f88-a20f-350640aba067 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Preline | Internal Strapping and Framing
0bf02229-49f2-4dce-8cec-58bf25490af7 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Preline | Suspended Celing
f39c4d20-76f3-4609-a2a8-e7079cb1fbc8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Preline | Internal Doors
07b6b691-4e58-423f-9190-b916370dbe8c |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Preline | First Fix Services
58056c48-69d9-4ac7-9def-c57421646313 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Preline | External doors and windows
11a216b5-4959-447b-9674-7a20237e8e48 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Preline | Insulation
9b11c5e2-6218-4d2c-a445-15d505d0ac64 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Preline | Passive fire/Approval to line
dd08b4dc-437d-4f4a-8aa6-be596dddb1f5 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Post-line
d88ea402-ccc7-44bb-8623-38de582b5613 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Post-line | Lining
95d201b6-120f-4769-8df3-e215c6d38c3d |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Post-line | Stopping
48045a38-2e3f-402c-a01b-6865ab7a3c00 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Post-line | Finishing lines
abae9fd1-7acb-4852-a2de-345c2f873a90 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Post-line | Flooring
2c309971-2497-413a-b3ba-813adea8176e |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Post-line | Painting
969a7db7-4e01-4026-b5e3-f074c76717d7 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Post-line | Second Fix Services
50001f03-fe8d-406b-9390-eca933f2e5dd |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Post-line | Fire Door
f8bca1dd-50d7-4d8c-8b12-89d614f1cd2d |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Finishing
92009cf0-2703-44a2-bdd0-3de68d84254b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Finishing | Flooring
e0af39b7-ed3b-43fa-87f3-3f4fa0a41dca |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Finishing | Exterior
fe800a27-efc8-4462-99d4-e01137f93551 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Finishing | Lounge/Dining Area
86f9904f-7e2e-4e7c-9290-11142728a5eb |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Finishing | Kitchen
c6c30ba8-4179-4ba6-923c-53109d2bef92 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Finishing | Bedroom
ff99fac4-0092-4ff9-b6ed-6991b2d0dac7 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Finishing | Bathroom
21db5a08-3d4c-4381-a0b6-63f00816d8ee |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Finishing | Ensuite
e2ba887a-308b-489a-b20e-e2b4e323f49d |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Finishing | Laundry
eef879b6-260c-4964-865e-2d9661659779 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Finishing | Hallway
3e11ab04-cef7-4968-bea4-e44804cab2ef |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Finishing | Toilet / WC
887fd3b6-b8d7-4825-abda-610260c3879b |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Finishing | Client extras
5df76661-c73b-4323-84bf-36b95ae2d630 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D97 | Finishing | Final check before locking the door
5d0d2468-771e-4cb0-892b-bfabbd58539b |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98
87a3892e-6ec8-4b70-a35e-05b1b14ba347 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Preline
875c1c55-39a7-4cef-a0af-982d3c6cdc4c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Preline | Timber Framing
feff60a4-6b7d-457d-b77f-a864003740e7 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Preline | Internal Strapping and Framing
1eb45a2f-6366-410f-b3df-66b4d218e2d6 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Preline | Suspended Celing
ee71356b-7302-44ed-8a16-88b7144cf54b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Preline | Internal Doors
d941dee0-daf3-4c07-a5b4-7398a50f2bcc |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Preline | First Fix Services
fb720d64-40ba-4806-b036-e7df06b19ecf |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Preline | External doors and windows
e694d3cd-7b50-4240-adf8-6dcab348668d |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Preline | Insulation
626ce722-0b56-48bc-a0cf-ca5e9eb96dac |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Preline | Passive fire/Approval to line
1d57a57c-1e2f-4e7b-ad46-b99559e10c9a |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Post-line
efc81c0b-cc2a-4885-9e54-1d54ae9860a7 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Post-line | Lining
a0a7ee83-d453-47f4-9b28-18836992fdae |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Post-line | Stopping
b15d8686-de73-4251-88d8-40e417c89fda |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Post-line | Finishing lines
231230ec-3eba-46b5-bc86-6c85da45f57e |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Post-line | Flooring
fff364ee-5092-4193-a5d6-e5cd46a00530 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Post-line | Painting
4bea3c3d-4e3c-467e-910f-26fbb41720f5 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Post-line | Second Fix Services
b3f63c5a-0cea-49a6-b47c-add0872c06d9 |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Post-line | Fire Door
15238d45-bb60-450d-a580-66e77ef44602 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Finishing
08a19bce-b213-4cdd-baf1-51bc3dcc6c9f |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Finishing | Flooring
2c2aabbd-3ecd-4cd2-be80-fc298b9e361b |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Finishing | Exterior
95b57a87-bc68-40c8-a31f-3af7c192637f |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Finishing | Lounge/Dining Area
42234211-08a9-4e71-90e0-485cd1b599ee |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Finishing | Kitchen
bf3d9f5c-c640-4a22-87fd-7fe88c826305 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Finishing | Bedroom
e5c9e1d8-1ec6-460e-baf4-33243c7cbb72 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Finishing | Bathroom
3eb79471-5e33-483a-b2f6-bd7e70da47f8 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Finishing | Ensuite
adff74e4-ffe1-4415-a026-2bd381d67c94 |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Finishing | Laundry
51a00013-8507-4415-9b19-d193708547b4 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Finishing | Hallway
6d06796e-fb36-4cc2-af0e-e8484992cc8b |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Finishing | Toilet / WC
3e22c1a9-4f3b-46ce-82a7-7236bc8b87cd |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Finishing | Client extras
7434ef82-17f1-4245-ab71-6e79c3b58303 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D98 | Finishing | Final check before locking the door
26213cc9-4049-435f-9876-470b167ed909 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99
98217dd3-e2d4-4c2f-b41c-83db3ed04da0 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Preline
2c13f049-04d9-4d9b-b59d-e05b4b0e49be |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Preline | Timber Framing
db73da9a-a216-4dea-baf2-7a8f1cb7c9cf |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Preline | Internal Strapping and Framing
7c45d968-961a-4795-ad9a-717b6ed5bb61 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Preline | Suspended Celing
ffe3001e-7d38-4c0c-a029-3ae65634eac9 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Preline | Internal Doors
23cc24b8-2bd5-4b6a-aed7-ac7ea3224ed4 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Preline | First Fix Services
83d17e41-a4e7-43ed-8eb8-7fa03e50492b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Preline | External doors and windows
e80d5096-d424-4938-a7eb-9d25dc799614 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Preline | Insulation
f30df786-f5a2-4e06-88c5-b638304b8af4 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Preline | Passive fire/Approval to line
51d2a685-3e81-416f-97d7-da04594720e3 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Post-line
cb66d3d6-e918-44d2-a273-d1b20eb8f050 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Post-line | Lining
5774209a-1f31-458a-85cc-1b6b3a0438c7 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Post-line | Stopping
e6e0f2a7-97ce-40ec-ab7e-6e1da244eb92 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Post-line | Finishing lines
0ddb7467-6f19-4b0e-8896-a144e952567d |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Post-line | Flooring
c6328ec2-80fd-409a-bbef-77d42caf8d6c |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Post-line | Painting
ef21187b-3561-4ccc-9cd9-7c524b675401 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Post-line | Second Fix Services
2343424e-6d78-4c90-af48-3026065080fc |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Post-line | Fire Door
5b9aba11-2347-444d-9ab2-ce01bb908056 |  | folder-progress | not-started |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Finishing
873574ff-8f94-47bd-b2ad-f52ce886191b |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Finishing | Flooring
f085a0b1-bd6f-4d01-8d8b-f74d79915dee |  | checklist-flat | not-started | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Finishing | Exterior
b8e2b2a4-717b-466c-bbd6-2531416d3e14 |  | checklist-flat | not-started | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Finishing | Lounge/Dining Area
9a885f2b-2740-4b7e-a3c0-a6047c66afdf |  | checklist-flat | not-started | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Finishing | Kitchen
9454e724-b775-4761-b9b0-8627b5f0ca99 |  | checklist-sectioned | not-started | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Finishing | Bedroom
441ee4b3-f026-46b4-bf78-6f2085026715 |  | checklist-flat | not-started | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Finishing | Bathroom
2bf7af11-d609-422a-a26d-9d6a35af4d39 |  | checklist-flat | not-started | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Finishing | Ensuite
b1c81c4f-218b-4084-8f3d-7de00bdb319a |  | checklist-flat | not-started | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Finishing | Laundry
cfbce6c0-2110-4367-af83-5371876ace13 |  | checklist-flat | not-started | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Finishing | Hallway
f7f9595c-1768-4b3f-9a27-b2c4ba71960c |  | checklist-flat | not-started | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Finishing | Toilet / WC
eabd321d-2494-4f4f-9115-ec509487ec95 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Finishing | Client extras
1dbba669-87c9-431b-a570-5bfe090a31c3 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D99 | Finishing | Final check before locking the door
b5b071e0-8025-4c5c-bd14-2aeabc8a8068 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100
e850a4a8-e856-44b8-926a-9109498b59e0 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Preline
b49618bd-641a-4751-9d85-4825976799c8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Preline | Timber Framing
94278c57-6c0f-455b-8a12-1b961c37c0ae |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Preline | Internal Strapping and Framing
4d153af9-43f3-40d6-b316-1f586daee221 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Preline | Suspended Celing
0b5e16df-2141-4ecf-adb0-f93e4b401253 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Preline | Internal Doors
c2874289-95f0-4ddd-aaba-664c4c654726 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Preline | First Fix Services
4b2357a0-4a6e-4711-8cf0-53f416879d1c |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Preline | External doors and windows
a482fbab-2c66-4e11-aa64-e33bcf19c20c |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Preline | Insulation
b363f271-8f80-4779-9b97-3f562b824398 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Preline | Passive fire/Approval to line
0bb9b9ec-0741-4e5b-af17-9d0167661ce2 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Post-line
b9c1a7ac-dec7-41b4-b098-d58849691e9f |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Post-line | Lining
e886f82e-df0c-43c6-bf4b-4dd7a67ddded |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Post-line | Stopping
b190142c-61cb-4695-8634-391588e2a5e1 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Post-line | Finishing lines
bf59bd2a-2424-425a-87a6-4f6f4caf59f8 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Post-line | Flooring
c0fdb455-3c37-4f71-90df-d74183374271 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Post-line | Painting
bb8075bd-499a-4b32-89b8-0122f76ece2a |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Post-line | Second Fix Services
22d5fd9f-6e8c-4ddc-8aa8-ea537b8e807a |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Post-line | Fire Door
d245e788-f561-4e00-b43c-8264b8711058 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Finishing
00b4b313-4a0d-4aff-8448-b975d79c8bf2 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Finishing | Flooring
7a55b34a-d1a2-4159-b447-327328df0794 |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Finishing | Exterior
75fbcf01-c016-4e65-9301-3a0ef60594cc |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Finishing | Lounge/Dining Area
7b934305-bb2d-466f-9381-ef90f47bea79 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Finishing | Kitchen
c3216ab9-feb1-402e-aaf3-3705438c85c5 |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Finishing | Bedroom
f3ebeacf-5b53-4f2d-8b45-f03a5f315ee0 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Finishing | Bathroom
6e777ee3-623d-4236-96b9-bca432501f75 |  | checklist-flat | work-in-progress | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Finishing | Ensuite
3fe160d4-f0f5-4c80-a77c-944adf9068d9 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Finishing | Laundry
8994fe5d-0ed1-40b3-ab26-05ce534c91d0 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Finishing | Hallway
4cc73a1e-a958-4d41-812a-b0cb8a2d9072 |  | checklist-flat | not-applicable | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Finishing | Toilet / WC
cbbf9614-5e49-4ab6-b53e-fb450ea461b9 |  | checklist-flat | pass | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Finishing | Client extras
3a2c8cfd-761c-4aa9-a3c1-7fe966037910 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D100 | Finishing | Final check before locking the door
683d07fb-7038-4a00-9fa6-84bbe5756548 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101
5d3a9d33-c4e8-4392-9be3-ddf483eb05d0 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Preline
c7f57b51-191d-4013-b618-5feed7c60bf7 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Preline | Timber Framing
661d18e4-df63-4f5e-9e25-907858dc30a7 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Preline | Internal Strapping and Framing
679ebea0-2e33-4f25-ba08-3777cb47bafe |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Preline | Suspended Celing
6230b953-891b-4fd0-8354-7b85413a5141 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Preline | Internal Doors
a1f10582-6fd2-43de-93e9-24afc7899ea7 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Preline | First Fix Services
b1452d4a-8dc9-4271-b81b-1c2bb716ae6f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Preline | External doors and windows
03a64262-1cb8-48e0-a9b5-52f5db724e94 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Preline | Insulation
086e0b6b-ae29-46f0-912e-a3e00649cbc6 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Preline | Passive fire/Approval to line
e9cd0d69-3e00-4ab4-9aff-02c8bce56fba |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Post-line
28163871-3689-49a6-8e59-0e79580c923d |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Post-line | Lining
db6fea5d-2b3b-4b60-bb48-fd171b9bab88 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Post-line | Stopping
f79af2f3-ec8b-45c9-80a5-4c7726ea7836 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Post-line | Finishing lines
a05bb122-2945-4c9c-be94-05a6b24a1a72 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Post-line | Flooring
a4642c32-53c6-4ca5-9331-3d4a60c33624 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Post-line | Painting
1326719c-218b-4264-9ede-71ed0ec425fa |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Post-line | Second Fix Services
b263c7be-ffed-48d7-9208-edb0a71796cf |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Post-line | Fire Door
98789aef-ecaa-4049-8fdc-1f4a70526187 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Finishing
12d2b2e6-88b9-4421-b9ee-fa6e8091d621 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Finishing | Flooring
01490ea4-4710-42d2-950c-ee0ed1745adc |  | checklist-flat | work-in-progress | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Finishing | Exterior
5f074d1e-adbe-4323-a5b8-1e788e8122aa |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Finishing | Lounge/Dining Area
6aa0d46a-3ed6-40c3-b1a1-fc50a95bf174 |  | checklist-flat | work-in-progress | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Finishing | Kitchen
102c2437-06e0-4619-bcc2-e48f66b33867 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Finishing | Bedroom
4b0e0ebb-cfb0-448e-888a-d4227f2b507f |  | checklist-flat | work-in-progress | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Finishing | Bathroom
bbf7d4f4-9487-40f8-b838-cab6ce6eac58 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Finishing | Ensuite
956ad232-15ac-47b7-b0fb-b50cd95624ec |  | checklist-flat | work-in-progress | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Finishing | Laundry
6ef426f3-d45b-4be5-b68e-9370ebb471a2 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Finishing | Hallway
9c14ee76-d7aa-4799-be96-9300a998a9f7 |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Finishing | Toilet / WC
18f99dc7-b713-4e0f-9d9f-24140193f483 |  | checklist-flat | pass | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Finishing | Client extras
a8a4f7eb-3adc-46e0-b5b6-8cec606364b7 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D101 | Finishing | Final check before locking the door
6fb980dd-fad0-42a1-b822-3df217b045c1 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102
b152124d-c1ee-482c-9252-5ecf922decb8 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Preline
4307ba84-1e7f-4988-b85b-97870546397b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Preline | Timber Framing
c3632037-49f9-4418-bcc8-5c5a76274466 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Preline | Internal Strapping and Framing
ccea175b-172f-4cb6-803a-7992ad783115 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Preline | Suspended Celing
383975d9-9408-4dee-8908-aea3989e370f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Preline | Internal Doors
3c23c800-c29a-4f94-8c5e-6b15c1a1bf8d |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Preline | First Fix Services
8563a65d-0877-4d33-a99a-3a3459a09547 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Preline | External doors and windows
b1752ff7-c72a-4cdc-af74-f4d0f0f048eb |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Preline | Insulation
7b8e6bc2-ef67-4a75-9975-761eb7162bcf |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Preline | Passive fire/Approval to line
4a1f0a43-52aa-4f64-bc4d-74e6ed112ce1 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Post-line
73603074-a99b-484d-a3ee-785b6e41813e |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Post-line | Lining
17b4984a-7b22-4d94-ad35-0a86fab5c9b6 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Post-line | Stopping
cce3c03a-40fb-4b08-bcb4-44245a0667f6 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Post-line | Finishing lines
250b2bf8-2b1d-4184-a11f-15592e5926a3 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Post-line | Flooring
b9dd827c-0135-43f4-94e8-d3b8e1bec0ac |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Post-line | Painting
490a16d1-c3f6-466e-926a-e8e984d8268f |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Post-line | Second Fix Services
267d98fb-df35-47da-8bee-2b5a3aac64ba |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Post-line | Fire Door
b9ea3b89-5b40-47e5-9da7-7541c91c30b6 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Finishing
d5fc2dac-362d-491f-961c-fe76ee6d6f91 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Finishing | Flooring
3ae75b33-647f-4964-9ac2-282cec728739 |  | checklist-flat | work-in-progress | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Finishing | Exterior
68398756-6b79-42d8-808e-a728257d1ead |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Finishing | Lounge/Dining Area
50a10a84-9f4b-455b-8417-5fd0c19dab33 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Finishing | Kitchen
75fc449c-cd5a-4e3f-aab6-dfbafcbf8c2d |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Finishing | Bedroom
1afe0330-588f-41a8-bf0e-918c0e90d89c |  | checklist-flat | work-in-progress | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Finishing | Bathroom
2d32ceae-6c61-4a51-b1e7-affa92ef8f53 |  | checklist-flat | work-in-progress | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Finishing | Ensuite
539d39a7-67dc-4189-b9d3-e310a1996452 |  | checklist-flat | work-in-progress | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Finishing | Laundry
dab0e0d5-ce50-448b-8c68-1851fbe754ab |  | checklist-flat | work-in-progress | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Finishing | Hallway
0af0e54f-9c91-4c21-82a5-01dcad5ae697 |  | checklist-flat | not-applicable | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Finishing | Toilet / WC
01d11432-bceb-4ded-a497-14f909f2d892 |  | checklist-flat | pass | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Finishing | Client extras
35c4bd69-8e44-4e94-80a3-ec90dbffeef4 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D102 | Finishing | Final check before locking the door
e1076e6b-e39b-491d-8e14-6c0bb37e3d0b |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103
2dcbe3da-7bd5-4d2b-b76d-7f5d53d371c4 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Preline
0afcd14c-a0f3-4135-b92f-12d03c757e22 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Preline | Timber Framing
4204e29d-212b-4595-b704-91046fcd5a42 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Preline | Internal Strapping and Framing
3f154190-c39b-433e-8aa2-a15bcacf8fcf |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Preline | Suspended Celing
2e7711d8-5320-4777-a3ef-220ed5cca470 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Preline | Internal Doors
fac4c485-2e0a-433e-9e22-6ee0e3b80487 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Preline | First Fix Services
1f5156f5-0933-4fb6-b3e3-fc6cd2497c09 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Preline | External doors and windows
01d43ac5-701c-492e-ac8f-31544b30cd43 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Preline | Insulation
f578da0b-874b-4a4a-b452-5bc93f36f630 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Preline | Passive fire/Approval to line
2f272c53-8540-4072-b3e6-b3669fcef828 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Post-line
1385a1ec-7722-43a9-8a05-3d5a3e838acc |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Post-line | Lining
8905bccb-00fa-48d1-a879-0c39fb35bde4 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Post-line | Stopping
99e3f94d-6e25-48d8-86b7-1bfe38b3b6a3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Post-line | Finishing lines
73faf6a9-6fea-4229-ab62-2069d2d4ee94 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Post-line | Flooring
978f42ab-a632-401a-ac14-ed436816361d |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Post-line | Painting
823021b6-2343-440d-b977-0cb123b25706 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Post-line | Second Fix Services
85804ba7-3e08-4c0d-976b-2b174541c3c9 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Post-line | Fire Door
f57d67ac-34d4-4595-8fa9-ac4390cb710a |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Finishing
511d987e-6406-4be0-89c5-1c632f563457 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Finishing | Flooring
f9b856df-74fc-4390-9ed7-7c86876545b0 |  | checklist-flat | pass | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Finishing | Exterior
ac335f2a-4183-4ac1-a348-73767e1e1eeb |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Finishing | Lounge/Dining Area
56c28f22-668f-4118-b0cf-f0d5236e332c |  | checklist-flat | work-in-progress | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Finishing | Kitchen
fed48753-509a-41e0-ae91-2b4b8966f6b3 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Finishing | Bedroom
ddbe413d-232e-444b-8c78-4cef15b08b60 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Finishing | Bathroom
9965f0fe-154f-497d-81f5-be00a2550c74 |  | checklist-flat | work-in-progress | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Finishing | Ensuite
12fb8f4a-a822-4b05-943e-9dafbfebe781 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Finishing | Laundry
33079572-4d7f-43cb-9c09-e52be449cd70 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Finishing | Hallway
8c113075-271c-48ea-a95e-9ca799afe56c |  | checklist-flat | not-applicable | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Finishing | Toilet / WC
21156e4d-c970-4971-bd33-eec77d09ede0 |  | checklist-flat | pass | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Finishing | Client extras
17c2fef5-bd52-44c6-8abd-78fa0f000083 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D103 | Finishing | Final check before locking the door
028d2fe7-f233-4488-8373-797c3735a852 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104
161cd31d-af7d-4689-b2b6-674e78170498 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Preline
c5f5ce15-a00d-4411-862f-53d5416bcd2d |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Preline | Timber Framing
febd173e-2c62-44dc-8ed1-51a220ea8eae |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Preline | Internal Strapping and Framing
99b34ca4-a100-4086-8d20-b6e4d6f42a29 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Preline | Suspended Celing
313f673b-0901-4785-acc1-f8862c4fb45b |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Preline | Internal Doors
81ae6d6f-c751-4db4-af53-94d3d69de3f4 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Preline | First Fix Services
95b55052-dd36-4cc6-a8fc-75c2de26a1da |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Preline | External doors and windows
5048ed9d-550d-421d-96c1-2abbb342b3d8 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Preline | Insulation
68cf29dd-2dc0-4143-9925-c2ed70cbbc97 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Preline | Passive fire/Approval to line
b75abd4e-35a1-4c68-8db6-fbb6778a917b |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Post-line
53ca3815-5ac0-43f4-b87a-cc149f489dd1 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Post-line | Lining
4e7d0288-cc9f-4d2b-b415-b3dfcabbf3b9 |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Post-line | Stopping
4d961fc0-cf06-4098-b112-39d3d9e70ff7 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Post-line | Finishing lines
0baedb93-8304-49d5-a00c-7c9ef77b3868 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Post-line | Flooring
bcba7aec-e3d7-4b41-bdbb-25acb0d8b9bc |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Post-line | Painting
56122413-0fa9-43c0-a082-16efff210ae8 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Post-line | Second Fix Services
f032c254-bb58-4379-9dee-d4f0500630cd |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Post-line | Fire Door
e6e17775-84c6-494c-809c-48ca68c0d910 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Finishing
b8d880f7-3cdd-4fb1-8caf-4249b4f941cd |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Finishing | Flooring
d074eb2a-8ff8-48ab-aa2e-dd3d170f0c87 |  | checklist-flat | work-in-progress | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Finishing | Exterior
a666b144-7489-4f30-9117-fe76a96cd6a5 |  | checklist-flat | work-in-progress | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Finishing | Lounge/Dining Area
84d9caf7-e914-4391-b5db-179dbd21aea3 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Finishing | Kitchen
197d3bb4-15e7-499a-81e1-acea0ef75256 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Finishing | Bedroom
d747711b-a160-4ad0-9d6b-c8f3b18dec2b |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Finishing | Bathroom
638d876f-41de-4f95-bbda-6e8f3c22d0db |  | checklist-flat | work-in-progress | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Finishing | Ensuite
940cc96d-84a4-4379-bc93-318581a5b2d9 |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Finishing | Laundry
4031dfee-09f6-4874-a7ad-fe100fc92d8f |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Finishing | Hallway
380a7c4e-b386-4b8d-b326-5532dfab2ffe |  | checklist-flat | not-applicable | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Finishing | Toilet / WC
9d888d51-ed62-439f-af1d-551dacca2f36 |  | checklist-flat | pass | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Finishing | Client extras
aed9a0c2-dfb9-41bf-9c49-b89baad80678 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D104 | Finishing | Final check before locking the door
21b34dc4-0ca5-460f-88a3-b3381b443240 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105
b7c0dd09-26b7-4b4f-ac2a-676a72e7b4ee |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Preline
d1c913e6-8598-42c5-b2ad-3e5a22186fa8 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Preline | Timber Framing
53972954-cd46-47a1-9870-b3d3219aa457 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Preline | Internal Strapping and Framing
29c7285e-e8e2-4b6b-92ce-8d3d9256ffed |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Preline | Suspended Celing
ae6d36c4-5c8e-4ef5-9ea1-34e52f9fa3ab |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Preline | Internal Doors
5d14968f-0405-49d2-9bd3-01dcb9688666 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Preline | First Fix Services
af65b74e-1899-4961-897d-8510035a2a9d |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Preline | External doors and windows
c5b1b556-5488-4cc1-aef7-20df3bce6f3a |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Preline | Insulation
2530d79d-332e-4589-88e6-7b4559f22ff1 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Preline | Passive fire/Approval to line
1f00d550-ae7c-404f-b63d-96b91429fe43 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Post-line
e9b33a51-1b19-45a9-9c85-93f7998aea96 |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Post-line | Lining
a592d872-3c73-49a2-8731-b7684da62f4a |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Post-line | Stopping
0583bc0b-737e-4857-944c-dc64439af52f |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Post-line | Finishing lines
103a4d43-c5d5-431f-abda-dd39b92429c5 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Post-line | Flooring
dc550e0c-57fc-453d-ac18-a5984dae8f73 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Post-line | Painting
842cfda1-8983-4c8c-be9f-7d595d8d238b |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Post-line | Second Fix Services
31dfbfdf-fcf8-4511-9abb-ce62c5ee8511 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Post-line | Fire Door
9fc74d70-69b3-40b7-be34-4db728abe53d |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Finishing
1154f3d0-9f3e-4b2d-bc5c-e04e90d5bbd2 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Finishing | Flooring
bf462716-7b82-48a0-97d4-f8d9ab08067d |  | checklist-flat | fail | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Finishing | Exterior
692475ac-18b9-43ab-9cbe-120ef91523b0 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Finishing | Lounge/Dining Area
102d24fb-8bba-42b0-a25d-78f47f31bfdf |  | checklist-flat | fail | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Finishing | Kitchen
efe96da4-e751-4844-838a-7929098d8870 |  | checklist-sectioned | fail | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Finishing | Bedroom
4ad978f8-3e6d-417d-b3d9-0b221a1a5caf |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Finishing | Bathroom
6e74e186-7d3f-417b-953c-db83cdbc1b45 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Finishing | Ensuite
c09c7bbb-288d-4614-b799-71b79181e8fe |  | checklist-flat | pass | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Finishing | Laundry
63f1d8a5-243f-4d25-be09-daa9d7ce4c9c |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Finishing | Hallway
760923f6-2a57-4dad-92c8-fd86e85b7571 |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Finishing | Toilet / WC
9d868351-3b9b-4a4d-a5fe-f89987a7e85a |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Finishing | Client extras
4b8bb4bb-8a55-4db0-9d6c-63d52a64ef4b |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D105 | Finishing | Final check before locking the door
7cb3195b-35e0-4f3d-af7a-771b969391f5 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106
e74e31e1-b54a-49d2-a641-9380132b18e6 |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Preline
41921fee-3140-4f1f-8522-b737b705ea96 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Preline | Timber Framing
6b6fd09a-cf9c-4ec4-b841-52a64f6724bd |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Preline | Internal Strapping and Framing
0f68397a-7c70-40ec-b442-0b1958e9c3e3 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Preline | Suspended Celing
bcb72e21-2475-4e80-97eb-4044f255ed32 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Preline | Internal Doors
b4fd07cb-9524-46c2-9da8-5847a182de58 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Preline | First Fix Services
a7ef3c17-8a04-414c-9d1c-8ee14d6e96c7 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Preline | External doors and windows
80e49191-4d3a-4d12-8e92-4279a8a1d81a |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Preline | Insulation
f27eacc4-ee88-4172-ba21-00dccd5d9070 |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Preline | Passive fire/Approval to line
f79e8b34-c6b5-43e5-9fd7-e98e868cf809 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Post-line
0562b0c7-7b90-4121-8912-74d20fb4e73c |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Post-line | Lining
6b6a3ebc-2339-421c-ac9f-cfabf6fb7acb |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Post-line | Stopping
1ea8766d-4634-4a61-8edc-3b732c4c17bf |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Post-line | Finishing lines
7674cd59-473a-44ab-a06f-a7eb1635f814 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Post-line | Flooring
947c35e1-5068-4122-9ba7-0449cefea7c4 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Post-line | Painting
3dc41315-6245-495a-9ac1-45966c5da072 |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Post-line | Second Fix Services
98affe6c-b9b0-45ea-a0c0-c18376d90381 |  | checklist-flat | pass | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Post-line | Fire Door
0ee6bac2-61c4-45d1-b0f2-8d2784994444 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Finishing
ceccacea-95c6-4f93-b35b-0665f7c7eb32 |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Finishing | Flooring
d9dcc852-dc58-449c-a8cd-05ac5df15741 |  | checklist-flat | fail | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Finishing | Exterior
2135c12a-d802-4ef0-bda5-c7e6a38a59dc |  | checklist-flat | fail | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Finishing | Lounge/Dining Area
0d5c1022-a54b-47b9-b75e-436c6bdcaccb |  | checklist-flat | fail | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Finishing | Kitchen
33606bec-5a33-42c3-8b2e-5220cf3acfb0 |  | checklist-sectioned | pass | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Finishing | Bedroom
25775f51-309c-431a-8ad8-e929094bd10e |  | checklist-flat | fail | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Finishing | Bathroom
d0b51494-1dfd-4581-900b-2018b3fa728b |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Finishing | Ensuite
70a8f844-9aad-4797-8701-8b058a0d0c95 |  | checklist-flat | work-in-progress | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Finishing | Laundry
c7d73c2d-34b3-421d-9434-4b6237384eb6 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Finishing | Hallway
b0a16d44-2192-49c0-94c0-181d9afcd580 |  | checklist-flat | fail | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Finishing | Toilet / WC
9b452c05-5b05-420f-af78-522a07782c37 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Finishing | Client extras
b8dc5f3b-5ff5-4426-9d53-8fd90bd50ae0 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D106 | Finishing | Final check before locking the door
2c4cb227-0690-4953-b3b9-e3a086236b16 |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107
9550b332-7cdf-480a-8670-d413d9393a9b |  | folder-progress | pass |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Preline
2c009fad-9a1c-4a9c-b09a-2f9c71ed69f1 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Preline | Timber Framing
0520c879-16cb-45fe-8158-239847413c35 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Preline | Internal Strapping and Framing
381255bc-dfff-4bbd-bab5-d7d661079976 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Preline | Suspended Celing
b6dfc136-7a6c-481e-b8cb-56b2eac0d5ba |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Preline | Internal Doors
b2940330-37be-471c-968c-5307c08fd899 |  | checklist-sectioned | pass | b5287fa4164613e744be437351dfd9ccacc35de0ddee90c8f53edd5a80d9489e | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Preline | First Fix Services
3e4ae8b4-3da7-48d3-a20a-32f19cf3cf58 |  | checklist-flat | pass | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Preline | External doors and windows
d92cd9cd-4940-426a-97fc-70bb7bffdb55 |  | checklist-flat | pass | d5e02a91ea93073fff0cdbd35d0888d09257d84c21f9a24b6558c646ec747e94 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Preline | Insulation
310afb24-8bc5-46b6-893f-c93f5a3c097d |  | checklist-flat | pass | a09d6a491e149fd697ae908d020633b94ba2cb995da1c31095fdc86a5e4b243c | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Preline | Passive fire/Approval to line
4630faea-424c-4982-b73c-51ce68664b05 |  | folder-progress | work-in-progress |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Post-line
df9ad719-a84b-4ed1-82e0-ba1909991e3f |  | checklist-flat | pass | a05096deb55e1420e11d80fb3da123f1ee69904020a51e48bb2a9e4bcc12a2e5 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Post-line | Lining
2543b12b-204d-46f0-ad99-afb3e8f9530a |  | checklist-flat | pass | 0831fa64c7ac8113335cf825de236838ae408a38d6272a7ab7a060dce787506b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Post-line | Stopping
7a827a5b-b28b-4ee5-9c3f-3d5b29abc6fc |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Post-line | Finishing lines
a38a5b58-50e8-435c-83af-2b41bcf21e7e |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Post-line | Flooring
520027fa-180c-4cf1-8cd6-24f2309b9e72 |  | checklist-flat | not-started | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Post-line | Painting
893aa900-0aa9-43ea-9c2a-fa13e2d2cb7c |  | checklist-sectioned | not-started | cdb6e064b5fc068350c7a5a55cfdcf4f7ab3fa20a24da0429db8f65bd58cfe54 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Post-line | Second Fix Services
7be42e4e-3dbd-42b3-8a84-f3d50a3c627d |  | checklist-flat | work-in-progress | 9f460d975d345a36f7db43227d19ec1de85eef2e6ba8ed12965984ab893edba8 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Post-line | Fire Door
1fc86178-98b7-4a5f-ac46-720ea8ae151e |  | folder-progress | fail |  | checklist | TRUE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Finishing
e62c77ab-9e4c-449f-8918-b8069deb590e |  | checklist-flat | work-in-progress | 50618689a6aea84e61d67777ff0c1bb666a1429ffe5ccecf4f846a1606482346 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Finishing | Flooring
252d9a7b-645b-4ce2-b7e1-380bc0ae811d |  | checklist-flat | work-in-progress | dcb443fc20e0d46112a237cade102f03e0b4fa99dcf7744beea04867d07f9410 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Finishing | Exterior
401ec6ce-8082-4b66-8f8a-90f887bf9721 |  | checklist-flat | pass | 63f29b26f5b522575a5278c8daff0674580fa7d4c5206b061d96963c3aa4380b | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Finishing | Lounge/Dining Area
5ca19057-6231-4ef7-91e0-a93908aebb35 |  | checklist-flat | pass | c559e03c2c58b710c2b6aa7b0081d5e444b6f1818cfbc7c719ce089ba7c6f8d9 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Finishing | Kitchen
2b2802e2-3b3d-4db6-bf38-c0dbae323c81 |  | checklist-sectioned | work-in-progress | 2c552a10fe08395bf4c8874a18f087e85b6cc4fe9b02a1d4177e28496b919ef8 | checklist | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Finishing | Bedroom
b7eac0f8-4df3-4d17-a165-c0cb2c58c920 |  | checklist-flat | pass | cee58fbbe94f388f4babd7861a3cd31993fb94059d7d37776ce28ee89db730dd | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Finishing | Bathroom
ba4a5e24-2ff0-42de-99c4-e8b6df3d90b1 |  | checklist-flat | not-applicable | 1a52104402fe895835d5570f6cd59d2f3a47e78cda85ecee3f170271ccf5d0da | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Finishing | Ensuite
71ea4398-085e-44b6-95eb-3460ee27d1cc |  | checklist-flat | fail | e0ae1e03c20ea6fe58b7eec1aeb69e770b480c4664f74a771326d8202219d081 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Finishing | Laundry
bdcd6644-53bc-453b-a540-19dd5af8d011 |  | checklist-flat | pass | d5c7d2b146e800946978a20f2c6ff7663c281f6081b2f682403d203e0944ffbf | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Finishing | Hallway
5440ef4a-e5a6-418a-86ca-1ced0571be1f |  | checklist-flat | pass | 910d4fb14e49043f82b5cdfe26a42df14a6121df9508b20da29d17bc82e68510 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Finishing | Toilet / WC
a2f672f8-1aa0-4f65-b214-b16bae721772 |  | checklist-flat | not-started | dbbdd39404e1447b6bcdd776eff9bfb3ab3d5a8ad81713ea6e25a98ceb8997b2 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Finishing | Client extras
e7bb12f6-af8d-4b6c-9e9c-22006bae1566 |  | checklist-flat | not-started | 8d567e4d759a2e989185694bc312283be2896f9cd9ed13f7333dfbf100fc15b0 | checklist-flat | FALSE | FALSE | Building B04 | B04 Fitout | Level 4 | Residential Areas | Apartment D107 | Finishing | Final check before locking the door
ae1c449a-b437-4621-a5c6-dcf79538b76c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B05
8ceb3699-eac9-4706-8f37-7654c5d805af |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B05 | Foundation/Tanking/Drainage & Subfloor Services
4dee7ca1-ff6e-4468-a889-82d3be40fb0e |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Foundation/Tanking/Drainage & Subfloor Services | Piling
d68f466b-9302-45fb-9016-c8b40b622b2c |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Foundation/Tanking/Drainage & Subfloor Services | Tanking/ Waterproofing - Foundation
8ab4193c-daee-4dfb-ad4b-d1fefe844855 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Foundation/Tanking/Drainage & Subfloor Services | Underground Services - Foundation
fedc9ee1-8cba-4959-af98-70e28f5982bf |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Foundation/Tanking/Drainage & Subfloor Services | Foundation Concrete - Pile Caps/ Strip Footing.
8a52a7c2-2340-4b31-9978-2b6cb3059fba |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B05 | Foundation/Tanking/Drainage & Subfloor Services | Excavation
762aab21-e14b-44dd-b323-0057605f4e4d |  | checklist-flat | work-in-progress | C - R - Detailed Excavation | checklist-flat | FALSE | FALSE | Building B05 | Foundation/Tanking/Drainage & Subfloor Services | Excavation | B05 Bulk Excavation
4c3c82d2-4312-49c8-9116-3de97efdbd96 |  | checklist-flat | not-started | C - R - Detailed Excavation | checklist-flat | FALSE | FALSE | Building B05 | Foundation/Tanking/Drainage & Subfloor Services | Excavation | B05 Detailed Excavation
b17d3290-ba11-4ce5-86f1-c518271da158 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Structural, Fire, Services
1cf1638e-3200-48d3-b129-c98a1a579a4a |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Structural, Fire, Services | Level 1
6412667e-33ba-49b6-90b7-34f9eb7c78e0 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Structural, Fire, Services | Level 2
c549558a-56e3-41c3-a22a-b8ed9d785c9e |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Structural, Fire, Services | Level 3
e3390dac-5a88-4e78-873c-54d8372b343f |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Structural, Fire, Services | Level 4
f59f2a4c-7df7-4770-857d-4e4de11f1608 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Structural, Fire, Services | Level 5
62b5e4f1-37d9-441f-b047-e352de0c41b8 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Structural, Fire, Services | Lower Roof
24f08822-b2ec-4922-9d6a-4846f2bbd014 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Structural, Fire, Services | Upper Roof
0fb1267f-c0b7-4caf-b803-d4e7d55212da |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Structural, Fire, Services | Main entry canopy
ce75ec95-31c7-471c-b173-9de6ea78ce47 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Structural, Fire, Services | L1 entry canopy
4950dfb5-80bc-48ea-8212-8ec2cb3f3100 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Facade
562e7fd8-ef26-42a7-b16c-5b3ecbf293db |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout
d1b4ed05-bf4f-4bc6-92f8-6470a78dc2f7 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 1
52eb3f1c-c337-49b5-9ba4-4c4afc6cbb18 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 1 | Common Areas
5d83f7f0-f372-43c4-adb3-e73c7fbe2f75 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 1 | Residential Areas
1b287edd-d75d-4ad1-b270-40d225583e30 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 2
eccec3f6-68a4-4db8-a6c7-a39c04b02219 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 2 | Common Areas
177e9516-d196-42d2-8f07-ab7b25d71651 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 2 | Residential Areas
9b84c4d7-5a70-45de-aea8-8aa9062412aa |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 3
48949f99-841c-4a3c-b04c-5c58bd578856 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 3 | Common Areas
06a71cea-b7e6-463f-bf28-4d80dea2d69c |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 3 | Residential Areas
5739307f-2a64-4d7c-a496-313378905593 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 4
12bd1e1f-21c5-4d40-8f2e-7687228c0230 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 4 | Common Areas
df42462b-4477-488c-9998-f58c9467a270 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 4 | Residential Areas
eea67745-a59e-4b81-9f0f-9f70c3dbac0c |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 5
38cf0bd2-869b-46d7-93be-34b861d40af9 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 5 | Common Areas
5ec600c7-edb3-4e38-b3fe-70adca8c70cd |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Fitout | Level 5 | Residential Areas
f86213a4-8d92-4821-8c12-7c3d0cb3e31a |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B05 | Ryman Construction (Backfilling, Subsoil Drainage, Fencing)
e09ceb99-c45d-4c98-8970-89c03e0a2cb0 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B06
cf7113f5-a671-4ddf-b7fd-8c1b15f9524b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B07
3f54e3d0-e885-40a7-abc4-9ecd679e2b59 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08
c8bfd670-6bc9-4b8a-bdf1-ebae2c88cb4f |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services
56e30039-f38e-40d5-9727-60cdfe572633 |  | checklist-flat | pass | d94b1a28d2a0b387f28888114a0eedb8651c093c757136360254f28f21ae3f6c | checklist-flat | FALSE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services | Piling
0d9aca68-7a23-4501-950e-7c911bfad359 |  | checklist-flat | pass | 0c2470ce9dba2c3ade5bcbf596c7d8d6e3a62f72b652bc053d94c0b5fbde3cc9 | checklist-flat | FALSE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services | Tanking/ Waterproofing - foundation
181e5248-63ea-48b4-bf72-098572ed7ac4 |  | checklist-flat | pass | ecc41129594f66cd8ea3ddc6d8c4bfca2bfc28a62bc311f2a04fcec391b6d69d | checklist-flat | FALSE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services | Underground Services
11bb0331-2ca0-43e5-b373-0a8fc8f9bad8 |  | checklist-flat | pass | 8749770115955f289c9d34532d4aa7b3c7e59dc70eac6d8eec21cc5a1776be02 | checklist-flat | FALSE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services | Backfill
213e604b-324a-4eee-85a3-dd8602b47a09 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services | Foundation Concrete - Pile Caps/Strip footing
3cca5578-8bf3-442c-bfe6-f72fa013d2dc | Child Pour Details(01d06ac5-9eb8-4931-9951-ceebb3dd1eca): Data not allowed on checkpoint-group: Area to be poured:(66c2b4ab-b686-4ba5-89b1-21e89ed21cb8), Date of pour:(2692ca7c-cce3-4b17-b285-c7cbcbdd1965) Child Concrete Supplier Specifics(60a89390-cfa1-48c4-a8e4-71714e279bd6): Data not allowed on checkpoint-group: Supplier Name:(7e86bb4a-ce8b-4042-a309-652dd7806eb1), Specified concrete strength:(9043f81f-10c1-4950-8388-4e7c14c6df53), Concrete strength ordered:(3396a915-62ce-4cc3-be2f-70bcb7bf2959), Concrete quantity ordered:(78043967-d8b8-467d-a2e6-b27fff4924fd), Test blocks booked(be26dc07-6de3-4db5-8a6e-57a76073df68) Child Concrete Distribution(ff9d1c61-b924-49ba-bacb-cafa78d5f7b2): Data not allowed on checkpoint-group: Who is distributing the concrete:(69995b14-aab9-4324-9a8f-da767487de19), How is the concrete distributed:(c3216281-807d-41b1-83b0-4f50d770ff77) | checklist-sectioned | pass | 5b1c3a171e403d3eb1a584916538367c528699877ebd3b4bbb4e199a743d73ef | checklist | FALSE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services | Foundation Concrete - Pile Caps/Strip footing | Concrete pour - Lift pit 2
dfd663d0-4d93-5256-8fd9-3d56b6a40db0 | Child Pour Details(a5797c68-6d9c-564a-86e4-6f59c29d16a9): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(845012b7-4972-5f2a-aa2f-2bb50666df74): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services | Foundation Concrete - Pile Caps/Strip footing | Concrete Pour - Level 1 foundation (area 4b)
3a25f712-83e4-573a-8af9-5176ca0623b4 | Child Pour Details(433803fc-49dd-5994-a8ac-7446e2f639ce): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(4d19ae7b-5f2d-5bf2-b0a6-03fb5b673702): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services | Foundation Concrete - Pile Caps/Strip footing | Concrete Pour - Lift pit 1 (level 1)
b33d8f41-57f4-5c39-99e8-9b0dbe7424a8 | Child Pour Details(71db876b-325d-59c6-a650-aca320637b71): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(b63a2625-e7e3-523f-9158-fa3ced0160ea): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services | Foundation Concrete - Pile Caps/Strip footing | Concrete Pour - Level 2 foundation (area 1a)
6dd1963f-971f-5bb7-b48b-42141fd45c32 | Child Pour Details(c0b4954e-6636-52d1-9d7c-ddd9db81c325): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(aad13489-0f22-54f2-ae68-8541deda786f): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services | Foundation Concrete - Pile Caps/Strip footing | Concrete Pour - Level 2 foundation (area 2a)
34efd9cd-03a9-53e3-9246-87cc0bdefa46 | Child Pour Details(155f8ecf-364a-5c40-adc1-95323b119961): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(329a8439-9e98-54ff-a67c-8ffd4313e0f0): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services | Foundation Concrete - Pile Caps/Strip footing | Concrete Pour - Area 4a & 3a
a829b5e2-99df-4eef-8d89-9280ad1c2ce8 | Child Pour Details(e7920edc-a4da-50ae-a264-ec7d75f9e271): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(b8e77d42-0261-5b6e-b4c4-0c08ef41a186): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services | Foundation Concrete - Pile Caps/Strip footing | Concrete Pour - GL 4-11 / N-Q' & 4-8 / M'-N
18a031eb-7516-4801-aa2c-b6145b69dd73 | Child Pour Details(c424ad2e-a86f-521a-a7bb-a1b61c307abd): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(a41693cb-1ba1-5c3c-b7d5-cc89ce914c9c): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services | Foundation Concrete - Pile Caps/Strip footing | Concrete Pour Area B GL 4-12 / Q-Y
acce0ca9-3cda-44ae-ab2d-db135e626c28 | Child Pour Details(67bf0632-be3c-5aaf-9e6d-979b19dd2642): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(42785b71-babd-5473-8397-373525ae3be7): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Foundation/Tanking/Drainage & Subfloor Services | Foundation Concrete - Pile Caps/Strip footing | Concrete Pour Area B between GL S-V & 11-18
375c908b-96d1-42af-93f8-a9086ae27666 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Structure & Roof
393390fd-0a0a-407d-9edd-cad3d8ee4d08 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 1
c9293266-1415-4db9-8ee7-9c6fd9b1e931 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/sprandells/edge beams)
a5bd21d0-edce-45b4-ab38-6f28b87c52e7 |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Wall Panels
f94705eb-a957-4088-a751-17b42f9b6e94 |  | checklist-flat | pass | 186af7613ed031677b0093c261520031dfc66d5a36f464c5cf2d6020929bb102 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Wall Brackets
21356c55-8015-4ab8-b1d3-857bd6ae3d5f |  | checklist-flat | pass | ab9d2bf20065318d75ace5b1329cdc6a3805504d8ac302f12ac33577d52b716a | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 1 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Spandrel Panels
d4f70105-14ec-4f55-a29a-d210cc50b609 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 1 | Insitu Stitch Joints and Columns
76c936e6-b636-414d-bded-d1f890605098 | Unsupported Children: checkpoint-no-status Pour Details(4260f6e5-ce56-42e1-9aee-98e9b70ec7f5) Child Pour Details(4260f6e5-ce56-42e1-9aee-98e9b70ec7f5): checkpoint-no-status must be display normal but was flat Child Concrete Supplier Specifics(c54169dd-2489-46a3-aaec-41e8ea23fcfd): DataPoint Test blocks booked(68605077-7e0d-4b89-bfcf-28e620568fb0) is missing 'button' values Child Concrete Supplier Specifics(c54169dd-2489-46a3-aaec-41e8ea23fcfd): Data not allowed on checkpoint-group: Supplier Name:(2c8c6f55-c4f0-4b8e-96b2-4b0244c55484), Specified concrete strength:(bc8a7892-9379-45f7-bf28-ae04914a1e0c), Concrete strength ordered:(8caaef8d-7d07-46f3-8643-7b4c72fcbabd), Concrete quantity ordered:(1ed1248a-9954-413a-8e0f-2dc5a34fdba6), Test blocks booked(68605077-7e0d-4b89-bfcf-28e620568fb0) | checklist-sectioned | pass | d99cb2d9f502dadc3eb8ec4715339fbaeeef2c276100f82c53dd73dc398d0aa0 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 1 | Insitu Stitch Joints and Columns | Insitu Stitch Joints
4fe0c359-c7f9-5b61-b3ae-e4f86b153628 |  | checklist-flat | pass | 54ea7daef64d6ad093ac7729c33f731524914ff7212604a6fec9d4e15031f2a1 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 1 | Structural Steel Flooring elements (beams and angles) - Level 2 Slab Area B - 4b
838bce61-252c-51dd-a884-f94840e85726 |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 1 | Inspection - Column at level 1 GL 18
1526cdd2-97cc-483c-903e-090fdf62560d |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 2
97b16292-9ace-4170-bec5-b018e2f661d0 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 2 | Structural Steel Components
4ba763ec-4af8-4b0d-8ccf-034fb6e3ad7d |  | checklist-flat | pass | 985f811c0486b69b709002737772d882798cfae539f89e96d6c3b60814b8fe1b | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Structural Steel Components | Structural Steel - Beams, Posts & Angles - Area A
9725075a-2852-42d1-9aac-e77c3f83dc24 |  | checklist-flat | pass | 54ea7daef64d6ad093ac7729c33f731524914ff7212604a6fec9d4e15031f2a1 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Structural Steel Components | Structural Steel elements (beams and angles) -
447d5697-ed95-4c15-a50b-4f36797eabb3 |  | checklist-sectioned | pass | 4537b7a0624b01970368556cc755cfb6006fb09e365f9ccb926cac7e79aef5b5 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Precast flooring - level 2 area B
32038ab8-5adf-4bea-af8a-7fe65cd704ab |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 2 | Concrete pours
b322e611-3e31-4133-868e-4156d228845a | Child Pour Details(7fc93b60-4969-408a-be35-95393411634e): Data not allowed on checkpoint-group: Area to be poured:(66c2b4ab-b686-4ba5-89b1-21e89ed21cb8), Date of pour:(2692ca7c-cce3-4b17-b285-c7cbcbdd1965) Child Concrete Supplier Specifics(427514a3-3882-4097-9002-9893249a0d68): Data not allowed on checkpoint-group: Supplier Name:(7e86bb4a-ce8b-4042-a309-652dd7806eb1), Specified concrete strength:(9043f81f-10c1-4950-8388-4e7c14c6df53), Concrete strength ordered:(3396a915-62ce-4cc3-be2f-70bcb7bf2959), Concrete quantity ordered:(78043967-d8b8-467d-a2e6-b27fff4924fd), Test blocks booked(be26dc07-6de3-4db5-8a6e-57a76073df68) Child Concrete Distribution(e587f896-05a0-4b9c-9a75-449d8bb82c0c): Data not allowed on checkpoint-group: Who is distributing the concrete:(69995b14-aab9-4324-9a8f-da767487de19), How is the concrete distributed:(c3216281-807d-41b1-83b0-4f50d770ff77) | checklist-sectioned | pass | 5b1c3a171e403d3eb1a584916538367c528699877ebd3b4bbb4e199a743d73ef | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Concrete pours | Concrete pour area 4b slab
31dc2c05-9a49-4331-ad3a-1f7b8c6b7237 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 2 | Precast Components (walls/stairs/brackets/sprandells/edge beams)
3b0f5ade-ba19-483e-b11d-c53d5f077c9a |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Wall Panels Area A
d0479754-9dab-40ef-9a9a-3a95ee37eda8 |  | checklist-flat | pass | ab9d2bf20065318d75ace5b1329cdc6a3805504d8ac302f12ac33577d52b716a | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Spandrel Panels
a342d49d-94b6-448c-85d9-cb54c6ade31e |  | checklist-flat | pass | 32054d014df66f84e223faeee9cebbb597d39c33e26d34f1d74efaef20f148c3 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Edge Beams
c116dc6e-95f9-543d-bc9b-10cfd5aa2407 |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Columns
fc55a391-fa1b-444c-bdd4-082b49871897 |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Wall Panels Area B
040abefa-99f2-4fbd-9e56-99afbd125702 |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Wall Panels 82P11
41c71953-17c5-4a9d-ae81-d73835187fb0 |  | checklist-flat | pass | ST - R - Stair Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 2 Stair Installation
cd3e8356-35b1-416f-a56f-1ccacca03c1a |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 2 | Insitu Stitch Joints and Columns
b6944f03-fdec-4371-9a69-46da09f05efb | Unsupported Children: checkpoint-no-status Pour Details(23994fcc-ff83-424e-80fb-1e37e6b57782) Child Pour Details(23994fcc-ff83-424e-80fb-1e37e6b57782): checkpoint-no-status must be display normal but was flat Child Concrete Supplier Specifics(e7db70f8-d967-4582-b762-a7411b44dd4d): DataPoint Test blocks booked(68605077-7e0d-4b89-bfcf-28e620568fb0) is missing 'button' values Child Concrete Supplier Specifics(e7db70f8-d967-4582-b762-a7411b44dd4d): Data not allowed on checkpoint-group: Supplier Name:(2c8c6f55-c4f0-4b8e-96b2-4b0244c55484), Specified concrete strength:(bc8a7892-9379-45f7-bf28-ae04914a1e0c), Concrete strength ordered:(8caaef8d-7d07-46f3-8643-7b4c72fcbabd), Concrete quantity ordered:(1ed1248a-9954-413a-8e0f-2dc5a34fdba6), Test blocks booked(68605077-7e0d-4b89-bfcf-28e620568fb0) | checklist-sectioned | pass | d99cb2d9f502dadc3eb8ec4715339fbaeeef2c276100f82c53dd73dc398d0aa0 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Insitu Stitch Joints and Columns | Insitu Stitch Joints
3b62ecfe-dae1-551b-bd52-fa5c9d90e8b8 | Child Concrete Supplier Specifics(40422659-9a7e-581e-89f5-61e722dc46ec): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | 176f9b38da8c2310bf0644221091f918dfff84540cc930c7eab551ac9f1fcdbe | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Insitu Stitch Joints and Columns | Concrete Pour - Column
68b884f9-7ead-45cc-ac7a-63c51e12be7d | Unsupported Children: checkpoint-no-status Pour Details(0a911d2c-2801-5088-a525-ca50cda7b890) Child Pour Details(0a911d2c-2801-5088-a525-ca50cda7b890): checkpoint-no-status must be display normal but was flat Child Concrete Supplier Specifics(66de710c-1d84-5520-b6e1-71e12e6b7fc0): DataPoint Test blocks booked(47b5772f-e793-4a2f-8d9a-9dd51e6f749d) is missing 'button' values Child Concrete Supplier Specifics(66de710c-1d84-5520-b6e1-71e12e6b7fc0): Data not allowed on checkpoint-group: Supplier Name:(65a56542-a1e1-4e32-970e-19d2d22eec2f), Specified concrete strength:(ce5ed86a-41fb-4acd-9b47-7c05c74e8d56), Concrete strength ordered:(63e9fd15-9292-4e1e-88ba-086727b230c5), Concrete quantity ordered:(4dec274f-21e9-4db1-9e6c-853fb3646910), Test blocks booked(47b5772f-e793-4a2f-8d9a-9dd51e6f749d) | checklist-sectioned | pass | 6b09c5317d3c4fc26fa8cb356be170cb57db76645abad2bd78fe113c85f75d8a | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Insitu Stitch Joints and Columns | Insitu Stitch Joint at GL J
8dfd03b1-7b52-46ed-b95c-2461bce4c8c2 |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Insitu Stitch Joints and Columns | Inspection - columns
a7340c86-1520-4359-a17c-6ba03f5ef444 |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Insitu Stitch Joints and Columns | Inspection - level 2 area B stitches
066660fd-6b41-430d-9033-f84c99804bcc |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Insitu Stitch Joints and Columns | Inspection - column at gl 17 - M+
ec4bde35-c719-4be2-93be-38419719cb7b |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Insitu Stitch Joints and Columns | Inspection - Column at gl V
3b643879-c7ae-4344-9d90-4fc7e61a3de2 |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Insitu Stitch Joints and Columns | Inspection - level 2 area B stitches at gl W+
0cf2edac-30c4-403c-a54c-820952716190 |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Insitu Stitch Joints and Columns | Inspection - a column and stitch at level 2
b27b125d-481c-4bce-85e8-62d3875431ff |  | checklist-sectioned | pass | 80d963d8eff66c99df7c9439e4c0227b9f9d3597850bc446da89c26f039c6048 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Insitu Stitch Joints and Columns | Insitu Column at Grid 9
5b602c97-d790-4db7-8b48-a4f5f18669fb |  | checklist-sectioned | pass | 80d963d8eff66c99df7c9439e4c0227b9f9d3597850bc446da89c26f039c6048 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Insitu Stitch Joints and Columns | Insitu Columns at Grid 10-11
e51fef6f-8b42-41de-8481-8f4f125e7101 |  | checklist-sectioned | pass | 80d963d8eff66c99df7c9439e4c0227b9f9d3597850bc446da89c26f039c6048 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Insitu Stitch Joints and Columns | Insitu Columns at Grid 9-10
99d30442-7089-4b9c-b9ef-0383e99a54f8 | Child Pour Details(edd68da5-a6c6-56a6-bd37-ec7893d798c6): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(ef4f3118-9064-5f26-a6b4-de9761f4b82d): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 2 | Concrete Pour - Insitu wall at GL B & 1
e2974d9d-f9ff-460e-98c3-72a1fcd455c6 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 3
a717b617-630f-4025-93c0-e2d86a1860af |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 3 | Structural Steel Components
086ae0e4-a2a1-4116-bbbb-00d490e6e3b6 |  | checklist-flat | pass | 985f811c0486b69b709002737772d882798cfae539f89e96d6c3b60814b8fe1b | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Structural Steel Components | Structural Steel - Beams, Posts & Angles
2601720f-4a0b-469d-874d-e2c7bd08e904 |  | checklist-sectioned | pass | 4537b7a0624b01970368556cc755cfb6006fb09e365f9ccb926cac7e79aef5b5 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast flooring - level 3 area A
796c1a2e-893a-4f68-8caf-eb9455f06f30 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3
fb184b74-633a-4cd4-997f-2b2f060a7f0c | Child Pour Details(a6bf5aa8-4c8f-438e-ac50-c5b1a2224419): Data not allowed on checkpoint-group: Area to be poured:(66c2b4ab-b686-4ba5-89b1-21e89ed21cb8), Date of pour:(2692ca7c-cce3-4b17-b285-c7cbcbdd1965) Child Concrete Supplier Specifics(04a78eeb-116b-4550-8052-aa3beaa49869): Data not allowed on checkpoint-group: Supplier Name:(7e86bb4a-ce8b-4042-a309-652dd7806eb1), Specified concrete strength:(9043f81f-10c1-4950-8388-4e7c14c6df53), Concrete strength ordered:(3396a915-62ce-4cc3-be2f-70bcb7bf2959), Concrete quantity ordered:(78043967-d8b8-467d-a2e6-b27fff4924fd), Test blocks booked(be26dc07-6de3-4db5-8a6e-57a76073df68) Child Concrete Distribution(776d2d43-cb81-4257-8bb7-dbb9cd5a6576): Data not allowed on checkpoint-group: Who is distributing the concrete:(69995b14-aab9-4324-9a8f-da767487de19), How is the concrete distributed:(c3216281-807d-41b1-83b0-4f50d770ff77) | checklist-sectioned | pass | 5b1c3a171e403d3eb1a584916538367c528699877ebd3b4bbb4e199a743d73ef | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | Concrete pour - Area 4B & 3B
3471fa89-f7c0-46af-8831-77c8002efbf4 | Child Pour Details(caba26b9-9ac9-5993-a96a-443c54dd2ce8): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(c4be388b-824b-5a8e-b1a4-8d37a4795d35): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | Concrete Pour at Level 3 Area A Podium Suspended Slab
f7ce15a3-0410-4394-a54e-fa73809702f0 | Child Pour Details(2394aaa1-eaaf-5c69-b521-5efb2fa46ee5): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(21f25535-c65d-5ab4-b3bf-4506b9ef0bd0): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | Concrete Pour at Grid 10-11/ A-B (43AB01)
8c15040b-9232-490f-9952-9cf784aa40e1 | Child Pour Details(5029a4d5-e0da-5cab-908a-55e72876429a): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(caebed56-caa4-5e84-8003-786dced7e64f): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | Concrete Pour at Grid 9-10/ A-B (43AB02)
5682cd2e-4b80-4a06-8d71-1a0170550f02 | Child Pour Details(ea91dd0d-4d4f-5325-b727-83ab327ffd51): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(c3f8c8f0-b201-594e-a5e3-72f07c385a52): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | Concrete Pour at Grid 9-11/ A-B (43AB03)
b86b54af-87ef-4ad9-9359-0c1b4de7e5e2 | Child Pour Details(6f04db06-de14-575c-92a4-c21732a9692d): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(d33cb74b-cd1d-5aae-89a0-6a9bf965b48e): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | Lev 3 Slab at Grid 7-15 / A-B
c5270001-3bce-4f7d-8084-6ca00d2c4ce2 | Child Pour Details(c9066aee-a8c8-58b9-885c-1cad7b6775b4): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(1f1462ff-3d0b-52c2-87b9-24ef5347721f): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | 43AB04
7031a442-4a31-4364-b4e5-ae147ac67265 | Child Pour Details(dfa255bb-1de1-577d-8488-80c889a5e636): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(654506d3-7fe0-5ba0-afd9-a873465cf158): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | 43AB05
08a8911d-27f9-4808-ad3e-7442caf3c612 | Child Pour Details(5ccba681-0d01-5c5b-8fd2-137077665a42): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(01873fc0-1322-54d4-9a06-00b91eb45d8f): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | 43AB06
fd3841e2-94ce-49a9-974d-8bdea4fc352a | Child Pour Details(6368654f-a426-5ebf-993a-babedcc10faa): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(27bc2256-1973-56ed-b752-f5d78d0c943f): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | 43AB10
abf1484f-3af2-4e17-b28f-214add790b64 | Child Pour Details(72c388fc-5b97-5bbc-9d6f-f55067e126d3): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(d2e48448-d80d-529f-82b6-21ab122e9b96): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | 43AB11
b521ca4a-5938-487e-931d-12e87aedae1b | Child Pour Details(cc9d6e1a-79cf-5db4-bae6-d21f290d113e): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(8e5d2ce2-d0b8-5236-a9aa-25b6858ca094): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | 43AB12
26e46d57-5c15-46c6-a561-b85e32a3d4af | Child Pour Details(c5b62e19-de7e-5476-9ad2-127c66061786): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(ded56165-bac0-591e-8bda-c353c2903949): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | 43AB18
dea37da6-cd7a-4174-aef3-e4353f119f81 | Child Pour Details(78df224d-1303-516f-830c-c4d0c8e8633c): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(b6d8a9b9-0a0c-509d-be3f-f01d790ecf6e): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | Suspended Slab at Area 3A (Gridlines G-M)
bda2c710-e21d-4e26-a29d-e716263369b2 | Child Pour Details(51c36da2-76f8-5e6a-8509-75df5008b9c6): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(fba58adf-835e-5b8b-a4f4-0a11f7b89d5b): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | Level 3 Area A Beam Stitch Joints from Gridline 12 to 17
04be5b0f-9a07-4371-b6ee-dc6131b4304e | Child Pour Details(e858d29a-7fef-5db2-9224-a6077df73116): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) Child Concrete Supplier Specifics(514d23e4-a450-5c74-8604-aeb7735af850): Data not allowed on checkpoint-group: Supplier Name:(dac13f13-1d96-4a2f-94d0-4a5c83ca7d88), Specified concrete strength:(10a1fc4a-3357-4563-8da8-f518c9f08bd2), Concrete strength ordered:(e3fafc38-2f2e-4f0c-8a53-5dc2f95c2567), Concrete quantity ordered:(7d231756-9479-4674-b41b-2a0532dd889d), Test blocks booked(425989be-bd71-4770-aa3c-6dea6d1bb8a2) | checklist-sectioned | pass | bd665d0dbd2f28cff6765caf4491c2202cb9683ff46f322010cc80ae8009a957 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | Lev 3 Slab at Grid 8-9+ / G+ - K+, 9+ -15 / B-K+ & 15-19 / C+ - K+
7f21eda0-a5d4-45e2-928d-44e500936067 | Child Pour Details(62b25e34-d69c-581b-89f5-2967b2c17f44): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) | checklist-sectioned | pass | 9bd0b0f824988d161b2b2ad2179e17d084a001f7036b7e20e98be54718b2c5df | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | 43AB23
a901c3cd-7383-4858-b76f-ce7a27e23abf | Child Pour Details(e0a7314f-3416-5120-b6eb-7f7ea44c2a2e): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) | checklist-sectioned | pass | 9bd0b0f824988d161b2b2ad2179e17d084a001f7036b7e20e98be54718b2c5df | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | 43AB24
ac8a9754-3225-41c6-a3c5-ab7b13f582b1 | Child Pour Details(ccfaa29d-29a3-530a-a2fd-b858203c72c4): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) | checklist-sectioned | pass | 9bd0b0f824988d161b2b2ad2179e17d084a001f7036b7e20e98be54718b2c5df | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | 43AB19
7435b519-a44a-4898-83f0-da709bdd7300 | Child Pour Details(742ff184-658a-5472-87b8-bca49df5e2e0): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) | checklist-sectioned | pass | 9bd0b0f824988d161b2b2ad2179e17d084a001f7036b7e20e98be54718b2c5df | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | 43AB17
c325d3f6-162c-4104-8baa-aab6ed6e8704 | Child Pour Details(7c032884-944f-551a-8993-ae7363a0ccd1): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) | checklist-sectioned | pass | 9bd0b0f824988d161b2b2ad2179e17d084a001f7036b7e20e98be54718b2c5df | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | 43AB15
ec852208-c2dd-4de4-83a6-e9500fcb0eac | Child Pour Details(7e2327a1-67c6-5b7f-93b3-66055960ea02): Data not allowed on checkpoint-group: Area to be poured:(6db33bf0-19e5-4688-92ec-48d3a30a1b72), Date of pour:(a326f385-818c-4941-8179-7bc89f1f557e) | checklist-sectioned | pass | 49370e1770a0e9dac5de0a377b68ebea3bd4a79d602027d937c931f0696b50ab | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Concrete Pour at Level 3 | 43AB21
cf6dd1a1-7e7c-4a6e-af1d-4753f08a7441 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams)
48630e03-bd3b-4f85-baa2-959a045f4678 |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Wall Panels at 3b & 4b
03338af5-5b69-4371-936b-96081286edbd |  | checklist-flat | pass | ab9d2bf20065318d75ace5b1329cdc6a3805504d8ac302f12ac33577d52b716a | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Spandrel Panels
1cc3a4cb-f1db-46d4-adb5-1adc5db6b539 |  | checklist-flat | pass | 32054d014df66f84e223faeee9cebbb597d39c33e26d34f1d74efaef20f148c3 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Beams
02288551-9fd0-4c92-b8b6-249331fa3447 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Column
2082b2d7-840c-4e54-9228-2e9e2435247c |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Column | Precast Column at 3B0 & 4B
ea56e9cb-60c4-4121-b3f0-a5a046ffaa64 |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Column | 43AC01 (Gridline A)
97a0e145-3188-4b39-a751-67d9078e157c |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Column | 43AC02 (Gridline A)
c365c640-e026-4f1c-a462-3f6503c215fe |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Column | 43AC01A (Gridline 5)
fb399b41-2116-4ff1-a9a6-a1e9004668fe |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Precast Column | 43AC02 (Gridline 5)
65a9f02c-0c59-40fd-9b72-7a763597b164 |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Wall Panel 83P34
ea821cb6-1d7e-4101-a7ec-998f4520a705 |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Wall Panel 83P35
21abcb7e-f1da-4b50-80fd-c8625644967e |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Wall Panel 83P16
c012ded4-766f-4041-9fe5-31b32354c803 |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Wall Panel 83P17
c0d9ae16-7fa7-410a-bd82-4b77ceac335b |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Wall panel 83P18
5a6396be-11a8-4362-80df-cacbf66534c9 |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Wall Panel 83P19
ef21594f-f999-4dc8-9cda-d6bb07ceb04e |  | checklist-flat | pass | 0b8b9d6b30f02b1f6e69299d99f0bf62b800ad5f490beedb701ffcc0a835330d | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Wall Panels 83P45
52be7286-51b5-433f-97b0-ec22329f5237 |  | checklist-flat | pass | b60dad1c3d6035a7a83d42eea9413d7382a7ec38062ba50dac94f497c036b80c | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Spandrel Panels 83P30
851b11d1-e1b0-489c-9f30-69b5935693f9 |  | checklist-sectioned | pass | cb015c0774f721e0622a965e160d42ad3879e0686d010f116ca47337341bf361 | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Precast flooring - level 3 area B
cbdc9450-8bad-4656-9daa-42abbdc54ac4 |  | checklist-sectioned | pass | 6fb1c6d69c1f3ca6cd3de6f8b7d3fb049634035faa9efbed613619f10022a57d | checklist | FALSE | FALSE | Building B08 | Structure & Roof | Level 3 | Level 3 Stairs Blockwork
14e8a167-c240-49e8-8969-d0d7d593ce1f |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 3 | Stair SW01, Insitu Wall, grid 5-7 / C-F
f04617a1-8f65-45d3-8e4b-d98dc5ab0e67 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 3 | Stair SW02, Footing, grid 3+ - 6 / U-W
28c82036-c91b-4d91-829e-2d6a5b36c57c |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 3 | Lev 3 Stair SW2 Stitches 1 & 2, grid 3+-6 / U-W
31ffe0b3-989d-400f-8d8b-2ba087d357e7 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 4
baa5fbae-302e-4725-b506-801ad99db6b1 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 4 | Concrete pours
1734a38c-e9dd-4746-b2be-1c3c311f5501 |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Concrete pours | Level 4 Slab Pour 1 12.04.22 grid 7-15 / A-G+ & 14+ - 19 / D-M Concrete Pour
6e76493d-06bb-4520-8c83-4ecabdaa6e51 |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Concrete pours | Level 4 Pour 2 26.04.22 slab at grid 1-7 / J-P, 7-9+ / G+ - O & 9+ -14 + / G+ - M Concrete Pour
6ccc369e-5359-416e-b681-132920c3875d |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Concrete pours | Level 4 Pour 3 09.05.22 Slab at Grid 9 -11+ / M+ - O, 4 -11+ / O-S & 3-4 / O-P Concrete Pour
e7107ac4-8c18-472a-9487-0545f47b14c7 |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Concrete pours | Level 4 Pour 4 16.05.22 Slab at grid 4-18 / S-Y Concrete Pour
9fa1087e-2c74-47bf-baf9-dca047ad1e3b |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Concrete pours | Level 4 Insitu Wall Grid 1 - B-G+ & B 1-1+
c36d08c8-0a51-4538-b39b-606dec7b2875 |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Concrete pours | Level 4 PB30 06.07.22 Grid 12 - 14+ / N
4d08d810-d4a2-424e-b626-e0b7a78f0cf5 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams)
d3899bd3-d400-4ce6-841c-9361fb4396b4 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Wall Panel
eb2c2771-82d7-4415-8348-1ed81dae79f5 |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Wall Panel | level 4 Precast Wall Panel 28.04.22
c40cc6d3-286a-43fb-a4e6-462262f87d39 |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Wall Panel | Level 4 02.05.22 Precast Wall Panel Installation
1927abfb-3004-4994-baa5-acc26df58d30 |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Wall Panel | Level 4 03.05.22 Precast Wall Panel Installation
c64915df-1e21-4a44-a7c2-22d59a5d2409 |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Wall Panel | Level 4 04.05.22 Precast Wall Panel Installation
f071dde0-9da7-40a5-a255-d34eb9c1da7c |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Wall Panel | Level 4 12.05.22 Precast Wall Panel Installation
bebf9a9e-a3e5-4e82-9da4-abf14667d750 |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Wall Panel | Level 4 13.05.22 Precast Wall Panel Installation
e2349aa8-890c-4c5c-86fe-56def4b4e1e5 |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Wall Panel | Level 4 20.05.22 Precast Wall Panel Installation
dd8abd1e-8f69-4497-863c-86bae8ff867e |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Wall Panel | Level 4 01.06.22 Precast Wall Panel Installation
b32a712d-5887-45c4-94d0-8770756574a4 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Spandrell Panel
72f39845-d48c-402e-b044-8d01108f29d0 |  | checklist-flat | pass | ST - R - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Spandrell Panel | Level 4 Precast Spandrel Panel Installation 12.05.22
feff70fc-db6e-4454-b7c4-d46b9145e9e1 |  | checklist-flat | pass | ST - R - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Spandrell Panel | Level 4 Precast Spandrel Panel Installation 18.05.22
ff74bb57-e26f-4b6c-9df0-6476fd993ed9 |  | checklist-flat | pass | ST - R - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Spandrell Panel | Level 4 Precast Spandrel Panel Installation 01.06.22
9862f381-269c-4903-a660-ebc1daace9e2 |  | checklist-flat | pass | ST - R - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Spandrell Panel | Level 4 Precast Spandrel Panel Installation 03.06.22
b6808eed-d09d-49aa-99c8-cbd5a588da38 |  | checklist-flat | pass | ST - R - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Spandrell Panel | Level 4 Precast Spandrel Panel Installation 16.06.22
2974e64e-42cb-4ea8-9782-bbaaca9241c3 |  | checklist-flat | pass | ST - R - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Spandrell Panel | Level 4 Precast Spandrel Panel Installation 20.06.22
29ded7da-9173-4ca3-9e23-44062990e28d |  | checklist-flat | pass | ST - R - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Spandrell Panel | Level 4 Precast Spandrel Panel Installation 30.06.22
bb027c09-b988-405c-a32d-cab1f10e97a2 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Edge Beam
9860116a-b040-4e43-9f0e-0980bb828bd2 |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Edge Beam | 44BC01 at grid 17-18 / S
9205d31f-dc8b-472b-be52-40edb2786aec |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Edge Beam | 44BCO2 at grid 17-18 / S
e30f70c8-7296-459a-951b-edd0e705e36a |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Edge Beam | 44ACO1a at grid 18 / T-U
610115af-9fac-4699-a466-a86b1454b7ff |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Edge Beam | 44BCO2 at grid 18 / T-U
16cd56fa-a410-4758-9c81-96d2be5d745c |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Edge Beam | 44ACO1a at grid 18 / W-X
fd608c74-18bd-41be-909b-22aeb54746d4 |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Edge Beam | 44ACO2 at grid 18 / W-X
33074c92-4ee2-4f39-9199-68389bff59b5 |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Edge Beam | 44BCO1 at grid 17-18 / Y
ef5de754-14ff-4c27-9b1e-8ffa9b982283 |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 4 Precast Edge Beam | 44ACO2 at grid 17-18 / Y
1d1d261e-caee-46a9-9dfd-8e4736fb359c |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Stair
34d61b82-d9c4-4a47-acd5-e5b976636060 |  | checklist-flat | pass | ST - R - Stair Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Stair | Level 4 Stair Installation
e448d6ea-342f-4797-8946-23a340f334d2 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 4 | Insitu Stitch Joints and Columns
ddf750d9-a56f-49a5-86ac-804082e9b003 |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Insitu Stitch Joints and Columns | Level 4 Panel Stitches 06.05.22
f9957d19-ace7-40e4-8650-a2d70341f59e |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Insitu Stitch Joints and Columns | Level 4 Panel Stitches 24.05.22
71da586a-07e9-4ad1-81b8-93355a2dc5c2 |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Insitu Stitch Joints and Columns | Level 4 Panel Stitches 08.06.22
75513790-0161-4b04-bb09-363eb049e625 |  | checklist-flat | pass | b44f5da93dbd62f04f0f164045dc742b372ff104dead0c7f19c49b43a0192970 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Insitu Stitch Joints and Columns | Level 4 Panel Stitches 16.06.22
b79d84f5-e144-4991-ae66-f63a78c3f5fd |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab
5a9fafbc-dd2f-4b80-b955-fa104547ed8c |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | level 4, grid 7-9+ / A-C 10.03.22
8089888d-5fd4-4164-9873-3654886f792b |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | lev 4, grid 10+ - 15 / A- B+
b4926c5b-933c-417e-8320-51241b12a999 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | lev 4, grid 10-16 / B+ - E & F-G
23fad8c6-c847-44fc-a122-87b47accef82 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Flat Slab Lev 4, grid 9+ - 10+ / A-B+
739790a3-9df7-4b21-bac4-10de1ec90d5f |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Rib & Infill at level 4, grid 7-9 / E-H
c12cbd07-5e3c-41d5-a85e-14eabc1c5e1c |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Flat Slab level 4, grid 10-16 / G-H
ea15027d-daa9-4d4a-9fac-dee25ea3d93e |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | lev 4, grid 10-16 H - M+
d91fea4b-4883-4e20-ac64-71f7fe7c1b23 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Flat Slab Lev 4, grid 17 - 19 / F+ - H
9190fba4-c3e8-4c37-8680-bf319ea099fd |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Flat Slab at lev 4, grid 9-10/ E-H
bfedf269-47bf-48f8-9a58-dd3e1da81811 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Rib & Infill at lev 4, grid 17-19 / H-M
db6c797f-b569-4915-ae98-835c585f64d1 |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Rib & Infill at lev 4, 17-19 / D-G
c26128c0-c06f-4299-99d2-f2acd9805d7f |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Rib & Infill lev 4 grid 1-3 / N+-P
7c1c416d-af54-478a-abca-b6aadb074576 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Flat Slab at lev 4, grid 1-3 / M+ - N+
2bb3196b-9476-4d06-bd43-1da6f9f6c643 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Rib & Infill at lev 4, grid 1-3 / J-M
8aefeb86-c5ac-4f3c-bc78-1e482c1f30b8 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Rib & Infill at lev 4, grid 3-9 / N-Q
d3b33727-be90-4106-b8dc-a157ea27c485 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Rib & Infill at lev 4, grid 4-9 / Q-R
142e7e36-36de-4ee3-abca-c67106bf9461 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Rib & Infill at lev 4, grid 4-9 / R-U
2fd382d0-22e4-43d1-a39a-c1d9cb8435e2 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Rib & Infill at Lev 4, grid 10-14 / N- Q
f37278a3-db7d-49e2-bd23-f50baf8b8bc4 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Flat slab at lev 4. Grid 9-10 / N-Q
6167336d-966c-409c-815e-1983d2e486ff |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Rib & Infill at level 4, grid 10-11 / Q-R
8b849c49-4f4b-435a-bed6-6ef77f5579df |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Flat slab at lev 4, grid 9-10 / Q-R
9921eea9-adc5-47f2-91a5-53978d6daffb |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Rib & Infill at lev 4, grid 17-18 / W+ - Y
4be63b4e-3035-43bd-b573-039f1dcd6681 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Rib & Infill at lev 4, grid 17-18 / S - T+
67c7734f-472a-4103-8931-a4dbbcff6e62 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Rib & Infill at lev 4, grid 14-16 / S-V
1099684e-ff13-4717-90f6-8c83a0c0845d |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Ribs and Infill at Lev 4, grid 14-16 / W+ - Y
831252cf-7ee7-44ea-b786-e60b6f0ea982 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Flat Slab at lev 4, grid 17 - 18 / T+ - W+, & 12-16 / V-X
9f7df926-53e0-4f64-8248-dc07a1b7c3b4 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 4 | Rib & Infill/ Flat Slab | Rib & Infill at level 4, grid 4-12 / W-Y
5f70306e-293d-4e12-bd44-8dcbf7f4d46b |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 5
4e4f047f-5bca-49c0-bd95-e20b2df7da5d |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 5 | Concrete pours
ac1b0edc-55b3-4f25-a406-c3521c2861c1 |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Concrete pours | Level 5 Concrete Pour 1 06.07.22 grid 4-12 / Q-Y & 12-18 / S-Y
7891600f-0680-4865-b3cd-e199d80be484 |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Concrete pours | Level 5 Concrete Pour 2 21.07.22 grid 1-7 / J-P+, 7-10+ / E - P+ & 10+ - 12 / M+ - P
eb5c1348-1e73-40a3-b5eb-711708ba9093 |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Concrete pours | Level 5 Concrete Pour 3 28.07.22 grid 7-15 / A-F & 10+ -19 / F-M
8e289441-e47a-44f8-a5eb-2191d4f938e6 |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Concrete pours | Level 5 PB30 21.07.22 grid 12-14+ N
180b09f5-f642-4f9b-b9b1-cbc42fd5d29f |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams)
25d72427-d706-4bb0-9db7-d7969ecee1f9 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Stairs
ce817961-effd-43f6-97d3-23df0519d598 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Wall Panels
8721a844-a3bf-473e-9325-a1652c6e9fc2 |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Wall Panels | Level 5 14.07.22 Precast Wall Panel Installation
925f3ad3-f3d0-4288-a5d7-50bda2fadfb9 |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Wall Panels | Level 5 15.07.22 Precast Wall Panel Installation
10d54bfb-adbc-4378-b58b-56f0da88cb27 |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Wall Panels | Level 5 18.07.22 Precast Wall Panel Installation
f59beba9-44da-4464-8fc2-89d961411878 |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Wall Panels | Level 5 04.08.22 Precast Wall Panel Installation
c9e42eaa-8416-421b-aa72-cf8ee443ad35 |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Wall Panels | Level 5 05.08.22 Precast Wall Panel Installation
41289a81-4538-4a3a-a707-b34e42d43148 |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Wall Panels | Level 5 09.08.22 Precast Wall Panel Installation
b63443a3-9d81-46c3-81e5-a148fc8b06c8 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Edge Beams
f275c69a-1a99-4bc2-b936-0ecc9133b957 |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Edge Beams | 45AC01A at grid 10-11 / A
e9b430c0-1952-4e7a-bb60-9a68bcfaaa7d |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Edge Beams | 45AC02 at grid 12-13 / A
263b1a1c-1aab-46b5-9cbb-0e063d15b3ac |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Edge Beams | 45AC01 at grid 15 / A-B
37509c4c-8634-462a-8f07-04d0542984d1 |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Edge Beams | 45AC02 at grid 15 / A-B
143c9941-06c8-464d-931a-98eda1952513 |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Edge Beams | 45AC01A at grid 17-18 / D
d8fa2ad9-a959-49f5-adf9-3852aaaa7b6f |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Edge Beams | 45AC02 at grid 18-19 / D
d16fd738-cb68-4cc0-88a1-f689cd42c55d |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Edge Beams | 45AC01 at grid 19 / F-G
f81b2e74-501b-434e-98df-b2696692e230 |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Edge Beams | 45AC02 at grid 19 / F-G
19eadb6b-9c55-4712-825c-215f73fc5896 |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Edge Beams | 45AC01at grid 19 / H-J
c2cf33a9-5048-4bdb-bd93-26aeaf9486b2 |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Edge Beams | 45AC02 at grid 19 / J-K
bd212323-8cfd-427a-982d-d480b0c437cc |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Edge Beams | 45AC01 at grid 17-18 / M
b3b74a70-8f66-48bc-b4cb-e38671acb54e |  | checklist-flat | pass | ST - R - Precast Edge Beams Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Edge Beams | 45AC02A at grid 18-19 / M
8c642ab2-9454-48d0-88bb-1a9aca644f79 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Spandrell
286bd557-b2b1-4399-be89-d8a4f985373b |  | checklist-flat | pass | ST - R - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Spandrell | Level 5 15.08.22 Precast Spandrel Panel Installation
1993c18f-e034-4bc8-8f7a-7d2ca16b6bae |  | checklist-flat | pass | ST - R - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Spandrell | Level 5 19.08.22 Precast Spandrel Panel Installation
b0b588b3-c155-4325-a5d8-680de81f20f8 |  | checklist-flat | pass | ST - R - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Spandrell | Level 5 25.08.22 Precast Spandrel Panel Installation
df4ba53c-b7b2-4cec-8408-36210175c009 |  | checklist-flat | pass | ST - R - Precast Spandrel Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 5 Precast Spandrell | Level 5 30.08.22 Precast Spandrel Panel Installation
75b8c08b-3d86-43d7-90d8-b7434e0acbdd |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 5 | Insitu Stitch Joints and Columns
5cf87b42-6f1b-4654-9d51-31ca8a269019 |  | checklist-flat | pass | b44f5da93dbd62f04f0f164045dc742b372ff104dead0c7f19c49b43a0192970 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Insitu Stitch Joints and Columns | Level 5 Panel Stitches 20.07.22
41aa3829-ff5a-415e-bced-be1b1468464a |  | checklist-flat | pass | b44f5da93dbd62f04f0f164045dc742b372ff104dead0c7f19c49b43a0192970 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Insitu Stitch Joints and Columns | Level 5 Panel Stitches 08.08.22
a229c4b2-59f7-4c47-81f8-ce3706738c85 |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Insitu Stitch Joints and Columns | Level 5 Panel Stitches 11.08.22
dd03762d-5ac9-4ee0-987f-72cbe80947f1 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring
9723a83d-bb13-4539-b5fe-721934db7808 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill
138ab366-01c8-47ac-8f45-414b2601ce8b |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | level 5, Grid 4-9 / Q-R
4a8e0bad-36e4-4851-9af3-07d05396de70 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5, Grid 4-9 / R-U
4c9e8f04-2e46-4e8f-baa6-8229c69d9005 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 10-12 / N-P
f7a2a5df-e393-4488-b9c9-8a547ab2f7d2 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 1-2 / J-M+
063dec28-fb14-4767-aa05-84298f517546 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 1-3 / N-P
74fe20c2-7070-4022-8e0e-081ce9478922 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 10-12 / N-Q
eeaf77df-b7d0-4769-a7a2-755c2c6ef3d1 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 10-12 / P-Q
5e772022-599e-42c8-af3f-00470b01816f |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 10-12 / P-U
eef341b7-d5bc-4ca5-b7c8-48ce75fad642 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 14-16 / S-U
b4c08ec7-4b8b-4db2-9d0f-deed6c3513d1 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 14-16 / W+-Y
d55e4816-8d5e-44bf-aa6c-82a5e46ede89 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 4-11 / W+ - Y
f79ff16d-dab8-4746-8ba9-ea3722082b89 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 17-18 / S-T+
52618327-bb8a-42ec-8737-62e4f9569992 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 17-18 W+ - Y
8773b123-1981-4d0c-a802-306603ed510d |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 10-12+ / H-M+ & 12+ - 16 / H-K
fd0167e5-5eef-4feb-b594-e83ae862fc60 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 17-18 / C-F+
dfd300da-39c0-43ff-9f36-b5aff9bcff51 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 17-18 / H-M
0b4ee0e1-b990-49d6-916e-471eb060e648 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5 Grid 2-5 / J-M+
09e32fd7-24ef-4b5b-bcc1-336b64924150 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5, grid 5-9 / H-M+
30bd0aa1-2d9a-46b7-8c83-dfd6a4cf352f |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5, grid 5-9 / N-Q
de0493b8-4250-41e5-ab29-b9c3b3ecda50 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5, Grid 10+ - 15 / A - B+
b727c648-dfb2-4f91-8d38-555fbaf1c5d5 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Rib and Infill | Level 5, Grid 7 - 9+ / A-C
60e136cd-ca2f-4275-beb8-4ccdb303694c |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Flat Slab
674b6242-a4ad-4f54-856e-827e5ff2147c |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Flat Slab | Level 5 Precast Flat Slab Installation Grid 9-10 / C-H
8cf6e88f-3d1f-44ec-8dc6-0f5c41b51fb0 |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Flat Slab | Level 5 Precast Flat Slab Installation Flat slab at lev 5, grid 9-10 / H-N
321312af-0f17-4716-bee0-ef0157959fc6 |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Flat Slab | Level 5 Precast Flat Slab Installation grid 9-10 / R-T
7ba7b668-0388-4f44-8fc8-56a90fce0f2f |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Flat Slab | Level 5 Precast Flat Slab Installation grid 9-10 / Q-R
3d7ad5c9-7e3d-4778-9677-421740a96c86 |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Flat Slab | Level 5 Precast Flat Slab Installation grid 9-10 / N-Q
deb9f9f4-142e-40a6-ad51-688431cd9983 |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Flat Slab | Level 5 Precast Flat Slab Installation grid 10-16 G-H
b8e0d314-af90-40d6-addf-fdb53fb9287b |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Flat Slab | Level 5 Precast Flat Slab Installation grid 1-2 / M+ - N+
5b08ad86-9915-4b9f-9bb4-b4844f167911 |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Flat Slab | Level 5 Precast Flat Slab Installation grid 17-18 / T+ - W+
78137f44-c340-400e-bf4e-40952a317814 |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 5 | Precast Flooring | Flat Slab | Level 5 Precast Flat Slab Installation grid 9+ - 10+ / A-B
2e82d3d3-25f8-4770-9f9a-f07afdaa0736 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 6
a72675f9-9cac-4878-b39e-8344d67a7bcb |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 6 | Structural Steel Components
c9f42e05-e78c-47a3-b859-8a4ff601d2df |  | checklist-flat | pass | 985f811c0486b69b709002737772d882798cfae539f89e96d6c3b60814b8fe1b | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Structural Steel Components | Structural Steel - Beams, Posts & Angles
982f6962-695f-4ce1-b0e9-6109f1b66e21 |  | checklist-flat | pass | 14969124506bc6f2cba3292faf9165f43e9972a295d485067488f2b9d5acd782 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Structural Steel Components | Intumescent Painting
8ae6cc3e-eccb-488c-b9ba-d36c6f4f34a3 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 6 | Concrete pours
830f0bb9-08a7-4f24-8733-7ddd4a2c7353 |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Concrete pours | Level 6 PB30 31.08.22 Grid 12 - 14+ / N
4ad86f08-d3d4-4656-9886-a506181d0530 |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Concrete pours | Level 6 Pour 1 31.08.22 Grid 3-12 / G+ - Q
151731e6-941a-43d0-a101-26f5300655ee |  | checklist-flat | pass | d3655525410904a94c155791d36de6cd124b3fc21c1e2b5662d77e4a4a209194 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Concrete pours | Level 6 Pour 2 16.08.22 Grid 7-17 / A-G+ & 10+-19 / C-M+
90810588-0b0e-4a83-b084-b52b6780ed1a |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Components (walls/stairs/brackets/sprandells/edge beams)
b542f814-e445-48a4-b689-5fd14c54c5c3 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 6 Precast Wall Panels
e93f9465-eceb-4c42-93e4-0652c0e6dc4c |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 6 Precast Wall Panels | Level 6 12.09.22 Precast Wall Panel Installation
a17fd388-5cb1-4d5a-b829-48c20ae2cfab |  | checklist-flat | pass | ST - R - Precast Wall Panel Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Components (walls/stairs/brackets/sprandells/edge beams) | Level 6 Precast Wall Panels | Level 6 04.10.22 Precast Wall Panel Installation
585c6118-244c-4f70-bf2f-35764379e096 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring
461129ec-6c35-4fa0-b2e4-c7defe50839d |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Rib and Infill
97c903ba-c8bc-44a4-8823-ea66a3eef3be |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Rib and Infill | Level 6 - Grid 3-9 / N-Q
dfe8877a-ff48-482c-a5ad-6bb1066551da |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Rib and Infill | Level 6 Grid 7-9 F- H
43403a05-0a83-4b3d-8690-0df37920dc29 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Rib and Infill | Level 6 Grid 5-9 H - M+
da6a7697-bdf1-47a8-8852-21e9ac1695f0 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Rib and Infill | Level 6 Grid 10-12 / N-Q
27eeeb9e-c997-4692-8374-77332357b2cf |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Rib and Infill | Level 6 Grid 3-5 / J-M+
46b544c1-74d1-4332-853d-ba06d48628a7 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Rib and Infill | Level 6 Grid 10 - 16 / B+ - G+
e2e9a2cf-2f6e-4ff4-bd2f-9f7d6c92e238 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Rib and Infill | Level 6 Grid 10-16 / H - M+
e2833ca8-b65a-4c4a-9c85-9ac336f3376e |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Rib and Infill | Level 6 Grid 7 - 9+ / A-C
c8d9b280-cd70-4599-b0c3-06f291830df6 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Rib and Infill | Level 6 grid 17-19 / D - F+
b287434e-a477-4d8b-a750-6a0416851ce9 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Rib and Infill | Level 6 grid 17 - 19 / H- M
22b0e0d1-1c8b-4e77-bcf4-6a1093f3def1 |  | checklist-flat | pass | 7504ded751417c5d81892cfc519bd942361d2ab5b75fdc88d60250763523a115 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Rib and Infill | Level 6 Grid 10+ - 15 / A - B+
28b9a5f2-1c64-43a6-91d9-1c6f0fd78247 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Flat Slab
0f554680-dbf3-48c7-8d3f-953a6a9ee839 |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Flat Slab | Level 6 Precast Flat Slab Installation Grid 9-10 / N-Q
7d9a767c-46a2-469a-aa65-145a96bd0aed |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Flat Slab | Level 6 Precast Flat Slab Installation Grid 4-12 / M+ - N+
4a7fc0c4-89b5-40f1-8dfd-5c42c8438641 |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Flat Slab | Level 6 Precast Flat Slab Installation rid 9-10 / H-M+
6c50f3df-c522-46d8-a6f6-450881b583cb |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Flat Slab | Level 6 Precast Flat Slab Installation grid 9-10 / B-H
fa263782-433b-46c2-95b6-ef7b875459c7 |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Flat Slab | Level 6 Precast Flat Slab Installation grid 9+ - 10+ / A+ - B+
a254968e-ba70-4406-a528-e8ea6bdc7f4c |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Flat Slab | Level 6 Precast Flat Slab Installation grid 10-16 / G-H
45d908a6-fe1b-4cbd-a0c5-8e3b894c8d5d |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Flat Slab | Level 6 Precast Flat Slab Installation grid 17 - 18+ / F+ - H
a752c3fc-c849-4db2-96ac-adf8fa9929b4 |  | checklist-flat | pass | ST - R - Precast Flat Slab Installation | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Level 6 | Precast Flooring | Flat Slab | Level 6 Precast Flat Slab Installation grid 3 - 6+ / O-Q
f7cf286f-a8b6-4f6c-83bc-f65a0f594f14 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Lower roof
5d94fd1a-f35b-4c7d-b3bd-dc4452c19102 |  | checklist-flat | pass | df540126020873bcab758e194673a0d88e77736ef476fc912494f2092d7c21fd | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Lower roof | Roof Checklist
1bb56f62-ab4d-4277-98f3-1e27f1ae3359 |  | checklist-flat | pass | 14969124506bc6f2cba3292faf9165f43e9972a295d485067488f2b9d5acd782 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Lower roof | Intumescent Painting
b2312ffc-0f87-42f3-b58c-380e9a9a042f |  | checklist-flat | pass | FC - R - Roofing | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Lower roof | Lower Roofing
cc297c54-5911-4670-b96a-93eb102573bf |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Upper roof
b6c6f829-20d9-4fa7-ba31-b8f46116d54e |  | checklist-flat | pass | df540126020873bcab758e194673a0d88e77736ef476fc912494f2092d7c21fd | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Upper roof | Roof Checklist
6d914dca-9c80-44b5-b3fd-3f800e20cdcc |  | checklist-flat | pass | 14969124506bc6f2cba3292faf9165f43e9972a295d485067488f2b9d5acd782 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Upper roof | Intumescent Painting
0acde4ea-83bc-42fc-ba16-402cd1fe86d5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Structure & Roof | Main entry canopy
dd0402bc-a349-4fb0-8559-896b4720f230 |  | checklist-flat | not-started | df540126020873bcab758e194673a0d88e77736ef476fc912494f2092d7c21fd | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Main entry canopy | Roof Checklist
16b401de-62ba-47ac-9cc2-517eccdaefa6 |  | checklist-flat | not-started | 14969124506bc6f2cba3292faf9165f43e9972a295d485067488f2b9d5acd782 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | Main entry canopy | Intumescent Painting
bd1b0ecb-631f-45b7-bc2b-531b72409aa8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Structure & Roof | L1 entry canopy
27e74cda-8375-499a-8e22-fbc525dc3751 |  | checklist-flat | not-started | df540126020873bcab758e194673a0d88e77736ef476fc912494f2092d7c21fd | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | L1 entry canopy | Roof Checklist
2da259fc-67c7-4314-addb-3d7eb68035bf |  | checklist-flat | not-started | 14969124506bc6f2cba3292faf9165f43e9972a295d485067488f2b9d5acd782 | checklist-flat | FALSE | FALSE | Building B08 | Structure & Roof | L1 entry canopy | Intumescent Painting
25a5cbd5-1b22-4b75-b6d1-f70451578ebb |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade
a93061ef-5688-4ad0-8248-358ad89ea8dc |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 1
f5d5d7c6-0e50-4bb2-a957-9d79b3749d30 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 1 | East Elevation
5a01c06d-de03-48db-9648-7f45b13813c2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Common Areas
b7cb694c-7b3d-46a2-9c41-b98cab3842f3 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Common Areas | Lift Lobby
444c6b9a-fc7d-4843-9fa8-c33d31404c36 |  | checklist-flat | work-in-progress | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Common Areas | Lift Lobby | Exterior Timber Framing
2922a2dc-2ac3-4817-a51c-4f044a5e1a4e |  | checklist-flat | work-in-progress | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Common Areas | Lift Lobby | RAB Board
9b326d45-a0bc-4c53-8c2e-99160445ca9b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Apartments
9b873b34-637b-462b-9f57-a95d607fc22c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Apartments | A69
4df2ef97-5e97-4bf6-854f-6cab7958b16f |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Apartments | A69 | Level 1 External Plaster - Nibs & Beams
ddce31f4-6172-4b52-bc2d-b132ca3139ae |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Apartments | A69 | Level 1 Exterior Timber Framing
7648c7b3-3453-4254-a92e-6aea03e77823 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Apartments | A69 | Level 1 RAB Board
4b443a77-c1b1-4a7f-9c77-e11f5fedf5ca |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Apartments | A69 | Level 1 Windows and Sliders
5c455249-ea22-44fd-8ce3-c69127f5dc77 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Apartments | A69 | Level 1 Eyebrow - Canopy
136f349a-8c6b-4c21-865a-5eba0f0961ba |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Apartments | A69 | Level 1 Flashing installation
1ae4994d-f5d7-4d7f-9703-993d6bd24428 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Apartments | A69 | Level 1 Brick Works
72d33570-d1c5-44fe-93ae-9b7f2f05c213 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Apartments | A69 | Level 1 Soffits
f89e72e0-ac71-499d-aad1-6f6c6becfae3 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Apartments | A69 | Level 1 Exterior Tiling
c5f44c05-78d5-4fe5-9fba-18e36bde6505 |  | checklist-flat | pass | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Apartments | A69 | Level 1 STO Poren Plaster
6ec3d20a-fb98-4e1c-90d9-c01f2b6c163f |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Apartments | A69 | Level 1 Air conditioning
dc38aa83-2905-4fc4-906e-69fed7cc998c |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Apartments | A69 | FC - R - Balconies
97e7c760-6417-4298-bea7-828a9ee4cc63 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Water Test
18ad1106-9169-441c-90ac-21882006614d |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Water Test | Water Test
30445222-9e84-4403-a7cd-1d31150ce6d1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Passive Fire
bc679e3e-cd78-4b41-adbf-d16493a398e4 |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | East Elevation | Passive Fire | Level 1 Passive fire
545670b8-a628-455f-a6cf-16cf8027e9f2 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 1 | Global Fire
a917f12d-6a1e-4aff-a17c-f96bbd2c4377 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 1 | Brick Installation
2b5d936a-be12-42d0-b409-ee922ff8d54c |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 1 | Brick Installation | Area C
2b57d9d6-c55a-418e-b354-35a7ad2f0ce1 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | Brick Installation | Area C | South Elevation Brick Works
4c3cdd5d-8d7b-4e51-bab6-1f10327cfb95 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 1 | Brick Installation | Area C | East Elevation Brick Works
61002312-6206-4811-bcf7-1bdcb1570884 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 2
eb728814-ffa7-49bd-b4f0-4e0c512744cb |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | East Elevation
b2e90d6e-ac11-4e08-93ea-93daad626e46 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Common Areas
e8f9ff63-9b55-453c-bcb2-4ad2194c909f |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Common Areas | Lift Lobby
3cdbe698-89ac-4f2d-99b4-486410c9e3ee |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Apartments
95bda65a-875e-4565-a19c-445ef62343e6 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Apartments | B69
4eadfd4e-b056-44b2-9456-92e70ce4e922 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Apartments | B69 | External Plaster - Nibs & Beams
69966685-28ef-483e-a824-7605c03b9aa4 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Apartments | B69 | Level 2 Exterior Timber Framing
acc8e541-3ffa-4373-97f7-6a46b54b1c2c |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Apartments | B69 | Level 2 RAB Board
d2e80fdb-fe67-41ec-9482-f6ff5150523f |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Apartments | B69 | Level 2 Eyebrow - Canopy
a5732ce1-6e8a-4d5e-a31d-6de8c8ae26a5 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Apartments | B69 | Level 2 Soffits
c1191c7b-34ca-43a3-b0fc-1857f97816ad |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Apartments | B69 | Level 2 Windows and Sliders
9b726a6e-81f1-41ef-aa13-4badd2f8b09e |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Apartments | B69 | Level 2 Brick Works
83ca0fb2-8dc6-477a-a4ec-728413b33ea8 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Apartments | B69 | Level 2 Flashing installation
b3a8b8b2-92b6-4381-846b-401e3adf792c |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Apartments | B69 | Level 2 Exterior Tiling
ea829e7e-36a5-4dfc-bfe9-30c70096bc04 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Apartments | B69 | Level 2 Air conditioning
f9f6efc7-84a2-48f0-8c0b-3ff943182e0d |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Apartments | B69 | Level 2 Soffits
b7054bcd-3151-487a-94a3-77f47e8ecaab |  | checklist-flat | pass | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Apartments | B69 | Level 2 STO Poren Plaster
c0e2a3f2-9ae8-4f1f-be90-c93c536a70be |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Water Test
27cf41a0-ab4e-4a2c-9861-8d6f77f3e92c |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Water Test | FC - R - Water Test
18a84636-193c-4c35-8602-57827dd741be |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Passive Fire
3f2df513-61df-441b-ac3c-33c39815abf5 |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | East Elevation | Passive Fire | Level 2 Passive fire
cd4d0e4e-c551-493e-9be5-2ce2fc7ed1e2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | South Elevation
3eef140e-c2b1-4678-bb48-5d6375ab97c3 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Common Areas
4a3e5960-402a-4807-97db-bacc8110a336 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Common Areas | Lift Lobby
0981752f-3cf4-47b6-b6d3-4cca0e9135e1 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Apartments
2df8494e-397c-45b7-9437-7da5fb2343c6 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Apartments | B70
ce5d851f-aa06-4fed-93d1-c1b2ae2d0345 |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Apartments | B70 | External Plaster - Nibs & Beams
e7ed31d9-c63b-40ad-8419-903ea1724ee3 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Apartments | B70 | Level 2 Exterior Timber Framing
02a8afca-26c9-4641-a9d5-6df3ec86998f |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Apartments | B70 | Level 2 RAB Board
9c2c2256-a6b8-49e3-b585-3657fbf3b99f |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Apartments | B70 | Level 2 Eyebrow - Canopy
8b4c9d11-adb4-4da6-ba86-ab4dfb317cd4 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Apartments | B70 | Level 2 Flashing installation
912f2cb2-99a4-46de-aab1-0d5a056eb513 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Apartments | B70 | Level 2 Windows and Sliders
3b670712-ed46-4cfc-9984-7107b578171b |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Apartments | B70 | Level 2 Soffits
ce0f09d2-4041-4e74-82e6-135be789c3f6 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Apartments | B70 | Level 2 Brick Works
b6901b70-a194-47c8-ab46-c2d262708b1b |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Apartments | B70 | Level 2 Exterior Tiling
dc684db4-f7bf-46c5-9f9e-2e7fb64e7cfe |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Apartments | B70 | Level 2 STO Poren Plaster
523e8c43-1bb5-40b0-9625-44cf24020d0a |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Apartments | B70 | Level 2 Air conditioning
5f883db2-741c-47a9-9b33-cfa1c580eac0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Water Test
90eafbbd-c811-47ce-af1c-b81e583b15b8 |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Water Test | FC - R - Water Test
ef5137fd-c359-4035-8136-e7cba527f24f |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Passive Fire
4a4444c6-bd54-4012-b330-df28e7388d90 |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | South Elevation | Passive Fire | Level 2 Passive fire
1a2e07c0-58bd-4783-8e78-6c371294d283 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | Brick Installation
59787e5f-a589-4540-b86a-90e5b52ce3d3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | Brick Installation | Area A
62346cc9-316a-4405-92a9-632ad7a189f4 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | Brick Installation | Area A | South Elevation Brick Works
b561462e-b2a6-4143-8e6c-b45e84430d79 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | Brick Installation | Area A | Part Elevation - West Elevation Brick Works
7218ec51-89cd-46f7-98b9-b1a370ac9a70 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | Brick Installation | Area B
ae428a53-da13-4804-9983-eecc70366b55 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | Brick Installation | Area B | South Elevation Brick Works
31f358ff-80f4-4de2-94fb-f9d69bd2c6e3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 2 | Brick Installation | Area C
b0607d7b-82f7-4214-9768-1d612649c91d |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | Brick Installation | Area C | East Elevation Brick Works
93373ded-99c4-4e0e-a520-0e4e29fe454e |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | Brick Installation | Area C | South Elevation Brick Works
5ff0624f-60bc-42de-8410-871ee0723884 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 2 | Brick Installation | Area C | Part Elevation East Brick Works
b88dcf1e-208c-4065-974d-eb4148e22623 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3
89a42c8f-9cda-430c-b936-51331e09889a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | East Elevation
c70d11de-c15e-4f19-96c9-dc7a526b8539 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Common Areas
f66d6d54-7cc6-45d6-a09c-a61eb7594c6b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Common Areas | Lift Lobby
c693f806-25bd-4a91-904b-71e689366ee3 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments
163084aa-2cb7-46e0-99f4-0f41d8085bd9 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69
5189c3b6-a8db-408a-a30b-4bcc45a5c944 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69 | External Plaster - Nibs & Beams
dcc09c63-984d-4e33-86ec-64e1bd026dee |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69 | Level 3 Exterior Timber Framing
e31f2809-4578-4c50-abc8-73f413583b30 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69 | Level 3 RAB Board
4ec6bd04-8477-4bbf-8e22-eb5d4f58b5a6 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69 | Level 3 Windows and Sliders
a6c4372b-64b5-40fc-b280-a488a9538aea |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69 | Level 3 Flashing installation
ca600ed9-fa8d-4591-89eb-75d723875767 |  | checklist-flat | not-started | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69 | Level 3 Waterproofing
440938f7-4025-4ac7-884a-93f35606911f |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69 | Level 3 Exterior Tiling
3dc70173-47c0-499e-ba68-a4e32ca2c61f |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69 | Level 3 Balconies
b3c014d3-cf4e-432b-8b1c-fec68ec7aba5 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69 | Level 3 Balustrades Installation
193bdf3c-fcb4-4a79-8c00-ceafd2e1ac22 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69 | Level 3 STO Poren Plaster
945418e3-b617-46a8-9e8b-843c7400a7f3 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69 | Level 3 Air conditioning
fa140f28-b957-4512-a2fb-34ba47c7f97a |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69 | Level 3 Eyebrow - Canopy
a10b26af-eb6d-4299-a313-178557643ec5 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69 | Level 3 Brick Works
fd31a04e-9709-4f77-88de-49f20f3dbb02 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C69 | Level 3 Soffits
fb639c0e-aeeb-4e48-a10b-1f2b1da64b8f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71
07bcdd07-3cb8-4ef6-a685-17e54fbba9e9 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | Level 3 Exterior Timber Framing
7db3ef06-2374-467d-8dae-e669f7a93358 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | Level 3 RAB Board
56f20fa0-d149-4513-88cc-9064982fe07d |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | Level 3 Flashing installation
ea0ad473-1940-45ad-adc6-576587214c8c |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | Level 3 Sarnafil Waterproofing
648f091a-c67c-49ba-b09b-8803428dfa53 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | Level 3 Windows and Sliders
03f3a6d7-1241-4d5c-a495-a10af825eeff |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | Level 3 Exterior Tiling
90405da9-c1ae-4458-bb91-ac3193d1f848 |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | Level 3 Balconies
2f12ad6e-fa00-4cf1-8e55-d1601c270483 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | Level 3 Balustrades Installation
d47e091c-d26b-428f-bebc-8ac57f71a7e1 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | Level 3 STO Poren Plaster
ef01a6cf-8fbd-44d6-8a29-878f3aeffb29 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | Level 3 Air conditioning
814d476f-dffd-43cc-9f00-261db61915af |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | Level 3 Eyebrow - Canopy
eb3d0ccf-f989-4cae-898c-98d0618c301f |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | Level 3 Brick Works
99e23204-4635-4140-a3e5-5f8ed5982232 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | Level 3 Soffits
33cb7adc-4ff3-4d8b-9c6f-b4995ebb1ff0 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | FC - R - STO Poren Plaster
c3a63e31-e3fd-4297-8993-562bee70e320 |  | checklist-flat | pass | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Apartments | C71 | Level 3 Sarnafil Waterproofing
f95604f0-e448-42d6-80ce-f3d53d543ca5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Water Test
140efe8a-6cad-4dd2-ae9c-33a6c4b2c07a |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Water Test | FC - R - Water Test
47679c26-4723-46ef-8878-f0134f3974f0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Passive Fire
74fcbee1-9f66-439e-be96-36ccdb9d3693 |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | East Elevation | Passive Fire | Level 3 Passive fire
45f99868-fba1-4c60-9da3-e92000e9a73c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation
783f2480-7034-41e5-9cfb-00510345c615 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Common Areas
c5b4c9e1-c2f0-4969-b79b-9fb6f0ff51b7 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Common Areas | Lift Lobby
b801b79c-5bf3-4a99-8f05-2d854ee509b3 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Services Areas
56d4cc05-62dd-4ccd-ba89-2953335a42c5 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Services Areas | Electrical Room 01
d7dbe230-ada5-4ca3-aa7a-5ed4b7216f53 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Services Areas | Electrical Room 02
8a597910-6aa8-401b-9362-ce523c205e3c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments
62bd2a97-3f06-49f6-aceb-1bf9cc437e7a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70
dce2a515-c7cb-49e2-b0be-70d546f06c3e |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | External Plaster - Nibs & Beams
55b3f5a7-5870-4051-9503-513b1a407782 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | Level 3 Exterior Timber Framing
b0dfbfac-c27e-4705-9477-555320f3732d |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | Level 3 RAB Board
47470c9f-4acb-420b-bf5e-1b9176abc9e2 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | Level 3 Eyebrow - Canopy
45d71bff-91fa-4e45-a47e-0da2f9d7ade5 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | Level 3 Windows and Sliders
c5542375-eeae-44d4-9698-05b36faebae8 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | Level 3 Flashing installation
d7b93a14-64fd-426e-a46c-34680b0db9ba |  | checklist-flat | not-started | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | Level 3 Waterproofing
50b3fe17-2e28-4ae7-a086-74f9c4c26a40 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | Level 3 Balconies
76e50e91-16a4-4a1a-9b7f-14b623cca1a5 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | Level 3 Balustrades Installation
33c99100-ac8b-4154-82af-eb1f48081689 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | Level 3 STO Poren Plaster
68d9d5d2-0336-4f57-b688-7ee26c4d02a9 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | Level 3 Air conditioning
3a65c8d0-0d2f-47ec-a765-caf1a9e3a729 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | Level 3 Brick Works
1339509f-9e21-4530-a82a-24c39994141e |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | Level 3 Soffits
35caae58-9cdf-4d67-b695-0d99f1ae87b2 |  | checklist-flat | work-in-progress | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | Level 3 Eyebrow - Canopy
db3f73a4-5d1e-42d9-b312-bb041b70a54c |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C70 | Level 3 Brick Works
703d7adc-5186-4a82-ae5c-8f48beca33a2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72
992cca39-e24f-4022-820b-bd98a08b4b4b |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72 | Level 3 RAB Board
402ca619-2d93-4b10-8c5b-3df478804064 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72 | Level 3 Exterior Timber Framing
20ed3538-ea0e-4543-9bc6-ad8ac2e1650d |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72 | Level 3 Windows and Sliders
23810a63-a531-46c1-8717-c680d41747a4 |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72 | Level 3 Flashing installation
a9435d7d-973e-4229-ad62-fe1c8292d9ba |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72 | Level 3 Exterior Tiling
fd0a1813-1a51-499b-be4f-b6871cdbafd8 |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72 | Level 3 Balconies
ddb82a33-bdfe-4d9a-8eb2-5556e0598514 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72 | Level 3 Balustrades Installation
6d3cc624-97f0-4dde-9983-bc7de4f02b2e |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72 | Level 3 External Plaster - Nibs & Beams
b5e57d3d-c116-4e71-861b-87c458777c62 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72 | Level 3 STO Poren Plaster
48e44608-5cba-443e-8dcb-632a90cac5a8 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72 | Level 4 Air conditioning
ad528919-95e2-422e-9521-b552d650a36a |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72 | Level 3 Eyebrow - Canopy
8924c2e3-6ba2-444f-bcba-1c5b867e1bfe |  | checklist-flat | work-in-progress | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72 | Level 3 Brick Works
7c7bbb44-29b3-41ce-ab82-57cab765a2b8 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72 | Level 3 Soffits
d59af0f8-b0a1-49c7-8a12-b3d2c3bb15cc |  | checklist-flat | pass | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C72 | Level 3 Sarnafil Waterproofing
913fce08-64bd-44a2-8597-cf16da53ebad |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74
6420387e-8785-41c6-b167-828b009739de |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | External Plaster - Nibs & Beams
8b07fc60-be0b-4032-b383-fd66a237056a |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | Level 3 Exterior Timber Framing
09e79098-adb2-4f80-a365-942a11994591 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | Level 3 RAB Board
232649b2-33fe-4463-acfc-390a2bfedf7c |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | Level 3 Flashing installation
780e7680-6e02-451f-b2b9-e4256fca9b02 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | Level 3 Windows and Sliders
6ef768c1-b900-4870-aa05-495560a07698 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | Level 3 Brick Works
ae2fc7cb-e979-42ee-ab2d-0ed6f2c09859 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | Level 3 Exterior Tiling
47988957-8398-4636-a6e6-5c01e77c9983 |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | Level 3 Balconies
0067b3fd-50fc-4e79-b7f5-41c9d94a38d2 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | Level 3 Balustrades Installation
e0eb5271-0f5c-4bb2-9ac0-e10acb839aa8 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | Level 3 STO Poly Plaster
e8609f71-aaca-4e07-b15a-7909559969c1 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | Level 3 Air conditioning
4c7f55fe-2c7c-4e83-805f-885d102e93db |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | Level 3 Eyebrow - Canopy
a1de85ea-5325-46b7-a6ad-519949e63245 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | Level 3 Soffits
b95c8ba7-fce2-483d-85aa-06424281d252 |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | Level 3 Sarnafil Waterproofing
c38d1b90-b0f4-47fb-8178-f966ca4deddb |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C74 | Level 3 Brick Works
b3313cca-4b58-4724-9337-3328f6955ca3 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76
677d1c39-ddd9-4946-a557-93083f6f2b17 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76 | Level 3 Exterior Timber Framing
1a652d52-abc4-43b2-a8ad-0425090a80c5 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76 | Level 3 RAB Board
a325f71b-2b19-4606-bc03-5a9a36a3ed6e |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76 | Level 3 Flashing installation
aa30527a-804d-4cf9-af7c-19740c2a4499 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76 | Level 3 Windows and Sliders
730264a2-aeb4-47c1-9b56-bfc3e813cfb8 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76 | Level 3 Brick Works
43749135-04a5-4abe-90f8-480a383ddb8e |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76 | Level 3 Exterior Tiling
ac6befe5-2768-41df-bd03-bdf4ca08cc16 |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76 | Level 3 Balconies
519e2c13-e1fc-4822-bf77-451add227888 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76 | Level 3 Balustrades Installation
e9b666e2-a786-4f1e-8964-7e0448749c80 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76 | Level 3 External Plaster - Nibs & Beams
003717fd-4a8e-405e-87c3-e76b13d0a27d |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76 | Level 3 STO Poly Plaster
b7714d22-fe7d-4e3b-9d30-15b731eb875a |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76 | Level 3 Air conditioning
5059c969-dcc9-4490-9a94-4d87a4f5d7e8 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76 | Level 3 Eyebrow - Canopy
aa8c3767-ef5b-4281-89b8-054e11f44e78 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76 | Level 4 Soffits
dff87387-6910-434a-a93b-409a21b69353 |  | checklist-flat | pass | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C76 | Level 3 Sarnafil Waterproofing
3377e32a-0d1d-401f-9688-7ab62a8adb0e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80
66141651-42cc-45f3-930d-073737003802 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80 | Level 3 Exterior Timber Framing
414e7696-5037-4986-87ee-8d568a0730cc |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80 | Level 3 RAB Board
5dfea6e3-1e02-497f-b8fc-af7ecd5221ef |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80 | Level 3 Exterior Tiling
3c8beb57-16b3-46bb-ab33-44858015307c |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80 | Level 3 Balconies
e84d753a-7322-4fa6-8572-01eef3ff4631 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80 | Level 3 Balustrades Installation
4701f8db-9c87-4451-b629-12734c38c516 |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80 | Level 3 External Plaster - Nibs & Beams
3e50f66c-a5d5-46b7-b66a-6e31a27dc570 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80 | Level 3 STO Poren Plaster
90fb60b4-c860-43aa-87c2-79be1450b544 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80 | Level 3 Air conditioning
53883496-1088-4c25-a577-909b867504cd |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80 | Level 3 Eyebrow - Canopy
201f7565-52cd-44e9-8343-685a3a96c92d |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80 | Level 3 Windows and Sliders
7aaba216-a30a-4067-ad16-79a82321ddba |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80 | Level 3 Flashing installation
9f7e8538-e21c-42c6-885a-5fee8e0acdad |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80 | Level 3 Brick Works
671bc38d-7531-4d80-8af6-6da69d20af54 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80 | Level 3 Soffits
79331fa1-080f-46cc-ac6f-2785f829b7d7 |  | checklist-flat | pass | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C80 | Level 3 Sarnafil Waterproofing
5d526f89-a391-4f2a-bbe6-c0ec95066d84 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87
751d439b-4c3b-49ee-a609-ef04d5966b90 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 Exterior Timber Framing
8485e3c1-f4f4-4be8-95ef-e64b2f868db6 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 RAB Board
b9a6c2ca-7ad6-480e-a10e-cb1776e4e2d0 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 Exterior Tiling
12b48345-1f74-49b1-a111-1e03438a3d99 |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 Balconies
8755f604-b37e-4ca1-a263-6652914cf8a0 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 Balustrades Installation
14e2c69a-1c85-4812-a3cc-7017f4614219 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 External Plaster - Nibs & Beams
3d349b77-aa5b-4f78-924b-c3e37cacb5ce |  | checklist-flat | pass | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 STO Poren Plaster
ef45ec95-bb01-4c8c-b434-d98810232fa7 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 Air conditioning
74cd9900-6412-42d1-b28e-ec936c825c34 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 Eyebrow - Canopy
01b245ce-1f2a-46bb-952b-ae91d5bc6537 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 Windows and Sliders
d524e5ac-c708-4e7e-8353-8f7d45bcbfd6 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 Flashing installation
703086e4-c9cc-4fe1-9660-9ee88f1af746 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 Brick Works
9b3ffdb6-b3a2-4c83-ba79-a10f633a93ee |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 Soffits
8194e464-5dbb-48e3-9206-d6393bdb3c47 |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 Sarnafil Waterproofing
d0df2d5d-6551-4c64-ac01-84fb25f133f4 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C87 | Level 3 Balustrades Installation
f519c09a-675f-4a0c-b817-3a948377d2ad |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86
b35b009d-0db1-4677-baac-fede64f4ddce |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86 | Level 3 Exterior Timber Framing
5da9b1c5-f82d-408d-a54a-05b65f2d2216 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86 | Level 3 RAB Board
93b5b100-a13f-4678-bf41-565af282f377 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86 | Level 3 Balconies
6e52f8f6-9d59-465b-8d0b-4d0c11f60cc7 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86 | Level 3 Exterior Tiling
f6de0262-c196-4bf1-8e59-d13f311182e9 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86 | Level 3 Balustrades Installation
7c8d90fb-a793-4223-bc53-33725516c86a |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86 | Level 3 External Plaster - Nibs & Beams
d9108d44-2068-4ca6-aff3-9477a60a14ce |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86 | Level 3 STO Poly Plaster
038c2488-ef6c-413a-9e21-83da7b285c4f |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86 | Level 3 Air conditioning
e8b35e75-a2a3-43e0-b62c-708a3b139c8a |  | checklist-flat | work-in-progress | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86 | Level 3 Eyebrow - Canopy
d25f03b5-3c77-4d4f-a5cf-ffd3883bd0a9 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86 | Level 3 Windows and Sliders
10fdf056-2ff5-4a26-94e2-d9eefb739ca4 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86 | Level 3 Flashing installation
9dacd2b2-c81f-4e48-886f-1b13ee80297b |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86 | Level 3 Brick Works
7b7a9c25-0517-4a3e-8864-51609550120d |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86 | Level 3 Soffits
bdf46543-7840-436e-998a-104400107279 |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Apartments | C86 | Level 3 Sarnafil Waterproofing
a342590b-a480-4cc3-af7d-25f2c5308e98 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Water Test
d1e1f56d-67b0-4325-9568-df9983d1fb60 |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Water Test | FC - R - Water Test
6e139278-7a14-476b-89e0-03ec14592ef2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Passive Fire
3c51c56d-3126-4613-b82b-49c3f6c84b0c |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | South Elevation | Passive Fire | Level 3 Passive fire
a5fbd8cd-81e6-4997-96d0-689a6058405e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | West Elevation
18ce2e8d-d6c0-4f78-be41-2690a3536a9e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments
7a5e8576-1ec6-428a-9529-2d940fe8acb2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83
8574aa57-abe1-459c-8405-c969cba9786e |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83 | Level 3 Exterior Timber Framing
302af766-646c-4e4a-b500-978f4682f263 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83 | Level 3 RAB Board
57b48456-5fcf-4f0f-b8dc-c4054d89a6f4 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83 | Level 3 Exterior Tiling
2ed83bfa-0475-4f0e-b151-dd98f2d87fb1 |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83 | Level 3 Balconies
b99091a8-4ca7-4618-9bc3-1b038fddac5e |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83 | Level 3 Balustrades Installation
0c5a92a5-133e-446a-add0-636f3c7aadb7 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83 | Level 3 External Plaster - Nibs & Beams
e6831ff0-f4da-4be4-b0d0-79238da826e6 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83 | Level 3 STO Poren Plaster
9b69119b-08e2-46bb-a2eb-24cdd2d63560 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83 | Level 3 Air conditioning
ff76fcbd-8435-4462-80c9-a438a3bc0ce9 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83 | Level 3 Eyebrow - Canopy
54ca3e8a-353b-419e-9ecf-393c30321ba8 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83 | Level 3 Windows and Sliders
b60d3a8b-7905-4e60-894a-427e31386d36 |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83 | Level 3 Flashing installation
147b6794-ebc2-4005-b036-620381653af9 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83 | Level 3 Brick Works
fb842e21-0be6-48b6-8b78-bbd98469a712 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83 | Level 3 Soffits
48e4b308-263f-4970-93fc-176e08514fc5 |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C83 | Level 3 Sarnafil Waterproofing
3046e1b1-de3c-4738-ac92-e4f63ffc653e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84
b9ffc731-0bfa-4c0e-9b38-0870205b8d98 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84 | Level 3 Exterior Timber Framing
6f736a1d-42e0-4565-a53d-4aba54411a54 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84 | Level 3 RAB Board
e0a7c5ab-4785-47ef-964d-91ea66605f34 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84 | Level 3 Exterior Tiling
835c44a7-4fe3-41cb-aa14-74ee3619e575 |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84 | Level 3 Balconies
4130c568-3990-4f5b-bebb-5d5bee502d01 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84 | Level 3 Balustrades Installation
41643d12-5a54-457b-95f0-b82da39a9a1d |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84 | Level 3 Air conditioning
362be75c-415f-4933-932d-bd34f2bfcb11 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84 | Level 3 External Plaster - Nibs & Beams
0c5d2478-362d-49d4-a124-caa652249d1a |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84 | Level 3 STO Poren Plaster
7d02b91d-5433-48ef-85a3-893870938a59 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84 | Level 3 Windows and Sliders
b2cc9aef-42d5-4d22-9ae0-87bb3072d61a |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84 | Level 3 Eyebrow - Canopy
5af4652f-6ad5-4da0-86d0-3194e8a2fb8e |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84 | Level 3 Flashing installation
27cade88-a297-4e00-a3d0-931609ba5981 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84 | Level 3 Brick Works
55174f9d-15e7-455a-b9ec-ec48b09e57fd |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84 | Level 3 Soffits
8fc7d8d9-435d-4b5d-9caf-6732d4dbba4d |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C84 | Level 3 Sarnafil Waterproofing
5db00191-45e1-48d2-a3c1-4bfe2776d03b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85
8abfb281-803e-4f8a-9e5c-f3221afa6c5c |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85 | Level 3 Exterior Timber Framing
b6da3bd9-72e7-4cdb-a8a8-c20031601fc8 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85 | Level 3 RAB Board
8b992af6-5c55-45fc-8fd6-8d846aa63c8e |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85 | Level 3 Exterior Tiling
b31b2fb9-c90d-4cd7-b566-d200be014017 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85 | Level 3 Balconies
daa358cb-b18a-47d6-8cf9-52a5408dfcd5 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85 | Level 3 Balustrades Installation
cb1b8de4-b663-44c4-9c27-31f8e797ff38 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85 | Level 3 Air conditioning
7997a786-1065-4a73-a766-1754d54a8074 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85 | Level 3 External Plaster - Nibs & Beams
1df5f1fb-4b37-4231-a4fc-cab1e6e6ea1a |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85 | Level 3 STO Poly Plaster
5f4c596d-5855-44b1-b655-38f514dfd792 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85 | Level 3 Eyebrow - Canopy
3ae0e0de-7a60-4241-a6b5-4ce18e91f3bc |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85 | Level 3 Windows and Sliders
4b785e99-8a89-40bc-a0bd-c260c5cf7478 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85 | Level 3 Flashing installation
c10dc0b4-b591-476c-b245-f767b116e270 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85 | Level 3 Brick Works
44ef5029-a25f-4d8d-9192-8885d7659bd6 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85 | Level 3 Soffits
139dffe1-efc5-4911-85e0-aaa5a353e420 |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Apartments | C85 | Level 3 Sarnafil Waterproofing
ab8448a7-be65-4f0d-a66a-14f7963a0e2d |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Water Test
5cdb3582-660b-4bd1-b6b8-8d0b6aefea7c |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Water Test | FC - R - Water Test
8852c92a-f967-4ee9-b770-f9e43831178e |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Passive Fire
048d6b10-d333-4314-a5e2-0e51b8f00224 |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | West Elevation | Passive Fire | Level 3 Passive fire
85cf2703-3297-49af-af60-736f27acdf1c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | North Elevation
d03ab83c-1522-4c45-be89-2b0dce54a3e1 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Services Areas
30fbe03b-4177-487f-bf19-df39b1b620c6 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Services Areas | Comms
11055b8e-1c0c-486e-8523-4a8f970db3aa |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Services Areas | Services Room
5789cf71-143b-4df7-913a-9f55bcb09711 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments
2a2bd3cf-d6cb-4df9-9776-8b7e743680ec |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73
cee1763f-1690-4a19-9eb7-a342dbf5708b |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3 Exterior Timber Framing
11194c56-269e-444c-8de4-77dd2d4d7e95 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3 RAB Board
01b621c3-4e05-4d75-8814-c359658cf3de |  | checklist-flat | work-in-progress | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3 Windows and Sliders
42462a6c-4a4e-4285-80e6-604ddaa79035 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3 Eyebrow - Canopy
9d699996-89cf-4c1d-8890-cd940fa9c089 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3 Flashing installation
20e2b786-52e1-469a-8f8c-3aa8e5da467f |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3 Brick Works
1ba345ed-66a4-4984-a827-676d4857c024 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3 Exterior Tiling
21b8cb4c-103e-4864-93ba-e5ce83474223 |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3 Balconies
24b91a7c-303b-4a5c-b3bf-23bd970e430d |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3 Balustrades Installation
b4e6c317-5834-462a-8993-2ec4e210c905 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3Air conditioning
607c921b-880a-4938-8e8a-21a4480af996 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3 External Plaster - Nibs & Beams
d53244f1-411b-4e0e-945b-9b9ff179224b |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3 STO Poly Plaster
dc753796-caec-462f-a259-a4c07ae988f1 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3 Air conditioning
9e5ad374-12e0-420c-8849-0c6de6f0954b |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3 Soffits
46f2cd22-06d0-4a2a-98aa-5dc491e13255 |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C73 | Level 3 Sarnafil Waterproofing
a1b5764f-9e3c-4138-b131-08b5113aa86b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75
fa882f4b-b551-48ba-99cf-cd65d1ae95cd |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75 | Level 3 Exterior Timber Framing
ae800af8-d7c9-4a33-9eaf-d49b7c2d3d6c |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75 | Level 3 RAB Board
a443845a-9f9d-4ac6-9b4f-17ff565ec188 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75 | Level 3 Windows and Sliders
611236cd-48a9-4e7b-825b-1dcb14268e0b |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75 | Level 3 Flashing installation
62e0a405-a5f7-49a3-a72b-e8d355efcfcd |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75 | Level 3 Exterior Tiling
dfcc3f92-dfc8-4826-80b4-7d7908b0dc3f |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75 | Level 3 Balconies
1e2eec2b-b122-4e1e-9c7f-807b51324917 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75 | Level 3 Balustrades Installation
e3b975a2-1399-4ccb-b257-3f59d2b30e96 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75 | Level 3 External Plaster - Nibs & Beams
9919e0ee-071a-402f-9b92-705057599248 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75 | Level 3 STO Poly Plaster
5ecd5a98-a819-4878-9918-fc57fb123e18 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75 | Level 3 Air conditioning
fef591fc-5be4-4f5c-85ce-651beba47280 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75 | Level 3 Eyebrow - Canopy
b10ef95d-1dbd-4445-b875-77e08b830bbf |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75 | Level 3 Brick Works
3d1aa8b5-dcb1-4dfa-9429-c2d078cd0119 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75 | Level 3 Soffits
f61ee7dd-48ba-4925-97a2-613a6cb86d12 |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C75 | Level 3 Sarnafil Waterproofing
144e0b48-7654-4e88-9bf7-8d661a2cc5cb |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77
c0d0dfec-c413-44d9-bb15-9cc70c001b20 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77 | Level 3 Exterior Timber Framing
18fb23c2-4c07-49a3-b8bd-10fdcdcd917c |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77 | Level 3 RAB Board
b2534863-ce7a-4419-9fcc-abcc84a652a8 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77 | Level 3 Exterior Tiling
d1675458-2648-4332-8813-56c3d63d8ba0 |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77 | Level 3 Balconies
602495d8-2d16-4af8-9330-9461b70d35d0 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77 | Level 3 Balustrades Installation
e963a0b0-ab88-4271-b9a8-f9699d21b56a |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77 | Level 3 External Plaster - Nibs & Beams
1c694c61-1bf0-437e-9999-d2e035091aa5 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77 | Level 3 STO Poren Plaster
5a7e6553-a590-4bd4-9979-74f6d091322f |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77 | Level 3 Air conditioning
80768ec3-d467-401a-bf17-e7e569121121 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77 | Level 3 Eyebrow - Canopy
f44a55d1-b9aa-4188-8022-69103b7d83b1 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77 | Level 3 Windows and Sliders
ad692bec-2a1e-4780-8173-c3e877f6b8e9 |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77 | Level 3 Flashing installation
096b978b-a2b4-42cc-a086-ea10bdaebe62 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77 | Level 3 Brick Works
d6820a9b-2d2e-42b3-b8c2-f95e4b634184 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77 | Level 3 Soffits
4e5937b2-87fa-47ac-9acd-76ffcec7121a |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C77 | Level 3 Sarnafil Waterproofing
d23b3120-0981-42ee-8d0c-c45928d025c2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78
3c79343f-2ccd-4d55-9eef-910796a02f8e |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78 | Level 3 Exterior Timber Framing
8fe26f46-aa42-4455-bc18-6128344459ac |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78 | Level 3 RAB Board
ce57276c-7e1b-4bbf-b385-e600c7a563f1 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78 | Level 3 Exterior Tiling
c6416744-4600-4b6c-9343-982be026ecfd |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78 | Level 3 Balconies
26c35463-7ccd-439d-8f73-9d304daed0b1 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78 | Level 3 Balustrades Installation
ec227d5f-db81-42c6-a0b9-f17ba5543c5a |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78 | Level 3 External Plaster - Nibs & Beams
d39049f2-decc-447a-b409-ab0cda6c52f4 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78 | Level 3 STO Poly Plaster
633ec8b4-80d6-4c67-a933-873e20a1e615 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78 | Level 3 Air conditioning
5783e4ca-e1dd-4d07-8f93-db9251e07bd2 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78 | Level 3 Windows and Sliders
bcd3f8dd-71e6-42e0-86bd-ece8ec6f077d |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78 | Level 3 Eyebrow - Canopy
5650d7f2-d29d-4109-ac9d-046ad8c3e16c |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78 | Level 3 Flashing installation
561a7e2a-ca78-413f-9bd3-894a7eced652 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78 | Level 3 Brick Works
1be8994d-2aec-468b-ab7f-c7670dd401b1 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78 | Level 3 Soffits
656e0e97-1cae-4060-a490-d4431b70e537 |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C78 | Level 3 Sarnafil Waterproofing
f59c7974-f116-4804-b3c7-1222489b9bbd |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79
063a3801-3be8-4db6-8a19-f0fc55b2c687 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79 | Level 3 Exterior Timber Framing
fbadbaae-0fc2-4db3-81ef-0861228a03a2 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79 | Level 3 RAB Board
f00249b6-410f-4d6b-a9f7-5f6ef691363f |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79 | Level 3 Exterior Tiling
aa28e767-ed43-4b3d-9f8b-c7423eea15ce |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79 | Level 3 Balconies
b811baa1-2795-483e-923f-86b44cb5a660 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79 | Level 3 Balustrades Installation
637108b6-f884-46ab-951a-7f32f7a1a56d |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79 | Level 3 External Plaster - Nibs & Beams
da26db9a-bdf7-4083-b5af-59a7840232b9 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79 | Level 3 STO Poren Plaster
71fe9ce2-8779-45aa-8285-5b2ec416d57a |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79 | Level 3 Air conditioning
39bac7df-6df2-4c09-95a6-93456fa100cd |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79 | Level 3 Eyebrow - Canopy
cff92b49-fc28-449b-b093-94caa598a4d4 |  | checklist-flat | work-in-progress | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79 | Level 3 Windows and Sliders
f8fdc7c1-3a38-4fac-8714-f37fc4b62d5d |  | checklist-flat | not-started | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79 | Level 3 Flashing installation
a25c8257-c6aa-4e52-acf0-e95753d8a467 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79 | Level 3 Brick Works
53d6a1db-1aa7-40c0-8e96-758f40213918 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79 | Level 3 Soffits
ce422e14-2686-481a-ae0f-ffdb01ccf1dc |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C79 | Level 3 Sarnafil Waterproofing
bd93558c-774b-48ad-b9c3-f1e2b2b0f578 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81
2f5336b8-cbe6-42e5-be0f-de31ba31a282 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81 | Level 3 Exterior Tiling
d3eb1484-6fa6-4b04-9d7c-773273777106 |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81 | Level 3 Balconies
1680e591-7968-40ee-a609-1ced0c029aaa |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81 | Level 3 Balustrades Installation
9de18d68-214a-44c6-8f99-6d81b1cb1c1f |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81 | Level 3 Air conditioning
292267d3-b9db-47f3-8c1c-bbfb3a77df1f |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81 | Level 3 External Plaster - Nibs & Beams
19e86e4c-831f-4391-a81b-8b9011793a7b |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81 | Level 3 STO Poly Plaster
488b9a7e-8928-42c0-b528-00a3f2720309 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81 | Level 3 Windows and Sliders
6da84683-fd5c-4042-bf8b-6257a61cba87 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81 | Level 3 Eyebrow - Canopy
ac2405d4-3fa0-4261-959a-f94c79cbefee |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81 | Level 3 Flashing installation
1dba7c26-e394-4b9d-896d-59c8c5a79a40 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81 | Level 3 Brick Works
6e112ca8-29cc-4472-bfaf-b1424ac1f4f4 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81 | Level 3 Soffits
b4b565f6-239c-45ec-87d7-0206264ff7d2 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81 | Level 3 RAB Board
975d5164-d180-4066-a034-051046241811 |  | checklist-flat | not-started | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81 | Level 3 Exterior Timber Framing
f5bab889-2d72-4910-b0a8-7fe8be512758 |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C81 | Level 3 Sarnafil Waterproofing
85141f08-26de-440a-8f41-6a16fbbf3890 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82
18f30598-8667-4495-bb26-76ad19903125 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82 | Level 3 Exterior Timber
9bf57a80-2e20-4b21-86c5-b06b8b2bb32c |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82 | Level 3 Balconies
298a552e-0ada-41f4-85a4-33f68b9269d7 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82 | Level 3 Balustrades Installation
0703aaf0-88ec-4314-968a-2dc9b0d7a056 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82 | Level 3 Air conditioning
ea7b7c3a-145d-4e05-87f8-d8d658ce0073 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82 | Level 3 External Plaster - Nibs & Beams
2b5f54e4-922a-4754-b2c3-92373167f46e |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82 | Level 3 STO Poly Plaster
02ca5558-a360-4a18-b25e-a8fa0386f262 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82 | Level 3 Eyebrow - Canopy
545efa40-26b7-4275-80e3-ead387a61e00 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82 | Level 3 Windows and Sliders
af3129f3-a092-46a5-84eb-672d6799f02b |  | checklist-flat | not-started | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82 | Level 3 Flashing installation
210373c0-81fd-4a91-9312-78eb33efbd02 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82 | Level 3 Brick Works
b3967be9-82ec-448f-9969-5fec0785de36 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82 | Level 3 RAB Board
90ed6038-5f23-465b-a250-7396bd2c2989 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82 | Level 3 Soffits
8da8c0f9-ddf6-469c-b4c0-abf82ecf1199 |  | checklist-flat | not-started | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82 | Level 3 Exterior Timber Framing
e5e5c274-ad4e-4689-bfb1-728c0a8b4b5e |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Apartments | C82 | Level 3 Sarnafil Waterproofing
436ca8a6-a0d4-4f6e-955c-82d75294f388 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Water Test
9f126ebb-b4d6-47e8-91ed-ada79859cfd0 |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Water Test | FC - R - Water Test
51235aa2-5108-4a3b-836d-c4a4f7894b8f |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Passive Fire
f92166ca-c252-4e47-a2f8-c6452bb41d0c |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 3 | North Elevation | Passive Fire | Level 3 Passive fire
7df07349-6c44-4dff-8754-cf6312279724 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4
a78fe9c8-8eba-41bd-b9f8-daa8e4529634 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | East Elevation
fe1e565a-f90a-4ba9-ba1d-05f4b3d6f71f |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Common Areas
cf0a9ca0-468c-4bdb-a68f-69462dcbbec6 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Common Areas | Lift Lobby
df1d0ff7-40c5-4002-b64d-b7d692933635 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments
b9e09604-d17f-4a87-b29d-83c0b49d1e1a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D69
8ed9d551-3fd0-435f-aca5-38658fedc013 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D69 | External Plaster - Nibs & Beams
e6319f4d-01ee-4f89-bb47-f160fdcba256 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D69 | Level 4 RAB Board
4177c32a-81d5-4ca2-b9a9-344296aa699a |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D69 | Level 4 Exterior Timber Framing
03024f74-7525-44e1-9ed8-cedf5d57e37e |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D69 | Level 4 Flashing installation
3d644360-a845-40cd-8f8f-c1d923db5acb |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D69 | Level 4 Windows and Sliders
ea1395a7-f258-4750-8630-d671b9e8983c |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D69 | Level 4 Eyebrow - Canopy
0af956f4-d0d7-42b2-9e5b-301768e836a9 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D69 | Level 4 Exterior Tiling
0c2f30b5-1e90-42f3-a02e-ee7f476948df |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D69 | Level 4 Balconies
835b0ac6-f452-44d2-abe7-4a5480731154 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D69 | Level 4 Balustrades Installation
85ca7301-b581-4df1-a45e-b471025692e5 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D69 | Level 4 Air conditioning
41d432de-a921-4868-a194-87ce9e82bf2c |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D69 | Level 4 STO Poren Plaster
beab829f-b8ae-4728-96e2-886fb08d1906 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D69 | Level 4 Brick Works
3a1eab7c-3ff8-4838-9b93-4f6a2373576d |  | checklist-flat | pass | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D69 | Level 4 Soffits
636eac70-3e56-46c5-8234-8e04873a801a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D71
4de928c4-2bbd-48d4-b4ee-0fc477682e08 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D71 | External Plaster - Nibs & Beams
2884eae7-c8b7-47d3-a4f4-9a61c2339c03 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D71 | Level 4 RAB Board
6119686f-3eb4-4e6e-a670-9a43f7519c4d |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D71 | Level 4 Windows and Sliders
6d93ce8c-f2b9-4e7c-8e97-2cdd0552cff6 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D71 | Level 4 Exterior Timber Framing
8025510a-a6f3-484a-9824-d5fe374b3903 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D71 | Level 4 Flashing installation
a4286784-e9dc-4026-89e2-3fa388017c86 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D71 | Level 4 Exterior Tiling
7df80324-dc52-47f7-8a79-ff1f6a159423 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D71 | Level 4 Balconies
c1f6b8ee-cb0b-4af8-8ae8-988cc61afff0 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D71 | Level 4 Balustrades Installation
85770c8b-1c8f-4bc9-b508-4a9bfdda8434 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D71 | Level 4 Air conditioning
5775a25b-33ab-472d-b240-b3e75ac2314e |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D71 | Level 4 STO Poren Plaster
23e0e793-ad90-4c1c-9817-a94f22d57736 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D71 | Level 4 Eyebrow - Canopy
7e0a1a29-c97d-4574-ad8d-5b825babe0c1 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D71 | Level 4 Brick Works
fe12108d-3a4e-4bb0-9f0c-d2073eee1123 |  | checklist-flat | pass | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Apartments | D71 | Level 4 Soffits
90cfa24d-0417-4492-86c3-93ebf27e59c5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Water Test
0fda9bae-2510-43f9-ac6a-7d6f1e00d6a7 |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Water Test | FC - R - Water Test
7a7aa265-313c-483e-b9ef-d81dd5e9b1ac |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Passive Fire
8052ecce-301c-4b37-bbaf-1d87adab62a4 |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | East Elevation | Passive Fire | Level 4 Passive fire
5acb5027-c528-455d-9ef9-1ccb0a4b64f2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation
21f1385d-39b8-4e19-aec2-285c2ed4f95a |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Common Areas
d20c8df4-1ccb-4c1f-a1cd-d33bff8bac7b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Common Areas | Lift Lobby
4d27369a-3f7a-402c-8d9a-9e6dd6876ec0 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Services Areas
f6d58a17-2590-485a-a803-f07b65854729 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Services Areas | Electrical Room 01
0a7c2d43-f46f-47ac-a5ab-a6715fdc3423 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Services Areas | Electrical Room 02
f39df189-8be2-4ff3-844c-f3ee9bb6e33d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments
6748dc68-aaf3-4c05-bc33-d3b34e549a66 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D70
de7aaf44-a46d-4555-b8bb-6005c50f38d1 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D70 | External Plaster - Nibs & Beams
e8550b68-571f-4303-ab93-845736d398d4 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D70 | Level 4 RAB Board
707aa754-957a-4dc7-b02d-32009110554c |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D70 | Level 4 Exterior Timber Framing
dbee7a89-a945-4ae6-ab51-f275912be722 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D70 | Level 4 Windows and Sliders
b37ddb18-fa9f-46ce-9c86-4d7b1b5e0186 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D70 | Level 4 Exterior Tiling
51d0b9fa-e013-42ee-9bb2-2566707f7276 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D70 | Level 4 Balconies
895487cc-413c-45ed-94ba-6c973de45d4e |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D70 | Level 4 Balustrades Installation
09eb60ee-4744-45ac-8dc9-92ad8f5d2000 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D70 | Level 4 Air conditioning
4d6f7372-e1a3-4b7e-aaba-ef42f8dafe72 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D70 | Level 4 STO Poren Plaster
9782cbd1-475f-4aa4-acd1-f0c113d96747 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D70 | Level 4 Eyebrow - Canopy
7232f628-ac79-463b-9dd1-9e2c8864114f |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D70 | Level 4 Flashing installation
5a227ae5-34ab-42a5-b216-8a7ed052667b |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D70 | Level 4 Brick Works
ef967df3-61ba-43ce-bedc-dc9ce1aef6d8 |  | checklist-flat | pass | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D70 | Level 4 Soffits
1adb02ad-881f-4a8c-9dcf-0f1d97fe4851 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72
7b38f7ca-20ef-437b-ada3-6b463c9278b8 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72 | External Plaster - Nibs & Beams
1dc90d71-9f75-45da-9d86-7ceab2ac167a |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72 | Level 4 Exterior Timber Framing
10e2a85f-e85b-4ce0-8e23-d667a0bb7ee1 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72 | Level 4 RAB Board
64fee58f-e6bd-4da2-95ef-aa98eaaa252e |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72 | Level 4 Windows and Sliders
e2f88831-ea21-4107-abfe-d1070b5d60dc |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72 | Level 4 Exterior Tiling
ca7bbeb8-095d-454f-aff7-c1cb5cb300bf |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72 | Level 4 Balustrades Installation
916f55ae-2d64-46bb-8e72-e962397f9df1 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72 | Level 4 Balconies
26938e9c-0086-4894-9d95-029d0f986489 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72 | Level 4 Air conditioning
6700da9b-fbd2-4433-b314-78fccbde37b3 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72 | Level 4 STO Poren Plaster
56dac93b-5418-4183-a5a1-44f7627cd5f9 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72 | Level 4 Eyebrow - Canopy
e6f550ec-fc8f-4cb2-8898-307e8b99886f |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72 | Level 4 Flashing installation
cb8b54f9-60fd-40c8-85ef-f03dc1d09cd2 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72 | Level 4 Brick Works
923de32e-feed-49cf-8efd-48bbb00ae221 |  | checklist-flat | pass | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72 | Level 4 Soffits
acdbaffc-cd6e-4b4e-89b4-ae9895267be6 |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D72 | Level 4 External Plaster - Nibs & Beams
fb36720f-1c31-42bc-b803-0be1e76bfb7b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D74
00ff002a-2c50-4385-bb99-b355925fb785 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D74 | External Plaster - Nibs & Beams
ea234d14-7ae4-4dd8-9934-ccaac6403475 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D74 | Level 4 Exterior Timber Framing
e6221c19-8611-483f-9e7d-6f2673c25402 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D74 | Level 4 RAB Board
949f9305-b21e-4820-bea3-25dbf2e8dc7d |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D74 | Level 4 Windows and Sliders
913e77d5-d91f-4b6f-ae88-80248010cbc0 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D74 | Level 4 Flashing installation
6849fe05-9f18-4a7c-b785-540486840c4f |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D74 | Level 4 Exterior Tiling
cbfb0167-2e78-4b1c-b6a9-429e3140ed38 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D74 | Level 4 Balconies
98d33c74-e453-4f9b-9e21-11885d9edd39 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D74 | Level 4 Balustrades Installation
3f442c1b-d44b-4978-922e-146c1864c599 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D74 | Level 4 Air conditioning
dc826b65-eca1-467e-825d-a0bc9c35f505 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D74 | Level 4 STO Poly Plaster
46018fda-3dd6-4c20-9046-a5e7f0714c18 |  | checklist-flat | work-in-progress | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D74 | Level 4 Eyebrow - Canopy
b2c62d48-9420-4ec5-bc50-cbd8a1676328 |  | checklist-flat | work-in-progress | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D74 | Level 4 Brick Works
cffc6cee-048f-45a1-a344-258329f5838a |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D74 | Level 4 Soffits
033d9a3a-95e2-41cc-9d8f-5de21bb69143 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D76
85295c35-0a07-455a-b59e-9b45767e1720 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D76 | D76 Exterior Timber Framing
57b173de-6604-44db-80ef-84b08e1af9e0 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D76 | Level 4 RAB Board
7b1aee36-1daa-436d-a226-39b9a2dc89e5 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D76 | Level 4 Windows and Sliders
4de5ef47-0890-40b8-9cca-04ae85e6c061 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D76 | Level 4 Flashing installation
bef454c3-c752-45c2-8048-236fa04591ea |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D76 | Level 4 Exterior Tiling
bc91b9de-a23d-4c09-b569-2a2e824f7708 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D76 | Level 4 Balconies
5d76a159-0b32-45c0-aafd-469c8a7d3a03 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D76 | Level 4 Balustrades Installation
d83a6b16-ed24-430d-aa7b-b66b8cdf897f |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D76 | Level 4 Air conditioning
7de1644f-8012-4d02-9e5c-db5318ee2575 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D76 | Level 4 STO Poly Plaster
c9ccd08c-4ed5-4a8f-a331-b758dd167006 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D76 | Level 4 External Plaster - Nibs & Beams
21a1b9e5-7854-45c5-8c79-694e5f9dab5a |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D76 | Level 4 Eyebrow - Canopy
07cb0639-ef2d-4f6b-89b0-e06f3dba52f9 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D76 | Level 4 Brick Works
cc449aba-e018-4007-ad9a-e8b60c157617 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D76 | Level 4 Soffits
2c3e1bd0-d61f-42ec-8d14-6d8c684a9da6 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D80
51d3f373-db74-485f-b3d1-996398d59808 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D80 | Level 4 Exterior Tiling
7798f959-c76d-4615-a0c5-9d4cc694618d |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D80 | Level 4 Balconies
9a5bf1ee-201b-4edb-a60f-b4ea0be7dcb3 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D80 | Level 4 Balustrades Installation
50377a0f-ae18-42d1-8527-c70a221e7cec |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D80 | Level 4 Air conditioning
c281e751-7a01-44f4-914d-b2584a25eead |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D80 | Level 4 External Plaster - Nibs & Beams
08baff77-2fd6-49b5-a3c0-e00bb5ce21c5 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D80 | Level 4 STO Poren Plaster
bbef1c6a-6d07-4144-b204-2df929aec125 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D80 | Level 4 Eyebrow - Canopy
09ac6ec1-0c3e-4701-a1a5-18db45681071 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D80 | Level 4 Windows and Sliders
25d761a0-b2d1-437e-8c60-f0ce37ebf4df |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D80 | Level 4 Flashing installation
262a02c2-277a-4570-9d1d-09f481512004 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D80 | Level 4 Brick Works
d00daba3-6216-484a-a0d6-7ccf462d0773 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D80 | Level 4 Soffits
d7ca9940-d533-42d3-b796-0426fec27729 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D80 | Level 4 RAB Board
07458feb-76c8-4e56-aac5-0072e3f8c767 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D80 | Level 4 Exterior Timber Framing
b47865c3-b200-4c2d-ab1c-2e2f9e94c69e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D87
76ee4a92-f1cd-4904-b232-bd146afe96b6 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D87 | Level 4 Exterior Tiling
1656fb6e-9a2e-4e71-a6c0-e3452a76767d |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D87 | Level 4 Balconies
2c6dae11-0824-4644-91e9-3ec2a52d5f29 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D87 | Level 4 Balustrades Installation
57ff8877-01a4-4e23-9b15-b7430e273308 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D87 | Level 4 Air conditioning
be11c6c0-49ad-436c-8bcd-29e0622cf02e |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D87 | Level 4 External Plaster - Nibs & Beams
40e31ca1-a009-4814-8e07-06ca5554e457 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D87 | Level 4 STO Poren Plaster
a46026d1-7cdc-4c53-8d29-eac952e66243 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D87 | Level 4- Windows and Sliders
a33d295e-4822-4a4b-85a1-61dd9c10ad99 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D87 | Level 4 Eyebrow - Canopy
df711d59-7850-461a-b505-373b5c451fb5 |  | checklist-flat | not-started | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D87 | Level 4 Flashing installation
dcd6e379-42f6-49e4-bd1d-d099a5e07f6e |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D87 | Level 4 Brick Works
e373d27f-93cd-44d1-bf01-14100703397e |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D87 | Level 4 Soffits
91a5042d-bac5-4044-b0cf-645ea57987e5 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D87 | Level 4 Exterior Timber Framing
3be4b8ec-0654-425f-ac83-660c2f3b21fe |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D87 | Level 4 RAB Board
b746a86f-a1a6-4dde-9b07-879425fd3b3f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D86
a6cde6b3-f215-4e97-abc5-6a6470246e62 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D86 | Level 4 Exterior Tiling
581a789e-69f7-4d2f-bbc5-11feb05e5ef1 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D86 | Level 4 Balconies
7d0c96c1-cc94-46c0-99c9-ad5b96aedab3 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D86 | Level 4 Balustrades Installation
e737905a-67a3-4f3c-b3fb-196c997c4287 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D86 | Level 4 Air conditioning
0c12465e-3d20-4595-8c7b-6f9056dc15a8 |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D86 | Level 4 External Plaster - Nibs & Beams
6c8c45de-b533-41cd-b231-76a848f5180c |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D86 | Level 4 STO Poren Plaster
ddedb5c8-f121-430b-a62a-7e4ca3f0548c |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D86 | Level 4 Eyebrow - Canopy
c778d5a6-7b3c-4f30-946b-a1677908840a |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D86 | Level 4 Windows and Sliders
487d516b-3178-4b4d-a28a-91cf81824bee |  | checklist-flat | not-started | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D86 | Level 4 Flashing installation
2b923a99-8244-41f8-bd52-9a116bbf1518 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D86 | Level 4 Brick Works
6ee0880b-51b3-41ca-985a-f46902c490aa |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D86 | Level 4 Soffits
13efcdf5-afb2-4200-8fb5-76a6df956283 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D86 | Level 4 RAB Board
08f0019a-95e3-42a0-85d7-52b4ced0695c |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Apartments | D86 | Level 4 Exterior Timber Framing
a093c6a7-d57c-4c03-8c70-e4dc8da3d904 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Water Test
0a37213e-eefc-4833-8497-3cf73bb0b4b5 |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Water Test | FC - R - Water Test
7cf02bfa-43a0-488f-84e3-b6494de2a54f |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Passive Fire
2be6c32c-00b3-452a-bfd6-c3d9fcd3ed96 |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Passive Fire | Level 4 Passive fire
56da51e1-c66a-4bac-ad34-810fc4f0665c |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | South Elevation | Level 4 External Plaster - Nibs & Beams
198a3a4a-b215-43e2-89dd-593d1634ec86 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | West Elevation
d1144448-f0ce-4749-8473-6d02fdb1d0ed |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments
754c1444-3588-4415-9422-92115926afb7 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D83
19edf605-5073-4d1c-a5bb-0e73623b7659 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D83 | Level 4 Exterior Tiling
33ab4c7f-f5da-4d92-a3ad-e736cc2d5f43 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D83 | Level 4 Balconies
fe33ed76-5739-48f8-b9c2-389b935e1476 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D83 | Level 4 Balustrades Installation
7ba2b7bb-9fe5-48a9-81c7-071ead62b20a |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D83 | Level 4 Air conditioning
d5337fb7-4d18-45b6-9306-157a3797831e |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D83 | Level 4 External Plaster - Nibs & Beams
39704c7d-f8e8-4b5a-9eaf-bcb1af98d4c1 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D83 | Level 4 STO Poren Plaster
79f636ea-a2e2-414b-bf1b-79eb4aa3e3b3 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D83 | Level 4 Windows and Sliders
7aaa9f91-0006-4c60-b553-f7f1d19c90a3 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D83 | Level 4 Eyebrow - Canopy
12cf820a-00e9-4a7a-9528-e0f7c4ec603e |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D83 | Level 4 Flashing installation
77aa8a68-e313-4fa4-a4b2-a8d673e0b3df |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D83 | Level 4 Brick Works
cab511f9-2cdc-430f-8a49-4ff49fecb214 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D83 | Level 4 RAB Board
98c202c0-528c-4b57-98e7-be94361d79db |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D83 | Level 4Soffits
d5263d93-ff34-4480-94b5-1f8039c77d4f |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D83 | Level 4 Exterior Timber Framing
ea54e27c-6482-418d-8897-8ab71c42a10f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D84
5ae89481-db3a-4133-84ce-dbac49f81c16 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D84 | Level 4 Exterior Tiling
ed5c6c46-3780-4933-bff7-5565eb41c388 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D84 | Level 4 Balconies
9d8fd3b6-e8bb-4140-adcc-60703a4ac93b |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D84 | Level 4 Balustrades Installation
2eeed9cb-5d97-4271-8e8a-4574b186aee2 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D84 | Level 4 Air conditioning
33f8e7ac-7492-4860-8c5f-5ead249cd7c1 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D84 | Level 4 External Plaster - Nibs & Beams
517e7383-6e68-42bd-a64f-34c6690684a5 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D84 | Level 4 STO Poren Plaster
9af1827f-4377-434f-8b9d-956244912cce |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D84 | Level 4 Eyebrow - Canopy
e404fddf-a67c-48e5-8c57-4cb8b3880246 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D84 | Level 4 Windows and Sliders
626066f9-30b1-4c44-b163-cc22912cca3f |  | checklist-flat | not-started | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D84 | Level 4 Flashing installation
8af5204a-0eae-4231-8549-9e72ae3c8b22 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D84 | Level 4 Brick Works
d9d6e82c-c504-46a6-a66c-e9755b3a88dd |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D84 | Level 4 Soffits
4b188d4b-357f-472c-a234-928a1ae51d52 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D84 | Level 4 RAB Board
da0e0f27-7d1f-44a3-9200-62bcab0cb214 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D84 | Level 4 Exterior Timber Framing
03ca1f30-d558-4b1b-96b9-88f5ed2289eb |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D85
2af2d729-c4db-4621-9188-7dc28e14c37d |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D85 | Level 4 Exterior Tiling
56b7ca49-bc12-4546-9603-f6611b6932f6 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D85 | Level 4 Balconies
80d77318-c281-4690-a08b-b09851017a30 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D85 | Level 4 Balustrades Installation
f79ba873-f96e-43a6-8310-1b97507d21e1 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D85 | Level 4 Air conditioning
18c4eef9-36be-46fc-bcfc-ba89b7592d39 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D85 | Level 4 External Plaster - Nibs & Beams
79b3ea8d-1f30-44b2-8437-5ad3e1f7617a |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D85 | Level 4 STO Poren Plaster
53c91574-8f7d-41cb-8865-a5a06b85fe6b |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D85 | Level 4 Windows and Sliders
953e39c2-d0ed-47a4-bfee-4d583957269b |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D85 | Level 4 Eyebrow - Canopy
565da6b7-3f10-48d9-a28a-76988a35a287 |  | checklist-flat | not-started | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D85 | Level 4 Flashing installation
34fcbf5b-da4d-4a07-bfa5-bc11a2216518 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D85 | Level 4 Brick Works
8ab724ba-63cd-4155-9f90-05f98dc09f45 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D85 | Level 4 RAB Board
6b75bbf7-e511-47c0-8623-2a66d5647339 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D85 | Level 4 Soffits
2bd8555e-5930-432f-a108-8f19ee352ee2 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Apartments | D85 | Level 4 Exterior Timber Framing
28e21374-e89c-48f0-9bcf-f871990d062b |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Water Test
c07ecd9a-b477-47fd-bdea-a2e14a44f07c |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Water Test | FC - R - Water Test
4eb1e3b1-a170-467a-8ac9-c416899e0946 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Passive Fire
b37282e8-ecac-4ba4-8236-4a6fd788dabe |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | West Elevation | Passive Fire | Level 4 Passive fire
114b0c4f-34d3-4403-acf3-4ba772193d66 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | North Elevation
2e45b781-f452-4993-8552-178c15b8a9a9 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Services Areas
79ac0de4-a49e-4e7b-8409-5367440d6501 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Services Areas | Comms
10bd4e84-efaa-4867-9164-f6dcf33e60d1 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Services Areas | Services Room
3b848a00-ffd6-4d53-abc1-ce6ce9216db3 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments
873b9c11-dba2-409a-9940-a8b5ff062961 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D73
628e1af1-3819-4a9d-9963-b130d0c86b47 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D73 | Level 4 Exterior Timber Framing
f163e7bf-556f-4309-818d-79f866284d2e |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D73 | Level 4 RAB Board
a2e4d4a4-0c0c-4485-8726-46452678c5fd |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D73 | Level 4 Windows and Sliders
1da2c068-0564-4a8f-b5d4-cf1e1d3a8301 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D73 | Level 4 Flashing installation
a9151c47-d50b-4e52-9634-d3035101f946 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D73 | Level 4 Exterior Tiling
4d00750c-3779-4c53-859d-8587f8754394 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D73 | Level 4 Balconies
2adf12c0-cc16-46e8-9d2c-d14145851717 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D73 | Level 4 Balustrades Installation
ae7b1c59-0fc6-4b62-9038-9a833c832116 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D73 | Level 4 Air conditioning
5f6223ea-6b83-4257-9b88-fcdb9fd39b04 |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D73 | Level 4 External Plaster - Nibs & Beams
64563efc-1465-403e-9c15-fdf4fcb9ddd0 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D73 | Level 4 STO Poren Plaster
1b0a2a0e-55d3-49e0-a2f0-251550b02cfe |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D73 | Level 4 Eyebrow - Canopy
366e5eaa-26d6-4c9a-9063-ac94f0115032 |  | checklist-flat | work-in-progress | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D73 | Level 4 Brick Works
e7fc99a8-17cc-4873-8bf6-d9955a94c079 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D73 | Level 4 Soffits
b47387b1-f579-48f6-812e-eb048010b96f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D75
aa26a132-e568-4e04-b050-4f0701d9b53e |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D75 | External Plaster - Nibs & Beams
2bc623fd-90aa-4d74-a987-96ce9aa7861a |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D75 | Level 4 Exterior Timber Framing
7d2b8ddf-7503-4cad-a354-5b50e3d51eb0 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D75 | Level 4 RAB Board
c0787aee-d82e-4acb-afe6-7cfa6df89aa8 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D75 | Level 4 Brick Works
3bd9b990-e005-418c-9539-105693d7ef44 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D75 | Level 4 Balconies
78914cce-039b-4731-b478-fca936474fde |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D75 | Level 4 Balustrades Installation
88db331e-ad07-4554-a2c5-6ff877db2959 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D75 | Level 4 Air conditioning
5f35f229-ca2a-45e1-b819-33155cfbc078 |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D75 | Level 4 External Plaster - Nibs & Beams
ace44b32-5c9f-49aa-97b9-e6b950133465 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D75 | Level 4 STO Poren Plaster
3d2a4b35-45fa-4b0a-9891-067705c4467d |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D75 | Level 4 Eyebrow - Canopy
e5fc5170-b399-4183-aa6a-91f55a389997 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D75 | Level 4 Windows and Sliders
9a439721-fe04-46a9-858b-7c71167b2f88 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D75 | Level 4 Flashing installation
84329d6f-60d9-4bb7-bc60-21f77a4cf713 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D75 | Level 4 Soffits
1db53921-816e-43aa-b587-7a9c1b6ca611 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D77
6a8de382-307b-4bfa-ad11-ed767b43a7fc |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D77 | Level 4 Exterior Tiling
e1940d43-f794-415d-823b-ba017248ca3b |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D77 | Level 4 Balconies
e8429cf9-3119-4ad5-8772-2f215902b762 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D77 | Level 4 Balustrades Installation
472118b1-93ba-4348-bf80-22a3158b85ca |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D77 | Level 4 Air conditioning
20df0c75-ab45-4003-9b2d-fd494acb5be4 |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D77 | Level 4 External Plaster - Nibs & Beams
f5fbaf89-280f-4096-a720-40523ad3041c |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D77 | Level 4 STO Poren Plaster
039fa1a2-f7ca-45db-970c-d01ecc56ec89 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D77 | Level 4 Windows and Sliders
dcf3d1c6-2206-42c9-8d19-1ee40cf71958 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D77 | Level 4 Eyebrow - Canopy
5de0e50f-be1a-45cc-bd0f-c4bb819c34b3 |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D77 | Level 4 Flashing installation
3c2d2c52-b55d-4bb1-8667-846b596e102f |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D77 | Level 4 Brick Works
9c1d49e4-1137-48c9-a405-c3b237bc03ce |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D77 | Level 4 Soffits
bdf55d13-df8d-410e-8334-eac678b73114 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D77 | Level 4 RAB Board
6c3ec68a-e06b-4b95-9762-984bdaeffdc2 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D77 | Level 4 Exterior Timber Framing
878fad1b-26e6-4ce0-95a0-afe54102d4ee |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D78
4fabdee3-4598-4e87-b484-7c12dcfdf3ca |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D78 | Level 4 Exterior Tiling
d29e673f-9538-4ea3-85fc-51058df58d49 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D78 | Level 4 Balconies
8f9c07fa-12e4-4e13-a35e-d357faa98fda |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D78 | Level 4 Balustrades Installation
976afe19-f50f-4999-aef8-a3e3837aa917 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D78 | Level 4 Air conditioning
e3aed79d-50ca-47f2-b73d-62eb3084ffb7 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D78 | Level 4 External Plaster - Nibs & Beams
70be6dea-6c3c-4c3e-a2c1-ceb8ed38bf61 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D78 | Level 4 STO Poly Plaster
6aaa6862-6359-4ec9-ab05-e8ec7cdc9f3c |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D78 | Level 4 Eyebrow - Canopy
14904544-b62b-4daa-b7e7-763cc0fd3d12 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D78 | Level 4 Windows and Sliders
d82f8048-9ae1-4da7-8658-abddfd162cec |  | checklist-flat | not-started | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D78 | Level 4 Flashing installation
90adde92-5ffe-441e-9983-293164874dc1 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D78 | Level 4 Brick Works
ed40811e-980a-4085-8eb7-411d4071f37f |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D78 | Level 4 RAB Board
f280f156-b459-4969-9b23-e9933da45f1c |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D78 | Level 4 Soffits
49aad445-d115-43c0-9975-ca181f7f90ac |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D78 | Level 4 Exterior Timber Framing
1fe88058-9f86-4a55-8aae-b0590c6ef822 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D79
c0f8bfd7-54dd-43ab-9d24-b5fcba3a8293 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D79 | Level 4 Exterior Tiling
5b805036-fb5b-4976-a5aa-c1c032fb078d |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D79 | Level 4 Balconies
696ba7cf-7987-4bd3-a05f-7042e5fc6071 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D79 | Level 4 Balustrades Installation
0beec01f-dbc5-4787-aaab-5fd1a3af38d2 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D79 | Level 4 Air conditioning
c375d11f-ca32-4215-9947-1e7a4158e7d8 |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D79 | Level 4 External Plaster - Nibs & Beams
ef8dfbb6-d08a-4fa4-8ea3-97c90fd1aa2c |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D79 | Level 4 STO Poren Plaster
14c99679-115d-4173-b1a1-345ce6c5beaf |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D79 | Level 4 Windows and Sliders
26daec82-966a-4b54-b912-78af48217b0b |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D79 | Level 4 Eyebrow - Canopy
aada9b2d-34f3-47bd-88f7-c6d16351d80b |  | checklist-flat | not-started | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D79 | Level 4 Flashing installation
598c0544-239d-40e6-9ddb-1d581f9b9001 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D79 | Level 4 Brick Works
2ed97438-ec20-4e37-b3e5-c206053bff37 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D79 | Level 4 Soffits
ffc99aff-f84a-40ee-81d5-cf402ea16b4c |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D79 | Level 4 RAB Board
77c14fdb-ccd2-417b-9a62-62e665d9e19f |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D79 | Level 4 Exterior Timber Framing
4f323ff1-bbc8-49f2-827c-a627dc1a74c3 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D81
7ff32299-9695-42c6-a080-965bb5695db2 |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D81 | External Plaster - Nibs & Beams
208705a3-c7a8-43a2-b66d-44428d95c048 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D81 | Level 4 Exterior Tiling
53268a05-e812-43e7-974f-7a14be732b20 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D81 | Level 4 Balconies
5090fc12-14a8-476c-bf06-aaa9acf5d10f |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D81 | Level 4 Balustrades Installation
42cc4df9-8b9a-4eca-9c7e-466b3401b676 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D81 | Level 4 Air conditioning
71b0f9c5-469a-4f20-82ea-a831f372d4e1 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D81 | Level 4 STO Poren Plaster
00d8174a-fcf1-4712-acdb-8129d73c66d2 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D81 | Level 4 Eyebrow - Canopy
e2e1363a-8f5b-4a29-b425-8fb357b0ea76 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D81 | Level 4 Windows and Sliders
bbf57aef-0962-43d1-b9cf-afe0c54ac456 |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D81 | Level 4 Flashing installation
1991aad8-bd79-4a8e-9c5c-7a908cde6435 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D81 | Level 4 Brick Works
0b762778-382f-442a-968f-5a575515dea7 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D81 | Level 4 RAB Board
ecbabe6e-2010-4175-b0a7-8e5abcb02d73 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D81 | Level 4 Soffits
6bb5f9e8-3d17-4704-9fe8-817d15caf5ae |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D81 | Level 4 Exterior Timber Framing
366393bc-97f9-4bc3-b1f4-4bec78cd463f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D82
c320ff62-c157-42f7-8733-b09816e1beed |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D82 | Level 4 Exterior Tiling
679572d4-b68c-42f6-856a-8bed27c1ce98 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D82 | Level 4 Balconies
8cb14d8f-3bc6-4c4d-a983-59de7bd8cc37 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D82 | Level 4 Balustrades Installation
06e7aae0-652f-41c8-be7e-7182a3df8fe0 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D82 | Level 4 Air conditioning
e1d8f54e-cce6-43ff-92b7-c766eca52457 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D82 | Level 4 External Plaster - Nibs & Beams
9a0d8533-57ca-401b-a062-d2b83fef6b0d |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D82 | Level 4 STO Poly Plaster
dbd8f8e9-d682-4a47-8d08-bc9fec2068ed |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D82 | Level 4 Windows and Sliders
62084f5b-52fc-4471-a725-f7b844427a7f |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D82 | Level 4 Eyebrow - Canopy
82b89d3a-7b56-49ca-a984-f8394d570519 |  | checklist-flat | not-started | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D82 | Level 4 Flashing installation
2b1be656-2b96-48b1-beac-b80e34e43b8e |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D82 | Level 4 Brick Works
d3c64191-c70b-425a-bd82-7f6238bf9dff |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D82 | Level 4 Soffits
f6360ccd-7a43-43e7-ae85-a3227cfdb8a2 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D82 | Level 4 RAB Board
18d729a7-2721-4e68-a8d8-93f0cc641580 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Apartments | D82 | Level 4 Exterior Timber Framing
43ebe192-df0b-4ac4-ac28-70cf4705018f |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Water Test
2a8a923d-4ba6-4183-ace0-96b36df34746 |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Water Test | FC - R - Water Test
e239be2e-de76-4f0f-a8c0-dc27714025c2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Passive Fire
2cece058-a40a-4324-8ea9-805b69e1c20b |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 4 | North Elevation | Passive Fire | Level 4 Passive fire
bbca1e62-e5f9-44a1-9349-8792c54974a9 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5
18392149-9c4b-4be2-9023-4524785195f4 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | East Elevation
0f49d0f1-5480-4309-9ce1-cde930761e84 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Common Areas
d12da653-7bd4-4353-b3fb-ecec8c555262 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Common Areas | Lift Lobby
02c0f887-e7a6-41d0-9255-42a13d1a09e0 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments
f2340556-9e9a-417c-972a-fa40836ebd21 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69
528f63f3-ae0b-464d-9270-e7eedce9a7f6 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69 | Level 5 Fascia/Gutter
dc33fdb9-ad7a-4c29-b16c-b16eb66f845a |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69 | Level 5 Exterior Timber Framing
bb0d8885-b625-4f22-9319-24abe1f923cb |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69 | Level 5 RAB Board
6a2fbef9-def4-4ed7-a853-c1df8811df98 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69 | Level 5 Exterior Tiling
3012b851-f77e-4f01-a8d4-154ba3e9789e |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69 | Level 5 Balconies
bec3b9c6-350a-4063-9d79-06ae80936c41 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69 | Level 5 Balustrades Installation
6cc848cb-8cd9-457f-b403-14a84bee312e |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69 | Level 5 Air conditioning
6e03b7fd-4d8d-4281-b910-e48b17ea2ad8 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69 | Level 5 External Plaster - Nibs & Beams
159432bd-b33b-461c-816a-dd91a4abcd96 |  | checklist-flat | pass | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69 | Level 5 STO Poren Plaster
59dd98ec-24b5-4f06-895a-a08b3b4241e6 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69 | Level 5 Eyebrow - Canopy
e346e1bc-c685-4324-b723-da479e07bd55 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69 | Level 5 Windows and Sliders
75e80a56-e6e0-420d-b90b-340a27a0dfb9 |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69 | Level 5 Flashing installation
7d3519a1-15e7-41f7-8ae3-78c1e71e15b2 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69 | Level 5 Brick Works
d75bda94-8348-4bbe-89e3-4bf2aa80181e |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E69 | Level 5 Soffits
f776f4e8-fbdb-4eec-9bb6-2f796d42e07a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71
f81034af-a36f-42f1-a7c1-eb4f49ff64de |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71 | Level 5 Exterior Timber Framing
d33155b7-6338-409e-bf9c-3145d6b996c9 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71 | Level 5 Fascia/Gutter
bc71effc-4cb8-453b-a69f-9fbc61306e10 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71 | Level 5 RAB Board
a7c84aea-7cfb-41fe-b7f2-2369f3f80f09 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71 | Level 5 Exterior Tiling
ba552a4a-c72a-4a2d-afa0-76f7c0a2f6a2 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71 | Level 5 Balconies
3ae9aab0-c530-4b89-ba89-46158128fb11 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71 | Level 5 Balustrades Installation
185ed1f1-9231-48b9-8132-efc903c19de0 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71 | Level 5 Air conditioning
540faf88-1b8d-43cc-950d-cf1d415e4a7e |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71 | Level 5 External Plaster - Nibs & Beams
3c95cbc5-43bb-4c20-8fee-3161a3b85542 |  | checklist-flat | pass | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71 | Level 5 STO Poren Plaster
ea477a8a-2112-40de-9795-6595891ba70e |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71 | Level 5 Windows and Sliders
e484394b-333f-4c00-9e09-122e711432fd |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71 | Level 5 Eyebrow - Canopy
3c5d5e60-d80f-4747-a119-af0cf5a21700 |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71 | Level 5 Flashing installation
3f7575bb-b4f6-4bf8-8024-bee21573fe7c |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71 | Level 5 Brick Works
655dc0b1-efe2-47c5-80ad-2fed565c8432 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Apartments | E71 | Level 5 Soffits
e51a2ea3-b6b5-49f8-bf7e-76ae45928303 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Water Test
f47c38ae-6391-42ed-b930-1593534dd18f |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Water Test | FC - R - Water Test
392c16fc-97e8-4ea6-8558-da95b389b0b5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Passive Fire
b93d3527-0d27-4e28-b99d-a27e1a29422a |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | East Elevation | Passive Fire | Level 5 Passive fire
c5a6f0f1-03b3-4521-9bb8-6ef5f9c78e6c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation
5416471f-dd74-49e1-a82b-fdfbe4af7eea |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Common Areas
750bdfb7-e182-476b-a92b-2edace82b4fe |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Common Areas | Lift Lobby
1e79d0e2-7861-4b90-8ae1-1dca2a1cd61e |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Services Areas
e1acb243-c17f-406b-b2ec-b89a66226ea4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Services Areas | Electrical Room 01
fa5f7265-0182-4edd-9115-fb64942219ad |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Services Areas | Electrical Room 02
5ca65311-051c-4180-830c-bc92ea1f1777 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments
a3cec4f7-5ad4-40d2-9a31-30ebfd242483 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70
a55e0d84-91e1-47cc-834b-4cba1f6b9930 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70 | Level 5 Fascia/Gutter
ae33a379-72b1-4deb-9df6-258998bccd0a |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70 | Level 5 Exterior Timber Framing
4ce92f79-e8c3-48a7-a642-ecc93737d312 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70 | Level 5 RAB Board
80f1ee49-6852-424b-9a5f-9c11ceb0b23c |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70 | Level 5 Exterior Tiling
e0e7b162-6e31-448b-a938-cc5032af5782 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70 | Level 5 Balconies
ecacff47-e5d1-4552-a008-cfc7c63447c5 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70 | Level 5 Balustrades Installation
8f5c3e21-575e-4e7e-a57a-35fe92a837b0 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70 | Level 5 Air conditioning
3ca21bef-c1ed-4a0e-b3b8-6104f7711bc4 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70 | Level 5 External Plaster - Nibs & Beams
8f5875f1-fad3-405d-ad58-e7bb87b6c67d |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70 | Level 5 STO Poren Plaster
24d1f192-813a-4927-934f-7d787b043bdb |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70 | Level 5 Eyebrow - Canopy
809add03-d2a9-4a7e-807f-309fae0ba988 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70 | Level 5 Windows and Sliders
e0a52b1f-0db6-4285-a395-5ec9f37037c8 |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70 | Level 5 Flashing installation
ba9f3246-d989-458b-a7c4-0cafe0a7c987 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70 | Level 5 Brick Works
ae8d73e4-6d01-46fe-8045-d9a49cc8fdb9 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E70 | Level 5 Soffits
2ccb995f-fe18-44ec-a1cc-e40f26884080 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72
135b2644-9dd6-4393-946b-10386afe1f88 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72 | Level 5 Fascia/Gutter
18191a2d-3b49-455f-af6b-55bb3dfaee9f |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72 | Level 5 Exterior Timber Framing
3f7b8ff8-ec64-4599-b098-37e7d455e475 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72 | Level 5 RAB Board
961b8cad-832e-4555-af32-e28266557524 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72 | Level 5 Exterior Tiling
a324ea35-2cca-4f59-8cbb-7af5ca42e539 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72 | Level 5 Balconies
bdc00f02-0c19-4872-8b93-af49937ab574 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72 | Level 5 Balustrades Installation
f75ed413-01ea-4d34-9c64-451aea2ea025 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72 | Level 5 Air conditioning
c76cfe4e-9f81-4281-a29b-444d34bfa619 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72 | Level 5 External Plaster - Nibs & Beams
9b0bb8cb-627e-4d28-ae4b-32a884b34a75 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72 | Level 5 STO Poren Plaster
ecccac2e-caa9-4868-b9e3-8900701ce43e |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72 | Level 5 Windows and Sliders
b52c6cd7-211e-46e3-b5da-253af3e602ef |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72 | Level 5 Eyebrow - Canopy
7d1b874a-1628-4516-b2c9-fad3911454fd |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72 | Level 5 Flashing installation
9badcb27-549e-4b7e-94a1-ea5b013701b9 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72 | Level 5 Brick Works
4fd1f9bb-ce94-4a24-ad96-191374656a48 |  | checklist-flat | pass | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E72 | Level 5 Soffits
2edb6765-bf4e-430a-8172-d8712577c1f0 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74
601d3943-c886-4343-84f3-b181c1e15a1a |  | checklist-flat | work-in-progress | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74 | Level 5 Exterior Timber Framing
cd5a7687-e22a-46fe-87c9-70aef145e284 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74 | Level 5 Fascia/Gutter
81ca2091-92e0-4afd-98c3-4991cde8f089 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74 | Level 5 RAB Board
d208fe53-189c-4def-a7d5-dfaf0a0587d7 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74 | Level 5 Exterior Tiling
6f83c488-bbd6-4eb9-9d2d-b9fcf4fec4ec |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74 | Level 5 Balconies
1d35cb8f-5d08-4a80-ae09-0ae97c18d10c |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74 | Level 5 Balustrades Installation
aa24f7b2-d12d-4b25-931e-9f6bffe7d761 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74 | Level 5 Air conditioning
623ce053-1f76-4f30-b91f-edbf13531777 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74 | Level 5 External Plaster - Nibs & Beams
78b0d34e-723d-4b42-ae38-2d7dca34f4b5 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74 | Level 5 STO Poly Plaster
2f2188c4-e53d-4746-93ed-29a2d0a8a999 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74 | Level 5 Eyebrow - Canopy
2ba5e99b-cf0f-49d1-b3dd-626779d42a57 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74 | Level 5 Windows and Sliders
54f366cd-29ae-4124-8b76-c9e36e26f634 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74 | Level 5 Flashing installation
83871cb6-a343-448e-a7c8-81d5f0495596 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74 | Level 5 Brick Works
d797d6c0-3ce7-4920-9d40-02afd6b934a0 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E74 | Level 5 Soffits
156ee8cc-8427-4e3d-858d-cfc2c75aba33 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76
a5e369c5-2964-4df2-8337-79a0e0710a9b |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76 | Level 5 Exterior Timber Framing
a43d8824-c097-4043-b114-c7a20709a56c |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76 | Level 5 RAB Board
6329c295-3b57-4bcc-89ac-6ed64eeb1f7f |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76 | Level 5 Exterior Tiling
936c10e5-8958-413f-80ab-f4412a2ee825 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76 | Level 5 Balconies
2cfb0c4b-e416-4c90-bcb1-6ec2caa3d0a0 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76 | Level 5 Balustrades Installation
a8b952bb-96ee-41f7-ac95-857f4982b3b3 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76 | Level 5 Air conditioning
c44bf2a8-345f-4490-9178-3cf4dfc9d97e |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76 | Level 5 External Plaster - Nibs & Beams
7ab90715-540b-42ab-92e8-d46684427496 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76 | Level 5 STO Poly Plaster
28e26e0d-3ba1-42b1-a578-169dbbaaae82 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76 | Level 5 Windows and Sliders
a86ec061-8889-4e4d-b39a-2e52dafe9b8a |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76 | Level 5 Eyebrow - Canopy
9e30d290-14cc-4d1e-b43f-719797e02754 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76 | Level 5 Flashing installation
e4213b29-1c4b-48a4-86ca-27d1a19f973b |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76 | Level 5 Brick Works
a0fd1a4d-9715-4224-9024-b924b4f392ef |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76 | Level 5 Soffits
c27ef0e8-c913-42f1-b5a7-85684d32b5b5 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E76 | Level 5 Fascia/Gutter
82ce4da0-7572-4edc-b9f8-4edcc28bcaeb |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E80
6692ec8d-2fb4-4221-91bb-8739f0fd29cc |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E80 | Level 5 Exterior Tiling
ac0e5d67-a59a-4ce3-9c28-1ea6580536f5 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E80 | Level 5 Balconies
19f3b0b5-0ae6-4c74-abf9-9c1830e06ee3 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E80 | Level 5 Balustrades Installation
d589fe37-50f0-4861-a5a3-5690394ee5ab |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E80 | Level 5 Air conditioning
224ddcc2-e89f-4f40-87e5-30e2e8d2289e |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E80 | Level 5 External Plaster - Nibs & Beams
bfac66ea-fa1c-4439-926d-56001f2ebb58 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E80 | Level 5 STO Poren Plaster
51fb305c-09dd-46de-af33-c65c7582ec2d |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E80 | Level 5 Eyebrow - Canopy
570a4bf1-0c0e-4d4b-b129-a5c59ca95aa3 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E80 | Level 5 Windows and Sliders
cf086314-7fd4-4f4d-8200-bb9ed1fa125b |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E80 | Level 5 Flashing installation
d7f22d37-e374-4738-aa8f-a30bdc1e5702 |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E80 | Level 5 Brick Works
1ad679a1-0e01-43a5-b9a3-038919886fb5 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E80 | Level 5 Soffits
bd426065-1d75-4933-bf73-b2af9c948f25 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E80 | Level 5 RAB Board
9d294caa-7d7f-4a45-b567-ee59643551f2 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E80 | Level 5 Exterior Timber Framing
823e5fb8-bc8e-4fa3-b797-6fe6da233fa8 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E86
04f3e66d-33f4-424a-9d63-a763ababdce6 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E86 | Level 5 Exterior Tiling
4dc3c689-5ed3-41d9-98cd-d80f141b86aa |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E86 | Level 5 Balconies
168086a6-da0d-43d5-be43-c959b62263f8 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E86 | Level 5 Balustrades Installation
5782c7f3-9427-414e-8c23-b9d9078552a4 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E86 | Level 5 Air conditioning
200e0fe0-3872-4826-9afd-3762a7d8657c |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E86 | Level 5 External Plaster - Nibs & Beams
18f95871-dfc1-4220-8377-a687e7a4e0be |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E86 | Level 5 STO Poly Plaster
dcbf2acf-35e5-47d2-a5d9-466b21a1658f |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E86 | Level 5 Windows and Sliders
ddef4212-0e4d-4646-992b-c131f41d5d86 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E86 | Level 5 Eyebrow - Canopy
3ffa3d07-6bbb-48da-982c-ddaca07521b5 |  | checklist-flat | not-started | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E86 | Level 5 Flashing installation
176ee0ce-df2c-4134-954d-5d05ccf86d7e |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E86 | Level 5 Brick Works
a6ca6046-464c-4c14-ac67-43567b6dbb3a |  | checklist-flat | work-in-progress | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E86 | Level 5 RAB Board
7e40c158-e015-4be3-9f00-e80ba5fa23f3 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E86 | Level 5 Soffits
1924e100-6a8d-4795-b297-914d0d796272 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E86 | Level 5 Exterior Timber Framing
9d8f303c-6419-430e-adcd-eb2f3e7ffd94 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E87
0d96c4ca-6b58-4a83-a499-044a27fb4676 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E87 | Level 5 Exterior Tiling
d0d1290e-b634-4ebf-8e14-f39af2297ec5 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E87 | Level 5 Balconies
7f4379a5-ec3e-41ce-b462-5f90fd4c39f0 |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E87 | Level 5 Balustrades Installation
88ae467b-d264-4940-8a87-50e8fcc50466 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E87 | Level 5 Air conditioning
10c1fc35-7e76-49f8-8fd0-44a00c113d18 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E87 | Level 5 External Plaster - Nibs & Beams
0341612d-a73b-4a5c-bbe1-1e3874b76916 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E87 | Level 5 STO Poren Plaster
f59a301c-d60d-4df7-96c6-716da380f898 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E87 | Level 5 Eyebrow - Canopy
68973a00-8802-4eb0-998c-512dfb351bfe |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E87 | Level 5 Windows and Sliders
e00a756d-c473-4ef3-90ee-8a8b161be855 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E87 | Level 5 Flashing installation
56538db7-1b9a-4bc9-ae3d-55447ac4e8af |  | checklist-flat | pass | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E87 | Level 5 Brick Works
e7ad5c37-dee7-485a-a783-691f4e54141d |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E87 | Level 5 Soffits
e2306711-5def-4bcd-a61e-5b4575313f0a |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E87 | Level 5 RAB Board
2509252d-fcfe-44d0-8eea-1ea809ba67ca |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Apartments | E87 | Level 5 Exterior Timber Framing
f6e097c0-e8ed-4baf-b6d9-55ab5faa7bfd |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Water Test
cf38490d-9485-4c8f-bf7c-2ffa137b1ec8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Passive Fire
c93d6738-6f1c-4925-9d11-98c19a8f27e2 |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | South Elevation | Passive Fire | Level 5 Passive fire
5d869be8-ab20-4ef1-b18b-aaa9585471a2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | West Elevation
f5671ff4-6d11-4538-9fce-4feeacfdfbbe |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments
d74eafe3-6045-4727-8a2a-790955e52378 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E83
5d02dab4-30d0-4ee6-966c-6c4626cbdfa8 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E83 | Level 5 Exterior Tiling
d2a2f1cd-bf27-4e19-abea-aeebe08db4b5 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E83 | Level 5 Balconies
018c2b77-4d41-44de-a353-3bab9d4c605d |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E83 | Level 5 Balustrades Installation
20317ece-dc44-4f33-81d5-d70b1f226aa5 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E83 | Level 5 External Plaster - Nibs & Beams
044c84ab-e9de-48b2-a89d-ba2ea72a972c |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E83 | Level 5 STO Poly Plaster
e3836602-4d20-453b-877c-1a666e71ceef |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E83 | Level 5 Windows and Sliders
ce2d70a8-8929-4321-8685-81fc3a0a4436 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E83 | Level 5 Eyebrow - Canopy
e9b8a75c-3f94-4c79-aeea-79ab1c7d4dae |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E83 | Level 5 Flashing installation
9cee84d8-ab07-4d8f-a6c5-f8b088cd244d |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E83 | Level 5 Brick Works
c29ce6cf-ec16-4029-bbe0-60f23eee1977 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E83 | Level 5 RAB Board
17924442-e307-493b-97a4-dfaed4919d59 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E83 | Level 5 Soffits
76dff827-cc5d-4eea-bfa7-e6fb728623f2 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E83 | Level 5 Exterior Timber Framing
da1480d7-2efd-442e-9492-e0fc2e4032ba |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E84
de7ad3f3-9ff8-4d78-aea2-21c3429c7e21 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E84 | Level 5 Exterior Tiling
6ef13e69-371e-4092-b5df-df2833fc5070 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E84 | Level 5 Balconies
b6bd1087-1755-4e47-9ca7-a07f0c38091f |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E84 | Level 5 Balustrades Installation
83f6ac9a-a5d1-40fb-b20f-b060cd7c8766 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E84 | Level 5 External Plaster - Nibs & Beams
416f34cd-8224-4677-8e08-0c2068faeec5 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E84 | Level 5 STO Poly Plaster
f55c1e68-1b63-4e0a-b811-414f2d4509af |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E84 | Level 5 Eyebrow - Canopy
8e15ac66-5431-46c4-92fb-b545476b459d |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E84 | Level 5 Windows and Sliders
ea55c7e8-5607-43bb-8075-e158382f99ce |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E84 | Level 5 Flashing installation
86025bd6-a6ff-4977-9915-ce381b8a91cb |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E84 | Level 5 Brick Works
7dad2206-a84d-489e-b25a-60e4e8e5765f |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E84 | Level 5 Soffits
28b12635-d4cb-43ef-8ed0-492b671ad7be |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E84 | Level 5 RAB Board
ed98a2ab-df73-494c-a496-e4810628e2c4 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E84 | Level 5 Exterior Timber Framing
653a930f-b9f4-4ca8-b564-65d90d665b2b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E85
005bfed1-7207-49c9-8ebe-720e7c700d1f |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E85 | Level 5 Exterior Tiling
8375b874-2d79-4583-bfd5-a82f456fda29 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E85 | Level 5 Balconies
677c530d-4634-4e3f-86c4-dc5d2e3e0931 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E85 | Level 5 Balustrades Installation
be65c6af-0791-40ba-83e5-a8ecf1f4db61 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E85 | Level 5 External Plaster - Nibs & Beams
e0f10b09-2568-4455-a5e1-802a5a58dd89 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E85 | Level 5 STO Poly Plaster
c8f118d5-05d1-4cce-b65e-8de6544c35ac |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E85 | Level 5 Windows and Sliders
6a4f76f4-eb96-42f5-9d2a-82aedf813d4b |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E85 | Level 5 Eyebrow - Canopy
3bb28a81-31bf-493f-add7-406c2af564e3 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E85 | Level 5 Flashing installation
1dbcf059-91be-49fd-9acb-a9d06daa850d |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E85 | Level 5 Brick Works
77b1bf81-19db-4574-ae88-80900f006c1e |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E85 | Level 5 RAB Board
5ebb5aa6-e8d6-444e-a412-f9e697201d9a |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E85 | Level 5 Soffits
12555e4d-2119-4ca6-9801-a1932a6b45cc |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Apartments | E85 | Level 5 Exterior Timber Framing
14ccd5dc-bd46-401a-bdb6-b73ba5f7c867 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Water Test
64cf2988-899b-4fc4-90d8-827872a1fc10 |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Water Test | FC - R - Water Test
b700bca8-dbc0-4b18-8bd0-63d08a1ab326 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Passive Fire
9a37d128-a3f9-48ed-88f4-5d4c553d354f |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | West Elevation | Passive Fire | Level 5 Passive fire
036fc43b-417d-42a1-9a2a-43ee01fabd20 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | North Elevation
139af04a-1513-4a5f-992b-bdf723f80604 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Services Areas
b6446387-18d1-4480-ae94-794a5275a05e |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Services Areas | Comms
42f76434-92e9-4c24-8bf9-ab1f734fc0ab |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Services Areas | Services Room
357aa4e1-2635-40ae-885d-a4af54c887da |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments
c5ac592a-cd36-4d68-a85e-ca329b093d1b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73
c3a6a4c2-abdf-4f76-bcee-4881b799ef8c |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73 | E73 Fascia/Gutter
4bf99b26-264d-46fe-8c80-063f10745c77 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73 | Level 5 RAB Board
99b38477-d579-4c0e-9179-ad669e5ef50b |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73 | Level 5 Exterior Tiling
579ad30e-045e-4676-8887-b5a227c79a39 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73 | Level 5 Balconies
3bab21d6-7034-4d45-80c5-60326cebec9e |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73 | Level 5 Balustrades Installation
f9b81713-e1c1-48ec-9ce1-9ef9ea0d1c70 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73 | Level 5 Air conditioning
724d5df3-6ac0-4c2f-bbcd-e90fd5edd068 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73 | Level 5 External Plaster - Nibs & Beams
1d0f3d05-925e-404a-9d2c-104e0b18d546 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73 | Level 5 STO Poly Plaster
18d49f82-8de4-4471-9ee2-3c80e668ea3b |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73 | Level 5 Eyebrow - Canopy
02e7e3be-d18a-4cfd-9459-3c9849fd3f46 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73 | Level 5 Windows and Sliders
f22797f5-89ea-47ea-a974-4d3dbfd93c41 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73 | Level 5 Flashing installation
25c79ffe-04f4-4f3c-9616-a92747a10e1e |  | checklist-flat | work-in-progress | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73 | Level 5 Brick Works
58889bd7-5326-4c29-9f3d-a3456ebd0580 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73 | Level 5 Soffits
54643429-4a0e-4788-abc9-cab58d1b6688 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E73 | Level 5 Exterior Timber Framing
6684ce10-cc58-426b-8a68-16b359debda5 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75
4a70f3f8-6063-46ad-989e-407511d22518 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75 | Level 5 Exterior Timber Framing
df15edd4-ae46-4477-bd23-48367c3c6ac2 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75 | Level 5 RAB Board
8c83cb3f-ee05-4a0b-a0b2-60328c1f0d13 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75 | Leve 5 Fascia/Gutter
00095075-9ba6-43a2-9ea6-617011db1e88 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75 | Level 5 Exterior Tiling
357afc5d-28c4-4b47-b3ea-b80c8449fb5c |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75 | Level 5 Balconies
5cbcf7f6-8f3d-4c05-a44b-2c63de089fdc |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75 | Level 5 Balustrades Installation
91de4dff-2edf-4f16-bd48-c7e1e7b386a3 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75 | Level 5 Air conditioning
b3b683d2-2450-4b50-807e-9ddb525d8e7d |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75 | Level 5 External Plaster - Nibs & Beams
cb50ce53-6fd3-46f9-b16b-964997c3856c |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75 | Level 5 STO Poly Plaster
58f925a5-0104-4d10-bab4-2074e0f2d372 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75 | Level 5 Windows and Sliders
d6de7f23-30ee-4168-b97a-67501d714298 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75 | Level 5 Flashing installation
6417de54-9cf8-4c60-ba8a-ce2c2ac9215a |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75 | Level 5 Brick Works
101a4fea-82ef-4536-960c-a7d91c328ae4 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75 | Level 5 Soffits
0c788dd4-b381-4e94-95af-d6cfa146ce26 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E75 | Level 5 Eyebrow - Canopy
5b3efa76-4342-4589-ba5d-b36e1f290ecd |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E77
7c521ac9-5dc4-4886-991a-109556f60003 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E77 | Level 5 Exterior Tiling
0988451d-415e-4d71-96a7-f7330482f071 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E77 | Level 5 Balconies
93746f48-576c-4189-aafd-3c277a301627 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E77 | Level 5 Balustrades Installation
eb7c7833-ff84-48ea-9902-77a5a9697988 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E77 | Level 5 Air conditioning
caf89629-c88a-4a7a-a7e3-beec3b8d598c |  | checklist-flat | work-in-progress | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E77 | Level 5 External Plaster - Nibs & Beams
69ad23ea-a486-4a56-af96-5726bdde2fda |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E77 | Level 5 STO Poren Plaster
ec938666-7a95-42ee-87f4-0acf42d74719 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E77 | Level 5 Eyebrow - Canopy
db423c1f-b978-4754-a7eb-a8752c1a1938 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E77 | Level 5 Windows and Sliders
58991103-db0d-4691-bf37-3ab5123a20d7 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E77 | Level 5 Flashing installation
fc26de55-0db6-49f7-a168-6b7b8a13b2ee |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E77 | Level 5 Brick Works
1ead9fba-f2da-40b2-9b7e-bc9b976e456f |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E77 | Level 5 Soffits
4145231a-815d-4254-9643-80b24f8a9173 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E77 | Level 5 RAB Board
28bde6ce-10ca-4b17-9bc3-23bc747cbae7 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E77 | Level 5 Exterior Timber Framing
3df69374-ef50-4a42-b677-f8365b754a3f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78
b3b6426b-dd65-4885-bcdd-4dd4cefe2491 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78 | Level 5 Exterior Tiling
65ea4267-df51-471d-bcef-60403e398dad |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78 | Level 5 Balconies
e3a8bc7b-fe06-416e-aa31-771d09c44c29 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78 | Level 5 Balustrades Installation
844987c2-750f-4e1f-b259-82ff7a89728c |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78 | Level 5 Air conditioning
af31dad9-5f90-4ee6-98f8-23882ab5206e |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78 | Level 5 External Plaster - Nibs & Beams
bfa488c3-b9dc-4935-8205-651835db81d2 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78 | Level 5 STO Poren Plaster
58ba0699-cf9d-48a0-9eaa-efeb7f2dda0f |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78 | Level 5 Windows and Sliders
006f6c7b-1ec0-4b99-a488-ef8915383dc3 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78 | Level 5 Eyebrow - Canopy
e991fc8f-7fc0-45fa-9008-e94caf5c5706 |  | checklist-flat | not-started | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78 | Level 5 Flashing installation
6fd23cf8-27b8-4f43-8c78-c6de70d462d9 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78 | Level 5 Brick Works
075130d6-76a8-4770-947e-7294654734a4 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78 | Level 5 RAB Board
e9babd45-41cd-47a7-aba8-f67722e06c37 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78 | Level 5 Soffits
9da86139-e4d7-455f-afd1-c9b7cbbe1b91 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78 | Level 5 Exterior Timber Framing
fabc5b68-798e-479a-be26-f790015e7d71 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E78 | Level 5 Fascia/Gutter
7cbf7723-cf8d-47ea-9527-a2f985f9c7e7 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E79
4418f187-3382-4110-83f2-2198a7a05482 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E79 | Level 5 Exterior Tiling
cb77b6ac-b707-4e33-a094-d1c61e1873a7 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E79 | Level 5 Balconies
92da465a-154e-46f3-a39c-3804f06410ea |  | checklist-flat | work-in-progress | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E79 | Level 5 Balustrades Installation
d2a59419-4db4-4c65-93b3-571757f60996 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E79 | Level 5 Air conditioning
8a1f8029-5182-4139-b649-750e03bb358d |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E79 | Level 5 External Plaster - Nibs & Beams
8dc48aa0-6c49-4d25-959b-d73932d3b162 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E79 | Level 5 STO Poren Plaster
ff9f260d-ba6e-4ee1-9d16-5533fa8300a2 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E79 | Level 5 Eyebrow - Canopy
b14793a8-9164-44ea-926c-64dbba2c9334 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E79 | Level 5 Windows and Sliders
6a81d5a6-eead-44c9-9b58-ba08c9e8c2cd |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E79 | Level 5 Flashing installation
dfc36e67-51d4-4769-8bf6-716fcef08bc9 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E79 | Level 5 Brick Works
05177da0-9e0e-48c8-8b93-2114b4779392 |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E79 | Level 5 Soffits
ffaaef95-5d77-4175-80fe-4c4401a6b773 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E79 | Level 5 RAB Board
bc9e2fc7-d29a-48e0-a64f-4b6895992f1c |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E79 | Level 5 Exterior Timber Framing
2e086f19-e1f4-4add-93db-6322cbfeed1f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E81
f8735b68-ed16-4dfa-92a5-8a1ee58e6c87 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E81 | Level 5 Exterior Tiling
d676319d-a264-4175-9969-c11af154b163 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E81 | Level 5 Balconies
15af4d8d-9b92-42f8-a2b5-34cb78774544 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E81 | Level 5 Balustrades Installation
02e070a5-abb7-4099-9d4b-95539abbd682 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E81 | Level 5 Air conditioning
b791272a-51e7-4090-8a71-727a8680bc15 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E81 | Level 5 External Plaster - Nibs & Beams
7151f95a-6e34-47dc-a6a5-324950a3e066 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E81 | Level 5 STO Poly Plaster
88da9567-8699-4d67-b9fa-22c0a26c6168 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E81 | Level 5 Windows and Sliders
79ceb7ae-c181-4a16-9e4d-9afeff53ae05 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E81 | Level 5 Eyebrow - Canopy
8b9b8df9-0ed3-42b5-9913-76fa277b7c11 |  | checklist-flat | pass | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E81 | Level 5 Flashing installation
3c9a3c57-bb29-4bc1-8415-b268dd6289f5 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E81 | Level 5 Brick Works
9277643e-e4bb-4892-a6c7-f65e56595594 |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E81 | Level 5 RAB Board
c24fd503-0ff1-4e11-992d-f346dd876598 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E81 | Level 5 Soffits
c5ebd0a0-1d0d-48f3-b929-012dad773021 |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E81 | Level 5 Exterior Timber Framing
859a85bf-0390-4800-a0d4-55c78f2064e2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E82
8e105bd0-1f0b-4141-a64e-0185cbb2ad4b |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E82 | Level 5Exterior Tiling
e643e971-1068-4663-9de7-b030eaf3187b |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E82 | Level 5 Balconies
7b10a5b7-ca9b-4626-9d6e-704a21d6d645 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E82 | Level 5 Balustrades Installation
9b9a916f-1d0c-4114-976e-10e57bc14831 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E82 | Level 5 Air conditioning
6f10c588-c5ed-444e-8103-fa6f88f58788 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E82 | Level 5 External Plaster - Nibs & Beams
975a225a-609e-489b-8107-98f5cbb03c48 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E82 | Level 5 STO Poly Plaster
1e7ebc07-36a2-4156-89b1-beb4b31ea2a4 |  | checklist-flat | pass | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E82 | Level 5 Eyebrow - Canopy
ba64f5ce-eff5-4ee6-995c-4f7f902a64a9 |  | checklist-flat | pass | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E82 | Level 5 Windows and Sliders
f72bb3fa-bdb2-45f1-adbf-ab9e61569265 |  | checklist-flat | not-started | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E82 | Level 5 Flashing installation
cc803b76-1665-4e23-bd3b-b8c88613fa58 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E82 | Level 5 Brick Works
05a9a16e-a1d0-4db2-9064-a9e4be71a62b |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E82 | Level 5 Soffits
8c394453-a1f3-4392-9992-7c393590968c |  | checklist-flat | pass | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E82 | Level 5 RAB Board
d7ff9b25-e8d4-4774-bbcf-73ee177de1cc |  | checklist-flat | pass | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Apartments | E82 | Level 5 Exterior Timber Framing
92f5013a-34c5-4878-8c2d-b67331f950d5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Water Test
5e5c2079-cb66-476a-baea-7cee38a736a1 |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Water Test | FC - R - Water Test
9585bd2f-42c2-49bf-8082-c96de1e98496 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Passive Fire
0645650d-3149-42f8-aee2-1b775c047bdb |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 5 | North Elevation | Passive Fire | Level 5 Passive fire
4d85a2ef-283d-40f3-a0fc-a6ed9f1ed364 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6
c89a22e0-0d9c-4ba1-9ea0-2974b2947a65 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | South Elevation
dd683cc1-7d7e-434d-ac0c-d37c0edc006e |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Common Areas
1d54a313-00ce-49cc-bddd-cc3ea43e8aac |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Common Areas | Lift Lobby
07826111-955f-4e8d-92da-5aa20d120971 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Services Areas
eaa52519-e911-43b4-9e43-fcf96db8e071 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Services Areas | Services Room
abf5c60f-0a6a-4703-9a9e-5b4a66540510 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments
fa1440cc-517b-4a6e-afa0-0bbe5654708b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69
3fe55940-1d6e-46da-8f26-732b4846363d |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69 | Level 6 Exterior Tiling
f9445ff4-5bbc-4d7d-8241-f67cf5347ecb |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69 | Level 6 Balconies
30da21bf-989d-415a-871e-aa3ae5235dbf |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69 | Level 6 Balustrades Installation
37665dd7-a99f-4dc4-bade-a3698b0681ed |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69 | Level 6 Air conditioning
639e15c4-fa89-41f0-ac00-8bbae322f464 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69 | Level 6 External Plaster - Nibs & Beams
55471a7b-9685-45a7-b597-0d04deced15b |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69 | Level 6 STO Poly Plaster
c23ff827-f3d1-454e-86f8-6825e4e7c590 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69 | Level 6 Flashing installation
3e60605a-8620-4026-9cbc-c81401de68fa |  | checklist-flat | work-in-progress | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69 | Level 6 Brick Works
630911d8-f6d6-481b-acad-86a9b45a0317 |  | checklist-flat | work-in-progress | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69 | Level 6 RAB Board
2b2d7227-aa04-4ccd-bfe5-796c47cfb54b |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69 | Level 6 Soffits
800590df-8161-4d9a-b210-c38e9b753edf |  | checklist-flat | work-in-progress | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69 | Level 6 Exterior Timber Framing
b92dc9ab-24c9-4e67-8389-221f4d731397 |  | checklist-flat | work-in-progress | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69 | Level 6 Eyebrow - Canopy
17bf1039-ae07-4ce5-b91c-2e5c72c9a922 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69 | Level 6 Fascia/Gutter
d598bc34-2a51-4dde-aea1-a63d5cbc9950 |  | checklist-flat | work-in-progress | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F69 | Level 6 Windows and Sliders
e5a1869b-98c4-428a-8d2a-912f786a1484 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71
a39aa93c-88df-4bbd-99f6-2bc131a58c64 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 Exterior Tiling
e1248179-a70d-4cce-8181-d7b8a37b400f |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 Balconies
ead4701d-778c-4f9f-af73-7826da45f1d9 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 Balustrades Installation
d95dd68a-68c4-4848-a5a2-0c30c5e5f07a |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 Air conditioning
80e9955e-80e2-49ae-b5d6-7b516c09773c |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 External Plaster - Nibs & Beams
6afa06eb-87c1-43fc-8796-6f5199550cf7 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 STO Poly Plaster
20ca8854-2b29-45ac-8c75-3af941445be1 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 Flashing installation
a429154e-3611-4b50-ba23-1fbca5d8e404 |  | checklist-flat | work-in-progress | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 Brick Works
75501914-0d39-440c-9609-7a98f25a0c93 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 Soffits
9d3ee33a-b3b9-425d-9c73-bb0dc0be04d6 |  | checklist-flat | work-in-progress | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 RAB Board
155dee41-787f-4871-89b2-1cc99a1cf89f |  | checklist-flat | work-in-progress | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 Exterior Timber Framing
319d0725-b5b7-4df1-a17e-9ba42a0f35d4 |  | checklist-flat | work-in-progress | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 Windows and Sliders
866f8d7a-dd31-460c-a73e-f02264181903 |  | checklist-flat | work-in-progress | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 Brick Works
6a56dd82-5142-46b2-b707-1687f1f6fa6e |  | checklist-flat | work-in-progress | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 Eyebrow - Canopy
e5595ded-3dc6-42ee-a734-e49f20305ca3 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F71 | Level 6 Fascia/Gutter
99684f33-4df8-4a9a-a169-073bb80ba534 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78
44427119-605a-4645-bcda-3f664c071807 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 Exterior Tiling
487b2891-7b70-4a52-bfca-4e9447fe03cd |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 Balconies
d13a5b42-486c-40f0-9e1d-0505e5b5b43e |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 Balustrades Installation
010ee218-def0-4726-be87-b80c32f52c04 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 Air conditioning
88cdef5e-73fc-457b-bcf2-ad05fe2a3d29 |  | checklist-flat | pass | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 External Plaster - Nibs & Beams
cf615903-f547-4ee4-8e7d-279830e4f182 |  | checklist-flat | work-in-progress | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 STO Poren Plaster
66cae60b-4140-4ce8-b7ae-75dc86d6de37 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 Flashing installation
ddfe42e7-6b73-498f-b1fb-3438c1fdacd9 |  | checklist-flat | work-in-progress | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 Brick Works
ddbf7212-953c-400e-983b-7373612cf53e |  | checklist-flat | work-in-progress | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 RAB Board
b954fd3a-73da-4f4e-a282-4bb8f60abf2e |  | checklist-flat | work-in-progress | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 Soffits
84fb32a6-d935-401f-9473-a2fceab3498e |  | checklist-flat | work-in-progress | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 Exterior Timber Framing
0b125301-142d-4983-9b80-d278a82b779d |  | checklist-flat | work-in-progress | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 Eyebrow - Canopy
e0582fa7-0572-4069-abe0-e940de4b12a6 |  | checklist-flat | work-in-progress | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 Windows and Sliders
67547dd3-1b16-4b98-af8b-d2bb5e7c6a3f |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 Fascia/Gutter
2db0eaf5-8ff8-4069-befa-0720890b8a4d |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F78 | Level 6 Waterproofing
bd675963-ace9-49a0-a176-579538ef0aaa |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77
c3942f02-ad1f-4617-b4e3-71f70e7ed526 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 Exterior Tiling
31443638-74bb-40a9-97ed-c62a851847bc |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 Balconies
be68420a-0caa-44c1-9aca-a693a2675cfe |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 Balustrades Installation
8f5d7b29-1d95-4cdc-90cf-5f088bbb9854 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 Air conditioning
0e269a23-7340-47f0-b233-7b6e6ff5d5b7 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 External Plaster - Nibs & Beams
717d7cf6-8de8-4d31-a5dc-cf07ca956528 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 STO Poly Plaster
15a9b84f-deb6-4fba-a740-42b30228d8c1 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 Flashing installation
24b79d10-5030-41cc-8242-862c22a61c57 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 Brick Works
906caa62-81cb-4cd0-963a-10d8848198a9 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 Soffits
3b55f080-f717-441e-b2c4-8fc7ff067b2e |  | checklist-flat | work-in-progress | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 RAB Board
71459997-e50c-4b43-97ef-02f1154e5d5b |  | checklist-flat | work-in-progress | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 Exterior Timber Framing
f6d73d16-c636-42c5-8d36-4452e6a442d5 |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 Sarnafil Waterproofing
c10204fe-7ed4-4fdc-a561-391b74612984 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 Fascia/Gutter
6a6d3825-4461-453c-bd2c-50782a4b3457 |  | checklist-flat | work-in-progress | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 Windows and Sliders
46774be9-ac1b-4be7-8783-0f8fb515ccc4 |  | checklist-flat | work-in-progress | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Apartments | F77 | Level 6 Eyebrow - Canopy
67f87d4c-73e7-4e62-b4a6-0c0e4079984d |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Water Test
e3c57515-0793-4337-8fec-e0a34e75fd97 |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Water Test | FC - R - Water Test
3528fb6f-3ef4-4bc0-8899-bff23ff486fe |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Passive Fire
f0ab3fc2-56c2-4b4a-891f-826a751f6deb |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | South Elevation | Passive Fire | Level 6 Passive fire
d5dc8ddc-3010-4075-ab97-d4db5a6d5cad |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | West Elevation
4d3e8c5a-7c7a-4407-9e14-5d672bce95c1 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Services Areas
8b2203dd-9d95-4b86-809a-4b98e6a08496 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Services Areas | Services Room
db0b2faf-6bc0-489e-a824-47cfac6268be |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments
ba107ec2-7cf9-41d1-9ed1-5c52b95462cc |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74
cf863b91-2032-4274-ae72-6712f7edd84e |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74 | Level 6 Exterior Tiling
59dfa642-7c98-4fd8-a137-2645578968db |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74 | Level 6 Balconies
56fb1319-8712-49e5-bb0b-e951d31fa9c6 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74 | Level 6 Balustrades Installation
e7228358-6ed9-48b9-a07c-7b0fc7250343 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74 | Level 6 Air conditioning
3dc6b73f-efa5-4843-b40a-c894cf0e7962 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74 | Level 6 External Plaster - Nibs & Beams
187a6ce7-f7d2-43ce-8b47-4813b89b192e |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74 | Level 6 STO Poly Plaster
a58abbe1-b85b-490c-984a-3db1812ac61e |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74 | Level 6 Flashing installation
8879a5a4-7b1d-4d83-82e4-87fd947fca5c |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74 | Level 6 Brick Works
1dc98302-d33d-41be-94dd-9409a086429d |  | checklist-flat | work-in-progress | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74 | Level 6 RAB Board
243f27cd-06a3-41a7-9e8b-17d32774438a |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74 | Level 6 Soffits
5717e57c-b7c9-424d-a966-76b40f9e3d4c |  | checklist-flat | work-in-progress | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74 | Level 6 Exterior Timber Framing
d5b46b9f-617b-4d0b-8898-933ce2a98976 |  | checklist-flat | work-in-progress | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74 | Level 6 Windows and Sliders
eb4f5ad3-7eff-40d8-9562-b75b44d3c9a5 |  | checklist-flat | work-in-progress | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74 | Level 6 Eyebrow - Canopy
6bc58d13-5e89-4efc-9a52-77738bd7bdc6 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F74 | Level 6 Fascia/Gutter
5261e443-0337-4be4-a6d6-e2f57c2c9ada |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F75
ce628ccf-dcd5-425c-8b90-66d39a4819e8 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F75 | Level 6 Exterior Tiling
3cfe0fa8-6d86-4dc7-a160-c41dc814abdf |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F75 | Level 6 Balconies
4e17608a-f506-4c84-babf-867c8bfbb125 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F75 | Level 6 Balustrades Installation
57c9b747-9154-47ec-84fa-f24427676bd7 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F75 | Level 6 Air conditioning
30ec554a-106b-4f89-9732-972a58a99808 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F75 | Level 6 External Plaster - Nibs & Beams
f8db6870-2d9c-4acd-bc72-64dc3fa5eb3b |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F75 | Level 6 STO Poly Plaster
e68d7663-dc75-437a-a438-0ba2cedb3a4d |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F75 | Level 6 Flashing installation
5a6f76ad-c9eb-4c6f-985b-8fe9198480d6 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F75 | Level 6 Brick Works
49ff7bba-2562-4cc6-9e1b-1c235ab10da5 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F75 | Level 6Soffits
eb3ba88f-ebef-4e50-bbf1-8639470936a5 |  | checklist-flat | work-in-progress | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F75 | Level 6 RAB Board
0dfd1f92-bb80-4c8f-8b64-436992cd9a97 |  | checklist-flat | work-in-progress | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F75 | Level 6 Exterior Timber Framing
03cc765e-93bc-4547-8fe8-1c76c0a14e69 |  | checklist-flat | work-in-progress | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F75 | Level 6 Windows and Sliders
1f60fb34-4a00-42e5-bb5e-8e02e68b0bea |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F75 | Level 6 Fascia/Gutter
389dde90-1030-4023-a3eb-6489c24416f7 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76
04052103-85ca-4b18-afe3-d8ce840c7b22 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6 Exterior Tiling
ee75d127-6518-4d9f-9c3b-740b2d498e48 |  | checklist-flat | work-in-progress | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6 Balconies
6de009a0-49b8-43d7-a87a-3ae0abc382e9 |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6 Balustrades Installation
53dea611-a958-4b68-a1db-f88231c9e136 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6 Air conditioning
b8c2eb24-1081-45e8-bfb1-36b9bd5b36b1 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6 External Plaster - Nibs & Beams
d042750f-e371-4eae-a51c-e7536ab967bc |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6 STO Poly Plaster
8d939afb-602c-4f5e-a457-a59c4d388cf7 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6 Flashing installation
7ff788db-f398-4f53-a446-ffb997b9512d |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6 Brick Works
030591dc-7e78-46d3-ae74-2397f190f2d3 |  | checklist-flat | work-in-progress | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6- RAB Board
3861c67a-d8d8-4961-93cd-8b8e300ae592 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6 Soffits
ae905fe2-f4e1-4f7a-9fc5-de4064e94969 |  | checklist-flat | work-in-progress | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6 Exterior Timber Framing
f7af35db-5ac2-4832-837b-d03ca270d2ff |  | checklist-flat | work-in-progress | F - R - Waterproofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6 Sarnafil Waterproofing
35f392bd-96a7-46c5-88c4-173774e5487d |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6 Fascia/Gutter
27a202bd-c9f2-467b-9901-3808091c0f28 |  | checklist-flat | work-in-progress | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6 Windows and Sliders
7216aa43-f4b0-449a-adb0-11c169a0dc38 |  | checklist-flat | work-in-progress | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Apartments | F76 | Level 6 Eyebrow - Canopy
ba8ddb22-f304-42a6-92bb-aa31b6d73a52 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Water Test
f6b470a5-06cf-4a90-b864-83e18c81f5eb |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Water Test | FC - R - Water Test
9dcc8912-2077-4fe6-a578-fd76ff9f46cb |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Passive Fire
6051b2a0-7bb0-43fe-a8aa-ecd6df859f64 |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | West Elevation | Passive Fire | Level 6 Passive fire
4633d356-6890-4690-918b-51502feb0b11 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | North Elevation
964db73a-af7a-408f-921e-2d30308fcbb9 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Services Areas
d9d48113-e9be-492a-853d-5cc805435c65 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Services Areas | Services Room 01
e3f6736b-a473-4869-a049-2a587caa38a7 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Services Areas | Services Room 02
7c5919e9-ba50-42dc-839e-28ba1432e1e7 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments
92c0aa7a-31c2-40a2-9250-25e222e81ca2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70
c87112ba-3b48-4fdd-84f6-8a1b4ddc80b7 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70 | Level 6 Exterior Tiling
e4bf539e-71f5-4535-a1e0-28d0763c4757 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70 | Level 6 Balconies
49710fb8-5f51-43f3-844c-109387c8d4ae |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70 | Level 6 Balustrades Installation
57bae328-5777-4b96-b55e-84790af780a6 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70 | Level 6 Air conditioning
19e5460c-f15e-4ccf-bb1f-f8d75d11c34e |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70 | Level 6 External Plaster - Nibs & Beams
8ebe4c1f-f030-493c-9080-e635503c5cfd |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70 | Level 6 STO Poly Plaster
b1f0efab-0967-4f30-87ec-9e769a7490ed |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70 | Level 6 Flashing installation
507f874c-ebc7-48df-8dc6-eafa9a6256ef |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70 | Level 6 Brick Works
2c438781-ca19-4315-958d-45660606c970 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70 | Level 6 Soffits
130f0604-e5e8-4fb8-9bbd-3644e1e4adc5 |  | checklist-flat | work-in-progress | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70 | Level 6 RAB Board
062d4722-2195-4195-abe5-143aaf3731da |  | checklist-flat | work-in-progress | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70 | Level 6 Exterior Timber Framing
678f3de3-2040-4ec1-9b1d-4708202cd2a1 |  | checklist-flat | work-in-progress | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70 | Level 6Windows and Sliders
3dad0dd3-27bb-4f65-baaf-71d9aad539ec |  | checklist-flat | work-in-progress | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70 | Level 6 Eyebrow - Canopy
19ef4b58-6951-4565-9fb6-9687907fa5c1 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F70 | Level 6 Fascia/Gutter
aef70106-ca24-4880-bb61-e92548775a4e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72
1d63d388-b925-4b17-8181-02bf1f29dc42 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72 | Level 6 Exterior Tiling
c57cea89-4e3c-4af7-ae49-4286ec62b185 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72 | Level 6 Balconies
770de69c-7a73-49b5-ab7f-07f3d7896a9e |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72 | Level 6 Balustrades Installation
ade8e207-3eb4-41b4-bc3a-6d9a47001cfa |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72 | Level 6 Air conditioning
db3499d3-2eb2-4eb9-950d-8c9bbf41451d |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72 | Level 6 External Plaster - Nibs & Beams
d6ab4d32-25f1-4363-820d-a990b3344245 |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72 | Level 6 STO Poly Plaster
7f51e790-5cdd-4d91-847b-327d3f66dc71 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72 | Level 6 Flashing installation
da304107-4650-42fc-8db4-d9bd55a130fa |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72 | Level 6 Brick Works
64fbd9ba-8661-40c3-a538-a4e3ede2027b |  | checklist-flat | work-in-progress | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72 | Level 6 RAB Board
e1b08e3d-689f-44cd-a34a-6b7b56059e18 |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72 | Level 6 Soffits
29b58f1b-d034-461b-a122-f2148f03296d |  | checklist-flat | work-in-progress | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72 | Level 6 Exterior Timber Framing
8d002468-6c61-4f10-881e-5e36643077e6 |  | checklist-flat | work-in-progress | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72 | Level 6 Eyebrow - Canopy
851f512b-01d4-410d-9412-01e10b66c9a2 |  | checklist-flat | work-in-progress | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72 | Level 6 Windows and Sliders
5b5f2a48-77a8-490d-89e4-914e4e5523d4 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F72 | Level 6 Fascia/Gutter
79174529-08c9-4135-9d81-b7e9c44e50dc |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73
03e30156-4e47-4a6a-948a-cf0af297a695 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73 | Level 6 Exterior Tiling
24d5f9aa-5223-42b2-807a-39ced4b405c0 |  | checklist-flat | not-started | FC - R - Balconies | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73 | Level 6 Balconies
7341cc08-dd08-4402-a6e8-264518998d5e |  | checklist-flat | not-started | FC - R - Balustrades | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73 | Level 6 Balustrades Installation
4dbaca2c-699c-4c27-9feb-6f4c3e9f9b90 |  | checklist-flat | not-started | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73 | Level 6 Air conditioning
e206955a-6430-4abc-8097-58e9527c5233 |  | checklist-flat | not-started | FC - R - External Plaster - Nibs & Beams | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73 | Level 6 External Plaster - Nibs & Beams
65bed1d1-57a9-4afc-914a-371dfde8a1fa |  | checklist-flat | not-started | FC - R - STO Poly Plaster | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73 | Level 6 STO Poly Plaster
6bd49358-7008-4cb0-9ff5-4775a7c6a5d3 |  | checklist-flat | work-in-progress | FC - R - Flashing installation | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73 | Level 6 Flashing installation
3e29e657-6556-4f29-a424-0d0aef96cb87 |  | checklist-flat | not-started | FC - R - Brick Works | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73 | Level 6 Brick Works
ac8eabed-dae5-4bf0-91d9-c41dc9b4aebc |  | checklist-flat | not-started | FC - R - Soffits | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73 | Level 6 Soffits
3c5073ce-457e-4854-b30f-0bff1750bd8b |  | checklist-flat | work-in-progress | FC - R - RAB Board | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73 | Level 6 RAB Board
a6cbc0a1-fb00-4c7c-95e5-42209adda775 |  | checklist-flat | work-in-progress | FC - R - Exterior Timber Framing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73 | Level 6 Exterior Timber Framing
e51a03a5-2e5f-46a1-a7a6-4d06da1cf4b7 |  | checklist-flat | work-in-progress | FC - R - Fascia/Gutter | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73 | Level 6 Fascia/Gutter
c7e24521-cebd-49d5-8b35-3cec8b74c796 |  | checklist-flat | work-in-progress | FC - R - Windows and Sliders | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73 | Level 6 Windows and Sliders
b533eb7c-251a-4d6f-ac93-5f30eeff1ba3 |  | checklist-flat | work-in-progress | FC - R - Eyebrow - Canopy | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Apartments | F73 | Level 6 Eyebrow - Canopy
e1b003f8-ef73-4790-9b73-180b874af0de |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Water Test
85981ce6-a1e3-4074-b123-acbdf74fd981 |  | checklist-flat | not-started | FC - R - Water Test | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Water Test | FC - R - Water Test
ce8d4805-592e-464f-9770-e17eb334368e |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Passive Fire
8c58ad55-2ce5-4f02-98ac-e23c9442a45f |  | checklist-flat | not-started | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Facade | Level 6 | North Elevation | Passive Fire | Level 6 Passive fire
c3c575cf-9786-4e4e-a5cd-4cc4028c0bf7 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Facade | Lower Roof
55af3ce3-448d-4028-aaa1-7b0da86f4f01 |  | checklist-flat | work-in-progress | FC - R - Roofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Lower Roof | Lower Roofing
0ed51336-efbf-4425-a0cf-c93880e44e79 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Facade | Upper Roof
edb8f95e-f39e-46cb-96c8-371c7e5e9ec7 |  | checklist-flat | not-started | FC - R - Roofing | checklist-flat | FALSE | FALSE | Building B08 | Facade | Upper Roof | Upper Roofing
37711a09-7c77-4def-9030-8b51c0a8d55d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services
a925b820-54fe-48d0-87d7-e77492092b2b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 1
1e1c3452-e7fc-4206-8ebd-8c158414c621 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas
aa89528a-5b01-4409-90eb-52a66a2ddd0f |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor
06138c6a-a282-4408-a2a1-b8c9f81f0bf6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Pre-line
53fc0967-5731-4d06-aa22-b94748b45c35 |  | checklist-flat | not-started | dfeb2f028ee0a6897a335405fc7b2a92664b26edef7fe040776c40a36aa4b748 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Pre-line | Internal Strapping and Framing
36b0b6f5-85d6-4c66-b44a-ec51ad6a9373 |  | checklist-flat | not-started | dfeb2f028ee0a6897a335405fc7b2a92664b26edef7fe040776c40a36aa4b748 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Pre-line | Suspended Ceiling
5e6dfbbe-4485-4438-a3fa-6fae34809807 |  | checklist-flat | not-started | dfeb2f028ee0a6897a335405fc7b2a92664b26edef7fe040776c40a36aa4b748 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Pre-line | Internal Doors
409515a7-7ebf-4c30-a816-16c78ad11510 |  | checklist-sectioned | not-started | a86d64217a4cd5d4362ebe8a2736e92d632cf4df3ceaffcc25cd7e9d20c90f64 | checklist | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Pre-line | First Fix Services
c3b9ad5a-2a40-441a-99d6-042a2f17e536 |  | checklist-flat | not-started | dfeb2f028ee0a6897a335405fc7b2a92664b26edef7fe040776c40a36aa4b748 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Pre-line | External doors and windows
5414dcca-4de9-47e8-b870-2ce64020aca8 |  | checklist-flat | not-started | 69fc5f65f4eb78b7ab41eeab4ccba6b67a12a46982c93b17c55c1e98b3bdf23c | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Pre-line | Insulation
3cb7ae58-e537-4261-b220-9859cce7a738 |  | checklist-flat | not-started | ed970cc82cb9ca07076eb958225750f8ea19d08f84837a60f6586112e6a74b4b | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Pre-line | Passive fire/Approval to line
304e79b9-bd03-47b5-9df5-6c12dcb216b6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Post-line
e1b2e8fe-02ff-4772-816e-27ab076b840d |  | checklist-flat | not-started | 6fdab81d418a1e8d60c755e4cb80e1f6bafa8e4f964f8172dbf2dd676efc1600 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Post-line | Lining
d390bc6d-d6ca-4584-86cf-dd268dcc591f |  | checklist-flat | not-started | 23829b41351bee7573d7e45c64d2e034242a2051a45690f7aa56dc90c152f742 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Post-line | Stopping
dbab451b-999d-425a-9771-2855696f103d |  | checklist-flat | not-started | dfeb2f028ee0a6897a335405fc7b2a92664b26edef7fe040776c40a36aa4b748 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Post-line | Finishing lines
ec69fb6a-8eec-4783-8586-3863a55d279e |  | checklist-flat | not-started | dfeb2f028ee0a6897a335405fc7b2a92664b26edef7fe040776c40a36aa4b748 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Post-line | Flooring
8d6abcd0-8ddd-4e52-8643-45d0912fcc5e |  | checklist-flat | not-started | dfeb2f028ee0a6897a335405fc7b2a92664b26edef7fe040776c40a36aa4b748 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Post-line | Painting
f77a4df3-f3b6-4cf5-abed-81d200307ab2 |  | checklist-sectioned | not-started | dd8aebb5a345904c4edd3308dd130ef1b875e51e6eae03c08b531afde2ded4b0 | checklist | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Post-line | Second Fix Services
f76d147e-80e6-4d5a-b769-9aa6dee0a5d5 |  | checklist-flat | not-started | 961f3e49ab2a89e9523e32b38d4d7120357e7a98b41e90873a5e396df6d691f0 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Post-line | Fire Door
8fea1d7c-9689-4cfa-adff-f1d452743bb1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Finishing
f1acde1d-2e88-44b1-9726-62caa5c3ead8 |  | checklist-flat | not-started | dfeb2f028ee0a6897a335405fc7b2a92664b26edef7fe040776c40a36aa4b748 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Finishing | Flooring
89d83097-0b2a-44e6-80e6-43bdc2ad7a45 |  | checklist-flat | not-started | 520fbf452c06e389f4e7f3dc4d8cbe72e0cc76c04aebf23369ad26d92f41fb7e | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Corridor | Finishing | Hallway
93128fa3-ba8c-4c97-ab8e-449d71c8bda1 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Lift Lobby 01
887d9a44-f4b4-4335-945c-8fc1fa07ed5d |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Lift Lobby 01 | Level 1 PRE-line
a2ca5d75-0e8e-4239-935d-0a1ad8700755 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Common areas | Lift Lobby 01 | Handover
a836ef6c-afe4-4578-9970-6e28b8f5f2a9 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 1 | Residential areas
236e6826-8ce9-4e7d-9cc3-4271a153402a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 1 | Residential areas | Apartment A69
e92d33fa-0a69-477b-ae0b-d8065db12671 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Residential areas | Apartment A69 | Level 1 PRE-line
3024bb0b-cd9e-4e00-b005-778db9c33b59 |  | checklist-flat | work-in-progress | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 1 | Residential areas | Apartment A69 | Handover
660ec541-97c9-4b09-add4-98af40fa6a2f |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 1 | Consultant Inspection & Test Reports
477f726b-e36d-4af0-8bdf-354866a0f9bd |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2
70d334c5-5365-4042-8638-d47ae50ba369 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas
f8f09d1a-56f8-4d91-b96e-3899435f8f76 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Lift Lobby 01
b183b796-cac9-4de0-a685-3140cb9d9c40 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Lift Lobby 01 | Level 2 PRE-line
e50af0ac-af5d-47d4-b179-25a612c47ab5 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Lift Lobby 01 | Handover
e994e089-f623-4e17-a6f4-7bd8fe76ad0f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Corridor
2485b25e-c159-4bff-9130-2d87e99e6eb8 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Corridor | Corridor 01
b0d99933-1c65-467e-8239-a32ca6fdfab0 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Corridor | Corridor 01 | Level 2 PRE-line
3009a1da-cbf3-4d3f-a8c9-ed98344889d0 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Corridor | Corridor 01 | Handover
cec061ba-eac0-45be-af00-3e20be3ddbb8 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Corridor | Corridor 02
9a351a25-0f44-4bfe-9070-3056fc7215bb |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Corridor | Corridor 02 | Level 2 PRE-line
186042a8-369f-4c5b-b3c4-4792d6349f82 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Corridor | Corridor 02 | Handover
6cb08b2c-686c-4aec-8b92-8d619afbfe70 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Corridor | Corridor 03
2535577d-cf0c-44b1-a8e6-ae197d4f0c56 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Corridor | Corridor 03 | Level 2 PRE-line
15d5d071-56f1-4edb-98df-1218490be55d |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Corridor | Corridor 03 | Handover
4a95ad5a-b7b9-4291-9077-c29e3c3886f8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Lift Lobby 02
8227bab1-35df-404b-88c4-835398a82c2b |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Lift Lobby 02 | Level 2 PRE-line
0bf3bf74-d585-4f5a-a7b8-e2169482641c |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Lift Lobby 02 | Handover
5152c646-5095-497f-8680-6340547a7744 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Carpark
30f6c2f7-42e6-4f47-ab85-71f111579be3 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Carpark | Level 2 PRE-line
c08ee92c-fb85-4b78-88f1-93208e888b25 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Carpark | Handover
9b49075f-d3c4-47d4-a915-009cd6d253a8 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Stairwell 01
da834881-774f-435a-b650-84398898dff9 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Stairwell 01 | Level 2 PRE-line
7ca9ca29-3143-4f41-81f6-d2df941d2ea8 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Stairwell 01 | Handover
ad57a800-ab88-4c21-ba17-4024a9133bd1 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Stairwell 02
ca201813-66f3-4d1a-be6b-30a59004b0cc |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Stairwell 02 | Level 2 PRE-line
a2603cc1-3ca0-4da1-84ab-8e23d5f05cee |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Common areas | Stairwell 02 | Handover
f60adacc-db4e-4c0f-adf3-f8c64ba5de07 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Service areas
ed8ee8d6-31e3-4da0-bfc5-fc3cd8565e3c |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Service areas | Gardeners Shed
271631d0-6264-4fad-b1e9-ea7ae92887a1 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Service areas | Gardeners Shed | Level 2 PRE-line
68318958-7f7c-4d20-b943-7b3df415b2e0 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Service areas | Gardeners Shed | Handover
352a34f1-e4b0-4940-83ed-6a82b8f3dbd9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Service areas | MSB
468f21d9-46a1-4d8a-a218-8e0b7004cef3 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Service areas | MSB | Level 2 PRE-line
71490204-eddd-46a4-915c-2765d67c6c9a |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Service areas | MSB | Handover
fb0b9aba-fa68-4906-8096-ffa7aee4af4f |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Service areas | Bin Store 01
a35dd1ee-f0d6-4324-b876-b25ce3c8b1ad |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Service areas | Bin Store 01 | Level 2 PRE-line
2adbb9bd-6eab-4603-b542-78f9f2809405 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Service areas | Bin Store 01 | Handover
7e3fc98c-b089-4789-9588-7cd252448834 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Residential areas
035795c3-5e3a-4e5f-bb4e-2a7a70fe6908 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Residential areas | Apartment B69
28581e77-365d-41de-841f-8affb264ceff |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Residential areas | Apartment B69 | Level 2 PRE-line
5142af91-412d-4cb2-91e4-cc7649983041 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Residential areas | Apartment B69 | Handover
fbb0bbf7-0e3a-40ab-b570-f028f5551740 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 2 | Residential areas | Apartment B70
d62f1618-c67d-4646-8ba0-69880d9738ff |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Residential areas | Apartment B70 | Level 2 PRE-line
30233c46-05c2-455a-9e7b-be646ff331c1 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 2 | Residential areas | Apartment B70 | Handover
d23712ca-1fe2-4e7b-b3d6-505320e5a66d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3
1dc06adc-a5cb-433a-b095-d9692002de71 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas
03da44f7-4413-4e98-a5f1-8ebaacb0190a |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Lift Lobby 01
0890bacf-4418-4824-bbf1-a706ddb9ee93 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Lift Lobby 01 | Level 3 PRE-line
c4b0813b-def1-4592-9be3-d7a5f7011b89 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Lift Lobby 01 | Handover
ce15df52-d544-4b42-83aa-de61e8d5c377 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Lift Lobby 02
2ee0d453-fe23-4384-90de-91ba74fff4fe |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Lift Lobby 02 | Level 3 PRE-line
7ebebb32-c0d4-4606-8619-a890124e67a1 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Lift Lobby 02 | Handover
f9743dee-013b-4bf7-89a4-8dc1d9a32bb5 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors
482528ba-d867-49cd-b902-e20e1e575b63 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area A
38021dd1-56f6-4dbf-8ddc-ece808c0748e |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area A | Corridor 01
bdb2ab9b-8439-4935-b8e5-f28ed6a87756 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area A | Corridor 01 | Level 3 PRE-line
c03c8ee0-1e51-4efc-90b7-62930642af3b |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area A | Corridor 01 | Handover
2ab89a4f-e2b9-4f93-a598-3883b3c85b63 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area A | Corridor 02
bdcd83c3-7fc3-420b-b7ee-d5c94d8db940 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area A | Corridor 02 | Level 3 PRE-line
53ef5b4d-d348-47db-94c5-5e723b6538b4 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area A | Corridor 02 | Handover
0954cd61-e795-480f-ad88-0813187661c4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area B
9a12f963-2d4e-4f0d-a6d3-46abaf12ecc9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area B | Corridor 01
0ea62498-c8f6-45ab-a853-c866645957e0 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area B | Corridor 01 | Level 3 PRE-line
8b8cf1e1-c567-4f5d-aef9-d84719e9ca84 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area B | Corridor 01 | Handover
42b8db80-54c2-4143-8656-7c6f7083a967 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area B | Corridor 02
ba36c11e-fbda-40b4-b1f9-481ca1d0f3b5 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area B | Corridor 02 | Level 3 PRE-line
72a0ce33-dcbd-4445-8221-381c4b614a9c |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area B | Corridor 02 | Handover
7c8c83e0-28f3-4975-8792-6ff675186046 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area C
f1d26eb1-fb74-422f-89dd-5bb557e8b72a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area C | Corridor 01
99e6cfdb-6a92-402f-961f-fbf428a380ee |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area C | Corridor 01 | Level 3 PRE-line
142289a8-a2fc-481b-b031-b7247a92e20d |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Corridors | Level 3 Area C | Corridor 01 | Handover
f71ff30b-3a03-4194-aee6-b1da8e849014 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Stairwell 01
792b6190-580e-4a7f-9a1b-4c03c5a4fab0 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Stairwell 01 | Level 3 PRE-line
7fb8a7a1-f8b5-404b-be61-50c0fcf057b9 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Stairwell 01 | Handover
5dc2316a-5f45-4e69-b452-40da40537f0f |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Stairwell 02
7e7703ed-f9ac-48dc-a656-d97f44baf4c4 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Stairwell 02 | Level 3 PRE-line
188f8e0c-c5ac-4102-b352-47f220422c82 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Common areas | Stairwell 02 | Handover
fad369ff-c505-46dc-9048-2ff12696e913 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas
5e28526d-e44a-47ec-9326-87b9dd3fcb3f |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area A
be8ab8a9-90bf-4844-b7ce-274730935d8d |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area A | Electrical Room
2e3430b4-76af-408f-a0e4-c6d65b4be2d2 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area A | Electrical Room | Level 3 PRE-line
e241abf1-b042-4b8f-a3c5-30177e10dcb7 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area A | Electrical Room | Handover
a607b621-82d9-4926-9021-9ad244c4f2b6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area A | Services Room
939c179e-ce54-48fb-ae0c-001b4065a45e |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area A | Services Room | Level 3 PRE-line
c79665ba-4fe5-46ba-894a-5bf7f518d9e4 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area A | Services Room | Handover
4cd79e1a-7bc0-4c02-8270-a4420528dde2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area B
111dc429-f57d-4594-b141-426a62785703 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area B | Comms
547f92c3-38eb-44b3-96d2-135f3e04c336 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area B | Comms | Level 3 PRE-line
e708d5b0-7a54-44b2-a35b-a673d07ed8d6 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area B | Comms | Handover
90a93b30-1ede-45bd-844f-1efb2665cbfb |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area B | Services Room
34f781cb-b2a4-47a3-b520-89fd244c158b |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area B | Services Room | Level 3 PRE-line
aeda75f5-f29a-48ff-82c9-24091dc4e058 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area B | Services Room | Handover
113ccda1-b574-46c6-9159-7b993e5d1f3e |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area C
e2809799-0ea6-422c-a99a-d15029609b97 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area C | Electrical Room
302143e9-d644-42f7-9c88-76181f972bc0 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area C | Electrical Room | Level 3 PRE-line
520d7466-51dd-420f-857c-426e03442949 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Service areas | Level 3 Area C | Electrical Room | Handover
ba1ce7e2-7def-4653-9d3b-a13f0fa77043 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas
22de38a3-655d-431f-9377-21f6c7375161 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C69
678ecffc-377e-4721-8fb4-c355889d9803 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C69 | Level 3 PRE-line
e42fdf74-92f6-4297-8d44-4c339a77f566 |  | checklist-flat | work-in-progress | 6a50f93579cfaf69850f7dc6d14e8b4e6f79c15018bb6c1f9dc731c9ed867501 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C69 | Handover
e09eb903-41e1-41e7-a1c1-0e072fc45201 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C70
9f8f2fa7-1a94-4081-b496-f49626285916 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C70 | Level 3 PRE-line
cbe04bc8-213d-417b-8b45-760e80fcda9f |  | checklist-flat | work-in-progress | 6a50f93579cfaf69850f7dc6d14e8b4e6f79c15018bb6c1f9dc731c9ed867501 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C70 | Handover
c444aa77-1f49-43cc-aa09-6629c540614c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C71
a9425687-e7f5-4507-9a63-00324bae6011 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C71 | Level 3 PRE-line
793127f7-ae49-4130-8cfb-e86114494202 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C71 | Handover
5c72172a-1399-44ba-8f51-241bfa45fcb6 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C72
7c219ecd-c506-49b2-9297-07133b77e49a |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C72 | Level 3 PRE-line
df7ec065-ee8f-413e-880b-562b21b1131a |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C72 | Handover
7b6bed45-39a9-4ef7-8b99-798b598439b7 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C73
92567ca2-26d2-4e00-8224-a6c2c7128350 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C73 | Level 3 PRE-line
e8aae915-87d3-4ee7-b82a-40cdefc47d77 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C73 | Handover
d6abf019-df7c-4096-86d0-68219a379cb6 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C74
af6ea055-119e-483a-8674-db06ce8db5d8 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C74 | Level 3 PRE-line
d3bb506b-bf4e-4d28-9322-ccd73ac6d307 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C74 | Handover
17aa1031-d9ea-419d-b3f8-5f2da81d9e02 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C75
1d5c4bce-2ccc-40c8-bcca-d548b318b439 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C75 | Level 3 PRE-line
e8453170-49ee-44e9-bba5-15748dd4ffc5 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C75 | Handover
a2c5aa91-1fba-4d98-a27a-e8c0fe722f06 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C76
32ccdf1b-c666-4d31-bc95-db65577f0c5d |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C76 | Level 3 PRE-line
b975cb56-6162-4661-9a9c-0a6fb61da9c1 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C76 | Handover
02735d03-362b-4757-b785-a29a25692535 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C77
e48b8566-2df2-4a5c-b4e3-a732eab78e13 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C77 | Level 3 PRE-line
8c37e8a1-ab49-493f-a1f1-5c369e153b6a |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C77 | Handover
bc9038d7-c1eb-4e65-88e8-c5f60d566083 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C78
eb120d49-df75-4f17-baac-7fcb5e81305f |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C78 | Level 3 PRE-line
01fa37a4-6b09-40ec-8fcc-152dec95910b |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C78 | Handover
1cc089a2-292e-4f88-b187-742cee8f8a19 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C79
ac05e0d7-f3f6-4c4c-b534-ff00d0131b22 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C79 | Level 3 PRE-line
cfb122c0-db85-4201-91c8-01fb00551f1c |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C79 | Handover
c4948f81-5e28-481e-9bee-a305bdbb87d3 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C80
ffe0a80e-261c-4de8-86a4-193ca010fee1 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C80 | Level 3 PRE-line
0036f1da-149b-4111-b230-a92f4f5db85f |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C80 | Handover
714f90ec-d732-4867-a454-e03b1fbadcb0 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C81
085ad4f4-3d36-4145-9783-f71a69bfff14 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C81 | Level 3 PRE-line
23f5069b-e7be-4639-bd28-22c97bebf4ed |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C81 | Handover
9063bdf2-70e4-429a-9187-3c4c53c81eb8 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C82
e7d00ff8-0a15-45a1-9f3c-96146a481c02 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C82 | Level 3 PRE-line
357771d1-2921-4efb-a50f-48a14d5d0bd4 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C82 | Handover
1cc921c7-38bb-4fe7-b700-982bd5297a36 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C83
17dcdeb4-f809-4b07-b331-a3d1445c5ab9 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C83 | Level 3 PRE-line
76943566-cb7c-4d62-8b67-11529d1bbdbd |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C83 | Handover
f126ccc4-16d5-41d4-b137-c9817178eefa |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C84
a5b2e5bb-3d93-4fa3-be41-89c804c72846 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C84 | Level 3 PRE-line
2ff22e8c-c2dc-431a-9ee9-8c127f3e57c0 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C84 | Handover
98a46a19-b370-492c-b983-db3fb2b40947 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C85
322c2294-c190-4356-885d-6a2866302c5c |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C85 | Level 3 PRE-line
4204ec4b-9ae1-4c9c-a0ac-8d496c0f64c3 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C85 | Handover
9a19bcd0-f0cf-48ad-8bf5-32457031594b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C86
e3e8fe4c-998a-4de6-b4f3-1730796afed1 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C86 | Level 3 PRE-line
75eecf86-6476-492b-9a76-d3349954fde7 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C86 | Handover
608e9fc6-b349-4f3f-a451-46ad8184265c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C87
b0bf5bcf-5760-4e59-9d4e-37cf4c21fb57 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C87 | Level 3 PRE-line
29c32675-24f9-43b5-a335-f20da12e8b6d |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 3 | Residential Areas | C87 | Handover
de77826c-d9bf-44be-9a7e-cc2bcfaef796 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4
5eb4f43b-5dc7-471d-b75a-dccfd3b4b7d6 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas
52907de0-e310-4baf-adbe-7f922b10a908 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area A
8f2258db-6430-4005-ac77-7aea0b37201e |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area A | Electrical Room
42853caa-ae2c-4406-a4fc-a57a7994174b |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area A | Electrical Room | Level 4 PRE-line
ea035140-b244-40d8-a673-6518b77e3b7e |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area A | Electrical Room | Handover
aa03ef22-7097-4f80-830a-30901c14c028 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area A | Services Room
06a1c559-dca5-4986-80c9-33aaaef3c321 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area A | Services Room | Level 4 PRE-line
0206885d-f7fe-42f1-a40b-686184a02c05 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area A | Services Room | Handover
bdfc5825-7d01-4207-9108-9b08f58c421e |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area B
82ba73f0-1213-4a7a-a1a4-d649f5ae9cde |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area B | Comms
af8bcb30-99fe-43ee-8853-343e91b6a101 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area B | Comms | Level 4 PRE-line
9426fc04-68e0-4ed5-9111-aa7fe10e735a |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area B | Comms | Handover
c4056970-51ff-451f-896a-f0126ed56cae |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area B | Services Room
5312afd8-0197-48a7-b2e4-5275f2a18781 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area B | Services Room | Level 4 PRE-line
861b2e34-2c6d-42a2-be51-bfccfd844d47 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area B | Services Room | Handover
13cc8f9b-d089-4aee-8c3c-689ce83b1549 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area C
6800ae15-0477-421a-a2e7-1775a0a9d452 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area C | Electrical Room
cdd11409-a693-4e6c-873e-668fdbd97d3b |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area C | Electrical Room | Level 4 PRE-line
d89fd092-f6bc-4e6e-8a07-bb297521ae26 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Service areas | Level 4 Area C | Electrical Room | Handover
2db7be6a-bcbd-4e22-9c0b-90f2f401fd6a |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas
8fe57257-038a-4e63-a9c1-14f935b092cd |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Lift Lobby 01
1fc1c0ab-a259-4ceb-be5c-2ba1a2aa4827 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Lift Lobby 01 | Level 4 PRE-line
e9a5748b-33f8-48aa-8b19-f788fda63863 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Lift Lobby 01 | Handover
dfac798e-e700-4029-85e2-19c8c1e4adea |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Lift Lobby 02
8400b66e-203d-4304-b3f0-d0bf81a66641 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Lift Lobby 02 | Level 4 PRE-line
affc7f08-8704-4a70-9468-50fc1f19ead6 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Lift Lobby 02 | Handover
8f1a2d07-17d8-4349-a9e5-145239ec18b5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors
08f669fd-acb9-4a60-a4c1-a6878bfdae5b |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level 4 Area A
f5133d8a-6fb9-4f61-a363-6cadda2ff96b |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level 4 Area A | Corridor 01
23a17819-28cf-425f-a335-9915a92f2b9b |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level 4 Area A | Corridor 01 | Level 4 PRE-line
498a5bb6-7658-406e-9423-bc6ad68365b8 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level 4 Area A | Corridor 01 | Handover
1cf500de-1d85-41ab-8540-47901576cd60 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level 4 Area A | Corridor 02
3ef0aa41-f33e-4cef-b3a7-a1b10b0d2ab1 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level 4 Area A | Corridor 02 | Level 4 PRE-line
b3848264-b66d-4eb4-8ad9-fc55d804c3ba |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level 4 Area A | Corridor 02 | Handover
d20afd70-b6da-42e1-8fc5-7028260a0625 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level Area B
bd7e7431-68ba-4729-aef6-68bf1d8aa2c0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level Area B | Corridor 01
38bc0b3d-c893-475c-88af-424ca5ed06ca |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level Area B | Corridor 01 | Level 4 PRE-line
bacc0748-92a3-4a26-9f88-b2eb80e0438f |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level Area B | Corridor 01 | Handover
148a7bb2-b2a8-441e-8971-1baab2a45f2d |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level Area B | Corridor 02
c3d77897-11db-4181-bfe7-7ac041b82cb4 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level Area B | Corridor 02 | Level 4 PRE-line
dcf76ec8-5771-472d-8c5d-21a8f61de00e |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level Area B | Corridor 02 | Handover
bb4bb6ac-bac5-4aa5-92e4-8c4010bcf36d |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level 4 Area C
5cc1eff3-d682-4721-94ef-a8a292c05bea |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level 4 Area C | Corridor 01
f5f605c8-b39c-4591-9727-401a8cbf1704 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level 4 Area C | Corridor 01 | Level 4 PRE-line
a79df905-95bd-46a9-9cc6-4916659b0a99 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Corridors | Level 4 Area C | Corridor 01 | Handover
057877e8-c88d-46bb-8009-58967d3d8f25 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Stairwell 01
ab143682-5efb-43d5-9ca8-29d29f7a10eb |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Stairwell 01 | Level 4 PRE-line
c1d89654-e1ca-40b0-a884-dc69a3664d29 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Stairwell 01 | Handover
51e79ca1-b1ac-44d4-b722-30cb9fd7e8da |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Stairwell 02
8aeee69e-d355-4526-86a9-ea97a99841a5 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Stairwell 02 | Level 4 PRE-line
929cba3b-7ca4-44c3-ac42-ca2beb0cf675 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Common Areas | Stairwell 02 | Handover
ae7e7c51-25b8-436f-b5d6-bd2e18d20a6f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas
12a3e9b0-a0fe-4c22-b218-36b6fbadc032 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D69
4ecbe382-bf4b-491d-bde7-641cf1af1b9e |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D69 | Level 4 PRE-line
da04b3a8-3806-4c6e-a1b3-887d36c94b0a |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D69 | Handover
128b0881-042d-41f1-8815-8f9126ecb619 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D70
4979fd2a-4276-4ebb-9a4d-0d74cd10f6d2 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D70 | Level 4 PRE-line
40faefcc-008f-4dc2-be04-a2b0275d8bd9 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D70 | Handover
32b9b63c-0e89-4126-88be-68eb1c962552 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D71
0c72a7c7-efd2-492a-8fae-bb604a9c9dbd |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D71 | Level 4 PRE-line
946cef68-b268-42d5-ab81-1b325efb2e74 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D71 | Handover
63a0b16e-2a34-486c-801e-704c2e6c0030 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D72
978fb6a8-84c8-432e-8721-c15cd4eaf2d4 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D72 | Level 4 PRE-line
3ecafb44-6c65-4373-8a4c-92309d1d46c5 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D72 | Handover
90e22225-4fb9-47b7-a339-eabdec11b41d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D73
b0b257d6-fd9b-4dcd-b617-6fcaafcdf159 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D73 | Level 4 PRE-line
9d97509c-cb33-4f69-91cd-5eb11c352ab2 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D73 | Handover
5c6757fc-5ce8-4168-863f-c3a29fd91c24 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D74
fd7d9163-83f9-449d-8af4-bf004c64fd46 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D74 | Level 4 PRE-line
15784a7a-36a6-42d5-9916-785d051de86f |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D74 | Handover
7e5aec30-03fe-4969-8616-26e4b40015aa |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D75
71339d8e-046e-4216-86af-5d5db21c4444 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D75 | Level 4 PRE-line
1cba3685-4bed-45ef-b0ca-5ec070e03024 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D75 | Handover
ee6b9c06-f086-4d5e-befe-8afcfede9d44 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D76
fdfe3c9d-32ea-4b64-ac18-65324e543ac5 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D76 | Level 4 PRE-line
901b4114-712d-412c-9a12-8a08e06dc25c |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D76 | Handover
76141681-6370-4d05-930e-b4ad8c3821bb |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D77
97ff2434-ed00-454f-aa88-4a2f147d2b97 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D77 | Level 4PRE-line
4ff5603e-40cb-4481-8edd-3e16fdd85150 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D77 | Handover
eae53635-b696-42ad-9faf-a324cc12e87e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D78
621bd04c-1d05-4789-b320-241f20b530db |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D78 | Level 4 PRE-line
e87e1981-ec1d-4dde-a903-b3998198c06c |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D78 | Handover
24992f91-a835-492c-b757-a125a9d6edd9 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D79
e2367356-084a-4398-939c-f06fe2af5fe0 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D79 | Level 4 PRE-line
2d7bce6e-1877-43ab-a261-9d9723eda462 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D79 | Handover
c18d9469-b401-4a55-993a-56ce3090aa02 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D80
214b58e6-9f6f-480d-9ab2-6d0a97a3650e |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D80 | Level 4 PRE-line
172e713e-4369-49fa-8717-8938aa0dfffa |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D80 | Handover
e9e9852a-6ea7-4500-96da-2b48de5c0f89 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D81
d9bbadf5-8396-4270-a6cb-61581054eac1 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D81 | Level 4 PRE-line
4079562c-37ed-4207-a663-025e44cac062 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D81 | Handover
9e51b403-a76a-498b-b71d-e26a12ba2b04 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D82
2bb7c7a7-335e-49f2-bccf-ae791177f931 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D82 | Level 4 PRE-line
f260b601-2fcd-45c1-8517-5fa5ca94c91d |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D82 | Handover
6c2adb99-ffbd-46fa-90ce-901e485f1e50 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D83
0f8fae25-8d3a-4f88-80fd-d0abed969d5a |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D83 | Level 4 PRE-line
2bbfc2c9-b995-4658-9360-2b1c31a9ac2d |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D83 | Handover
4b2ae30f-c4c4-4c72-a314-c618e15a80ba |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D84
041e1a1e-6a35-4191-8ead-f903dad53aed |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D84 | Level 4 PRE-line
9a3fc6d5-c0dd-4dff-8c1c-703f02f5cb12 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D84 | Handover
a8129f3e-5ffa-4624-91d7-a80880f1c27f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D85
c8f7b888-f3d2-4b3f-be03-fb29465aefdf |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D85 | Level 4 PRE-line
ec315d0c-a40c-48ee-b9c6-dd782cf0320b |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D85 | Handover
2276d020-bab7-4484-9238-2ada4eaf8c3a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D86
b94b265e-bab0-4029-a9b7-1880873411df |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D86 | Level 4 PRE-line
3bd5b85f-fcd0-4c6d-b01d-ff5d4f823b8b |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D86 | Handover
13ec30a2-6dee-4d30-bf6a-c35d88ca01b1 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D87
c0253d68-fd19-4bff-b4d9-9202db0b8ea7 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D87 | Level 4 PRE-line
67c7f3db-4e08-4b99-8ac9-eec7e6dd7618 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 4 | Residential Areas | Apartment D87 | Handover
f91d42fb-7f47-4b29-b7f0-78dab3cc1f5d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5
de07eb24-81e6-49c7-82b5-2908422dd93d |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas
f46cdb8d-1722-4743-b291-ba5e80681d4a |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area A
fe74168c-6048-4528-9216-c821563a9887 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area A | Electrical Room
3552a47c-9039-4cb0-9d0c-c618fd45bf3a |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area A | Electrical Room | Level 5 PRE-line
91a7e20f-e251-4a0d-bf02-9a4215ecf857 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area A | Electrical Room | Handover
fac2ec3a-751a-4cb9-b189-aaeb07ad0ffa |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area A | Services Room
f6dd711b-3590-4858-9f55-8d950b2fb8ae |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area A | Services Room | Level 5 PRE-line
7a93ad0b-111b-4b06-a8ef-6d06a750063b |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area A | Services Room | Handover
b3321ffa-9ee2-4eff-a717-22e203906e15 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area B
89425651-2717-4c06-a4f2-e4125ba97d7b |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area B | Comms
a3c33049-8cd0-464f-b0d9-2b250e9b5ab2 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area B | Comms | Level 5 PRE-line
d9f5937d-1146-4af0-8d13-82c6cd4301ec |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area B | Comms | Handover
b7358ffc-aebf-4840-9cdd-c77be7dce103 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area B | Services Room
c85602dc-48ff-4b5f-825b-08cb81ed586c |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area B | Services Room | Level 5 PRE-line
13a6ce12-32b6-4fa6-bfea-a173b847a691 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area B | Services Room | Handover
1d7f4324-4849-4d06-9d13-605e3b15f25e |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area C
a204306d-a1cd-417e-b10d-0a096fee636c |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area C | Electrical Room
f3483808-29ea-4d25-b577-3e9ecd51b8e2 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area C | Electrical Room | Level 5 PRE-line
8829a5af-786f-4496-b179-afe453bb25a7 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Service areas | Level 5 Area C | Electrical Room | Handover
d006b069-dc73-4a72-9c3e-251d61f53571 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas
bb630868-bbd4-473a-9927-750f3e5e6e96 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Lift Lobby 01
a5a5b3b4-ec2d-4945-8479-93cf8e182857 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Lift Lobby 01 | Level 5 PRE-line
5aedc367-c4d5-4bff-9275-269dfc5f9bc7 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Lift Lobby 01 | Handover
7bb8c57f-6b8a-4982-8225-26d58b89d781 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Lift Lobby 02
dbdd5721-bd49-499b-a7ba-9f4a0b9132c5 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Lift Lobby 02 | Level 5 PRE-line
66d2db60-84fd-47cb-b585-4a7e1a34f5cc |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Lift Lobby 02 | Handover
5085f8dc-26d9-481b-aded-a3b237441d5e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors
47437c57-204d-4a11-b5f0-8684dab56f53 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area A
a8b91c32-b48f-431c-b213-7f55fd58c901 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area A | Corridor 01
9e682085-1558-4d9b-9ae2-10f8dee2d187 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area A | Corridor 01 | Level 5 PRE-line
b5c12b56-169f-490a-93e4-71b3a60bb69b |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area A | Corridor 01 | Handover
d6bfb3cf-24b3-45a5-852e-56ffbd8bf460 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area A | Corridor 02
fc2d7e81-3e36-4053-a2f5-3ed4dc7852ff |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area A | Corridor 02 | Level 5 PRE-line
6e3802c1-88a7-4303-9bb8-e8cae9214d56 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area A | Corridor 02 | Handover
b4fb9eac-662a-4dbc-a52c-0f6cfeef0841 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area B
2493d2a7-b729-4026-b3cb-72ef8229f713 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area B | Corridor 01
e2616c87-e047-476e-b319-242c90565b10 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area B | Corridor 01 | Level 5 PRE-line
81b3aae4-9738-4b6c-8ef6-8a4f2722e835 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area B | Corridor 01 | Handover
f560471a-5c57-4a74-b1d8-dc4246d8e2b6 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area B | Corridor 02
cd894f5a-17be-4923-badd-c18014af6a51 |  | checklist-flat | work-in-progress | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area B | Corridor 02 | Level 5 PRE-line
8d7c6fef-d9c5-4ad2-a212-4346cfc05bd4 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area B | Corridor 02 | Handover
650d254b-daf0-4e88-87ab-ac1dff47d3fd |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area C
b8ba36c8-ec6f-47ff-a423-9f702cc45c40 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area C | Corridor 01
752a6680-d1eb-4ade-8904-8e4b2c06f1e5 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area C | Corridor 01 | Level 5 PRE-line
ae323bec-329e-425c-8d5a-c1ecdc179f13 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Common Areas | Corridors | Level 5 Area C | Corridor 01 | Handover
42859c7f-9106-4a84-9f6b-41ac3a6457b5 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas
a61d527c-c5de-41a4-8462-5bad6092a8db |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E69
02d36920-2987-4201-afb3-af608509d84a |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E69 | Level 5 PRE-line
ebedffb3-f6f9-4603-89de-a59c5dab644d |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E69 | Handover
01f6c80a-d63d-4ae6-995b-5b981dac65cf |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E70
9a643450-088f-47d2-94ea-453e61575e56 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E70 | Level 5 PRE-line
4a55a5d6-78b0-4cb9-ba32-be9d84525b74 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E70 | Handover
70448a97-3c52-4669-94a8-c1e0f636d074 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E71
006b53dc-3a01-4730-9d08-886f3110ae21 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E71 | Level 5 PRE-line
1bb22550-43c9-4385-8fc5-908b08481b3e |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E71 | Handover
21d6d67e-9ce4-4fb5-9bcb-09b2730fcad0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E72
73526390-dc54-45a2-841b-67468706e8a0 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E72 | Level 5 PRE-line
8be881d5-769b-4edf-b459-15c4fce89399 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E72 | Handover
691a342d-0c98-4893-867c-60b581e594a4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E73
5bd300cc-9302-4277-b0b2-80622efcd55f |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E73 | Level 5 PRE-line
8f7cc076-33e2-47a6-939a-42a092243313 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E73 | Handover
c29a30fb-79a8-4305-8b00-9cb45943434c |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E74
3a30e353-0c81-4bf2-b7f9-87251a2dd60c |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E74 | Level 5 PRE-line
faa3f1e7-9452-4330-a50c-5eb72000c4c1 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E74 | Handover
e24f5771-0029-43c4-9d7b-f8f7b81ff8d2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E75
66e25263-8bb9-4dc7-8f04-e71a880c22d6 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E75 | Level 5 PRE-line
fee36632-9804-4fe8-955d-2f46bd3f3b7f |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E75 | Handover
05629475-6564-4b4e-aff7-d7dded9a3c71 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E76
f675ee29-b2ca-4878-bea5-f2b18ac0bdc6 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E76 | Level 5 PRE-line
db39c87b-3e24-4074-ae99-31cdb772d53d |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E76 | Handover
644eb9b9-dd93-485e-99a0-322f696e8391 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E77
4262003b-7c08-44d3-aff6-0d3f6774c1d8 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E77 | Level 5 PRE-line
9abf2320-5cbc-49bf-84af-f599727436e5 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E77 | Handover
f3508326-e945-4bc1-a6e3-71a4c59b9689 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E78
0bda5a6a-e0c2-4617-bb68-645dcfa1fe1a |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E78 | Level 5 PRE-line
558f2293-a480-4991-ac5f-172a9704d98d |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E78 | Handover
1fdfa5ba-dc4e-40d2-9aed-56118b788e72 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E79
8952965e-da6d-4641-89fb-ee477de29cb6 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E79 | Level 5 PRE-line
f335c0c1-84dd-423d-84cc-fd0ab43b52c0 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E79 | Handover
1393acc6-1b67-44c9-9cb9-682a29533de0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E80
ca126203-3f32-433e-bbe6-278300a81a1b |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E80 | Level 5 PRE-line
3c7060f0-4942-48bd-8c81-b0e548507617 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E80 | Handover
98111095-7947-4ef6-84c3-0e9bff86e17d |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E81
7cb5deb1-34e1-4ecb-ad76-05ea71600949 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E81 | Level 5 PRE-line
0245ea94-f523-4f2b-9a52-a6153f553704 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E81 | Handover
ae06d9a0-3323-4eef-92b2-4af60b777ff0 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E82
0808abf0-9405-488f-a51e-83bfb15b0979 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E82 | Level 5 PRE-line
72123e96-a0a4-4e43-9b7f-f3e634129a44 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E82 | Handover
ec434074-d284-4a60-bbc0-789620d9b366 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E83
441f283f-4a38-4dba-8726-7412f3fe4234 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E83 | Level 5 PRE-line
3349e016-b81d-482c-bcd0-3110f9256362 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E83 | Handover
a6c65807-812b-4aa9-8b97-a3b0c51dd94d |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E84
3ba1899d-d48c-4208-b8cf-44dbc98e18c4 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E84 | Level 5 PRE-line
fdae976e-295e-4535-998e-22ea808351b2 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E84 | Handover
4a8e7aa6-5166-4c22-b888-60b664e41884 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E85
4580d5eb-fc5c-47eb-ae7a-abc9b6b03960 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E85 | Level 5 PRE-line
1fd6f464-bcd1-4841-a235-c21321f80770 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E85 | Handover
34052316-e0f7-428e-b268-7c43d6ef7a02 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E86
f76d833a-acd2-4668-9294-81f5343344bd |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E86 | Level 5 PRE-line
98c3b0da-d65b-461c-a2f7-e9edfb5c4fd7 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E86 | Handover
b1e627f7-c647-4d34-8d7c-097393a5cac7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E87
49711ef8-7c0a-4431-8a70-c75641ef78e0 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E87 | Level 5 PRE-line
3c560afb-a869-4b79-98e0-9531a25995c3 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Residential Areas | Apartment E87 | Handover
53ca7d3e-02e7-4063-9855-2c2b5e495445 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Stairwell 01
8c0860a7-100f-4162-b5a4-bb8f03e9d7a3 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Stairwell 01 | Level 5 PRE-line
1cda4e58-93ca-4210-9dc2-00ed49c8e1e3 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Stairwell 01 | Handover
43f7ab0a-fad0-49da-abcd-d5af4e8d1569 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 5 | Stairwell 02
2f53cea9-0f66-455c-9b05-5dfef91039d3 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Stairwell 02 | Level 5 PRE-line
e0bc6ae7-6379-4bd0-be54-f4382ccde97c |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 5 | Stairwell 02 | Handover
c96f3fb3-ba95-4cac-9d04-0b3f79a6c675 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6
580d7c2a-8962-49e6-a189-63049ac475e7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Service areas
c1ef1f27-dbac-40c8-85a7-8db944c0199e |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Service areas | Electrical Room
e4320ba9-1051-4b90-beec-8dca0fb1439c |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Service areas | Electrical Room | Level 6 PRE-line
dfe64278-5391-4382-a9eb-abe39972a9fa |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Service areas | Electrical Room | Handover
56845510-a32e-4fef-955c-a1ab2094edc3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Service areas | Services Room
bd61ec27-235b-4efd-bff2-093e1cca0c0f |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Service areas | Services Room | Level 6 PRE-line
c472b2db-48a4-4620-a9a1-7f3de9f4270f |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Service areas | Services Room | Handover
437cb63e-5a51-46b4-9d0b-594a89e93bd2 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Service areas | Comms
87b54a2e-a393-4cf3-b632-4e13b1ac3e9b |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Service areas | Comms | Level 6 PRE-line
6ff1fef3-bad4-4d95-8988-e9a6b10afdc6 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Service areas | Comms | Handover
87279e9e-229d-4bb2-ae5d-b503e24e3bbb |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Common Areas
3bb451cc-3433-444d-b42b-d806c03466af |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Common Areas | Lift Lobby 01
84256a5f-af80-4a77-9110-e8aefbb1c8ab |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Common Areas | Lift Lobby 01 | Level 6 PRE-line
103885a3-c949-495f-af43-a86a988cc3d5 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Common Areas | Lift Lobby 01 | Handover
a36b2244-a232-4040-a204-6e2010bcb293 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Common Areas | Lift Lobby 02
bcc0af35-a733-4e7a-82a2-1316c0df5222 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Common Areas | Lift Lobby 02 | Level 6 PRE-line
908a35ae-d356-490f-a9e0-76cf82bbaebb |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Common Areas | Lift Lobby 02 | Handover
aa080af5-404f-4cc0-8d91-cb2d5773645c |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas
5ae0ac86-9552-49e5-9508-b7e8d26e72da |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F69
694b9174-836b-4ad4-bbd3-06a558e01ed1 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F69 | Level 6 PRE-line
a6ab8420-787c-4ffd-b611-93e508ac5d74 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F69 | Handover
bef1bb8c-aa06-4466-b2f5-7a9a5e9830cf |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F70
fb136fbc-0c41-4fe1-9108-d474b0b4f085 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F70 | Level 6 PRE-line
10b2398f-962e-4e34-95ca-28966cd1f19d |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F70 | Handover
198226c1-9422-488d-8aed-0a4bb20496f4 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F71
213b5f3a-648a-4ac8-b5d1-dbb697de3a31 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F71 | Level 6 PRE-line
817ce5a5-e824-4349-ab2c-2bade2ed4cc0 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F71 | Handover
c7efe0db-b944-48e4-a3e8-9fc0161d3b6e |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F72
9326c04d-1fb0-4b02-b2be-5e91435ed6bf |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F72 | Level 6 PRE-line
bf792769-d264-40f4-a656-c10681f72fd8 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F72 | Handover
d34a62dd-01c2-4547-a681-79e349d31c60 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F73
05881e95-b7bd-421b-8c00-f96005adf03a |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F73 | Level 6 PRE-line
c0bc189d-9cc8-42b5-80a1-2d2ff7c8968c |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F73 | Handover
a7cafc83-95f5-463f-9a7d-92d8b4683f8b |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F74
fd6d3250-afb3-4149-a464-fcfeade83985 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F74 | Level 6 PRE-line
28c338db-b7d7-4e1b-9a39-e105369f764d |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F74 | Handover
70ba0f68-19e1-4fe1-a19c-686d43158750 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F75
a21f269e-1e81-4f5d-b50c-83af7f673c1b |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F75 | Level 6 PRE-line
cce354a0-fc40-43b8-b040-7ded30bc378c |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F75 | Handover
8135b7e1-9eef-4af3-a872-9f4d613b82ce |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F76
021a0347-fb10-400f-9b7b-40f992743e42 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F76 | Level 6 PRE-line
38f5a1fa-bd3c-4d72-82f4-58ab62e1792e |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F76 | Handover
48e8708f-419c-4618-a2f5-148539151da3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F77
075f1fe8-39dd-41d2-af38-abc85e8aa1c5 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F77 | Level 6 PRE-line
afd60db7-1d58-45e4-8b3a-a422b8fe1aac |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F77 | Handover
4248d54c-4c30-4667-85fc-29820745ade9 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F78
5c7ad0c6-07cc-4bc2-84ee-aa31ca8216bd |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F78 | Level 6 PRE-line
98121310-6828-47be-814d-4f62e4521eec |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Residential Areas | Apartment F78 | Handover
4f4521e4-7eed-4ffc-bdbe-b7c7fd9b2d71 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Stairwell 01
49c3c00f-70bc-4d0a-af97-7480f95862f2 |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Stairwell 01 | Level 6 PRE-line
5f2d86a4-84e1-4e79-9add-499b2d0a1390 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Stairwell 01 | Handover
5e37fcea-d203-4133-a845-f764ba43ba70 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Level 6 | Stairwell 02
fa3950eb-13e0-4734-befa-4b34bf6026bd |  | checklist-flat | not-started | a3dd5b6f5e78b984aaba55d8bb575191da2ae1ffed327a75a077a556b1da0fb1 | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Stairwell 02 | Level 6 PRE-line
9c7471c4-51cc-4c60-9710-b00589543266 |  | checklist-flat | not-started | H - R - Handover | checklist-flat | FALSE | FALSE | Building B08 | Fitouts and Services | Level 6 | Stairwell 02 | Handover
9dbc60da-8047-4577-9f97-bd2d21fe7aae |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Ryman Construction
d717bd3f-d02a-4c88-862e-992e8cd29470 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Ryman Construction | Level 1
e9c91284-344a-4c7f-be55-0e513ec63ce4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Ryman Construction | Level 2
e883df71-4f5a-47e5-aa76-56c652e6d8db |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Ryman Construction | Level 3
19b21971-db84-4313-8139-d3215ca030a4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Ryman Construction | Level 4
cbf13130-616a-4552-aca3-ac29f23b26ee |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Ryman Construction | Level 5
61ddf6ea-7aaa-4458-b5d3-60b6f7a231a5 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | Ryman Construction | Level 6
87b6bce6-51d7-4ec3-9e56-e3d496249dab |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | As-builts
877b5646-9cc1-418b-aa4e-dfcbf090d54c |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building B08 | Fitouts and Services | As-builts | IPL
33b7d1c6-2403-4076-80e2-cb6aaf0bf1a5 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Global Fire
361c23f9-d449-431b-b056-719e11209a9d |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Global Fire | Level 1
fcd7a563-eff6-4225-b412-0bf0acec5168 |  | checklist-flat | pass | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Global Fire | Level 1 | Level 1 Passive fire
3bbc7e42-4b8c-43d2-81f8-8af7f6d32b46 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Global Fire | Level 2
a9994a15-4e06-402c-b9cc-82cf13d8fa1c |  | checklist-flat | pass | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Global Fire | Level 2 | Level 2 Passive fire
89b23067-6688-4381-9361-0484d2b8e024 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Global Fire | Level 3
2cac8083-6db3-4679-920a-a25813f89857 |  | checklist-flat | pass | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Global Fire | Level 3 | Level 3 Passive fire
08775fc1-ceb2-4c64-850e-f3f3e6591289 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Global Fire | Level 4
30a7c95f-2c6a-431b-be46-fa9d245da267 |  | checklist-flat | pass | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Global Fire | Level 4 | Level 4 Passive fire
11c1c4d6-10b0-4637-9fec-1f1fb03d9278 |  | folder-normal | pass |  | step | TRUE | FALSE | Building B08 | Global Fire | Level 5
f8bcb54f-52a1-4920-9dac-d6221a50c83a |  | checklist-flat | pass | FC - R - Passive fire | checklist-flat | FALSE | FALSE | Building B08 | Global Fire | Level 5 | Level 5 Passive fire
7877c25d-74a9-46a6-ac64-88209c51df49 |  | folder-normal | fail |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs)
7b28956f-1403-44cd-b46d-afaebdc8fdc2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BC010249662 - Civil
22396820-769d-47f5-bdb7-ed1a69e796ec |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BC010249662 - Civil | Building Consent - BC010249662
76654c40-bd6f-470d-bbc6-123129e6db93 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BC010249662 - Civil | Minor Variation(s) BC010249662
48fa3495-366f-4c1c-9c3e-7a3059ccc0d8 |  | checklist-flat | not-started | 6e7d7f453688aa574c9c028ffd95658a8cbb93c11f518499c4dcb35cb43a5216 | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BC010249662 - Civil | Minor Variation(s) BC010249662 | Minor Variation - BC010249662
0adf04c1-4928-460c-8832-422fc75006e2 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BC010249662 - Civil | Council Inspections BC010249662
0a5b8049-1dd3-4a95-98b7-e98102cc35af |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BC010249662 - Civil | Council Inspections BC010249662 | Other Inspections for BC010249662
93780db4-9a33-4477-a99b-e7738e8af148 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BC010249662 - Civil | Council Inspections BC010249662 | IFO Siting (1)
f7bb553c-1540-5e4f-933b-a992968be564 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BC010249662 - Civil | Council Inspections BC010249662 | Council Inspection - IME (Site Meeting) 08/06/2020
f2dcc607-c5e8-5f5a-89a5-092a27686ea4 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BC010249662 - Civil | Council Inspections BC010249662 | Council Inspection - IDT 14/07/2020
40f20a08-871c-5434-a5f3-dd7ed185a186 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BC010249662 - Civil | Council Inspections BC010249662 | Council Inspection - Site meeting (IME) - 02/11/2020
6b614625-a7ea-4952-84fb-f112eb0cfeb5 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BC010249662 - Civil | Council Audits BC010249662
29a68e52-77c3-4884-9e81-a48ee0a7fcfb |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BC010249662 - Civil | Compliance Documentation BC010249662 - (TBC Send checklist to Conqa)
6d5bfcb4-399e-4329-b29a-513996360f25 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BC010249662 - Civil | Compliance RFI's BCO10249662
5926eae6-2b84-4359-a697-604e52766bb3 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BC010249662 - Civil | Code of Compliance (CCC) BCO10249662
7634022b-c422-43a7-a4fa-a2ae2cdece9c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls
b296eab3-873f-4005-b574-0eece0dbef59 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10270990 - Retaining Wall Dementia Ward
1acefee8-425d-4d3f-ac6f-beb5e7561ea8 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10270990 - Retaining Wall Dementia Ward | Building Consent - BCO10270990
77eb5c73-d9f0-42d5-a039-9c9dd5ead04d |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10270990 - Retaining Wall Dementia Ward | Council Inspections - BCO10270990
f0ee021e-5c51-5dc8-8643-8644392d2d23 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10270990 - Retaining Wall Dementia Ward | Council Inspections - BCO10270990 | Council Inspection - 24.10.2019 (IF2)
4eb5cd71-9021-4b9c-b16b-af9b9a8277e3 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10270990 - Retaining Wall Dementia Ward | Compliance Documentation - BCO10270990
d0fd0811-397a-569d-8698-77aa65645607 |  | checklist-flat | pass | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10270990 - Retaining Wall Dementia Ward | Compliance Documentation - BCO10270990 | Retaining Wall Consent
4e09fc91-b7ae-4c7c-b780-ee0e03a690cc |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10270990 - Retaining Wall Dementia Ward | Compliance RFIs - BCO10270990
1cba89f6-1c41-59a5-adef-70167d6156b6 |  | checklist-flat | work-in-progress | 3ae4689b652b141d8784980bb34ee6e555ea80d26f41df3ba8fbaa97c4e5ff65 | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10270990 - Retaining Wall Dementia Ward | Compliance RFIs - BCO10270990 | RFI - 15/05/2020
68e2ae49-0e56-4ce0-ac4c-6d4cfc0fb1e3 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10270990 - Retaining Wall Dementia Ward | Code of Compliance (CCC) - BCO10270990
5ea268d2-791b-49fe-8fbf-5d9572ec5441 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10271394 - Retaining Walls RW 1-2 & 1-22
369634a6-7155-443d-a173-eb43d7a1521e |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10271394 - Retaining Walls RW 1-2 & 1-22 | Building Consent - BCO10271394
c42569a5-aa1b-45d5-8a81-cbc2508a2d9b |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10271394 - Retaining Walls RW 1-2 & 1-22 | Council Inspections - BCO10271394
e58d2717-0fd0-5a13-bb7d-7c221ba34718 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10271394 - Retaining Walls RW 1-2 & 1-22 | Council Inspections - BCO10271394 | Council Inspection - 12.11.2019 (IF2)
21e53abf-0ddd-4424-a27e-eff88a1a6d9b |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10271394 - Retaining Walls RW 1-2 & 1-22 | Compliance Documentation - BCO10271394
630bff0f-68b3-57d7-aaf6-31ceca671d86 |  | checklist-flat | pass | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10271394 - Retaining Walls RW 1-2 & 1-22 | Compliance Documentation - BCO10271394 | Retaining Wall Consent
bd30cc5f-b228-47ce-b07f-4620cfc59b71 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10271394 - Retaining Walls RW 1-2 & 1-22 | Compliance RFIs - BCO10271394
fa0373fd-4a63-5181-9a4b-d15493d8e4bb |  | checklist-flat | work-in-progress | 3ae4689b652b141d8784980bb34ee6e555ea80d26f41df3ba8fbaa97c4e5ff65 | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10271394 - Retaining Walls RW 1-2 & 1-22 | Compliance RFIs - BCO10271394 | RFI - 18/05/2020
d9f5e2f4-3070-4996-bfc8-c43f4af9b103 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10271394 - Retaining Walls RW 1-2 & 1-22 | Code of Compliance (CCC) - BCO10271394
3508a931-3615-4655-ba45-2b48b5d4a55e |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280112 - Retaining Walls RW 1-5, 1-6, 1-7, 1-8, 1-9, 1-11, 1-12, 1-13 & 1-14
dc5fd2f5-c25a-4838-b13a-f13c524c4f93 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280112 - Retaining Walls RW 1-5, 1-6, 1-7, 1-8, 1-9, 1-11, 1-12, 1-13 & 1-14 | Building Consent - BCO10280112
0ec3b133-9e6b-4721-b1c3-bb504d2c0304 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280112 - Retaining Walls RW 1-5, 1-6, 1-7, 1-8, 1-9, 1-11, 1-12, 1-13 & 1-14 | Council Inspections - BCO10280112
a0100973-c241-562d-9f75-f31ae9d317da |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280112 - Retaining Walls RW 1-5, 1-6, 1-7, 1-8, 1-9, 1-11, 1-12, 1-13 & 1-14 | Council Inspections - BCO10280112 | Council Inspection - IFO 26/08/2020
4241fd33-94c9-5a1f-86e1-b445bff3c79d |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280112 - Retaining Walls RW 1-5, 1-6, 1-7, 1-8, 1-9, 1-11, 1-12, 1-13 & 1-14 | Council Inspections - BCO10280112 | Council Inspection - IME (Site Meeting) 24/09/2020
06c2af13-a0c2-5be6-8e63-1a57997e26d8 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280112 - Retaining Walls RW 1-5, 1-6, 1-7, 1-8, 1-9, 1-11, 1-12, 1-13 & 1-14 | Council Inspections - BCO10280112 | Council Inspection - IME (Site Meeting) - 29/10/2020
9d80e3c7-5b43-5a41-b912-e57f5eb60076 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280112 - Retaining Walls RW 1-5, 1-6, 1-7, 1-8, 1-9, 1-11, 1-12, 1-13 & 1-14 | Council Inspections - BCO10280112 | Council Inspection - IF2 - 10/02/2021
c44b2e58-da50-400f-a7e8-6ac0f22c4d6b |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280112 - Retaining Walls RW 1-5, 1-6, 1-7, 1-8, 1-9, 1-11, 1-12, 1-13 & 1-14 | Compliance Documentation - BCO10280112
dd108f9b-7c5f-5432-aa0d-60518dad3456 |  | checklist-flat | pass | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280112 - Retaining Walls RW 1-5, 1-6, 1-7, 1-8, 1-9, 1-11, 1-12, 1-13 & 1-14 | Compliance Documentation - BCO10280112 | Retaining Wall Consent
66ad8976-93fb-4bf1-b274-3249218bea38 |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280112 - Retaining Walls RW 1-5, 1-6, 1-7, 1-8, 1-9, 1-11, 1-12, 1-13 & 1-14 | Code of Compliance (CCC) - BCO10280112
e0d7b4bf-974f-4e3c-a323-5ca5cf0aa45e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10278772 - Retaining Walls RW 1-15, 1-16, 1-17, 1-18 & 1-19
905c27f5-e044-464e-aa7e-c5b72ea720c1 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10278772 - Retaining Walls RW 1-15, 1-16, 1-17, 1-18 & 1-19 | Building Consent - BCO10278772
15920103-d9be-4c9e-a57b-30ca719632eb |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10278772 - Retaining Walls RW 1-15, 1-16, 1-17, 1-18 & 1-19 | Council Inspections - BCO10278772
3ffdb243-3918-59f1-8038-9922beacda1a |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10278772 - Retaining Walls RW 1-15, 1-16, 1-17, 1-18 & 1-19 | Council Inspections - BCO10278772 | Council Inspection - 10.12.2019 (IF2)
de1ca974-5172-427c-80cc-2cb8171440bd |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10278772 - Retaining Walls RW 1-15, 1-16, 1-17, 1-18 & 1-19 | Compliance Documentation - BCO10278772
20e1c745-f2c0-5f11-90f5-6be46ec09fa0 |  | checklist-flat | pass | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10278772 - Retaining Walls RW 1-15, 1-16, 1-17, 1-18 & 1-19 | Compliance Documentation - BCO10278772 | Retaining Wall Consent
09ea8d70-9c01-4324-8fcc-1fc55b0e3f3e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10278772 - Retaining Walls RW 1-15, 1-16, 1-17, 1-18 & 1-19 | Compliance RFIs - BCO10278772
43547124-2da7-5184-95b7-bc80848a45c1 |  | checklist-flat | work-in-progress | 3ae4689b652b141d8784980bb34ee6e555ea80d26f41df3ba8fbaa97c4e5ff65 | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10278772 - Retaining Walls RW 1-15, 1-16, 1-17, 1-18 & 1-19 | Compliance RFIs - BCO10278772 | RFI - 18/05/2020
c5055b18-db5e-4a7e-9d87-e35456d86df8 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10278772 - Retaining Walls RW 1-15, 1-16, 1-17, 1-18 & 1-19 | Code of Compliance (CCC) - BCO10278772
a0af60b7-bb1c-446f-bd1a-37fe6a8dbec6 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280410 - Retaining Walls RW 3-4, 3-5 & 3-9
a0226be4-ddbe-4735-9934-fb8cf26d3933 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280410 - Retaining Walls RW 3-4, 3-5 & 3-9 | Building Consent - BCO10280410
ed9cb15a-bd35-4d39-9d4f-fcb2c362ea1d |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280410 - Retaining Walls RW 3-4, 3-5 & 3-9 | Council Inspections - BCO10280410
3c86bdff-6e9a-542b-9038-34933115fc90 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280410 - Retaining Walls RW 3-4, 3-5 & 3-9 | Council Inspections - BCO10280410 | Council Inspection - 09/12/2019
46b77ec5-837b-4148-970e-853d5ee1d7c5 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280410 - Retaining Walls RW 3-4, 3-5 & 3-9 | Compliance Documentation - BCO10280410
b5785a5c-4bed-5dfa-91bb-c2aa2d82b6d1 |  | checklist-flat | pass | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280410 - Retaining Walls RW 3-4, 3-5 & 3-9 | Compliance Documentation - BCO10280410 | Retaining Wall Consent
455f0d8c-cbc1-4f49-8322-0b9caf7a4cc2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280410 - Retaining Walls RW 3-4, 3-5 & 3-9 | Compliance RFIs - BCO10280410
0d3aacaf-e5e6-540e-83d4-9e5f700dc76f |  | checklist-flat | work-in-progress | 3ae4689b652b141d8784980bb34ee6e555ea80d26f41df3ba8fbaa97c4e5ff65 | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280410 - Retaining Walls RW 3-4, 3-5 & 3-9 | Compliance RFIs - BCO10280410 | RFI - 18/05/2020
bea625ff-75ff-4473-b680-6ee459ee0b8b |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280410 - Retaining Walls RW 3-4, 3-5 & 3-9 | Code of Compliance (CCC) - BCO10280410
8bdd236f-00d1-4d36-aa80-756462304e26 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289811 - Retaining Wall - RW 1-12A
9609f30b-2af9-4cda-880d-ea6524e6fae2 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289811 - Retaining Wall - RW 1-12A | Building Consent - BCO10289811
55ec8787-6c6a-41be-8041-bcb49bb8082d |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289811 - Retaining Wall - RW 1-12A | Council Inspections - BCO10289811
40919644-80b1-521e-b394-ee6ba1e1a7a6 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289811 - Retaining Wall - RW 1-12A | Council Inspections - BCO10289811 | Council Inspection - Pre-Construction Meeting 16/06/2020
20a4e857-fa32-595c-96a5-409f161639f3 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289811 - Retaining Wall - RW 1-12A | Council Inspections - BCO10289811 | Council Inspection - IME 25/06/2020
e8f88d51-9654-537a-a7bb-99ca4dee10e6 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289811 - Retaining Wall - RW 1-12A | Council Inspections - BCO10289811 | Council Inspection - IFO 09/07/2020
df40fbc8-794a-5ffb-9a16-f10f530854d2 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289811 - Retaining Wall - RW 1-12A | Council Inspections - BCO10289811 | Council Inspection - IME 29/07/2020
39c1b3a3-2f0c-544f-86d9-2cd15052d021 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289811 - Retaining Wall - RW 1-12A | Council Inspections - BCO10289811 | Council Inspection - IME 18/08/2020
a880a153-de37-53d0-8ca1-c5af99792240 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289811 - Retaining Wall - RW 1-12A | Council Inspections - BCO10289811 | Council Inspection - IME (Site Meeting) 24/09/2020
9556a478-e6e3-5913-aaa6-f08d94c2b671 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289811 - Retaining Wall - RW 1-12A | Council Inspections - BCO10289811 | Council Inspection - IME (Site Meeting) - 29/10/2020
1ae8fa2a-f34c-55d8-91e7-d250e68aeac6 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289811 - Retaining Wall - RW 1-12A | Council Inspections - BCO10289811 | Council Inspection - IF2 10/02/2021
26e361cd-a068-4c99-910f-01daa8b3362b |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289811 - Retaining Wall - RW 1-12A | Compliance Documentation - BCO10289811
da6b6fb2-74ca-5f55-bc27-419c0591f1ec |  | checklist-flat | pass | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289811 - Retaining Wall - RW 1-12A | Compliance Documentation - BCO10289811 | Retaining Wall Consent
caa736eb-9b1f-4bb6-aa73-377dcdd57f7f |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289811 - Retaining Wall - RW 1-12A | Code of Compliance (CCC) - BCO10289811
dda42566-86b8-4282-bfc0-9cf1c649c9bf |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289829 - Retaining Walls RW 3-1 & 3-2
30d6a827-de03-4a22-a0bd-e6e3d587cda0 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289829 - Retaining Walls RW 3-1 & 3-2 | Building Consent - BCO10289829
e02052c8-1527-452c-915e-f0af5bdf5586 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289829 - Retaining Walls RW 3-1 & 3-2 | Council Inspections - BCO10289829
e1f07d08-f883-4e3e-942a-856331cb35be |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289829 - Retaining Walls RW 3-1 & 3-2 | Compliance Documentation - BCO10289829
a82879aa-c67f-5a61-99fe-bedea13b7d30 |  | checklist-flat | work-in-progress | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289829 - Retaining Walls RW 3-1 & 3-2 | Compliance Documentation - BCO10289829 | Retaining Wall Consent
dacac22a-74b7-4d98-be82-07e64d9cfe20 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289829 - Retaining Walls RW 3-1 & 3-2 | Compliance RFIs - BCO10289829
0bb2d695-e761-48e7-b802-f9b84cd20aa5 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10289829 - Retaining Walls RW 3-1 & 3-2 | Code of Compliance (CCC) - BCO10289829
267c09bb-ea49-4db9-a90c-0e8c2e844f60 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10290541 - Retaining Wall RW 4-1 & 4-2
5e30b4e1-0e19-4dfd-9827-02d5aece4dcd |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10290541 - Retaining Wall RW 4-1 & 4-2 | Building Consent - BCO10290541
8ae9ce6d-a5f6-4fa3-b94c-2a7e02d366fa |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10290541 - Retaining Wall RW 4-1 & 4-2 | Council Inspections - BCO10290541
51debab3-9dd9-5a22-8d66-fc86c3dcfb8a |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10290541 - Retaining Wall RW 4-1 & 4-2 | Council Inspections - BCO10290541 | Council Inspection - IME 09/07/2020
2f64033c-a940-5f2d-974e-a0606fb93948 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10290541 - Retaining Wall RW 4-1 & 4-2 | Council Inspections - BCO10290541 | Council Inspection - IF2 10/02/2021
800401ba-6933-4677-8c3e-328c0d9f4106 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10290541 - Retaining Wall RW 4-1 & 4-2 | Compliance Documentation - BCO10290541
5f2179ed-3872-5de8-9b2c-f518c5d94169 |  | checklist-flat | work-in-progress | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10290541 - Retaining Wall RW 4-1 & 4-2 | Compliance Documentation - BCO10290541 | Retaining Wall Consent
c84014df-365e-4045-bccc-305916d57f08 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10290541 - Retaining Wall RW 4-1 & 4-2 | Compliance RFIs - BCO10290541
47eddb8e-a354-4c42-82ec-61b1b699081d |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10290541 - Retaining Wall RW 4-1 & 4-2 | Code of Compliance (CCC) - BCO10290541
bb7f51ad-92b4-4474-9452-3f748e8064a5 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10262840 - Retaining Wall RW 2-1 & 2-2
5d63e20a-8a49-4f4a-b00b-3759b6a52799 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10262840 - Retaining Wall RW 2-1 & 2-2 | Building Consent - BCO10262840
02762180-5f05-4415-b749-90ccc3732326 |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10262840 - Retaining Wall RW 2-1 & 2-2 | Code of Compliance (CCC) - BCO10262840
7c658162-d4b9-4229-b226-dd6189a13b30 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10267419 - Retaining Walls RW 2-3 & 2-4
57fc5ba2-6afb-48e7-9ec2-9fd32ad912ea |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10267419 - Retaining Walls RW 2-3 & 2-4 | Building Consent - BCO10267419
bb0d4c82-0667-4a89-9f5f-2e6b1b2fd590 |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10267419 - Retaining Walls RW 2-3 & 2-4 | Code of Compliance (CCC) - BCO10267419
5c2a1252-e61f-4c4c-8254-76f5a4975123 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10260554 - Retaining Wall RW 2-5
04ef7d56-0362-4c7f-84b0-94ce76f13c56 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10260554 - Retaining Wall RW 2-5 | Building Consent - BCO10260554
5f3d9d5f-00c8-427e-8b2c-9dd42c367b05 |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10260554 - Retaining Wall RW 2-5 | Code of Compliance (CCC) - BCO10260554
2ff6a826-0e6a-480c-ba8a-0870ce22e418 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10269645 - Retaining Walls RW 3-1, 3-2 & 3-3
da8fa146-ddc3-4072-b143-d35d40e2139e |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10269645 - Retaining Walls RW 3-1, 3-2 & 3-3 | Building Consent - BCO10269645
5ed3f6b1-0f51-45bc-a3f9-2688313c7c14 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10269645 - Retaining Walls RW 3-1, 3-2 & 3-3 | Council Inspections - BCO10269645
21d665de-76cd-4ea6-9f1a-f932120c87c2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10269645 - Retaining Walls RW 3-1, 3-2 & 3-3 | Compliance Documentation - BCO10269645
0fde4ac4-e8a3-50f0-a9cc-e9f9c206d45b |  | checklist-flat | work-in-progress | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10269645 - Retaining Walls RW 3-1, 3-2 & 3-3 | Compliance Documentation - BCO10269645 | Retaining Wall Consent
a9d6c5d1-02d5-40aa-ba83-0c5cac0d8a89 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10269645 - Retaining Walls RW 3-1, 3-2 & 3-3 | Compliance RFIs - BCO10269645
6ba101ee-7636-4a9c-86e0-4d7c9f16c99a |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10269645 - Retaining Walls RW 3-1, 3-2 & 3-3 | Code of Compliance (CCC) - BCO10269645
fc8601d2-7b07-45ef-ba4a-6e57a7b2bfc2 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10264195 - Retaining Wall RW 1-4
3a2fafe2-933b-445f-a2e1-78f622f5812d |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10264195 - Retaining Wall RW 1-4 | Building Consent - BCO10264195
20fa71ad-0cfb-4011-bc40-b100fce32218 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10264195 - Retaining Wall RW 1-4 | Council Inspections - BCO10264195
fa7c8519-cf9d-53ee-b769-2a239433760a |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10264195 - Retaining Wall RW 1-4 | Council Inspections - BCO10264195 | Council Inspection - 10.12.2019 (IF2)
2b15a3ab-4aa9-40d1-a07f-88fd8695e142 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10264195 - Retaining Wall RW 1-4 | Compliance Documentation - BCO10264195
2e69d01f-bd01-5484-9314-34ca3978aae0 |  | checklist-flat | pass | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10264195 - Retaining Wall RW 1-4 | Compliance Documentation - BCO10264195 | Retaining Wall Consent
09ceb5f2-e44e-4816-9ae9-9c3ae17ac477 |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10264195 - Retaining Wall RW 1-4 | Code of Compliance (CCC) - BCO10264195
9ee8f490-e469-4f48-b267-a56a3476b32d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10302744 - Retaining Wall (B08)
345ee94e-2434-55e4-a150-40eddfe45110 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10302744 - Retaining Wall (B08) | Building Consent - BCO10302744
07243801-eb4f-483c-94e3-c047f5146fde |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10302744 - Retaining Wall (B08) | Council Inspections - BCO10302744
9d8a9aa3-c5b9-5b43-80b8-74ce5e96749b |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10302744 - Retaining Wall (B08) | Council Inspections - BCO10302744 | Council Inspection - IME 26/05/2020
3439c4a5-fe8a-55d5-b98d-609756894a58 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10302744 - Retaining Wall (B08) | Council Inspections - BCO10302744 | Council Inspection - IME 01/07/2020
6669a643-3bf7-5dbb-a283-ea6830bbfdd1 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10302744 - Retaining Wall (B08) | Council Inspections - BCO10302744 | Council Inspection - IME 29/07/2020
3ebb8615-92ba-5c35-bf12-527a88436af2 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10302744 - Retaining Wall (B08) | Council Inspections - BCO10302744 | Council Inspection - IME 19/08/2020
ea3972b0-033a-5439-bcb1-2d9161d6cec8 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10302744 - Retaining Wall (B08) | Council Inspections - BCO10302744 | Council Inspection - IME 17/09/2020
1f52e94c-1b1e-4c88-af79-54001b2b4a46 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10302744 - Retaining Wall (B08) | Compliance Documentation - BCO10302744
ed19e3c6-e081-5903-851f-e0e47985def0 |  | checklist-flat | not-started | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10302744 - Retaining Wall (B08) | Compliance Documentation - BCO10302744 | Retaining Wall Documents
1c9dceb9-6733-4acd-9ea5-0b775bfc7cd4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10302744 - Retaining Wall (B08) | Compliance RFIs - BCO10302744
7ed3a1eb-b675-5cf8-8a02-a19fdc2a501f |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10302744 - Retaining Wall (B08) | Code of Compliance (CCC) - BCO10302744
c32fc594-69af-410d-b6bf-b6b644fc557f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10304240 Retaining Wall RW 7-2 & 8-5
b18998f2-e096-506e-94dc-7ed98177d4cd |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10304240 Retaining Wall RW 7-2 & 8-5 | Building Consent - BCO10304240
a99072c0-4a6c-4df1-8732-58b24fb29793 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10304240 Retaining Wall RW 7-2 & 8-5 | Council Inspections - BCO10304240
1183952e-065d-5eb7-952d-2987014f9d85 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10304240 Retaining Wall RW 7-2 & 8-5 | Council Inspections - BCO10304240 | Council Inspection - IME (Site Meeting) - 19/08/2020
880a7bd6-1348-4ee6-9150-1779445f6bea |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10304240 Retaining Wall RW 7-2 & 8-5 | Council Inspections - BCO10304240 | Council Inspection - Site meeting (5/07/2021)
9a104de7-4755-562c-8534-b84ca039a00f |  | checklist-flat | not-started | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10304240 Retaining Wall RW 7-2 & 8-5 | Compliance Documentation - BCO10304240
0da4a919-af0f-570a-bac5-620ba03875d7 |  | checklist-flat | not-started | 3ae4689b652b141d8784980bb34ee6e555ea80d26f41df3ba8fbaa97c4e5ff65 | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10304240 Retaining Wall RW 7-2 & 8-5 | Compliance RFIs - BCO10304240
fbb56633-cb92-59df-a178-a7cf5f16eb6f |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10304240 Retaining Wall RW 7-2 & 8-5 | Code of Compliance (CCC) - BCO10304240
da2ed95f-0e11-4eac-a679-309feca0e068 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310899 - Retaining Walls 4-1 & 4-2 (New Design)
cf3f4edf-c7d5-5a44-a344-241cb7c94e6e |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310899 - Retaining Walls 4-1 & 4-2 (New Design) | Building Consent - BCO10310899
0d672964-ae4e-47ed-8b58-73e6c8cfa5c5 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310899 - Retaining Walls 4-1 & 4-2 (New Design) | Council Inspections - BCO10310899
5850acc5-3609-54e9-9137-710997b4e613 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310899 - Retaining Walls 4-1 & 4-2 (New Design) | Council Inspections - BCO10310899 | Council Inspection - PCO (Pre-Construction Meeting) 23/09/2020
8c99a57a-7c18-5bef-8c44-dce0ad33229f |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310899 - Retaining Walls 4-1 & 4-2 (New Design) | Council Inspections - BCO10310899 | Council Inspection - ICB (Concrete Block/ NIB / INSITU) - 19/10/2020
d67741ef-193d-5f2d-8d17-2ad06ead1d6a |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310899 - Retaining Walls 4-1 & 4-2 (New Design) | Council Inspections - BCO10310899 | Council Inspection - Site Meeting (IME) - 03/11/2020
4779ed1b-234c-587d-85d2-612890680999 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310899 - Retaining Walls 4-1 & 4-2 (New Design) | Council Inspections - BCO10310899 | Council Inspection - IF2 (Commercial Final) - 26/11/2020
86b5694a-0998-5a58-a05f-899180382cb8 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310899 - Retaining Walls 4-1 & 4-2 (New Design) | Council Inspections - BCO10310899 | Council Inspection - IF2 (commercial final) 10/02/2021
34813024-67fe-5452-b68e-136cf754b7d1 |  | checklist-flat | pass | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310899 - Retaining Walls 4-1 & 4-2 (New Design) | Compliance Documentation - BCO10310899
28fc5a5d-5819-5dc1-a01f-8c4d37f1204f |  | checklist-flat | not-applicable | 3ae4689b652b141d8784980bb34ee6e555ea80d26f41df3ba8fbaa97c4e5ff65 | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310899 - Retaining Walls 4-1 & 4-2 (New Design) | Compliance RFIs - BCO10310899
2668db61-9497-5708-83f5-1d4597a79c17 |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310899 - Retaining Walls 4-1 & 4-2 (New Design) | Code of Compliance (CCC) - BCO10310899
95a317cb-ea99-4622-918c-30b79ddfc99b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310692 - Retaining Walls 4-3 & 8-2
40299302-bcbc-5f65-bb80-3f8174e4d292 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310692 - Retaining Walls 4-3 & 8-2 | Building Consent - BCO10310692
d0b829ce-67d2-48f6-aa91-f078e294328c |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310692 - Retaining Walls 4-3 & 8-2 | Council Inspections - BCO10310692
e6a599ee-63fb-50b8-b4b4-a693f7d053fe |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310692 - Retaining Walls 4-3 & 8-2 | Council Inspections - BCO10310692 | Council Inspection - ICB (Concrete Block/ NIB / INSITU) - 19/10/2020
d99aa9cd-5ab5-5b2b-9b5c-dba1e2736b74 |  | checklist-flat | work-in-progress | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310692 - Retaining Walls 4-3 & 8-2 | Council Inspections - BCO10310692 | Council Inspection - IME (Site Meeting) - 29/10/2020
3dad7d78-7e57-5313-9f57-fc7e7dea4d5c |  | checklist-flat | not-started | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310692 - Retaining Walls 4-3 & 8-2 | Compliance Documentation - BCO10310899
42958db6-f532-5f54-a42d-d21e963c2a00 |  | checklist-flat | not-started | 3ae4689b652b141d8784980bb34ee6e555ea80d26f41df3ba8fbaa97c4e5ff65 | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310692 - Retaining Walls 4-3 & 8-2 | Compliance RFIs - BCO10310692
4bd2e73f-a27e-5bb8-b5f8-ba5c2c603ea9 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10310692 - Retaining Walls 4-3 & 8-2 | Code of Compliance (CCC) - BCO10310899
231947f0-176b-4f25-8ea4-8c68864aad03 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10303734-8 - Retaining wall 8-1
2e65dfa5-a9b8-49d6-a79f-20fb635b8377 |  | checklist-flat | work-in-progress | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10303734-8 - Retaining wall 8-1 | Building Consent -
59982c8d-c632-4909-a5b1-293978bd4bad |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10303734-8 - Retaining wall 8-1 | Council Inspection
f423cb06-1213-4b21-b01e-608266b4754a |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10303734-8 - Retaining wall 8-1 | Council Inspection | Council Inspection - (IME) - 4/10/2021
802ffe14-8100-4f51-a8d8-096914984a95 |  | checklist-flat | not-started | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10303734-8 - Retaining wall 8-1 | Retaining Wall Consent
561e4d0e-f192-4843-a1d1-be303a3e03b9 |  | checklist-flat | not-started | Add Council BC Minor Variation Checklist (V3) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10303734-8 - Retaining wall 8-1 | Council BC Minor Variation -
d6748a26-76d0-45d1-afd9-e354db43edfd | Unsupported Children: folder-normal Code Compliance Certificate RFI's(8b928724-7bb4-5749-b43e-575eef381ab2) | checklist-sectioned | not-started | Add CCC Code Compliance Certificate Checklist | checklist | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10303734-8 - Retaining wall 8-1 | Code Compliance Certificate -
8b928724-7bb4-5749-b43e-575eef381ab2 |  | folder-normal | no-status-not-started |  | step | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10303734-8 - Retaining wall 8-1 | Code Compliance Certificate - | Code Compliance Certificate RFI's
eb4b23a5-4dfa-46fe-80b4-55caaa9c3728 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280737-8 RW Behind B08
51b750e1-a098-4ea3-a0c5-1a6a654e4fbb | Unsupported Children: folder-normal Code Compliance Certificate RFI's(62ae904f-d280-5900-9023-facb28f904da) | checklist-sectioned | not-started | Add CCC Code Compliance Certificate Checklist | checklist | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280737-8 RW Behind B08 | Code Compliance Certificate - BCO10280737-8
62ae904f-d280-5900-9023-facb28f904da |  | folder-normal | no-status-not-started |  | step | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280737-8 RW Behind B08 | Code Compliance Certificate - BCO10280737-8 | Code Compliance Certificate RFI's
7567feed-1fcb-43b9-b26d-7ae3833a9627 | Unsupported Children: folder-normal RFI Management of Individual Items(1e2d77af-5b42-5729-ae5f-4f376003f3ed) | checklist-sectioned | not-started | Add CCC RFI Checklist (V3) | checklist | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280737-8 RW Behind B08 | RFI - BCO10280737-8
1e2d77af-5b42-5729-ae5f-4f376003f3ed |  | folder-normal | no-status-not-started |  | step | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280737-8 RW Behind B08 | RFI - BCO10280737-8 | RFI Management of Individual Items
eb5cff46-3f49-4aaf-a051-837786587792 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280737-8 RW Behind B08 | Building Consent - BCO10280737-8
1c45fa6d-c2ad-4f5b-a532-a0a31312f147 |  | checklist-flat | not-started | Add Council BC Minor Variation Checklist (V3) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280737-8 RW Behind B08 | Council BC Minor Variation - BCO10280737-8
ac1b6084-6571-41f0-81f7-385ab9d4890a |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280737-8 RW Behind B08 | Auckland Council Inspection
268400c6-2eda-41ac-9ebb-520ebd11165e |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280737-8 RW Behind B08 | Auckland Council Inspection | Auckland Council Inspection - 13/06/22
42548ab7-6d45-46b4-bc38-368054e4b5a0 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Retaining Walls | BCO10280737-8 RW Behind B08 | Auckland Council Inspection | Auckland Council Inspection - 13/05/22
ea668566-c1c4-461d-9ad4-9bc4e387775a |  | folder-normal | fail |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01
7c7f5659-d206-4db6-9653-1fe5700a0bee |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-1 - Structural Consent - B01
aa8804dc-9b2b-4613-86aa-1aec716d4b76 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-1 - Structural Consent - B01 | Building Consent - BCO10250493-1
13542300-1dac-4e72-955e-9c41e8e50258 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-1 - Structural Consent - B01 | Minor Variation - BCO10250493-1
34bdb20b-03c9-47da-b0db-968b7893ef7e |  | checklist-flat | not-started | 6e7d7f453688aa574c9c028ffd95658a8cbb93c11f518499c4dcb35cb43a5216 | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-1 - Structural Consent - B01 | Minor Variation - BCO10250493-1 | Minor Variation - BCO10250493-1
783ea1bf-95d8-4127-a3b3-d9df1b8242f5 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-1 - Structural Consent - B01 | Council Inspections - BCO10250493-1
58b5b362-d324-51be-b910-a24795ea3fce |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-1 - Structural Consent - B01 | Council Inspections - BCO10250493-1 | Council Inspection - 05.06.2018 (ICB)
cc00619a-0047-5343-91ec-deac856429ca |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-1 - Structural Consent - B01 | Council Inspections - BCO10250493-1 | Council Inspection - 04.04.2019 (ISF)
d0ca6bb1-0f77-5aeb-a826-dfe364ddbdb3 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-1 - Structural Consent - B01 | Council Inspections - BCO10250493-1 | Council Inspection - 09.04.2019 (ICA)
2ea45549-06f2-5603-bb2e-5b2ecf0f5c5a |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-1 - Structural Consent - B01 | Council Inspections - BCO10250493-1 | Council Inspection - 04.09.2019 (IF2)
347c5792-ac8c-402f-a00e-78dc5edb69c4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-1 - Structural Consent - B01 | Council Audits - BCO10250493-1
0b5a7113-35ba-4ecb-8cc6-fd6b5d7db846 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-1 - Structural Consent - B01 | Compliance Documentation - BCO10250493-1
e962024f-4844-4d37-aff5-34321c102944 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-1 - Structural Consent - B01 | Compliance RFIs - BCO10250493-1
b255016e-f4cb-4240-82ac-5ffb58ec3e70 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-1 - Structural Consent - B01 | Code of Compliance (CCC) - BCO10250493-1
3ef48cff-2acf-4afd-b5bd-a058a060f843 |  | folder-normal | fail |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01
a19462dc-a58b-4d2c-aa97-d778d310eab0 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Building Consent - BCO10250493-2
700f0ef5-9a99-4904-8859-ac8201451352 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Minor Variation - BCO10250493-2
058b08fd-28f7-4733-9d29-ebc31c7217ca |  | checklist-flat | not-started | 6e7d7f453688aa574c9c028ffd95658a8cbb93c11f518499c4dcb35cb43a5216 | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Minor Variation - BCO10250493-2 | Minor Variation - BCO10250493-2
2260ae5c-3126-4752-a217-3fd863e3ccc0 |  | folder-normal | fail |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Council Inspections - BCO10250493-2
f39e676f-81db-549b-89d3-77ab99d6545b |  | checklist-flat | fail | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Council Inspections - BCO10250493-2 | Council Inspection - 28.02.2019 (IPL)
83e51fa5-13a6-5c49-b153-90c4813b67e1 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Council Inspections - BCO10250493-2 | Council Inspection - 08.05.2019 (IPL)
ffae9fdf-835c-548c-9cb2-9f8e87f8e40d |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Council Inspections - BCO10250493-2 | Council Inspection - 17.06.2019 (IPL)
ddaeb0fa-9ccc-5617-abba-c7c3386e34fb |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Council Inspections - BCO10250493-2 | Council Inspection - 19.08.2019 (IPB)
f18d4511-364e-5bf7-a7f6-879e7c7bd948 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Council Inspections - BCO10250493-2 | Council Inspection - 26.08.2019 (IPB)
5c6edcf3-fa05-5147-b6ba-220a965b463d |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Council Inspections - BCO10250493-2 | Council Inspection - IME (Site Meeting) 25/05/2020
5e9ae1b2-7d71-46a7-a643-a8f6b2d826b0 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Council Inspections - BCO10250493-2 | Council Inspection - 26/07/2021 (Final IF2)
f0507214-32c5-4e20-8057-f3f6bd483408 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Council Audits - BCO10250493-2
0c6a5197-435c-4d79-b93c-2b821d3ee0d8 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Compliance Documentation - BCO10250493-2 (TBC - Send to Conqa)
055bafa3-2ba1-4b79-b493-47a2b2930752 |  | checklist-flat | work-in-progress | Add Compliance - Fire consent (V1) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Compliance Documentation - BCO10250493-2 (TBC - Send to Conqa) | Fire consent -
7cbc065d-659e-4860-8a2e-7743fad548a8 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Compliance RFIs - BCO10250493-2
614add0c-ff50-4261-a123-e065c7cfaa57 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-2 - Fire Consent - B01 | Code of Compliance (CCC) - BCO10250493-2
82350f1a-362c-4bf3-8af5-1db60f8bf534 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01
7510ba3d-d371-43f2-8b82-55efa22a3ece |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Building Consent - BCO10250493-3
6f87a26a-0b51-46e4-9a65-23d22dc059ee |  | folder-normal | not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Minor Variation - BCO10250493-3
cfedfc24-5047-486c-b78b-b54bcc5e1071 |  | checklist-flat | not-started | 6e7d7f453688aa574c9c028ffd95658a8cbb93c11f518499c4dcb35cb43a5216 | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Minor Variation - BCO10250493-3 | Minor Variation - BCO10250493-3
fb10cf1d-e638-4315-bd0d-1e03a9fad0b9 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Council Inspections - BCO10250493-3
19ea9787-7f3b-5df7-86a2-be8e8f8ab052 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Council Inspections - BCO10250493-3 | Council Inspection - 01.03.2019 (IPP)
784b91bc-88cd-565c-97e6-8d1f55a3a816 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Council Inspections - BCO10250493-3 | Council Inspection - 01.04.2019 (IPP)
f039b862-dcf0-5267-b3e0-fbb730706424 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Council Inspections - BCO10250493-3 | Council Inspection - 08.07.2019 (IPP)
d0232f9b-2bd3-5ca5-8906-818b8fb7738c |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Council Inspections - BCO10250493-3 | Council Inspection - 13.08.2019 (IPP)
3d094477-29d8-5e86-bd0f-451286c90398 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Council Inspections - BCO10250493-3 | Council Inspection - 02.09.2019 (IPP)
b4542048-3cb1-5844-bf6c-775a9dbbb1e3 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Council Inspections - BCO10250493-3 | Council Inspection - 17.09.2019 (IPP)
cf46e1c4-7ee9-5b1e-85b6-9c18e29ba8fb |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Council Inspections - BCO10250493-3 | Council Inspection - 21/05/2020 IF2
f0c24249-1658-4193-aa6b-e521ed522227 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Council Audits - BCO10250493-3
f02dffc0-2a41-409b-bd82-f85ee1b72861 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Compliance Documentation - BCO10250493-3
496f69da-694a-4a8b-8e07-a52cf8384e3f |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Compliance RFIs - BCO10250493-3
f10f98c2-4139-4b58-b29e-63bf1bf0fd74 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-3 - Mechanical & Hydraulic - B01 | Code of Compliance (CCC) - BCO10250493-3
1163e176-c24f-4f82-9886-2562743530e0 |  | folder-normal | fail |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01
3c261f8a-cc41-42d5-9831-f85bbd3010b8 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Building Consent - BCO10250493-4
1bc428bd-45c4-425d-be83-9243a54bdf34 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Minor Variation - BCO10250493-4
6c3249c6-d0dc-48eb-9129-24e04651565c |  | checklist-flat | not-started | 6e7d7f453688aa574c9c028ffd95658a8cbb93c11f518499c4dcb35cb43a5216 | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Minor Variation - BCO10250493-4 | Minor Variation - BCO10250493-4
3076899e-45e9-41d0-985d-805c172249b7 |  | folder-normal | fail |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Council Inspections - BCO10250493-4
38ab9371-353f-5068-b67f-271fc3289617 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Council Inspections - BCO10250493-4 | Council Inspection - 20.02.2019 (IPL)
e17cfff7-614f-5cfb-8df5-64c65a87efe4 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Council Inspections - BCO10250493-4 | Council Inspection - 27.02.2019 (IPL)
5f38aa1b-e9c6-5c92-a816-03d73df10483 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Council Inspections - BCO10250493-4 | Council Inspection - 13.03.2019 (IPL)
47ce8b3d-18ba-5b5b-b4c0-af93ffb22cfc |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Council Inspections - BCO10250493-4 | Council Inspection - 01.04.2019 (ICA)
a0ace88f-2fbf-58a3-8709-2f6619eb549e |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Council Inspections - BCO10250493-4 | Council Inspection - 27.03.2019 (IPL)
04c1928e-3a98-5338-b492-814eebce0581 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Council Inspections - BCO10250493-4 | Council Inspection - 27.03.2019 (IPB)
801986d3-b0ce-5e0e-b911-71e8ec0b48c5 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Council Inspections - BCO10250493-4 | Council Inspection - 11.04.2019 (IPL)
982e3d72-0414-5eec-b61c-c751540485b9 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Council Inspections - BCO10250493-4 | Council Inspection - 12.04.2019 (IPB)
818a0565-01b1-51a1-a1c3-f0eb5adfc015 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Council Inspections - BCO10250493-4 | Council Inspection - 04.04.2019 (ISF)
06847f15-79b2-541d-a96b-332053b7f8c3 |  | checklist-flat | fail | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Council Inspections - BCO10250493-4 | Council Inspection - IF2 (Commercial Final) 29/05/2020
7da097af-7e19-40c5-b614-1d18c5400b92 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Council Audits - BCO10250493-4
833ef04e-47a7-4830-88fd-ceef4c28f5e3 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Compliance Documentation - BCO10250493-4
17f5441c-0b3b-4359-8569-bdd5bcdd562d |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Compliance RFIs - BCO10250493-4
ddbf5f6e-44a3-480b-b750-3215677bab25 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 01 | BCO10250493-4 - Envelope & Fit out - B01 | Code of Compliance (CCC) - BCO10250493-4
1ae4140a-a1a2-409c-9aa1-4a2e112bdd06 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02
c2ad61e7-c157-4617-ae14-054fdbe93ef9 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-1 - Structural Consent - B02
b1539a3c-e1d0-4e52-a65e-f19912cea20d |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-1 - Structural Consent - B02 | Building Consent - BCO10175131-1
e1b4a425-0582-4c99-acb8-7b8c2902e18b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-1 - Structural Consent - B02 | Council Inspections - BCO10175131-1
263af9ec-d810-42c6-b44e-de0a99268173 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-1 - Structural Consent - B02 | Compliance Documentation - BCO10175131-1
14e8f8b0-9aba-413b-92a9-a87678713763 |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-1 - Structural Consent - B02 | Code of Compliance (CCC) - BCO10175131-1
b57683a7-75ee-4d86-ac55-ba8f98733c40 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-2 - Mechanical & Hydraulic - B02
d9febced-158d-44e1-8e9c-402c63153493 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-2 - Mechanical & Hydraulic - B02 | Building Consent - BCO10175131-2
4c067d2f-9c3f-4b4e-875d-6fdd3345963e |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-2 - Mechanical & Hydraulic - B02 | Code of Compliance (CCC) - BCO10175131-2
c33365ad-3a9e-4bfc-84d3-27cc8ee24a42 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-3 - Fire - B02
0ce7df3c-5483-46fd-ac2e-3d48380cc2aa |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-3 - Fire - B02 | Building Consent - BCO10175131-3
7b19857a-9953-41f7-8840-344f876d71a4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-3 - Fire - B02 | Council Inspections - BCO10175131-3
921e710e-aca2-45cb-9805-89874a45aa68 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-3 - Fire - B02 | Compliance Documentation - BCO10175131-3
cc362ce5-cfdd-4d5d-a87f-035cae67b0a2 |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-3 - Fire - B02 | Code of Compliance (CCC) - BCO10175131-3
7d4c6d57-7602-4964-b575-e816a95a6907 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-4 - Envelope & Fit out - B02
25278176-251a-4e38-8485-cdc9d11d44c9 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-4 - Envelope & Fit out - B02 | Building Consent - BCO10175131-4
0e84d2a7-14c8-4982-b389-01c201d0dab1 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-4 - Envelope & Fit out - B02 | Council Inspections - BCO10175131-4
baffaada-b9ca-4889-9d9c-915e43d74c27 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-4 - Envelope & Fit out - B02 | Compliance Documentation - BCO10175131-4
9326e5bc-7895-4e00-bd30-da318a4c0e20 |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 02 | BCO10175131-4 - Envelope & Fit out - B02 | Code of Compliance (CCC) - BCO10175131-4
1413611b-aa64-4c79-bffc-b6a8c15ff265 |  | folder-normal | fail |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03
5b67d574-7e5a-488e-af14-419935646f5a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-1 - Structural Consent - B03
8fa6872e-2602-4a45-9c47-a5559c84ffdb |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-1 - Structural Consent - B03 | Building Consent - BCO10267070-1
dcdbc97e-6942-46f2-8384-1b153cb188c3 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-1 - Structural Consent - B03 | Council Inspections - BCO10267070-1
b46a5e62-9a92-50d6-ae8b-43a023563be9 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-1 - Structural Consent - B03 | Council Inspections - BCO10267070-1 | Council Inspection - 14.05.2019 (IME)
b746a7ab-7782-5d4e-afdb-efdeb7f31fd6 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-1 - Structural Consent - B03 | Council Inspections - BCO10267070-1 | Council Inspection - 16.06.2019 (IFG)
0c2396ce-d2ea-5401-b9f9-4d3959acebd4 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-1 - Structural Consent - B03 | Council Inspections - BCO10267070-1 | Council Inspection - 11.09.2019 (IF2)
a9d8a87b-7052-4419-9a6c-60b0bfcf4726 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-1 - Structural Consent - B03 | Compliance Documentation - BCO10267070-1
a0180823-e6c2-455e-8b51-1e4f0e885ce3 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-1 - Structural Consent - B03 | Compliance RFIs - BCO10267070-1
789d456c-a376-4a96-8ccb-85f97f32d062 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-1 - Structural Consent - B03 | Code of Compliance (CCC) - BCO10267070-1
3e2b3ffc-5914-4f86-845f-28cb953f32d1 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-2 - Mechanical & Hydraulic - B03
3f7638bb-c525-450c-9046-1605b70bee9e |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-2 - Mechanical & Hydraulic - B03 | Building Consent - BCO10267070-2
2d594357-1e10-43a9-b2fc-1cb08c30b36a |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-2 - Mechanical & Hydraulic - B03 | Council Inspections - BCO10267070-2
00342963-4cd4-58c4-8a10-d4711d0cce34 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-2 - Mechanical & Hydraulic - B03 | Council Inspections - BCO10267070-2 | Council Inspection - 06.11.2019 (IPP)
cea5cfaf-94a5-507e-b303-a29d91b33e65 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-2 - Mechanical & Hydraulic - B03 | Council Inspections - BCO10267070-2 | Council Inspection - 29.07.2019 (IPP)
31362b1e-c1a8-5ddf-af04-5709df6af927 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-2 - Mechanical & Hydraulic - B03 | Council Inspections - BCO10267070-2 | Council Inspection - 02.08.2019 (IPB)
024c9002-7a75-5892-ad49-36185f17546f |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-2 - Mechanical & Hydraulic - B03 | Council Inspections - BCO10267070-2 | Council Inspection - 18.12.2019 (IF2)
0ff8d868-54fa-471b-8464-74149962b2b7 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-2 - Mechanical & Hydraulic - B03 | Compliance Documentation - BCO10267070-2
098a3083-21bd-57be-b648-d152b96f5e03 |  | checklist-flat | pass | Add Compliance - Mechanical & Hydraulic consent (V1) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-2 - Mechanical & Hydraulic - B03 | Compliance Documentation - BCO10267070-2 | Mechanical & Hydraulic consent - BCO10267070-2
7e17bbf3-ebf9-44cf-86c8-7fbc9fbc2a10 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-2 - Mechanical & Hydraulic - B03 | Compliance RFIs - BCO10267070-2
d8d41570-c6e2-49ef-91c5-282279505e0c |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-2 - Mechanical & Hydraulic - B03 | Code of Compliance (CCC) - BCO10267070-2
6d558c1f-6671-4210-92a7-5aecd3fc46b1 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-3 - Fire - B03
85ee56ea-cb29-40c9-a7c2-1176b1762b18 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-3 - Fire - B03 | Building Consent - BCO10267070-3
84aa3ca4-750d-49a7-a342-bfe9dc35d482 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-3 - Fire - B03 | Council Inspections - BCO10267070-3
e03e6908-69f2-5c56-9eff-d3a5aa82e67d |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-3 - Fire - B03 | Council Inspections - BCO10267070-3 | Council Inspection - 18.12.2019 (IF2)
aa0bc064-42e5-4f2d-8469-1e424064136e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-3 - Fire - B03 | Compliance Documentation - BCO10267070-3
6884ae72-85bb-4e37-a27e-91289673cb8d |  | checklist-flat | work-in-progress | Add Compliance - Fire consent (V1) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-3 - Fire - B03 | Compliance Documentation - BCO10267070-3 | Fire consent -
13a90f18-91ee-4796-aefd-19d86ddfd410 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-3 - Fire - B03 | Compliance RFIs - BCO10267070-3
c1338602-14fd-4c24-bd1c-5254de150423 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-3 - Fire - B03 | Code of Compliance (CCC) - BCO10267070-3
47b6b66d-bdfd-4f04-a47b-a96f2cd657e1 |  | folder-normal | fail |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03
d6d60b11-6565-4fe6-9b84-e0fe74c7f3a9 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Building Consent - BCO10267070-4
cd2e30d1-09e5-4e76-b611-dcb0a7b2b9e9 |  | folder-normal | fail |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4
258c94cc-8d64-5ec3-8fe5-5ceff30bcbf3 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 12.06.2019 (IFG)
5a8b4168-54b7-5e46-b394-99ef93fa45db |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 25.06.2019 (ICA)
9ac460df-a2a4-57a8-9b16-a87cc2d08022 |  | checklist-flat | fail | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 04.07.2019 (ICA)
f58bf53c-134a-569e-8e5f-f6b684353b7b |  | checklist-flat | fail | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 12.07.2019 (IFG)
ed6daf52-f3dd-59a9-8f4f-bf36cda195e8 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 15.07.2019 (IME)
3319ec44-2375-5387-b7bd-fb039083b648 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 22.07.2019 (ICL)
68e291cc-cd3f-5da2-98ac-0e33968c22e1 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 27.07.2019 (IPL)
ca270b33-63bb-5292-81a7-7a2ba893c48a |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 29.07.2019 (IPP)
becde84d-8304-50b2-a528-b68f5ae3accf |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 14.08.2019 (ICA)
6335dd3e-f0e4-5255-83ec-874f9e8ce5f1 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 14.08.2019 (IPB)
fd0ea6e3-7564-5d07-8cf8-d81f2601d184 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 16.08.2019 (IPB)
7e45f997-9b3d-5a42-8fd7-1d9ab2e1cbad |  | checklist-flat | fail | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 08.09.2019 (ICA)
09c2a878-c7ce-550b-be20-58ad72ddc0ec |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 05.09.2019 (ICL)
12424244-9370-54f2-ad5a-5b96b1c5411f |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 27.09.2019 (IPB)
e5baab24-fe85-5128-a6dc-735bdbaf2240 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 19.11.2019 (ICA)
d6f5bb0d-aca5-5b8a-9d8b-463fb802fe0b |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 29.11.2019 (IF2)
13ee8acd-c399-5ab5-9141-236c0ae2c316 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 29.11.2019 (IF2)
9897aae0-2943-521a-82a1-6d0a978aae00 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 03.12.2019 (IF2)
28498e54-11af-56b0-8031-0d05b0cd8e34 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 05.12.2019 (IF2)
e2f73e65-68ca-5d18-b90b-5a0b36995317 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 09.12.2019 (IF2)
fa83d9d6-8467-5eb2-82d2-fed327587058 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Council Inspections - BCO10267070-4 | Council Inspection - 12.12.2019 (IF2)
c4e82f79-d8ea-4ebb-b973-edc7e2e569c8 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Compliance Documentation - BCO10267070-4
95dba1da-2e0a-409b-b621-a8ea551e5f7a |  | checklist-flat | work-in-progress | Add Compliance -Fitout consent (V1) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Compliance Documentation - BCO10267070-4 | Fitout consent -
ea45bc23-9f64-4d01-9693-1b06f354da51 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Compliance RFIs - BCO10267070-4
7dd948e3-704b-4cca-983d-380c97e757d5 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 03 | BCO10267070-4 - Envelope & Fit out - B03 | Code of Compliance (CCC) - BCO10267070-4
062fcb3c-e794-42df-aa1e-aa8e491d6859 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04
33f9818d-0847-45b8-bb16-3e6f5a1b43c7 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-1 - Piling/ Foundation Consent - B04
088c59c5-caac-4576-aa34-51352065efb4 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-1 - Piling/ Foundation Consent - B04 | Building Consent - BCO10280737-1
519adb4a-1ef5-4f3f-9fa8-8270a55a1f37 |  | folder-normal | not-applicable |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-1 - Piling/ Foundation Consent - B04 | Minor Variations - BCO10280737-1
86901ec4-5e86-5e5f-bba2-2dd9cea3f82b |  | checklist-flat | not-applicable | 6e7d7f453688aa574c9c028ffd95658a8cbb93c11f518499c4dcb35cb43a5216 | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-1 - Piling/ Foundation Consent - B04 | Minor Variations - BCO10280737-1 | Minor Variation - No Minor Variations
b5dff954-f441-4d66-b08c-373433ea1c89 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-1 - Piling/ Foundation Consent - B04 | Council Inspections - BCO10280737-1
d495d05f-457f-5c2f-902a-02314e7dd4c5 |  | checklist-flat | not-applicable | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-1 - Piling/ Foundation Consent - B04 | Council Inspections - BCO10280737-1 | Council Inspection - 26/05/2020
2df02efa-8aa1-52f6-898e-56baa7649a30 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-1 - Piling/ Foundation Consent - B04 | Council Inspections - BCO10280737-1 | Council Inspection - IME (Site Meeting) 06/08/2020
9691fb90-3bed-52a1-bacc-fd2454a4e1fc |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-1 - Piling/ Foundation Consent - B04 | Council Inspections - BCO10280737-1 | Council Inspection - IME (Site Meeting) 30/09/2020
3df442b1-210c-53b5-83a9-7066276e74c7 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-1 - Piling/ Foundation Consent - B04 | Council Inspections - BCO10280737-1 | Council Inspection - IF2 (Commercial Final) - 25/11/2020
4f53b47b-4e08-4077-82b6-5a9fe41d74e0 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-1 - Piling/ Foundation Consent - B04 | Compliance Documentation - BCO10280737-1
ac56426e-1f79-55d2-9c74-7ebef1f439fa |  | checklist-flat | pass | 5b6f70e4695add13b302441403f0cac79477f4b50d6644741b4f2c4a20028470 | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-1 - Piling/ Foundation Consent - B04 | Compliance Documentation - BCO10280737-1 | Piling/ Foundation Consent
cc59a572-7ab3-4c5c-a630-22ebe9f0ef81 |  | folder-normal | not-applicable |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-1 - Piling/ Foundation Consent - B04 | Compliance RFIs - BCO10280737-1
1f0b5832-9e6b-5201-b862-1049ab9aa4f4 |  | checklist-flat | not-applicable | 3ae4689b652b141d8784980bb34ee6e555ea80d26f41df3ba8fbaa97c4e5ff65 | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-1 - Piling/ Foundation Consent - B04 | Compliance RFIs - BCO10280737-1 | RFI
1ba62015-7b29-475e-946e-981037558edb |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-1 - Piling/ Foundation Consent - B04 | Code of Compliance (CCC) - BCO10280737-1
3ce4e80f-b1d0-4ecb-89a0-42c62caf7649 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04
ad1d54dd-56cd-449f-a23b-22d64236f575 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Building Consent - BCO10280737-3
cdb9158c-2ad8-4268-af70-f4e78c75a7bf |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Minor Variations - BCO10280737-3
96f34663-7e2f-4ff9-a67c-46ce81ddd093 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Audit - BCO10280737-3
f9d2362f-2305-563a-a723-21de48f356ee |  | checklist-sectioned | not-started | 4ff51df14d1e64ef7395b0188dfe9fc98db1723c77511edcef21873e06ab43e2 | checklist | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Audit - BCO10280737-3 | Constructor Assessment- Superstructure -B04
96d9f585-7fe4-462b-9ee6-aa7f785bd2db |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3
689500d8-aa22-4a11-8507-c44479a0e4eb |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IPP (Plumbing) - 29/10/2019
4a85364d-7c5a-4ed6-8087-770f91c6dd44 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - ISF (Waived) - 06/12/2019
29cc2e45-905d-49dc-ad53-160a96c09692 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 11/03/2020
1cff1e00-7b04-4ed1-975e-f0f00ef11256 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 11/03/2020 | Council Inspection Uploaded - 11/03/2020
41960cf1-8d32-4967-a85d-c74fb4aa26d3 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 11/03/2020 | Close out of observations - 11/03/2020
a06c4a59-046f-5420-93e9-892cc1ba4c2f |  | checklist-flat | pass | Add Observation Closeout Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 11/03/2020 | Close out of observations - 11/03/2020 | Observation 1 - Setout plans
a3573db3-7c28-5908-abe5-7de1045ce16e |  | checklist-flat | pass | Add Observation Closeout Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 11/03/2020 | Close out of observations - 11/03/2020 | Observation 2 - Geotech inspections
b47b1b9d-0f6d-5651-84d3-1d2978e57b1c |  | checklist-flat | pass | Add Observation Closeout Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 11/03/2020 | Close out of observations - 11/03/2020 | Observation 3 - Waterproofing
e8911f58-033e-530b-b025-262f6fb3003e |  | checklist-flat | pass | Add Observation Closeout Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 11/03/2020 | Close out of observations - 11/03/2020 | Observation 4 - MV Site notes
5fcd53bc-112f-58ea-a484-bf4a41a350e2 |  | checklist-flat | pass | Add Observation Closeout Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 11/03/2020 | Close out of observations - 11/03/2020 | Observation 5 - Precast concrete production certificates
7b76e0c3-c971-5696-9420-f787f82cef59 |  | checklist-flat | pass | Add Observation Closeout Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 11/03/2020 | Close out of observations - 11/03/2020 | Observation 6 - Documentation evidencing all in-situ concrete works
3805289b-8983-5006-b3b4-1c224dc9039f |  | checklist-flat | pass | Add Observation Closeout Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 11/03/2020 | Close out of observations - 11/03/2020 | Observation 7 - Ryman Healthcare QA evidence
4c6a5290-a195-5dcd-bc0f-bf8dd0383afd |  | checklist-flat | not-applicable | Add Observation Closeout Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 11/03/2020 | Close out of observations - 11/03/2020 | Observation 8 - Any other documentation or third party evidence
209e0a43-7d34-5606-8eac-91144f97f7c9 |  | checklist-flat | pass | Add Observation Closeout Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 11/03/2020 | Close out of observations - 11/03/2020 | Observation 9 - Change Register
e39c038c-1872-55e4-84e1-079249f5affe |  | checklist-flat | pass | Add Observation Closeout Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 11/03/2020 | Close out of observations - 11/03/2020 | Observation 10 - Under slab wastes
0e286ef3-219b-5d8a-a184-2383588fedfe |  | checklist-flat | not-applicable | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) 02/06/2020
e7e2c8a6-0ae8-5b8d-84f8-bcdd6a3f10c1 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - ISF (Concrete Floor Slab) - 12/06/2020
b1006c59-502b-5a95-beb7-83e88ee190cf |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - ICB (Concrete block/nib/Insitu) - 12/06/2020
790dc643-9dc7-5957-8c5a-92c443659521 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 17/06/2020
ebe44737-fc5c-5ce5-a672-f94cb6bc4771 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - ISF (Concrete Floor Slab) - 23/06/2020
5b238b63-3dbc-5ba2-b417-c9d859f611b5 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) - 04/09/2020
8d327505-4487-539e-8efe-17bdadbaca84 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IME (Site Meeting) 02/10/2020
adb06f72-9035-5e5d-b6f7-04aba4ff38f1 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Council Inspections - BCO10280737-3 | Council Inspection - IF2 (Commercial Final) - 25/11/2020
b2d7d641-6716-4720-a191-a42b66163da1 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Compliance Documentation - BCO10280737-3
5257d20a-9b19-5af1-8fc9-f27445e6ec19 |  | checklist-flat | work-in-progress | f6e09ef19f2a604fce90a7a9f17759762b8631d64674076215ba97eae9d2fdc4 | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Compliance Documentation - BCO10280737-3 | Structural Consent
1bb08e6a-243a-4589-8a25-a1e7a2a77eff |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Compliance RFIs - BCO10280737-3
6a5022ba-4fa7-4b18-9c2b-65a3271ccbb4 |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-3 - Structural Consent - B04 | Code of Compliance (CCC) - BCO10280737-3
ff9a2a5e-916f-4fde-98ca-dcf2c37b1592 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04
f3dbb4f6-44fb-46c0-8415-5a0f601499c8 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Building Consent - BCO10280737-4
82466f78-37c7-40cf-940f-2f575a90a060 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Minor Variations - BCO10280737-4
452d4c94-cd2e-5011-a78d-b49de726a37e |  | checklist-flat | pass | 6e7d7f453688aa574c9c028ffd95658a8cbb93c11f518499c4dcb35cb43a5216 | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Minor Variations - BCO10280737-4 | Minor Variation - 10/09/2020
2450f3bd-4933-4544-b4f2-6f60f73bfe66 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4
25ba38a2-4112-50c3-9600-b1cecc119a8f |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 15/06/2020
43469186-9b3a-589e-8cbf-b5ae53b817bd |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 23/06/2020
4e030954-c115-5e28-8562-3b09060b095e |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 30/06/2020
706a3919-8bbe-5815-b621-2eb1a7f490c4 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 07/07/2020
dcfc3c83-43ca-533a-9121-181c88914c28 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 14/07/2020
462b3925-4de2-5a53-b695-395ac603ed81 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 21/07/2020
337af581-0c3a-56b7-a112-682ebe90ca06 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 28/07/2020
50d8ed81-4350-5a04-b526-863d3cc06e03 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IME (Site Meeting) - 03/08/2020
aff9a3b0-1813-5453-88af-756ee62652c3 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 04/08/2020
69fcfc9e-70f6-50c3-8813-b64fbecba25b |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 12/08/2020
b23e7bfe-f1c6-5b28-8437-f41942b58757 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 18/08/2020
b4ebaa95-2051-52ec-bd7c-8b8372143108 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 20/08/2020
22c8beb2-0a8c-576c-8f79-bafdc96b0b0b |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 25/08/2020
db33d906-f6ac-5b9f-9a88-e1d72c242715 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 01/09/2020
6d78bd58-1234-55ac-a4c4-a31d294f3a72 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 08/09/2020
cd7a266a-5a23-58de-9505-d3417161efa4 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 10/09/2020
d59ddbea-9eee-5346-81d7-7d16b55751a1 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 15/09/2020
cb3fedda-d0ab-5cca-8add-c60897f4063b |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 17/09/2020
18835850-c08d-5dd2-8b48-c06d52ab9a76 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 22/09/2020
4df40e22-fcdf-5447-a1b9-770bd8ee818f |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IME (Site Meeting) 29/09/2020
5ed8ac79-a26b-5bac-bc50-7aee59c53a36 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 06/10/2020
b5307b44-4a3d-5ce6-b162-e24e8d8dcbf1 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 13/10/2020
435d8570-21e6-5447-b0bc-50a85659d1ae |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IPP (Plumbing) - 20/10/2020
d595bf86-b403-5f48-ac17-f0f961dcadf6 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IME (Site Meeting) - 27/10/2020
64cf8d65-7231-5f8c-8fb1-da4ae11049ea |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Inspections - BCO10280737-4 | Council Inspection - IME as final on 09/04/2021
af8a9634-aa01-4ff8-82fd-1edefefa184a |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Council Audits - BCO10280737-4
646f8198-7b53-4660-83f4-7561ff67e13f |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Compliance Documentation - BCO10280737-4
11486384-3b37-5b26-9459-65704530b722 |  | checklist-flat | pass | Add Compliance - Mechanical & Hydraulic consent (V1) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Compliance Documentation - BCO10280737-4 | Mechanical & Hydraulic consent - BCO10280737-4
fce7c6f7-a6b4-4850-8aea-9a800c661bde |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Compliance RFIs - BCO10280737-4
452f691f-f811-425e-8bdd-ea37633c172f | Unsupported Children: folder-normal RFI Management of Individual Items(3f2d63df-e341-5862-8a1b-de0a684c2755) | checklist-sectioned | pass | Add CCC RFI Checklist (V3) | checklist | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Compliance RFIs - BCO10280737-4 | RFI
3f2d63df-e341-5862-8a1b-de0a684c2755 |  | folder-normal | no-status-started |  | step | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Compliance RFIs - BCO10280737-4 | RFI | RFI Management of Individual Items
4af435f6-50c9-4612-be67-922a40cf5341 |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Code of Compliance (CCC) - BCO10280737-4
586fa4a0-8bd5-498d-8130-80bf46421ddb |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Fluid Hydraulic Services Inspections Job no. FHD522
c94d607a-fdc9-5fc5-837c-6e016b721423 |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-4 - Mechanical & Hydraulic - B04 | Fluid Hydraulic Services Inspections Job no. FHD522 | Inspection - 29/10/2020
8879a90a-b451-4653-9154-0f38c582a5ae |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04
d17c978f-ad72-4161-a974-de081aa32ada |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Building Consent - BCO10280737-5
d1fc61ae-f1e4-401d-8108-9e414baafbc3 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Minor Variation - BCO10280737-5
dca043c3-d06e-4446-b3c5-c49aefac9c85 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5
645a1a50-eb07-5931-8716-786523412d96 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IPL (Post-Line) - 03/07/2020
0cd9441c-bc65-5e42-b4ba-b01580d49829 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IPL (Post-Line) - 15/07/2020
1063636c-1ec4-5531-84cd-faa82da9c79f |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IPL (Post-Line) - 22/07/2020
c3790155-0e17-56d3-b252-f7a8c7358993 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IME (Site Meeting) - 29/07/2020
cab8b7b6-702b-573b-bb08-b314695caf1e |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IME (Site Meeting) - 26/08/2020
ea8f0068-a003-5f66-bb8c-e7c47ef85f8b |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IPL (Post-Line) - 02/09/2020
791448b8-8bb1-5fd1-af8f-4d3797707294 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IME (Site Meeting) - 09/09/2020
955b3174-0d39-5fda-b1d0-105e9ec6b842 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IME (Site Meeting) - 16/09/2020
32fef966-3486-50d9-b437-db38c9026014 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IPL (Post-Line) 23/09/2020
b3cfa059-7fc8-5af0-b516-34b3d1d1087b |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IME (Site Meeting) 30/09/2020
124bf8dc-b3e5-58b1-96a6-c20c1d753281 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IPL (Post-Line)- 07/10/2020
f2ad90e2-b85e-59db-bff8-bd0cebacddad |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IPL (Post-Line) - 14/10/2020
ac5ad140-91fb-5c93-ba3a-27f7229bb5e9 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IME (Site Meeting) - 21/10/2020
93930a3f-d37f-5d3e-ad33-d6afd89ebbc0 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IME (Site Meeting) - 28/10/2020
3f7672fd-caae-5715-bf95-6a8ad1b916d2 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IPL (Post-Line) - 04/11/2020
d0522b9f-27d0-5e5c-9ee3-563a4f3c1b64 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IME (Site Meeting) - 11/11/2020
f2e23b27-003a-5dfa-bb2a-3f13e4344726 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IME (Site Meeting) - 02/12/2020
6de41961-155c-5ea5-813b-4ff6f831ca02 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IME (Site Meeting) 09/04/2021
4dd0bc6b-4fb3-5d17-b448-462ceeb6def4 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IME (Site Meeting) 12/04/2021
e628a324-9fb3-54ff-8577-1d894f5a6745 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Inspections - BCO10280737-5 | Council Inspection - IF2 (Final Inspection) 07/05/2021
71266040-a8fb-4771-acb1-2cb7ee5ffe54 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Council Audits - BCO10280737-5
f0fb8f5b-aea0-4751-8039-85b5b338ab92 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Compliance Documentation - BCO10280737-5
10f33e00-4a40-5038-8786-3f1244edb038 |  | checklist-flat | pass | Add Compliance - Fire consent (V1) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Compliance Documentation - BCO10280737-5 | Fire consent - BCO10280737-5
c57c1667-8ee5-4cd8-bbdd-3761fdbb2007 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Compliance RFIs - BCO10280737-5
2ec2131e-b72e-41ef-a461-f86e31b2ad8d |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-5 - Fire - B04 | Code of Compliance (CCC) - BCO10280737-5
e13bf516-41b2-482c-8cb4-f4e85e235cae |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04
fd93820c-96ba-4e14-bef1-d3bfc014245a |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Building Consent - BCO10280737-6
def3194a-c0dc-419d-ba3c-07150192a8ff |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Minor Variation - BCO10280737-6
7586831b-214a-5d5f-8dca-f4d40e7ed8c0 |  | checklist-flat | pass | 6e7d7f453688aa574c9c028ffd95658a8cbb93c11f518499c4dcb35cb43a5216 | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Minor Variation - BCO10280737-6 | Minor Variation - 9/06/2020
cc462631-2f82-5e34-a64b-24188c43527b |  | checklist-flat | pass | 6e7d7f453688aa574c9c028ffd95658a8cbb93c11f518499c4dcb35cb43a5216 | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Minor Variation - BCO10280737-6 | Minor Variation - 10/09/2020
2e5aa7a3-f5e3-5cc2-ba3d-66f39102cd38 |  | checklist-flat | pass | 6e7d7f453688aa574c9c028ffd95658a8cbb93c11f518499c4dcb35cb43a5216 | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Minor Variation - BCO10280737-6 | Minor Variation - 15-09-2020
557d7538-3f00-55bf-b4d5-9c52c2d8908e |  | checklist-flat | pass | 6e7d7f453688aa574c9c028ffd95658a8cbb93c11f518499c4dcb35cb43a5216 | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Minor Variation - BCO10280737-6 | Minor Variation - 25/08/2020
67f8f6a6-4ffc-43f7-9cf3-48d70c6f1843 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6
d6aee41d-8ad0-51dd-a519-2cdf5cbe0c8a |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - PCO Fitout (Pre-Construction Meeting) - 03/03/2020
24269cbb-db41-5b04-a7ef-feb6d17c8332 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - PCO Facade (Pre-Construction Meeting) - 03/03/2020
2fea9e1b-016a-5580-b1e7-42d03ad92d19 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - ICA (Cavity Wrap) - 14-05-2020
895e00f4-583b-58c1-9c2d-f2f8d00ded34 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection -IME (Site Meeting) - 04/06/20
b667d8a7-d12f-584a-85a6-f94b5ce58e4d |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - ICA(Cavity Wrap) - 27/05/2020
2c7899b7-b3e9-55e3-abfb-4f888a2aa181 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 09/06/2020
2d24218f-5cdb-5f63-93a1-1cf32d9766c8 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - ICA (Cavity Wrap) - 11/06/2020
e5024e71-9ec5-5dd9-b82e-629957a08baf |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IFG (Framing) - 16/06/2020
930f11ab-a4e7-5b11-a3ec-b2897b04978a |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IFG (Framing) - 18/06/2020
7f1da03f-d3ba-5316-90bf-ffeda58bc597 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Pre-Line) - 23/06/2020
4bfe2ead-71f1-5803-8f45-ad4bdfc79112 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 25/06/2020
b909dc31-0b6b-54d8-a480-e36d24f7f8a9 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Pre-Line) - 26/06/2020
2f813cf3-52c3-5cfc-b301-579b64ceb6b2 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - ICA (Cladding) - 29/06/2020
72c4640e-a6f8-5c6c-aadf-3fee2972cddf |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Preline) - 30/06/2020
11e042f9-cc72-57f8-8bf9-92d6f80295b9 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IFG (Framing) - 07/07/2020
8dbef4b3-717f-52db-a4ee-1e7afbea117f |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Pre-Line) - 09/07/2020
e8b8601a-2a8b-5b95-ae90-f43931cc9124 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - ICA (Cavity Wrap) - 21/07/2020
d9709103-0693-555d-843b-d7b3fe95eaf2 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Pre-Line) - 22/07/2020
e75f79da-f400-5d7b-a58f-cc64e921bb1b |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - ICL (Cladding) - 27/07/2020
4cc7995e-62d0-51b4-8ce2-ae254e0702bc |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Preline) - 31/07/2020
b993215b-ba09-50f4-b8c0-0edf57d77410 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPL (Post-Line) - 04/08/2020
c87db32f-bd69-549e-85b9-671b0df8e8b5 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - ICL (Cladding) - 05/08/2020
5e6c3482-8791-516a-ab07-d4e0fe9486ae |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Pre-Line) - 04/08/2020
ffa7bb78-b491-5bef-9533-435b327207d3 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Preline) - 06/08/2020
01130d61-4c5b-50cb-b630-09e1d51f3bc9 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - ICL (Cladding) - 10/08/2020
dd73aeab-84e6-5c3d-baff-19408c88e53d |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Pre-Line) - 11/08/2020
19d3e0be-fc0a-50fd-8992-354fbcbfcd44 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IFG (Framing) - 17/08/2020
9f6ee210-cd85-5490-9bc2-80c9c07852c7 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IFG (Framing) - 18/08/2020
7e892ada-8e0b-5b41-af8e-702fd4f57627 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Pre-Line) - 21/08/2020
52ce4219-b2f0-56d3-9ffb-dc85f41dd248 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 25/08/2020
eddbcd2a-ad9d-5275-af30-05c061021e5c |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPL (Post-Line) - 27/08/2020
3f2c1107-800d-5575-93fb-44eb3d414b80 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 01/09/2020
f8a07f60-2b8c-5a95-aa8a-9267a4b6ec6e |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 03/09/2020
531aea8f-5917-5741-a2b4-fc3e7e456442 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 03/09/2020
189aabf8-1891-500e-9d7a-b86235f6c185 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - ICA (Cavity Wrap) - 03/09/2020
89ca4f4d-72a4-5241-a13d-3285076c2419 |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Pre-Line) - 09/09/2020
701a093f-7ac2-5028-a79c-0c4259a39f85 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 15/09/2020
629a7cdb-918b-5e7e-85ad-aed2e6097a47 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 17/09/2020
45be4101-fbe3-5325-82b9-8650f7bd5141 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Pre-Line) - 22/09/2020
a8773384-d952-523b-93c8-2cbd0bad9af9 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 22/09/2020
808664d2-9827-5de4-8361-30de1f1922bb |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 24/09/2020
edf70b1f-e90b-570d-a3fd-1a886c61a31b |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 29/09/2020
157c800f-8885-5c58-a48b-ac2e2ede6d13 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Pre-Line) - 30/09/2020
3a4655ff-602d-5d4c-b4c3-86c29f5927bb |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - ICA (Cavity Wrap) - 01/10/2020
845d13d2-ce65-5183-81ec-c0ef37ccebda |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPL (Postline) - 06/10/2020
a0f4cd2f-3bd6-58fe-9ed7-8d22925966ac |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Preline) - 06/10/2020
abd6910d-8716-5a16-9c3e-1ad1855d0792 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IFG (Framing) - 06/10/2020
651f5919-be59-516f-b128-1176c8592bda |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 06/10/2020
1d6020c4-2c9e-5247-9200-1b25526eff88 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPB (Pre-Line) 07/10/2020
8e33fca6-0ce2-547c-ae5b-bfe8169d4559 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 07/10/2020
9fee5a70-c2fd-5298-a695-f1c07bdba111 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 07/10/2020
5646603b-1e34-54be-9710-83d5bcf2c15d |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - ICA (Cavity Wrap) - 08/10/2020
9806b8fe-be59-56e4-88c6-15226818a56d |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 08/10/2020
ae587b1b-153e-5355-9d5a-51d361a5c2cd |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 14/10/2020
ee3bdd6f-be97-57f4-b15b-2495708e7714 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 15/10/2020
a59cd10f-cda7-5f9a-a955-f2e997d78b39 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 21/10/2020
5e93f596-beb4-5c61-abf4-c60ff7e51408 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 22/10/2020
3da7484e-e571-50de-ac2c-82d24f92b3bb |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 29/10/2020
2d87a3f3-6d31-52e1-a43b-00fece06daba |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 28/10/2020
cbb62dad-a688-54f5-aefc-bd718482e755 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 29/10/2020
3e1a3bdc-e409-559f-89ce-77923f3c6285 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 29/10/2020
5915c6e0-f610-5ca7-956f-c578f3f08ec6 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 04/11/2020
b90f3604-8acb-591e-ac0f-4f33b2683233 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 05/11/2020
99e8d0b8-9088-574c-b7d0-d33a6d38b196 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 06/11/2020
cfe7d53b-5e2d-5a3d-a020-6b587f64a5df |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 11/11/2020
aab52d0f-ac42-5a05-b8c6-a010bd285c28 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final - 29/10/2020
697f1e52-ca27-52d6-ba80-f37b78004ba2 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 11/11/2020
b8997c7d-b186-5b37-a435-0ce8618b6b4a |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 12/11/2020
985834f1-81d6-59b6-91d3-034a9d271639 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 12/11/2020
da9d60a4-efaa-5007-914e-c4f81fd0628e |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 05/11/2020
58479676-96ae-5f20-a73a-d685e1f4ddde |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 13/11/2020
a4abecf8-7f84-512b-98de-17ba169c2df5 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 16/11/2020
f2ab4128-d61c-5604-8455-08421126c526 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 16/11/2020
32dc965b-7d70-5df0-9724-ca2d697e161d |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 18/11/2020
9a17d710-545b-5dac-abea-f323a34c96c6 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 25/11/2020
92ac685a-6ad4-5a8e-9cbe-f96abd2a7184 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 25/11/2020
5addbdbd-ada5-52a2-a3fb-4d1c4591a195 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 02/12/2020
51c9467b-3591-5ded-980c-06f76264d2fb |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 03/12/2020
4df06139-180f-5cb1-9fe3-0e0ef0c82bed |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 09/12/2020
c8e1aaff-56b1-58d8-9f2a-4efed0957e1e |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 10/12/2020
93e81f00-c8c6-570e-96af-0813ac518bd3 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 18/12/2020
a279ffb6-c645-5c4a-976c-7314e06ebc57 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 12/01/2021
ff6b530d-a716-5f69-9865-169fa9ad6095 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 14/01/2021
d73d2487-5715-5bc5-a8a0-7e24a620085c |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 21/01/2021
f9900f7a-b053-53f4-a9e6-302bb665382e |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 28/01/2021
f88c64a4-dc48-5a1b-a3d1-a655fff54324 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IPL (Post-line) - 24/02/2021
0dc3b491-dd8e-567f-94e8-c4ea62282e54 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 25/02/2021
321c7c80-dfab-5a2b-b54d-773f0656e483 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IF2 (Commercial Final) - 10/03/2021
6921826c-037b-5d5c-9325-75fb2aec19de |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME (Site Meeting) - 13/04/2021
8110caa2-c2fa-5801-99e6-28ef6e26cc88 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Inspections - BCO10280737-6 | Council Inspection - IME 11/5/2021
5aeecb39-8ab8-4414-b1e5-a1d788b4e0dd |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Council Audits - BCO10280737-6
cc92a586-687e-4e48-87af-60856f25d8d2 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Compliance Documentation - BCO10280737-6
b04d2faa-f6ff-576d-acd0-9e94414d4221 |  | checklist-flat | pass | Add Compliance -Fitout consent (V1) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Compliance Documentation - BCO10280737-6 | Fitout consent - BCO10280737-6
bd748da6-ed01-5b1e-ac2a-201a3280d842 |  | checklist-flat | pass | Add Compliance - Facade consent (V1) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Compliance Documentation - BCO10280737-6 | Facade consent - BCO10280737-6
0550a044-6300-43ba-901a-4af8c5891a8d |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Compliance RFIs - BCO10280737-6
968abb29-967c-5516-95de-5abbc048cbe2 | Unsupported Children: folder-normal RFI Management of Individual Items(8edfd677-1f9a-52d2-b678-53cc6c5ff32c) | checklist-sectioned | pass | Add CCC RFI Checklist (V3) | checklist | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Compliance RFIs - BCO10280737-6 | RFI -
8edfd677-1f9a-52d2-b678-53cc6c5ff32c |  | folder-normal | no-status-started |  | step | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Compliance RFIs - BCO10280737-6 | RFI - | RFI Management of Individual Items
4ce19d34-be53-4d04-b919-fe7791f8a66e |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-6 - Envelope & Fit out - B04 | Code of Compliance (CCC) - BCO10280737-6
cdf5633a-1a7c-4aea-824a-b5fb73ab08d1 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-7 - Retaining Walls & Fire Egress Stairs- B04
f8390886-84aa-5271-ac45-71b173de247a |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-7 - Retaining Walls & Fire Egress Stairs- B04 | Building Consent - BCO10280737-7
f8ffe13f-4ccb-47f3-867c-c87094926b4f |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-7 - Retaining Walls & Fire Egress Stairs- B04 | Minor Variations - BCO10280737-7
5344c077-ae0a-4f5b-9fd8-1e7803de2503 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-7 - Retaining Walls & Fire Egress Stairs- B04 | Council Audit - BCO10280737-7
ecdc2847-e53b-42b0-b5ec-e7617cecc4ef |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-7 - Retaining Walls & Fire Egress Stairs- B04 | Council Inspections - BCO10280737-7
25104ec1-e4ae-5ba8-b8c7-69826469ade5 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-7 - Retaining Walls & Fire Egress Stairs- B04 | Council Inspections - BCO10280737-7 | Council Inspection - PCO (Pre-Construction Meeting) - 26/08/2020
528c37d9-e45e-5aef-aa2c-df15f60ae726 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-7 - Retaining Walls & Fire Egress Stairs- B04 | Council Inspections - BCO10280737-7 | Council Inspection - IME (Site Meeting) - 21/10/2020
444ebba5-55d7-5341-8183-79f5b86635de |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-7 - Retaining Walls & Fire Egress Stairs- B04 | Council Inspections - BCO10280737-7 | Council Inspection - IME (Site Meeting) - 26/11/2020
f1e9cdf4-ee5d-5409-ab7e-831f82c6d158 |  | checklist-flat | pass | Add CONSENT - Retaining Wall Consent | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-7 - Retaining Walls & Fire Egress Stairs- B04 | Compliance Documentation - BCO10280737-7
7eba68fd-a1df-598a-a5aa-3c1fdbd8a573 |  | checklist-flat | not-applicable | 3ae4689b652b141d8784980bb34ee6e555ea80d26f41df3ba8fbaa97c4e5ff65 | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-7 - Retaining Walls & Fire Egress Stairs- B04 | Compliance RFIs - BCO10280737-7
2f7a7a08-2ede-5216-b110-ee63003cc13b |  | checklist-flat | pass | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 04 | BCO10280737-7 - Retaining Walls & Fire Egress Stairs- B04 | Code of Compliance (CCC) - BCO10280737-7
216a81ef-22da-41cd-a0e8-b0c943f45913 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 05
70f5ad09-94a0-4762-a21f-515b35c07019 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 06
35ca91f1-a07f-469b-997f-e6b8ee4c691b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 07
97cefb86-cce1-4055-a43f-f41d987691c2 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08
dc50c5e8-fe84-47b7-8c85-78d00cca3c6e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08
5b7a4bbe-4d48-5fb8-b8dc-dfc0d7571059 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Building Consent - BCO10303734-1
ea811b1d-14ef-421b-ad9a-38c98a38c253 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Minor Amendments - BCO10303734-1
81accc34-b00a-59d8-aa0c-26fc22b5f479 |  | checklist-flat | not-started | Add Council BC Amendment Checklist (V3) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Minor Amendments - BCO10303734-1 | Council BC Amendment - Shell Beams & Waterproofing
79b003fe-0c9a-429d-aa6b-6858069844c3 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1
39520391-36a3-52dc-b879-034d400872f7 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - Pre-start Meeting - 29/04/2021
9fff0caf-91a2-5e73-94e8-5bdfe4771b84 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - Variation with consented drawing 1 - 02/06/2021
7ade5eea-f10c-5c50-9519-d255ffbe8885 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - Variation with consented drawing 2 - 16/06/2021
f8fa42be-3656-525e-8cd5-68dafab36e91 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - Plumbing (IPP) - 01/06/2021
adacad6d-9fe5-51d4-b8ba-bf6261e9076e |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - Plumbing (IPP) -23/06/2021
95a7a9b9-41a1-5998-80df-8bc09192e10a |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - Membrane tanking(ITK) - 23/06/2021
14038bb4-785a-571b-966e-c68bc1e02bfe |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - Plumbing(IPP) - 30/06/2021
522e72f0-bf9a-5a17-a3a5-ead49b90810a |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - IFO - 01/07/2021
62f471ea-a389-4cce-ac20-644c0413f76c |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - PCO -15/07/2021
b5bd0a24-de67-4a6c-aa53-e2b61c0ffabe |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - ACO - 16/07/2021
9c50f03b-4f36-448f-9754-c852b9c7cd8d |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - ACO - 03/08/2021
9acf6d98-6771-431a-9400-e393dd82ba06 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - IPP - 10/08/2021
2f8517c1-e996-4c4f-8244-003cc1931d1b |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - IPP - 11/08/2021
1cd36b58-78af-4a23-8248-db6a2fa78234 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - ITK - 27/09/2021
30f23e69-8c8b-45a6-8f9a-9902616f7d1c |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - IFO - 29/09/2021
6c8e1c33-9d39-4764-9f74-13eef7bc6a30 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - IME -09/11/2021
28c1b028-12b6-487e-96a3-dc7fcf58575b |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Council Inspections/Audits - BCO10303734-1 | Council Inspection - IF2 PASS - 09/11/2021
cc5faea0-8de7-45f4-8824-14f00362d97d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Compliance Documentation - BCO10303734-1
901291fb-d7b5-5d7f-a18e-1b9514c1d25f |  | checklist-flat | work-in-progress | Add Compliance - Piling Foundation Structural consents (V1) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Compliance Documentation - BCO10303734-1 | Piling Foundation Structural consents - BCO10303734-1
f6ff420a-c648-59cd-b1bf-c331faf3b6a0 | Unsupported Children: folder-normal Code Compliance Certificate RFI's(62007627-3774-5484-bbff-f46d9f201c4b) Child Code Compliance Certificate RFI's(62007627-3774-5484-bbff-f46d9f201c4b) -- RFI -(5268d19f-1fbe-5791-8e10-5487165c2233): Unsupported Children: folder-normal RFI Management of Individual Items(037221cd-5c64-52f1-aa66-90a9440459fa) | checklist-sectioned | not-started | bc185ddc8e692eb56186a0eaa54992897089f68b14bb2d119183977dbd11be63 | checklist | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Code Compliance Certificate - BCO10303734-1
62007627-3774-5484-bbff-f46d9f201c4b |  | folder-normal | not-started |  | step | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Code Compliance Certificate - BCO10303734-1 | Code Compliance Certificate RFI's
466a7777-be52-5137-a721-b0e28bf92e7c |  | folder-progress | no-status-not-started |  | checklist | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Code Compliance Certificate - BCO10303734-1 | Code Compliance Certificate RFI's | RFI -TEST
5268d19f-1fbe-5791-8e10-5487165c2233 | Unsupported Children: folder-normal RFI Management of Individual Items(037221cd-5c64-52f1-aa66-90a9440459fa) | checklist-sectioned | not-started |  | checklist | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Code Compliance Certificate - BCO10303734-1 | Code Compliance Certificate RFI's | RFI -
037221cd-5c64-52f1-aa66-90a9440459fa |  | folder-normal | not-started |  | step | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Code Compliance Certificate - BCO10303734-1 | Code Compliance Certificate RFI's | RFI - | RFI Management of Individual Items
e712fce6-9190-5cb4-ae7e-c9d5f007b7bb |  | checklist-flat | not-started |  | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Code Compliance Certificate - BCO10303734-1 | Code Compliance Certificate RFI's | RFI - | RFI Management of Individual Items | Individual RFI -
e00c147b-7251-426e-b14f-9fde521db30f |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Minor Variation - BCO10303734-1
006ebb82-6ad8-4379-be14-b2b99abb28d9 |  | checklist-flat | pass | Add Council BC Minor Variation Checklist (V3) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Minor Variation - BCO10303734-1 | Auckland Council Minor Variation - 14/02/2022
dbd421a8-acb7-453a-a6a6-53e42d66a08e |  | checklist-flat | pass | Add Council BC Minor Variation Checklist (V3) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-1 Foundation Consent - B08 | Minor Variation - BCO10303734-1 | Auckland Council Minor Variation - 09/05/2022
f60d9052-33e0-4b87-aaa9-e9905680b9f5 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08
8b9487de-9992-5f5c-9e03-cd02b5fa2289 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Building Consent - BCO10303734-2
e8d0f068-b349-461d-96c4-45bfa82d490b |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Minor Variations - BCO10303734-2
be0c84f3-13d7-46b4-8198-c745aad47bc9 |  | checklist-flat | pass | Add Council BC Minor Variation Checklist (V3) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Minor Variations - BCO10303734-2 | Auckland Council Minor Variation - 09/05/2022
75abbb39-a866-455e-a182-aaa9c91f90c8 |  | checklist-flat | pass | Add Council BC Minor Variation Checklist (V3) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Minor Variations - BCO10303734-2 | Auckland Council Minor Variation - 07/06/2022
550fc018-9b24-4b79-86bd-a054bd2f7015 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Council Inspections - BCO10303734-2
4a2f0ab5-a10e-40a1-bcd0-d141bb7f0bb6 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Council Inspections - BCO10303734-2 | Council Inspection - (IME) - 14/07/2021
86a1a422-58fd-4f9f-8e65-495b0616b8fe |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Council Inspections - BCO10303734-2 | Council Inspection - PCO -15/07/2021
8ad253d3-83c7-4f3d-bc2c-bb4a4a057a18 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Council Inspections - BCO10303734-2 | Council Inspection - IPP - 11/08/2021
3767b3a4-564c-4716-94e3-213a18cb56a8 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Council Inspections - BCO10303734-2 | Council Inspection - ICB - 04/10/2021
f73318b8-e474-4a78-812e-b74fedffe6c3 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Council Inspections - BCO10303734-2 | Council Inspection - ACO - 19/11/2021
0310f378-dc2a-48f6-a03b-39e04a04bcb2 |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Council Inspections - BCO10303734-2 | Council Inspection - IME - 12/04/22
ad757d2c-3671-427c-901a-e082927a2d43 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Council Inspections - BCO10303734-2 | Council Inspection – IME – 04/05/22
da9ece94-dad7-4e55-9ddb-a001ac59d543 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Council Inspections - BCO10303734-2 | Council Inspection – IME – 13/05/22
40b060fd-a56d-47d0-9629-66e92a609104 |  | checklist-flat | pass | Add Consultant Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Council Inspections - BCO10303734-2 | Council Inspection - IME - 20/05/22
c6efc67c-6786-4d1d-94f6-0f5146445178 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Council Inspections - BCO10303734-2 | Council Inspection - ICB - 24/05/22
5057518b-e2f7-4ced-8471-0871a377949b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Compliance Documentation - BCO10303734-2
d6b099ea-cc06-4296-9750-174a565fa2d6 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Compliance RFIs - BCO10303734-2
88994ea5-23ba-59ca-bd43-194d3bd11037 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-2 - Superstructure Consent - B08 | Code of Compliance (CCC) - BCO10303734-2
d1185586-1106-4518-af9f-a653a53bb320 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-3 - Mechanical & Hydraulic Consent - B08
4a6eb1a2-e499-5713-9442-7aadd5458f65 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-3 - Mechanical & Hydraulic Consent - B08 | Building Consent - BCO10303734-3
7d9973f2-b001-47a9-97ce-5ee23268bda3 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-3 - Mechanical & Hydraulic Consent - B08 | Minor Variations - BCO10303734-3
46b5e3cd-c3f0-4be8-98e3-fc7d9d575bdb |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-3 - Mechanical & Hydraulic Consent - B08 | Council Inspections - BCO10303734-3
5a8283d0-3fd5-4b27-9ccf-d0569cebdc27 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-3 - Mechanical & Hydraulic Consent - B08 | Council Audits - BCO10303734-3
4f5206f8-14a2-465a-b97d-1a8fb0ab7a94 |  | checklist-flat | pass | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-3 - Mechanical & Hydraulic Consent - B08 | Council Audits - BCO10303734-3 | Council Inspection - IPP - 14/10/2021
cd5fe0c5-2110-4009-9ef4-cf175103acc3 |  | folder-normal | not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-3 - Mechanical & Hydraulic Consent - B08 | Compliance Documentation - BCO10303734-3
e007ff8f-cada-5325-bd44-05129489424e |  | checklist-flat | not-started | Add Compliance - Mechanical & Hydraulic consent (V1) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-3 - Mechanical & Hydraulic Consent - B08 | Compliance Documentation - BCO10303734-3 | Mechanical & Hydraulic consent - BCO10303734-3
1e200927-267e-4f91-ad4c-1604246813aa |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-3 - Mechanical & Hydraulic Consent - B08 | Compliance RFIs - BCO10303734-3
6becd122-45e4-5330-a4e5-9602cb9ecfe5 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-3 - Mechanical & Hydraulic Consent - B08 | Code of Compliance (CCC) - BCO10303734-3
f4f94825-5842-48a2-8663-4bcfd3bde552 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-4 - Fire Design Consent - B08
9189133d-1b66-5ad0-9cc8-12e12c13cb9d |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-4 - Fire Design Consent - B08 | Building Consent - BCO10303734-4
1b4bbb52-5d86-4f2d-98ee-8ce631d370d8 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-4 - Fire Design Consent - B08 | Minor Variations - BCO10303734-4
13d5e978-d1b4-4532-a647-ed465a6bad0d |  | checklist-flat | pass | Add Council BC Minor Variation Checklist (V3) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-4 - Fire Design Consent - B08 | Minor Variations - BCO10303734-4 | Auckland Council Minor Variation 05/05/22
64ff2e80-a7c3-46c8-86a6-2fda3b5751dd |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-4 - Fire Design Consent - B08 | Council Inspections - BCO10303734-4
6016e749-51b5-4736-9a40-3e079ddb1af4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-4 - Fire Design Consent - B08 | Council Audits - BCO10303734-4
a0bc2934-ba42-46dd-80af-ee5fa325c14a |  | folder-normal | not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-4 - Fire Design Consent - B08 | Compliance Documentation - BCO10303734-4
66e29598-0785-5072-b044-3af6a3c8e2fb |  | checklist-flat | not-started | Add Compliance - Fire consent (V1) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-4 - Fire Design Consent - B08 | Compliance Documentation - BCO10303734-4 | Fire consent - BCO10303734-4
7f137e62-e635-4f21-9218-00a765ff2b70 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-4 - Fire Design Consent - B08 | Compliance RFIs - BCO10303734-4
8f42ebc7-72c4-5e05-9146-8a329b89c707 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-4 - Fire Design Consent - B08 | Code of Compliance (CCC) - BCO10303734-4
5cdef810-32a3-4d24-8b8f-042aaa3a08ca |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-5 - Fitout & Envelope Consent - B08
b8a514c8-4252-45dc-9676-f00c7c68d2fa |  | checklist-flat | not-started | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-5 - Fitout & Envelope Consent - B08 | Building Consent - BCO10303734-5
a38faf00-46b3-4cb9-93fa-6bd8f909ae31 |  | folder-normal | pass |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-5 - Fitout & Envelope Consent - B08 | Minor Variation - BCO10303734-5
6e4814a0-8fc1-4e6e-89ca-98c712006955 |  | checklist-flat | pass | Add Council BC Minor Variation Checklist (V3) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-5 - Fitout & Envelope Consent - B08 | Minor Variation - BCO10303734-5 | Auckland Council Minor Variation 05/05/22
540ca303-6d28-49ae-a018-136c80b93c9c |  | checklist-flat | pass | Add Council BC Minor Variation Checklist (V3) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-5 - Fitout & Envelope Consent - B08 | Minor Variation - BCO10303734-5 | Auckland Council Minor Variation - 03/05/22
d3f574f8-4804-4d29-8023-6ee1dd3f9c25 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-5 - Fitout & Envelope Consent - B08 | Council Inspection - BCO10303734-5
6c156a06-d00b-4da6-86be-44f547a05a54 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-5 - Fitout & Envelope Consent - B08 | Council Audits - BCO10303734-5
03514128-d986-43eb-9404-fc835d538d7a |  | checklist-flat | work-in-progress | Add Compliance -Fitout consent (V1) | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-5 - Fitout & Envelope Consent - B08 | Compliance documents - BCO10303734-5
599c1170-a10c-485f-9c3c-e79d9fbe4b32 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-5 - Fitout & Envelope Consent - B08 | Compliance RFIs - BCO10303734-5
23a6f09c-afa4-4803-851b-522f23a8d5da |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | Building 08 | BCO10303734-5 - Fitout & Envelope Consent - B08 | Code of Compliance (CCC) - BCO10303734-5
d540c220-63ba-4b33-ac91-148366067022 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BCO10268029 - Generator Enclosure
1103715f-c7b5-4ad9-ac54-dc3813142838 |  | checklist-flat | pass | Add Council BC Upload Checklist | checklist-flat | TRUE | TRUE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BCO10268029 - Generator Enclosure | Building Consent - BCO10268029
2c5232b8-98ca-4ca8-a8a9-61b329d9faca |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BCO10268029 - Generator Enclosure | Minor Variation - BCO10268029
7481ee9a-5fa7-4e63-8b74-f311b7b48d07 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BCO10268029 - Generator Enclosure | Council Inspections - BCO10268029
89860122-7ee4-5843-8f24-ec4324269e19 |  | checklist-flat | work-in-progress | Add Council Inspection Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BCO10268029 - Generator Enclosure | Council Inspections - BCO10268029 | Council Inspection - IME (Site Meeting) 25/05/2020
f5599665-22ca-4a8a-9b02-b5ea1c29884e |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BCO10268029 - Generator Enclosure | Council Audits - BCO10268029
22c93830-d1cf-4b5a-97cb-5f8726c4d1a6 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BCO10268029 - Generator Enclosure | Compliance Documentation - BCO10268029
61624263-4e56-4949-99cc-bf720bf0967a |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BCO10268029 - Generator Enclosure | Compliance RFIs - BCO10268029
eefe3b5f-d6d8-49a6-9345-39a5837042f4 |  | checklist-flat | not-started | Add Council CCC Upload Checklist | checklist-flat | FALSE | FALSE | Building Consents (Includes BC, Inspections, Audits & Compliance Docs) | BCO10268029 - Generator Enclosure | Code of Compliance (CCC) - BCO10268029
ae741fc1-5ec7-4392-97cf-23df05f7c7c3 |  | folder-normal | not-started |  | step | TRUE | FALSE | TEST FOLDER - EXAMPLE AC CHECKLISTS
f9c6baab-33c3-426e-8714-1c2519d6b2b9 |  | folder-normal | not-started |  | step | TRUE | FALSE | TEST FOLDER - EXAMPLE AC CHECKLISTS | EXAMPLE AUDIT TEMPLATES
0bca951f-0f0d-43f5-85a5-ad6e0774ebc5 |  | checklist-sectioned | not-started | 4ff51df14d1e64ef7395b0188dfe9fc98db1723c77511edcef21873e06ab43e2 | checklist | FALSE | FALSE | TEST FOLDER - EXAMPLE AC CHECKLISTS | EXAMPLE AUDIT TEMPLATES | Constructor Assessment- Structural Superstructure - test 27/04/20
581703f9-0548-4efd-b461-291f4f4eeeb6 |  | checklist-sectioned | not-started | 4ff51df14d1e64ef7395b0188dfe9fc98db1723c77511edcef21873e06ab43e2 | checklist | FALSE | FALSE | TEST FOLDER - EXAMPLE AC CHECKLISTS | EXAMPLE AUDIT TEMPLATES | Constructor Assessment- Structural Superstructure - 28/04/2020
40e2e512-6328-505d-bedc-c19fdf83b8d4 |  | checklist-sectioned | not-started | 4ff51df14d1e64ef7395b0188dfe9fc98db1723c77511edcef21873e06ab43e2 | checklist | FALSE | FALSE | TEST FOLDER - EXAMPLE AC CHECKLISTS | EXAMPLE AUDIT TEMPLATES | Constructor Assessment- Structural Superstructure - test 3
e24444a2-2b33-5131-803a-40087b23e5c7 |  | checklist-sectioned | not-started | e32093df1767002a43ac1e61c48c18ad34610d2a6c0c69ebfc40b6078572c196 | checklist | FALSE | FALSE | TEST FOLDER - EXAMPLE AC CHECKLISTS | EXAMPLE AUDIT TEMPLATES | Constructor Audit - Structural Superstructure - Test 5
76b4414e-6b36-52cb-a3a8-0eebf5ba0b07 |  | checklist-sectioned | not-started | 057979c7ce2b5ef7233f793491e6beb4ea0f5bdb7827e65c670d9b4794db7e3d | checklist | FALSE | FALSE | TEST FOLDER - EXAMPLE AC CHECKLISTS | EXAMPLE AUDIT TEMPLATES | Constructor Audit - Structural Foundations - Test 6
ddef5146-61b4-58e3-9b6c-45e432fcd7fe |  | checklist-sectioned | not-started | 0eff3d8f9292982d54bfc055b4a941b7109c4ada019c04ff5f34457df949e155 | checklist | FALSE | FALSE | TEST FOLDER - EXAMPLE AC CHECKLISTS | EXAMPLE AUDIT TEMPLATES | Constructor Audit - Structural Superstructure - Test 7
2f2709d4-899b-4b3e-9dfb-3c76006bdbaa |  | folder-normal | not-started |  | step | TRUE | FALSE | TEST FOLDER - EXAMPLE AC CHECKLISTS | EXAMPLE INSPECTION TEMPLATES
5d231e3b-6328-5e0d-97a7-aefbf81564d9 |  | checklist-flat | not-started | c6822500abf06f86b9d564fa9c8e7b9e83a756cd7295deef986f9fd5b8f65ef3 | checklist-flat | FALSE | FALSE | TEST FOLDER - EXAMPLE AC CHECKLISTS | EXAMPLE INSPECTION TEMPLATES | Piling
7b5577c4-985e-519c-9f5f-0fc86db89e32 | Unsupported Children: folder-normal RFI Management of Individual Items(ecf356fc-ee14-512e-86ca-7b6236067eb3) | checklist-sectioned | not-started | 79977f2eedd9cd7fe7e8ca813b7edd79af3eeb0b7ab602b5f8e549c049f6bbef | checklist | FALSE | FALSE | TEST FOLDER - EXAMPLE AC CHECKLISTS | RFI - test
ecf356fc-ee14-512e-86ca-7b6236067eb3 |  | folder-normal | not-started |  | step | TRUE | TRUE | TEST FOLDER - EXAMPLE AC CHECKLISTS | RFI - test | RFI Management of Individual Items
3fa6aeab-c8e3-5557-9395-dfd0868e8519 |  | checklist-flat | not-started |  | checklist-flat | FALSE | FALSE | TEST FOLDER - EXAMPLE AC CHECKLISTS | RFI - test | RFI Management of Individual Items | Individual RFI - 1
e734c3b5-8059-5f60-9581-a4905fa4e330 | Unsupported Children: folder-normal Code Compliance Certificate RFI's(577f165c-dece-5262-8dc7-76c9ba7ec53c) | checklist-sectioned | not-started | bd105343009616f51f47c05d7aa2704d4c21589e8225aa4c76a9d0fa08e6f379 | checklist | FALSE | FALSE | TEST FOLDER - EXAMPLE AC CHECKLISTS | Code Compliance Certificate - BC0 - tst
577f165c-dece-5262-8dc7-76c9ba7ec53c |  | folder-normal | no-status-not-started |  | step | TRUE | TRUE | TEST FOLDER - EXAMPLE AC CHECKLISTS | Code Compliance Certificate - BC0 - tst | Code Compliance Certificate RFI's
76b8ce2e-ed13-5f6e-9c0c-46a338c025ff | Unsupported Children: folder-normal Code Compliance Certificate RFI's(28ac8c67-b537-58a8-88bb-4acc379fde12) | checklist-sectioned | not-started | Add CCC Code Compliance Certificate Checklist | checklist | FALSE | FALSE | TEST FOLDER - EXAMPLE AC CHECKLISTS | Code Compliance Certificate - test
28ac8c67-b537-58a8-88bb-4acc379fde12 |  | folder-normal | no-status-not-started |  | step | TRUE | TRUE | TEST FOLDER - EXAMPLE AC CHECKLISTS | Code Compliance Certificate - test | Code Compliance Certificate RFI's