## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Queens Dr Invercargill | itp |  |  |  |  | ITP - Queens Dr Invercargill
section | 1.0 General
checkpoint | 1.1 - Public Notification
label | VERIFICATION ACTIVITY - Communication
label | METHODS OR REFERENCE - Media/Letter Drop
label | FREQUENCY - Prior to establishing on site and as situation changes.
label | ACCEPTANCE CRITERIA - All relevant properties and stakeholders contacted by works notice.
label | ○ TREIS notification
label | RECORDS - Letter
label | RESPONSIBLE PERSON - Paving Manager / Contract Manager
holdpoint | Mandatory HOLD POINT
checkpoint | 1.2 - Crew Instructions / Crew Briefing Plans
label | VERIFICATION ACTIVITY - Approval
label | METHODS OR REFERENCE - Written Plan
label | FREQUENCY - Prior to work commencing.
label | ACCEPTANCE CRITERIA - Crew Instructions available including all surfacing requirements of the site.
label | RECORDS - CBPs
label | RESPONSIBLE PERSON - Paving Manager / Contract Manager
holdpoint | Mandatory HOLD POINT
checkpoint | 1.3 - TMP
label | VERIFICATION ACTIVITY - Approval
label | METHODS OR REFERENCE - Approved Plan
label | FREQUENCY - Prior to work commencing.
label | ACCEPTANCE CRITERIA - Approved plan from Southland TMC (Simon Wilson)
label | ○ CoPTTM onsite record form used
label | RECORDS - TMP
label | RESPONSIBLE PERSON - Paving Manager / Contract Manager
holdpoint | Mandatory HOLD POINT
checkpoint | 1.4 - Pavement Marking - pickup of existing
label | VERIFICATION ACTIVITY - Data
label | METHODS OR REFERENCE - Road Runner or site measurement
label | FREQUENCY - Prior to milling commences
label | ACCEPTANCE CRITERIA - Road Runner or site measurements
label | RECORDS - Data
label | RESPONSIBLE PERSON - Paving Manager / Contract Manager
holdpoint | Mandatory HOLD POINT
checkpoint | 1.5 - Weather
label | VERIFICATION ACTIVITY - Approval
label | METHODS OR REFERENCE - Weather Forecast Data
label | FREQUENCY - Daily
label | ACCEPTANCE CRITERIA - Consistent dry weather with no significant rainfall. +10oC for duration of paving operations.
label | RECORDS - Site Diary
label | RESPONSIBLE PERSON - Foreman / Contract Manager
holdpoint | Mandatory HOLD POINT
checkpoint | 1.6 - Resurfacing Extents
label | VERIFICATION ACTIVITY - Approval
label | METHODS OR REFERENCE - Site-visit
label | FREQUENCY - Prior to commencement
label | ACCEPTANCE CRITERIA - ICC and Paving Manager visit site to mark and agree extents.
label | RECORDS - Site-visit notes
label | RESPONSIBLE PERSON - Paving Manager / Contract manager
holdpoint | Mandatory HOLD POINT
section | 2.0 Milling Operations (Key Cut + Transation milling + 50mm)
checkpoint | 2.1 - Services located and marked-out.
label | VERIFICATION ACTIVITY - Lay out
label | FREQUENCY - All services within milling limits
label | ACCEPTANCE CRITERIA - Site walk over to confirm all services are marked prior to milling operations beginning and also documented on CBP so all staff are aware.
label | RECORDS - Site Photos
label | RESPONSIBLE PERSON - Foreman / QA
holdpoint | Mandatory HOLD POINT
checkpoint | 2.2 - Dip-checks
label | VERIFICATION ACTIVITY - Measure
label | METHODS OR REFERENCE - Measure each side of the cut the milling machine makes
label | FREQUENCY - Every 10m, each mill run
label | ACCEPTANCE CRITERIA - Dip check during milling to ensure 45mm mill depth achieved prior to placing mix.
label | RESPONSIBLE PERSON - QA / Foreman
holdpoint | Mandatory HOLD POINT
checkpoint | 2.3 - Overmilling
label | VERIFICATION ACTIVITY - Photos and measurements
label | METHODS OR REFERENCE - Photos and measurements
label | FREQUENCY - Prior to resurfacing
label | ACCEPTANCE CRITERIA - ICC and Paving Manager visit site to mark and agree extents.
label | RECORDS - Photos and measurements
label | RESPONSIBLE PERSON - Paving Manager / QA
holdpoint | Mandatory HOLD POINT
checkpoint | 2.4 - Pre-levelling
label | VERIFICATION ACTIVITY - Photos and measurements
label | METHODS OR REFERENCE - Photos and measurements
label | FREQUENCY - Prior to resurfacing
label | ACCEPTANCE CRITERIA - ICC provided opportunity to inspect surface and agree extents of any pre-levelling if required.
label | RECORDS - Site-visit notes
label | RESPONSIBLE PERSON - Paving Manager / QA
holdpoint | Mandatory HOLD POINT
section | 3.0 DG10 PMB Paving (40mm)
checkpoint | 3.0 - DG10 PMB Mix Design verification
label | VERIFICATION ACTIVITY - Lab Testing
label | METHODS OR REFERENCE - NZTA M/10
label | FREQUENCY - Prior to commencement
label | ACCEPTANCE CRITERIA - Mix design compliant with traffic category (Heavy Traffic)
label | ○ Mix design compliant
label | RECORDS - IANZ Lab Reports
label | RESPONSIBLE PERSON - Paving Manager QA
holdpoint | Mandatory HOLD POINT
checkpoint | 3.1 - Production Testing: Binder Content, Aggregate Grading, Maximum Specific Gravity, Temperature
label | VERIFICATION ACTIVITY - Lab Testing
label | METHODS OR REFERENCE - NZTA M/10
label | FREQUENCY - 1 / 200t or maximum of 3 required per production lot
label | ACCEPTANCE CRITERIA - As per material mix design and JMF specification and within production tolerances of table 5.3 NZTA M/10.
label | ○ [exception to production testing that night if <100T were produced after a night where production testing was performed]
label | RECORDS - IANZ Lab Reports
label | RESPONSIBLE PERSON - Paving Manager QA
checkpoint | 3.2 - Membrane
label | VERIFICATION ACTIVITY - On-site check
label | METHODS OR REFERENCE - NZTA M/10
label | FREQUENCY - Prior to DG10
label | ACCEPTANCE CRITERIA - Single coat G4 chipseal with 1.5 l/m² residual binder.
label | RECORDS - Photos
label | RESPONSIBLE PERSON - Paving Manager QA
holdpoint | Mandatory HOLD POINT
checkpoint | 3.3 - Preparation
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - NZTA M/10
label | FREQUENCY - Every section
label | ACCEPTANCE CRITERIA - Paving Plan to be completed for every night with dimensions
label | RECORDS - Paving plan and CBPs
label | RESPONSIBLE PERSON - Paving Manager / Foreman
checkpoint | 3.4 - Cold Joints
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - NZTA M/10
label | FREQUENCY - Every join
label | ACCEPTANCE CRITERIA - Joints not to be below a trafficked wheel path - M10
label | ○ Transverse joints (start and finish) to be offset by 2m in each layer
label | RECORDS - Photos
label | RESPONSIBLE PERSON - Foreman
checkpoint | 3.5 - Check asphalt surface for deficiencies and self identify
label | VERIFICATION ACTIVITY - Visual Inspection
label | METHODS OR REFERENCE - NZTA M/10
label | FREQUENCY - Continuous during paving operation and site walk over post paving.
label | ACCEPTANCE CRITERIA - Visual inspection during paving operation, any areas of segregation are to be addressed prior to compaction
label | RECORDS - Photos and visual inspection
label | RESPONSIBLE PERSON - Paving Manager / QA
holdpoint | Mandatory HOLD POINT
checkpoint | 3.6 - Laying Temperature and Compaction
label | VERIFICATION ACTIVITY - Approval
label | METHODS OR REFERENCE - NZTA M/10
label | FREQUENCY - Every truck load
label | ACCEPTANCE CRITERIA - Arrival temperature within 150deg +/- 10deg to ensure compaction can be achieved as per mix design.
label | RECORDS - IANZ Lab Reports
label | RESPONSIBLE PERSON - QA
holdpoint | Mandatory HOLD POINT
section | 4.0 Quality Assurance
checkpoint | 4.0 - DG10 Sample Results Submission
label | VERIFICATION ACTIVITY - Lab Testing
label | METHODS OR REFERENCE - NZTA M/10
label | FREQUENCY - Once samples have been tested
label | ACCEPTANCE CRITERIA - Production samples meet NZTA M/10 specification
label | RECORDS - IANZ Lab Reports
label | RESPONSIBLE PERSON - Paving Manager
checkpoint | 4.1 - Core sampling result submission
label | VERIFICATION ACTIVITY - Lab Testing
label | METHODS OR REFERENCE - NZTA M/10
label | FREQUENCY - Once samples have been tested
label | ACCEPTANCE CRITERIA - Core samples meet NZTA M/10 specification
label | RECORDS - IANZ Lab Reports
label | RESPONSIBLE PERSON - Paving Manager
checkpoint | 4.2 - Surface Inspection
label | VERIFICATION ACTIVITY - Check ride quality and surface irregularities using straight edge
label | METHODS OR REFERENCE - NZTA M/10 T/10
label | FREQUENCY - Continuous
label | ACCEPTANCE CRITERIA - Site passes the initial NAASRA, <5mm deviation from 3m Straight edge.
label | RECORDS - Site Inspection Record, NAASRA report
label | RESPONSIBLE PERSON - Paving Manager
checkpoint | 4.3 - Pavement Marking
label | VERIFICATION ACTIVITY - Completed
label | METHODS OR REFERENCE - NZTA P/22
label | FREQUENCY - Once
label | ACCEPTANCE CRITERIA - Re-applied as per the existing layout and complies with NZTA P/22 specifications
label | ○ Reinstatement within 24hrs of project finishing. Temporary limit lines installed daily.
label | RESPONSIBLE PERSON - Paving Manager
checkpoint | 4.4 - Service Lids
label | VERIFICATION ACTIVITY - Completed
label | FREQUENCY - At completion
label | ACCEPTANCE CRITERIA - Any service lids that were lowered and not at correct level following works are raised.
label | RESPONSIBLE PERSON - Paving Manager / QA
checkpoint | 4.5 - Bandaging
label | VERIFICATION ACTIVITY - Completed
label | FREQUENCY - At completion
label | ACCEPTANCE CRITERIA - Start and stop extents bandaged.
label | RESPONSIBLE PERSON - Foreman / QA
checkpoint | 4.6 - RAMM pavement and surface records
label | VERIFICATION ACTIVITY - RAMM records
label | METHODS OR REFERENCE - As requested by Asset Management Team
label | FREQUENCY - Within 7 working days of work completed.
label | ACCEPTANCE CRITERIA - Pavement structural layer extents recorded and verified by Paving Manager
label | ○ Surfacing layer extents recorded and verified by Paving Manager
label | ○ Mix design information of all mix provided.
label | RECORDS - RAMM records
label | RESPONSIBLE PERSON - Paving Manager
checkpoint | 4.7 - Final Measurement Check
label | VERIFICATION ACTIVITY - Site measurements
label | METHODS OR REFERENCE - Standard practice
label | FREQUENCY - At completion
label | ACCEPTANCE CRITERIA - Accurate as-built measurements recorded for claim.
label | RECORDS - As Builts
label | RESPONSIBLE PERSON - QA / Paving Manager
checkpoint | Quality Assurance Close Out by:
textbox | (name):
date | Date:
label | This record to contract file.
holdpoint | (signature)