## Table 1
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-002
[11 empty] | Revision : 1 | Date : 23/01/2024
Client: | MRPA |  |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Fitzgerald Road Carpark |  |  | Stripping Topsoil & Topsoil Replacement |  | Name: Fynn Riddick |  | Name: Justin Sciacca |  |  | Name:
Job No: |  |  |  | Specifications: VicRoads Specifications Section 204
|  |  |  | Structure / Component: Earthworks/Civil |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Fitzgerald Road Level Crossing Removal Project |  | Date : 18/01/2024 |  | Date : 25/01/24 |  |  | Date :
Lot No: |  |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub- contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | ITP Signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS | OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS | Visual Inspection | ITP Signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.3 | Ensure correct materials are being used |  | Prior to commencing any activity | -Topsoil placed on formations and disturbed areas shall be capable of supporting healthy, full cover of grass growth, and contain organic material -Topsoil material shall be free from subsoil, tree roots, clay balls, stones, rocks, rubbish, contaminants, weeds, pathogens and toxic levels of any element with a pH in the range of 5 to 8. -Imported topsoil shall conform to the material properties outlined in Table 720.042 | 204.04a | Verify | ITP Signed Material Test Report (Import Only) | TP | Site Engineer | N/A |  | N/A
2 | Stripping Topsoil
2.1 | Survey Set Out |  | Prior to commencing stripping | Area has been pegged out in accordance with the drawings | Work Procedure | Verify | ITP Signed | IP | Site Engineer / Surveyor | N/A |  | N/A
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub- contractor | Date
2.2 | Archaeological monitoring |  | Prior to commencing stripping | The Contractor shall immediately notify the Superintendent if an archaeological site is encountered, or if any suspected artefacts are found. A ‘No-Go Zone’ shall be established for identified Cultural Heritage sites that are to be protected during the work under the Contract and in accordance with the CHMP | CHMP | Visual inspection | ITP Signed | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.3 | Excavation Permit |  | Each lot | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | ITP Signed | HP* | Site Engineer | N/A |  | N/A
2.4 | Designation of stock pile area or disposal site |  | Prior to commencing stripping | An area for stockpiling has been designated or a disposal site identified | 204.05c | Visual Inspection | ITP Signed | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.5 | Weed treatment |  | Prior to commencing stripping | Site has been inspected for noxious weeds and weed treated if present | 204.05c | Visual Inspection | ITP Signed | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.6 | Maintenance of stockpiles |  | Each lot | -Stockpiles maintained neatly and away from stormwater drains -erosion controls in place -stockpile treated to minimise spread of weeds and pathogens | 204.05c | Visual Inspection | ITP Signed | IP | Site Engineer / Site Foreman | N/A |  | N/A
3 | Placing Topsoil
3.1 | Surface finish of cut and fill batters |  | Each lot | The surface of cut and fill batters to be topsoiled shall be textured by scarifying or horizontal grooving | Cl 204.06 (i) | Verify | ITP Signed | IP | Site Engineer / Site Foreman | N/A |  | N/A
3.2 | Topsoil Placement |  | Each lot | Confirm underlying cut/fill areas comply with Cl204.03 before placing topsoil. All disturbed areas not paved or landscaped topsoiled to the following depths: • batter slopes > 2:1 = 50mm min • planting beds = 100mm min • verge - 50mm outer edge to 20mm within 100mm of seal • all other areas – 75mm min | Cl 204.17 | Visual Inspection | ITP Signed | IP | Site Engineer / Site Foreman | N/A |  | N/A
3.3 | Surface level |  | Each lot | Area topsoiled spread, levelled, but not compacted (except verge area). | Cl 204.17 | Visual Inspection | ITP Signed | IP | Site Engineer / Site Foreman | N/A |  | N/A
Final Inspection
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub- contractor | Date
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
6
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent