## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0398-ITP-032 GRE Installation Rev 1 | itp |  |  |  |  | INF-HSEQ CC0398-ITP-032 GRE Installation Rev 1
section | 1.0 Preliminaries
checkpoint | 1.1 - Set out
label | Ref docs - Drawings
label | Acceptance criteria - Is the position of the pipe in accordance with the drawings?
button | Acceptance | Yes,No,N/A
label | Key - H
label | MDR/VIVA - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
textbox | Drawing No.
textbox | Rev
checkpoint | 1.2 - IFC Submission & Approval
label | Ref docs - Drawings
label | Acceptance criteria - Is IFC Construction Drawing and Most Current Revision Approved by the client?
button | Acceptance | Yes,No,N/A
label | Key - W
label | MDR/VIVA - W
checkpoint | 1.3 - GRE pipe confirmation
label | Ref docs - Drawings, QF-108-01 Material Receipt Initial Inspection
label | Acceptance criteria - Has the correct class & type of GRE pipe been supplied and free of defects?
label | ○ Verification of material tag (heat) number
button | Acceptance | Yes,No,N/A
label | Key - H
label | MDR/VIVA - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Material Inspection Checklist
checkpoint | 1.4 - Permits
label | Ref docs - Symal Safety Procedure
label | Acceptance criteria - Have the below permits been created as required.
label | – GPP
label | – Working at Heights
label | – Hot Works
label | – Confined Space
button | Acceptance | Yes,No,N/A
label | Key - H
label | MDR/VIVA - W
checkpoint | 1.5 - Determine Lot Size
label | Acceptance criteria - What is the lot size?
button | Acceptance | Yes,No,N/A
label | Key - S
label | MDR/VIVA - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Lot Map
checkpoint | 1.6 - Joint Pre-Qualifications
label | Ref docs - Qualified technician qualifications and this ITP
label | Acceptance criteria - Technician qualifications submitted to client for approval
label | ○ Welding Qualifications Equipment Calibrations
button | Acceptance | Yes,No,N/A
label | Key - H
label | MDR/VIVA - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Certifications provided to client
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Material Approval
label | Acceptance criteria -
label | Have all materials been approved for use
textbox | Bedding/Haunching Material
textbox | Backfill Material
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
textbox | Material Approval Reference
section | 2.0 Excavation and Bedding
checkpoint | 2.1 - Service Locating
label | Ref docs - DBYD & Services marked on current IFC drawings (if applicable)
label | Acceptance criteria - Current DBYD documents received and works executed by qualified service locator
button | Acceptance | Yes,No,N/A
label | Key - H
label | MDR/VIVA - S
checkpoint | 2.2 - Excavation
label | Ref docs - 235929-000- CV-SP-00006 UG PIPE FAB and INSTALLSect ion 12.1.12
label | ○ SUN_ENG_P RO_015 Bondstrand Piping UG Installation Procedure Section 3
label | Acceptance criteria - Excavation shall be to depth adequate to provide full specified bedding depth.
label | ○ Width of excavation to be 1.25 * OD + 300mm
textbox | Pipe Diameter
label | ○ Earthworks for trenches shall be done in accordance with standard drawing, has this been completed?
label | ○ Trenches to be benched and battered as required (if trench >1m deep). Benches/batters to be 1:1. No material/plant to be placed within zone of influence.
button | Acceptance | Yes,No,N/A
label | Key - W
label | MDR/VIVA - W
checkpoint | 2.3 - Bedding
label | Ref docs - 235929-000- CV-SP-00006 UG PIPE FAB and INSTALL Section 12.1.8.
label | ○ 239529- MG1668- 15740-0400- SD-000010- NOV Bondstrand pipe installation guide - GRE
label | ○ SUN_ENG_P RO_015 Bondstrand Piping UG Installation Procedure Section 3
label | Acceptance criteria - 150mm Bedding to be placed & compacted at the base of the trench.
button | Acceptance | Yes,No,N/A
label | Key - S
label | MDR/VIVA - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Delivery docket
section | 3.0 Bonding & Laying
checkpoint | 3.1 - Above ground fabrication
label | Ref docs - 235929-000- CV-SP-00006 UG PIPE FAB and INSTALL
label | Acceptance criteria - Has works been conducted as per Sunrise ITP SUN_23_003?
button | Acceptance | Yes,No,N/A
label | Key - W
label | MDR/VIVA - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | QF-068-18 – GRE Bonding Joint Record
checkpoint | 3.2 - Lifting into trench
label | Ref docs - 235929-000- CV-SP-00006 UG PIPE FAB and INSTALL Section 12.2.1 Item 12.2.7
label | Acceptance criteria - Before lowering in, caps shall be placed on open ends, flanges, etc., which shall remain in place until piping connection can be made. Particular attention shall be given to the need to protect pipes from damage due to loads from heavy plant, has this been completed?
label | ○ Have pipes been laid to true line and level?
label | ○ Has MDR been notified before the laying of pipework?
button | Acceptance | Yes,No,N/A
label | Key - W
label | MDR/VIVA - S
checkpoint | 3.3 - In ground fabrication
label | Ref docs - 235929-000- CV-SP-00006 UG PIPE FAB and INSTALL
label | Acceptance criteria - Has works been conducted as per Sunrise ITP SUN_23_003?
button | Acceptance | Yes,No,N/A
label | Key - W
label | MDR/VIVA - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | QF-068-18 – GRE Bonding Joint Record
checkpoint | 3.4 - Haunching
label | Ref docs - 235929-000- CV-SP-00006 UG PIPE FAB and INSTALL
label | Acceptance criteria - Has the pipe been haunched?
label | ○ Have voids been removed from haunching material?
button | Acceptance | Yes,No,N/A
label | Key - W
label | MDR/VIVA - S
checkpoint | 3.5 - Survey Pickup
label | Acceptance criteria - Has the pipe been picked up by the surveyor? Tolerances in alignments shall be limited to +/- 25 mm vertically or horizontally, unless otherwise specified on engineering drawing, has this been completed?
button | Acceptance | Yes,No,N/A
label | Key - H
label | MDR/VIVA - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Survey as-built report
section | 4.0 Testing and Conformance Check
checkpoint | 4.1 - Test Pack
label | Ref docs - SUN_ENG_P RO_010 R0 GRE Hydrotesting procedure
label | Acceptance criteria - Has the test pack been reviewed and accepted prior to Hydrostatic Testing?
label | Test Pack to include:
label | – Pipe Runs/Location of testing
label | – Materials initial inspection
label | – Joint Inspections
label | – GRE Bonding Joint Record Form
label | – Flange Record Sheet
button | Acceptance | Yes,No,N/A
label | Key - H
label | MDR/VIVA - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Test Pack
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Hydrostatic Testing
label | Ref docs - 235929-000- CV-SP-00006 UG PIPE FAB and INSTALL Section 13.2
label | ○ SUN_ENG_P RO_010 R0 GRE Hydrotesting procedure
label | Acceptance criteria - Has the pipework been tested as per the manufacturer’s specification for the required duration?
label | Integrity Test
label | ○ 2-hour test –1.5 x design pressure for 2 hour hold (Refer to Hold Point in Subcontactor ITP below). Visual Inspection required of joints upon completion.
label | Leak Test
label | ○ 1.1x design pressure.
bool | 2-hour test – Visual Inspection required of joints upon completion to verify no leaks.
label | ○ Has the pipework passed the testing requirements with no leaks?
label | ○ If no, proceed to item 4.2.
button | Acceptance | Yes,No,N/A
label | Key - H
label | MDR/VIVA - H
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | QF-129-01 – Hydrostatic Test Log Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Repair
label | Ref docs - SUN_ENG_P RO_012 Re-condition of Adhesive Bonding Socket - Joint repair
label | Acceptance criteria - Has the leak been identified?
label | ○ Has the leak been repaired as per the manufacturer’s specification/approved methodology?
label | ○ Has the pipework passed subsequent testing requirements?
button | Acceptance | Yes,No,N/A
label | Key - H
label | MDR/VIVA - H
holdpoint | AUTHORITY HOLDPOINT
section | 5.0 Backfill
checkpoint | 5.1 - Sand Backfill
label | Ref docs - 239529-MG1668-15740-0400-SD-000010-NOV Bondstrand pipe installation guide - GRE
label | Acceptance criteria - Has Sand Back fill been placed to 300mm above Pipe?
label | ○ No compaction equipment to be used until 300mm above pipe.
button | Acceptance | Yes,No,N/A
label | Key - S
label | MDR/VIVA - S
checkpoint | 5.2 - Select Fill Backfill
label | Ref docs - 239529- MG1668-15740-0400-SD-000010-NOV Bondstrand pipe installation guide - GRE
label | ○ 235929-000- CV-SP- 00002 – Earthworks
label | Acceptance criteria - Has select backfill been placed in layers not exceeding 150mm loose thickness?
label | ○ No compaction equipment has been used between 0-300mm above top of pipe, light compaction equipment has only been used from 300-600mm above pipe.
button | Acceptance | Yes,No,N/A
checkpoint | 5.3 - Compaction Testing
label | Ref docs - 235929-000- CV-SP- 00002 – Specification for Earthworks
label | Acceptance criteria - Sand Fill - not less than 90% of maximum density or 70% of relative density, except that under paved areas the entire depth shall be compacted in 150mm layers to not less than 95% of maximum density or 80% relative density
label | ○ Select Fill - Backfill under pavements shall be compacted to a dry density ratio of no less than 98% modified comp active effort.
label | ○ Testing Frequency: Minimum 2 field density tests for each 185 m2 of each compacted fill layer, but no less than 3 tests for total area
button | Acceptance | Yes,No,N/A
label | Key - W
label | MDR/VIVA - S
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | Geotechnical Test Report
section | 5.0 Documentation Submission
checkpoint | 5.1 - Subcontractor ITP
label | Acceptance criteria - Has the subcontractor ITP been signed off and accepted by relevant parties?
button | Acceptance | Yes,No,N/A
label | Key - W
label | MDR/VIVA - W
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -
bool | ITP_SUN_23_ 003