## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-259-CIV-FRMS-Westkon Permanent chain mesh Fencing | itp |  |  |  |  | ITP-259-CIV-FRMS-Westkon Permanent chain mesh Fencing Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-259-CIV-Westkon Permanent chain mesh Fencing
label | ITP Description: Westkon Permanent chain mesh Fencing
label | Discipline (e.g. CIV/STR/RAIL): 259-CIV
label | Revision Number: 0
label | Revision Date: 29/04/2025
label | ITP created by: Kamel Alshobaki
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - IFC Drawings AS1725.5 Vic Roads SD 3131
section | 2. Materials
checkpoint | 2.1 - Concrete
label | Reference - IFC Drawings
label | Acceptance Criteria - Min 20 MPa concrete to be used as per IFC drawings & Vicroads SD3131.
label | Method - Document Review
label | Frequency - Each Mix
label | Category - HP
label | Responsibility - SE/Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Steel components including posts, mesh and fittings
label | Reference - IFC Drawings AS1725.5
label | Acceptance Criteria - All Steel must comply with Australian Standards.
label | ○ Steel section sizes must be checked on site.
label | ○ Steel posts to be CHS with a medium grade.
label | Method - Document review, Visual and Measure
label | Frequency - All elements
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Supplier Certificate of Compliance
date | Date Completed:
section | 3. Pre-construction / Pre-installation Activities
checkpoint | 3.1 - Survey Set-out
label | Reference - IFC Drawings
label | Acceptance Criteria - Survey to set out the following but not limited to: existing services, and fence start and end points.
label | ○ Offset checked against the running edge prior to installation of posts.
label | Method - Visual and Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Construction / Installation Activities
checkpoint | 4.1 - Excavation works
label | Reference - IFC Drawings
label | Acceptance Criteria - Excavation completed by auger outside of service working limits.
label | ○ Follow asset owners guidelines for work around their service.
label | Method - Visual
label | Frequency - Each fence footing
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Ground Conditions
label | Reference - IFC Drawings
label | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | Method - Visual
label | Frequency - Each post
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Fence Footing
label | Reference - IFC Drawings
label | Acceptance Criteria - Footing dimensions for intermediate post is 600mm deep x 250mm diameter and for Intermediate Strainer post is 750mm deep x 250mm diameter. Corner and Ebd post is 900mm deep x 300mm diameter. Gate post with 1.0m - 1.2m Leaf size is 900mm deep x 300mm, Gate post with 1.3m - 3.6m Leaf size is 1000mm deep x 300mm diameter and Gate post with 3.7m - 4.8m leaf size is 1100mm deep x 400mm diameter.
label | ○ 25 MPa concrete with min. 80mm cover when cast against ground. Concrete sampled as per VicRoads Table 610.161 (1 sample taken for 0-10m3). Slump test to be performed for each sample, and three cylinders for testing of compressive strength taken for each sample.
label | Method - Measure
label | Frequency - Each footing
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP, Concrete Dockets
date | Date Completed:
checkpoint | 4.4 - Fence Post Installation - Non-sleeved
label | Reference - IFC Drawings
label | Acceptance Criteria - DN80 MS Pipe (88.9 X 4CHS) to be installed with min. 80mm cover.
label | Method - Measure
label | Frequency - Each post
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.5 - Chain Wire Mesh Installation
label | Reference - IFC Drawings
label | Acceptance Criteria - Chain-wire mesh 1800x50x3.15 to be fixed to fence post with cable ties in accordance with manufacturers specifications.
label | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire or clips.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Post-construction / Post-installation Activities
checkpoint | 5.1 - As-Built Survey
label | Reference - IFC Drawings
label | Acceptance Criteria - Posts are to be checked for verticality and ensure spacings do not exceed standards.
label | Method - Measure
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP