## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
84b5fc46-9c95-40a8-9b7f-6a58111a1b33 | checklist | Document Attachment |  | Document Attachment
8545ab79-ca54-4563-a9c6-b6e34dc08dd4 | checkpoint | Please attach document
80450a1b-262e-404f-a68d-c327d9051c28 | checklist | Equipment Delivery Verification |  | Equipment Delivery Verification
c72f8ed4-6aad-45b1-b8e9-327636cafbf7 | checkpoint | Delivery docket attached or photographed
24d252a9-9678-53c6-9bf2-b87e62421b51 | textbox | Report Reference:
c008dcbd-f3cb-58ee-8fee-408e2efd802a | textbox | Date of Delivery:
2909a866-79bb-57fd-8933-1077f0f4a1a8 | textbox | Manufacturer/Supplier:
608475e6-4fb8-5a82-bb53-dced0767df6f | textbox | Equipment Description:
85bb3038-6caa-52b3-80f3-c1b2084cf054 | textbox | Technical Approval Ref:
7772d12c-cf43-57c9-862b-4796889ff912 | textbox | Drawing Approval Ref:
78efeea3-9387-4e67-bb68-aaf5b85048ae | checkpoint | Photo(s) of serial number(s)
419e776b-c3cc-42d2-b906-6e37e2b06371 | checkpoint | Approved by Supplier / Manufacturer
9aabaaae-080f-4672-81db-040d5f11b0a3 | checkpoint | Approved by Subcontractor Representative
a6b74ff4-3dbc-47ea-8f01-a4f7d9383910 | checkpoint | Approved by Scentre Group
c1491542-a708-523e-9c3c-43de072c06ce | textbox | Date/Time of Inspection:
01b2f89f-30a4-4d8f-bb4b-7c51f44277e6 | checklist | ITP 1- In Ground Pressure Services - Polyethylene (Fusion Weld) |  | ITP 1- In Ground Pressure Services - Polyethylene (Fusion Weld)
0319938f-1752-4fd2-9f3a-d437a6b2d07f | section | Survey & Set Out Works
97c6e023-e19c-4de5-9749-e551d34cf8fd | checkpoint | Take dimensions off drawings and record any remarks / deviations
239acf3c-9549-4475-8a6e-b40ea6a2da65 | checkpoint | Review Dial Before You Dig information. Ensure not more than 30 days old.
bd0d0e24-c742-4f51-887f-456f5899ebf2 | checkpoint | Refer to dimensions on drawings & note any changes. Clearly mark trench line
ef24dc7a-02e8-4d9a-8987-7d983b703a50 | checkpoint | Inform all personnel of existing services and mark with appropriate coloured paint
5c280dca-1170-46ad-bf94-50d2856a22c6 | checkpoint | Please take a photo of plan title block. Ensure plan number & revision number visible
1a2d8aab-e4f5-453d-a9e6-c708b2b99822 | section | Excavation & Bedding Materials
0891133a-c57f-46bc-bde6-147d8a57d666 | checkpoint | Dig trenching to required depth as per AS3500 minimum cover requirements
e321395a-77f6-479f-8422-ceddec15f425 | checkpoint | Ensure minimal over excavation (minimum 75mm below pipe invert)
51bdd09b-b7f1-41b4-986b-7816efa8fc7d | checkpoint | Lay & compact appropriate bedding material to required thickness, providing a consistent level surface
9c9276cf-29d1-44dd-b685-8260c2dba216 | section | Install Pipework
5f8cb02a-8b0a-46f7-b21d-f2753574e054 | checkpoint | Ensure that the pipe to be fused is the correct size for the electrofusion fitting being used
7e1362d9-79d0-4736-beb4-b0a3a2254b45 | checkpoint | Ensure correct fitting is being used and leave in packaging until ready to install
67beae2b-e0eb-4a4b-a822-f3f1d69c2f6e | checkpoint | Cut the pipe ends as evenly and squarely as possible using made for purpose tools
6bdc2215-c594-458d-a5b4-6b97d931bb3a | checkpoint | Clean pipe end with isopropyl alcohol to an area that is at least 2 times the full length of the coupling on each pipe end
55e5950b-c4e9-49a0-85b5-ac77cf5c6489 | checkpoint | Scrape pipe end to an area that is at least 2 times the full length of the coupling using made for purpose scraping tool
01dc031c-a242-4111-a9ec-6c07a6b2130b | checkpoint | Ensure proper insertion depth of pipe end into electrofusion coupling
a7cb4030-a49e-4c6f-8c0e-2a03c27ebc95 | checkpoint | Use assembly clamping if required
84da643f-7f5f-4c91-88c1-1eb352b9415c | checkpoint | Complete weld as per welder/ manufacturer steps
a5314e86-c037-416a-8999-e3eedae82260 | checkpoint | Ensure proper observation of cooling time
230c2803-5147-46af-bb57-79ac598e99ce | checkpoint | Use trace wire for plastic pipes
fdc71c63-438a-422e-be42-9191c9b1835d | checkpoint | Lay pipework on bedding material ensuring no sagging in pipework. Multiple pipes keep 100mm Spacing, 300mm for non potable
ee88d7be-6ca2-4380-ad88-74e2c6a8d389 | section | Test Pipework
23365cba-6e2d-4f0c-87d7-b8b7c68e52db | checkpoint | Photographic record to be kept of process. Take photos of gauges before and after
7e8064f9-4042-4ba8-8ce6-8bcd7ac0bfd0 | checkpoint | Pump test pipework to required kpa and time period as per AS3500 & AS5601.1
191f016b-341a-4bdf-b4da-206d70b7c86d | checkpoint | For water test pipework to 1500kpa for a period of not less than 30 mins. Ensure no air left in pipelines
46a03ffd-0479-479e-9447-39c5f2321216 | checkpoint | For reduced pressure water systems test pipework to manufacturer's specification kpa & time period
dc0ccb77-f3d1-4f3f-b115-22cbc1244bd9 | checkpoint | For Gas Installations Test pipework to min 7Kpa or 1.5 times the working pressure whichever is greater for min 5min period
97b7b8ad-4cfd-4947-8742-36303ccc5ae2 | checkpoint | For Fire Service Installations Test pipework to min 1700Kpa for 30mins or specified time & pressure
d48b7e40-110f-4a60-a00f-5a66a7ebe3be | section | Inspect Pipework
cb3fdcb3-9c3e-4cae-9185-e4ba77c5f2c1 | checkpoint | Complete all required inspections by third parties (client, authorities etc) Name/Sign
5273b48c-ff40-4a2e-96de-92f1062a474b | signoff | Work verified by Scente Group
1e681e18-9434-41e8-8ce3-6a67e285c2b7 | section | Backfill
4e801ff8-c21e-4963-92e2-4a1a3ca6f825 | checkpoint | Backfill pipework with appropriate material (sand/fine grained soil) not less than 75mm above the pipe soffit when compacted
f1bf8eee-a64c-487a-96a2-f69f33795594 | checkpoint | Place layer warning tape that identifies the specific service 300mm above on compacted backfill directly above pipe
e5952faf-8932-4fb1-99ee-c24a1930a504 | checkpoint | Complete backfill in layers with appropriate material to existing ground level ensuring compaction is achieved via mechanical aids
fdab1fdd-f324-4d3a-b4ef-d8956ae36aeb | section | Photographic Record
1a2e4dd5-50e2-4808-992a-cff316c2076f | checkpoint | Photographic record to be kept of process.Photos to include pipework belly filled and once overlay material installed
11bcf89b-3617-447c-9fba-368aec6642ac | checkpoint | Works verified as conforming (McPherson Plumbing Representative):
2d56c761-681c-4f23-bf5b-5c84530f3809 | signoff | Work verified by McPherson Plumbing
a3a1c510-ca6c-4a71-b9fb-90085371da66 | checklist | ITP 1- In Ground Pressure Services - Pressure PVC-U |  | ITP 1- In Ground Pressure Services - Pressure PVC-U
ea4d9e58-8090-4256-bd57-bdc88980a397 | section | Survey & Set Out Works
fd705643-f5e8-4c4f-aada-d43178651930 | checkpoint | Take dimensions off drawings and record any remarks / deviations
de1091e6-f35f-4c08-be3d-44c5fdfe9a30 | checkpoint | Review Dial Before You Dig information. Ensure not more than 30 days old.
b0371a4b-3f1a-4032-837b-2608337cc67c | checkpoint | Refer to dimensions on drawings & note any changes. Clearly mark trench line
497538e7-b5b8-41b4-a8ed-9a473d992074 | checkpoint | Inform all personnel of existing services and mark with appropriate coloured paint
9e983472-949d-4315-9b34-f09711137b62 | checkpoint | Please take a photo of plan title block. Ensure plan number & revision number visible
8cd65c81-19c5-4df9-8a4e-c34f27087619 | section | Excavation & Bedding Materials
a022f762-3646-4394-9353-5804c62bb2e5 | checkpoint | Dig trenching to required depth as per AS3500 minimum cover requirements
a4cc7b9e-fec4-4989-aa43-91c5f0b73545 | checkpoint | Ensure minimal over excavation (minimum 75mm below pipe invert)
e36e3ca9-d1bb-4087-9705-4c9d6b7ee311 | checkpoint | Lay & compact appropriate bedding material to required thickness, providing a consistent level surface
a0e72272-f203-4141-ae8b-b39d353f03d4 | section | Install Pipework
64ab4428-9ff5-41f8-bccc-11ab10fe2dac | checkpoint | Accurately measure length of pipe & cut square. Deburr inside & outside of cut end
5182cb7b-7607-4fd8-883c-623d4548a765 | checkpoint | Ensure sockets are primed and clean and apply a sufficient amount of Type P solvent cement
eaaba1e0-8500-474b-885d-a7ba8e17fb72 | checkpoint | Gently insert the pipe and fitting to full depth with a quarter turn & hold for 30 seconds
89978f77-dfbc-43fe-a4ca-ecfdb5cab89d | checkpoint | Do not disturb joint for at least 5 minutes
2c47d45e-cb60-48c8-904f-94ef01374850 | checkpoint | Wipe away any excess glue and inspect joint for soundness. Allow to cure for 24 hours before pressure testing
24763b6f-4db4-4d79-a460-be30ebaf0d87 | checkpoint | Use trace wire for plastic pipes.
82250fdf-6844-41c0-888a-e48a7a61d00e | checkpoint | Lay pipework on bedding material ensuring no sagging in pipework. Multiple pipes keep 100mm Spacing, 300mm for non potable
a233a408-3bfd-46ef-b81a-a61c0352a8b4 | section | Test Pipework
ac14deb1-7e52-42d3-bc8e-cf68f31524f6 | checkpoint | Please take a photo of plan title block to be taken. Ensure plan number & revision number visible
52c6f927-68bd-4c11-8fe8-0c0d405010ff | checkpoint | Pump test pipework to required kpa and time period as per AS3500 & AS5601.1
4b110495-225d-409b-ad21-0a230604e25f | checkpoint | For water test pipework to 1500kpa for a period of not less than 30 mins. Ensure no air left in pipelines
bc9be2e0-183c-4294-ae7c-f4cbd6fad853 | checkpoint | For reduced pressure water systems test pipework to manufacturer's specification kpa & time period
1b3be501-4bb5-48a0-a38a-2241e1655dad | checkpoint | For Gas Installations Test pipework to min 7Kpa or 1.5 times the working pressure whichever is greater for min 5min period
79a1cfe0-29f9-4d32-bb23-7aa6484c2e22 | checkpoint | For Fire Service Installations Test pipework to min 1700Kpa for 30mins or specified time & pressure
727d1da2-cc47-4659-b8a4-df24ece10a8f | section | Inspect Pipework
58dcac41-a8ef-4dba-81b1-f4c74dd6ce09 | checkpoint | Complete all required inspections by third parties (client, authorities etc) Name/Sign
9a00b191-c4dc-4f76-b00d-8efea4785e45 | signoff | Work verified by Scente Group
564be31f-0b8c-4c2c-92d9-4a6a5a0afe53 | section | Backfill
21193957-1acb-42e7-a548-f656185a09b2 | checkpoint | Backfill pipework with appropriate material (sand/fine grained soil) not less than 75mm above the pipe soffit when compacted
5c7cb363-64a6-4a2a-8924-d892e02338f0 | checkpoint | Place layer warning tape that identifies the specific service 300mm above on compacted backfill directly above pipe
e4cbbee3-8108-425b-a862-f17a25c9a939 | checkpoint | Complete backfill in layers with appropriate material to existing ground level ensuring compaction is achieved via mechanical aids
372def73-b039-4f7c-8b47-fb68adc9e159 | section | Photographic Record
625d09e8-6fc2-4d38-845a-12fb3c54a06a | checkpoint | Photographic record to be kept of process.Photos to include pipework belly filled and once overlay material installed
2ce9e337-439f-40b5-9479-138178e0d9d8 | checkpoint | Works verified as conforming (McPherson Plumbing Representative):
44754ae6-a07f-417e-81e0-58e380176388 | signoff | Work verified by McPherson Plumbing
93b458a3-d7e4-41b7-b3c0-f4c638d0ce7b | checklist | ITP 2 - In Ground Drainage Services |  | ITP 2 - In Ground Drainage Services
06246455-2a6e-4c36-8671-8cb83ef5a553 | section | Survey & Set Out Works
e8bda5ad-cba1-496d-97b9-5162cb498edd | checkpoint | Take dimensions off drawings and record any remarks / deviations
61dbf47a-8815-42c2-9dda-ed580f74acf4 | checkpoint | Review Dial Before You Dig information. Ensure not more than 30 days old.
f80fddab-b1d2-48af-891a-27549d81a1af | checkpoint | Refer to dimensions on drawings & note any changes. Clearly mark trench line
73a86855-9ca4-4f81-91fc-be1dc6e3771a | checkpoint | Inform all personnel of existing services and mark with appropriate coloured paint
39d5aa4e-6ba7-4afa-bb4d-7c7468b1f658 | checkpoint | Please take a photo of plan title block . Ensure plan number & revision number visible
f5ffc8ac-2586-461f-b7ae-1c9b7bc82c28 | section | Excavation & Bedding Materials
efc1a1bf-a814-4a66-88e7-fd1da7e8305f | checkpoint | Dig trenching to required depth as per AS3500 minimum cover requirements
d6ba4ee7-a161-42ca-9374-8347a1138d67 | checkpoint | Ensure minimal over excavation (minimum 75mm below pipe invert)
ab86d29d-28eb-45f9-b0cd-fb4915a99a47 | checkpoint | Lay & compact appropriate bedding material to required thickness, providing a consistent level surface
0eac0a83-4516-479b-b375-5fa56bd5b348 | section | Install Pipework
454e5fe9-86d1-4ca2-a27f-7dcc295ac30d | checkpoint | Lay pipework to appropriate invert and ensure correct alignment. Document inverts on As-Built
cd47f556-c175-5c10-b648-cd901c1a6677 | dropdown | Type of pipe | DWV PVC-U, HDPE
ffc5d639-5430-5d32-95ee-31c7b7b20ae8 | dropdown | Inground Services Type | Sewer, Tradewaste, Stormwater, Rising Main
f2c2fce6-7381-4c4e-b470-dfb9b501b10d | checkpoint | Ensure pipe is scrapped with appropriate tool to expose bare pipe
ea4c42b8-a767-4127-99d9-4a3a04a6ff91 | checkpoint | Allow for all required inspection openings at change of direction and not more than 30m intervals
00c0b262-04f5-4fdc-8a96-0bed1c49c847 | checkpoint | Install turn up points as per grid setout or surveyor markings
69d2fb1c-a058-4544-9002-9418963f744b | checkpoint | Ensure required depth of cover and proximity from other services is achieved
0db7bc41-c0e9-4447-8f75-a11b98c34dce | checkpoint | Belly Fill Pipework to keep in a stable position, but still visible for inspection
1255f7f5-1294-4fc3-9f26-d003e90a9562 | section | Test Pipework
95327e77-cdfe-4c5d-844f-009626d3394a | checkpoint | Photographic record to be kept of process. Take photos of water level before and after
d7539eeb-0fea-4f71-aeea-76bad6c3c794 | checkpoint | Hydrostatic test of pipework for a period of not less than 15 mins
df20e8b3-d949-4374-bce0-9f3f2e5646b9 | section | Inspect Pipework
fa49c350-55b1-4cfa-9419-05859ce37989 | checkpoint | Complete all required inspections by third parties (client, authorities etc) Name/Sign
c1f8670e-72e9-435d-98a0-9546c3e8ac9f | signoff | Work verified by Scente Group
a3a90f3a-5774-47f3-b580-1887679ce545 | section | Backfill
f68c8c1b-e17c-4428-bf3d-80ddd74a5147 | checkpoint | Backfill pipework with appropriate material (sand/fine grained soil) not less than 75mm above the pipe soffit when compacted
0604a4f2-8a60-4318-bdae-64e8e2cf901f | checkpoint | Place layer warning tape that identifies the specific service 300mm above on compacted backfill directly above pipe
74473934-8ad4-4f55-8dab-187a2f4c5092 | checkpoint | Complete backfill in layers with appropriate material to existing ground level ensuring compaction is achieved via mechanical aids
4afd44f5-8185-455e-919e-f49c9848c503 | section | Photographic Record
f7976f7f-b46a-4785-9a52-12be9ac5aea3 | checkpoint | Photographic record to be kept of process.Photos to include pipework belly filled and once overlay material installed
35799211-c53d-4063-8b86-efacf067e674 | checkpoint | Works verified as conforming (McPherson Plumbing Representative):
45b54b7f-747c-480d-9b7d-857338fd3c2a | signoff | Work verified by McPherson Plumbing
0fb439b8-4086-4999-a54d-9be423ed1799 | checklist | ITP 3 - In Ground Pits & Tanks |  | ITP 3 - In Ground Pits & Tanks
2a237d24-6fce-4ec8-bc1a-4c7fc7cde1a9 | section | Survey & Set Out Works
26ee9492-c053-48d9-8668-50f4268bdf89 | checkpoint | Take dimensions off drawings and record any remarks / deviations
bfe07804-d48c-469d-8f5a-13cf2deb1016 | checkpoint | Review Dial Before You Dig information. Ensure not more than 30 days old.
bddd54da-9a6a-45d7-b115-6e257aa01200 | checkpoint | Refer to dimensions on drawings & note any changes. Clearly mark pit location
5e564246-dfdb-4186-9613-933cff82bd9d | checkpoint | Inform all personnel of existing services and mark with appropriate coloured paint
4b2bc0e0-fa26-45ab-9cad-7488084032e6 | checkpoint | Please take a photo of plan title block. Ensure plan number & revision number visible
86bd4641-682d-47ab-b891-c9d8c1cd21ae | section | Excavation & Bedding Materials
32f480db-0112-452e-a364-34e4a0fc1566 | checkpoint | Establish invert's & RL's and excavate to required depth
e3a13faf-51bc-4fd1-a3ef-07d5b2899c9b | checkpoint | Ensure minimal over excavation and as per tank/pit specifications
2782071a-2802-4d96-9895-20eb24dbf0fb | checkpoint | Lay appropriate bedding material to required thickness, providing a consistent level surface
31797685-d3ee-4e00-8788-ed9d9acec996 | checkpoint | Check bedding level to ensure that it corresponds correctly with pit finish height
015e42bb-840c-4bad-946e-ecf465b5ddae | checkpoint | Ensure required depth of cover and proximity from other services is achieved
bd8d707c-4658-46eb-a95f-8ff5ee43beeb | section | Installation of Pit & Risers
22985d65-5eab-4d14-bff7-30aea10dd4ba | checkpoint | Lift in pit to appropriate level and ensure correct alignment as per plan. Document levels on As-Built
b87dbbe6-0165-57a4-943b-24785eb1dc9e | dropdown | Type | Concrete Pre - Cast, Fibreglass, Plastic
cd87c33d-07f1-4bec-b2d0-be27b53b35ac | checkpoint | Seal pit and riser/ lid segments together using a site-approved non-shrink grout or mastic-type product
d8932466-472d-473d-a00f-a03cff0ef423 | checkpoint | Leave the segments undisturbed until the period of curing is completed
8d3ec8b2-8a16-4dfb-8d69-164da67e8696 | section | Installation of Pit Connection Pipework
0722a022-ce4e-4af5-91f8-705dc745c0b0 | checkpoint | Establish pipe invert levels entering the pit and mark out on the thin knockout section of the pit wall.
9dd599ed-29d6-47cd-a5ba-97f07e93f6c2 | checkpoint | For concrete pits break is to be made in the centre of the knockout carefully widening the penetration to suit the pipe size
7914b00b-3289-4be1-ad22-9e452a68db2e | checkpoint | For fiberglass pits/tanks use hole saw to suit pipe size
3744aa8d-cea9-4c07-aa55-5ad20deaf1b7 | checkpoint | Pipe to be placed into the penetration and cut to the required engagement within the pit/tank
10b95a36-2362-4ab1-b69a-12f5831fc2a7 | checkpoint | Seal outside of pit/tank wall around pipe connection with cement mix or approved sealant
408621c0-524f-4372-a081-4c6aab7af52f | section | Inspection
051ea8a3-4f9e-4383-8bab-3860b1c5726d | checkpoint | Complete all required inspections by third parties (client, authorities etc) Name/Sign
d7e3e422-9871-468b-a38b-927f8cf112e5 | signoff | Work verified by Scente Group
48c07039-8b99-4c33-9522-2133cb3b06fe | section | Backfilling
34fa5bab-e63d-4b3c-b90e-0b4104e197f4 | checkpoint | Backfill around pit sides with the same aggregate/ material that was used for the base of the pit/tank
38e9d675-6614-42cb-810b-367d0ed6762f | checkpoint | Complete backfill with appropriate material to existing ground level, ensuring that suitable compaction is achieved
a285843b-89d8-4a0b-ae12-19b195817027 | checkpoint | Photos to include backfill material around the pit/tank and the connection point
c59b49d3-645d-4686-b5a0-1bd4da29f811 | section | Pit Finishing
e660f865-62b4-4e94-ab35-33f7dba6388e | checkpoint | Seal inside of pit wall around pipe connection with cement mix or approved sealant to obtain a smooth surface consistent with pit
f14a1f82-4deb-4d74-b3f6-48bff52d3869 | checkpoint | Installation of step irons or ladders if required
c99fa91e-5292-48ae-bb94-867b939b9665 | checkpoint | Provide protection of lid/grate gatic lift points or threads during construction period
479cdd36-658f-49c2-a094-9b8e84748fc9 | checkpoint | Top the base of the pit to match the invert level of the pit outlet pipe where required. Record pit invert level on as-built
13d348fa-0038-4674-90ca-c7a2049130b9 | checkpoint | Photos to include pit finished & clean and free of debris/construction rubbish
07701723-b798-4c89-b782-9b8987334a7e | section | Photographic Record
aca63ed6-2c90-4f90-94d8-973a30be7f0f | checkpoint | Photographic record to be kept of process.Photos to include entire installation process
8289736c-f7bf-49f5-a9ab-58bf4b244db9 | checkpoint | Works verified as conforming (McPherson Plumbing Representative):
bd71f715-8414-4a4b-b1f8-ed08f5e8d201 | signoff | Work verified by McPherson Plumbing
5dabfe90-67c2-432a-83b5-f56fcfd507f0 | checklist | ITP 4 - Set Out - Penetrations & Fire Collars |  | ITP 4 - Set Out - Penetrations & Fire Collars
d7d2fe5c-f281-49d4-9829-9b01116bda61 | section | Survey & Set Out Works
772549c2-be11-44d1-876e-dbfc48b6bc69 | checkpoint | Take dimensions off drawings and record any remarks / deviations prior to installing
6a2ca7b7-a400-56d6-8c3e-ba9dbe4d2d81 | dropdown | Set Out | Survey Plotted, Manual Set Out
53bf4d3b-95ba-48b3-84c7-9bde39eceee5 | checkpoint | Photo of title block to include drawing number & revision
240fedfa-30d2-49d7-a952-c002e4a2e264 | section | Structural Interface
5672f0cc-1ffc-4832-8e09-9e92c93f247c | checkpoint | Consult structural drawings to ensure no structural effect with penetration or cast in position
a9a0a903-2d93-4d37-9897-05fc9ef30535 | checkpoint | Ensure pipework within set downs and beams are cast in/out of set downs where required and indicated on penetration drawings
88c12847-b6b1-4530-a6a4-bfc7eeb4cf83 | checkpoint | Check that penetration does not clash with elements downstairs e.g. Walls, Beams ETC
0f4fb628-4320-43f6-8c76-b7a16c965177 | section | Fire Collar Installation
6c9e9792-bfb7-4c3c-84d3-c6ce0fc24c0f | checkpoint | Ensure that fire collar is installed as per manufacturer's specifications and is spatially acceptable
7e347815-b178-56af-9f9b-fe2e7ad0791e | dropdown | Fire Collar Type | Promat, Snap, Hilti, Other
b8e1069a-fafe-4e50-bbd6-124581f8fdcc | section | Pipe Insertion to Collars
7e440ea5-7f3f-44eb-b6aa-cd0d55c8f395 | checkpoint | Ensure pipe is fitted correctly
9090edd1-e882-421c-8d24-0961ff6b6e50 | checkpoint | Ensure pipe is fitted to maximise the efficiency of the next sequence of work e.g. Pipe is easy to knock through
563f6ba0-856c-41a2-bc34-8a4f75a691da | section | Cast in Conduits
40802857-ea2e-421f-8966-8a9af6ac6f7a | checkpoint | Ensure conduit is within wall or carcass range
ceab5a0e-38ca-4947-8c6b-ac7a81daa80e | checkpoint | Use 15/45 degree bends on all changes in direction
dac4ba45-be96-4723-be80-262f6887a7c0 | section | Cast in Balcony Outlets
8fcb9564-f4a8-4644-9278-83446f20f741 | checkpoint | Ensure pipe is supported correctly without affecting balcony soffit
74ef6fe0-7cc6-4038-a1c1-21cec7a1fada | checkpoint | Ensure pipes are not damaged after top steel and set downs are installed.
47dae450-f90f-48ed-b7f9-180e35525473 | section | Safewaste or Puddle Flange Installation
45de8ff5-0b0a-4552-bb96-a65517284afb | checkpoint | Ensure safewaste or puddle flange is installed to all required outlets
f52fccf0-9214-4b45-ba26-a7f931172234 | checkpoint | Ensure safewaste or puddle flange is installed to the correct height
ef65c93c-bf46-4788-bcfa-eb45d4b7d395 | checkpoint | Spray all floor wastes to identify falls
212d0b3f-ff7a-464f-aa73-02480d12b477 | section | All Pipes & Casting Capped & Supported
a9432bce-10fe-4ce4-8d17-23d155f67b04 | checkpoint | Ensure no open ends by installing dust cap or ductape on risers
0351ffe3-7bd5-44b7-a98b-a9d9a5e2b035 | section | Pipe Sleeves
038fdf41-d416-47f6-9568-d31ed5f9f7c8 | checkpoint | Ensure all sleeves installed in in situ walls at the correct height
a24aed86-8f56-4808-954e-d01c994f499a | section | Castin Downpipes
5d1c61d8-c7b3-4862-be70-100f383d92ea | checkpoint | Ensure pipes are clear of any obstructions prior to extending riser
451927b7-c094-4f74-a820-e1a74cfca1ac | checkpoint | Ensure pipe is fitted correctly where agreed by structural engineer
c3d709cf-87d1-428c-b0e8-4e549b38114e | checkpoint | Ensure pipes are wrapped where required
5c9c6262-7008-47bb-8212-abeb1e19a941 | checkpoint | Ensure downpipes capped and taped to riser
12d847d8-8b08-4990-be09-c32420d60840 | checkpoint | Ensure pipe is filled with water for concrete pour where required
91c2406f-65a2-472d-a8f2-05ceb8366cdc | section | Inspect Pipework
f215c8e0-a977-44d2-b7fb-759fda2c2638 | checkpoint | Complete all required inspections by third parties (client, authorities, builder, etc)
956bd841-766f-48b8-8663-88151bfff1e2 | signoff | Work verified by Scente Group
fe5aaf0f-b375-4e21-962d-0c8c405a9f1b | section | Photos
e61e5e26-abf0-498f-a7f0-6c6896914d00 | checkpoint | Ensure photos are taken of entire installation inc fire collars and casting prior to concrete pour
29e0f8c4-39ae-4e9d-8134-0a1621bdda8e | checkpoint | Works verified as conforming (McPherson Plumbing Representative) Name:
565c3827-55cf-4b01-8469-3370c2e541de | checklist | ITP 5 - Drainage Services |  | ITP 5 - Drainage Services
95a6dab6-20c8-43e2-84c8-146b8a2fbc67 | section | Setout & Location
4e9d61d5-1263-4038-83be-4a7e960dea1e | checkpoint | Check dimensions on drawings and record any remarks / deviations on as built drawings & take photo of title block
66d12964-29cf-46e6-b3ea-5c5b506a9ccc | checkpoint | Review wall set out plans and ensure pipe passes through wall square
7280c2fe-ca4b-4068-a88d-ddbe5c695aa4 | checkpoint | Review interfacing services and ensure no clashes
2b7e4147-7318-483d-ad96-50ca0d37fbdb | checkpoint | Always set out off metre mark where applicable and when possible transfer for later reference (e.g inside inwall cistern)
b144ace9-5175-4874-99e6-926731ee38f8 | checkpoint | Review wall set out plans and ensure that bare pipe only is passing through fire rated walls to allow for fire rating
79f4920e-f72e-53f5-9314-6ccdc1d9f095 | dropdown | Pipe Type | DWV PVC-U, HDPE
3b42085e-1696-589f-adc2-e19cbbbd7fb8 | dropdown | Pressure Services | Suspended, Rough In, Risers
fe88e257-5e51-5442-bb74-0ec7e2f8afd7 | dropdown | Type | Sewer, Stormwater, Trade Waste, Rising Man
bb207256-142b-4456-829a-17e82bc8e5ac | section | Bracketing, fittings & Noggins
ad598d9e-9565-4d62-87eb-387e9c35d83d | checkpoint | Install Brackets as required, check alignment and spacing as per manufacturer's specification & applicable Australian Standard
0c6e2877-355e-4faf-969f-6ffb05577b3c | checkpoint | Ensure correct brackets are used dependant on material selected
3144521d-a5e3-4962-b689-3ba497229030 | checkpoint | See extract from AS3500.1 for water services
ac07b772-4530-424a-bb05-d5ccd2034168 | checkpoint | Ensure correct fittings are used as per pipe weights, element exposure & project specification
d9534d36-9158-4cc8-a2cd-c70f34e0ddd3 | checkpoint | Ensure all Noggins are installed prior to sheeting of walls (e.g wall hung basin/shower rail/ fire hose reel)
b6288b05-99be-4194-aeff-70f43b0a1573 | checkpoint | Ensure supports are installed min 600mm from penetrations through slabs or walls where insulation is required
0d438fcf-a1bd-471c-9bdf-079eed84d026 | section | Install Pipework
cfe53017-0eb3-4117-af41-da7386260833 | checkpoint | Accurately measure length of pipe & cut square. Deburr inside & outside of cut end
1f92f4af-c470-4853-8d28-c76d6fbd7cef | checkpoint | Ensure sockets are primed and clean and apply a sufficient amount of Type N solvent cement
b4387b8a-832e-4768-933a-e38b1e5263d3 | checkpoint | Gently insert the pipe and fitting to full depth with a quarter turn & hold until joint sets
883bb4b4-41d1-4366-8155-ac883bf6a1db | checkpoint | Do not disturb joint for at least 5 minutes
5490086f-8d49-4fc2-a7e4-4e6aa964f4fc | checkpoint | Wipe away any excess glue and inspect joint for soundness. Allow to cure for 24 hours before pressure testing
8f59c654-1088-4e70-aeef-2897be135541 | checkpoint | Allow for expansion joints & inspection openings as per as per AS3500
8ce77a9d-9894-416a-a55a-c4b1f87d3bea | section | Test Pipework
e17118dd-d8a7-4a03-9567-2681b884acea | checkpoint | Plug and fill stack with water at expansion and gate and ensure plug is unable to release into pipe system
28e497c7-a612-4dcb-95fa-af5d11d227a2 | checkpoint | Gravity test of pipework for a minimum of 15 mins
60c099c4-e940-4eba-87a3-c010c49792ff | checkpoint | Tape gate and expansion and initial cap with date, stating 'TESTED'
04233323-e5ab-4289-87b8-a4aa3c938195 | checkpoint | Photograph of riser clearing showing testing info
6c75bb12-df8f-48df-89e7-57db32792146 | section | Inspect Pipework
6837d203-52ca-499b-abcc-d43b186bd76e | checkpoint | Complete all required inspections by third parties (client, authorities etc)
c0c8528a-834e-4f86-a699-898c37eca36b | signoff | Work verified by Scente Group
60d1786a-bfdc-4c36-9d8f-de791898a66b | section | Acoustic Installation & Pipe Identification
d8bbfab7-7ba8-43f6-be38-006b549f891d | checkpoint | Apply correct pipe identity stickers to indicate flow direction
a5828bfd-591f-4703-9c2a-fdb764469457 | checkpoint | Apply thermal insulation to any hot water pipework. Thickness & type as per project specification
39fe653b-7670-4bfd-afa9-d92d33cd364c | section | Photos
bb62bce9-88a9-43db-82ed-5eae0f4cb4d4 | checkpoint | Photographic record to be kept of process. Take photos of entire installation
6aed0094-0e63-4898-85e9-0602db7eb446 | checkpoint | Works verified as conforming (McPherson Plumbing Representative)
60029af1-b8e7-414f-9efd-bf5704d0240a | signoff | Work verified by Scente Group
499a9f3a-1033-4fc6-a728-af4e5c40f863 | checklist | ITP 5 - Drainage Services DWV PVC-U |  | ITP 5 - Drainage Services DWV PVC-U
d651287e-4128-4a80-b064-aecf92e54dbd | section | Setout & Location
0401de9e-9a19-47ce-bd51-c10ae4a2d356 | checkpoint | Check dimensions on drawings and record any remarks / deviations on as built drawings & take photo of title block
47c53ce8-2014-4af4-8f40-c98ae9ad3a98 | checkpoint | Review wall set out plans and ensure pipe passes through wall square
f70fd123-e441-4645-89f8-28af60ae9bac | checkpoint | Review interfacing services and ensure no clashes
04400ea3-01ba-4af9-a213-21c410711be7 | checkpoint | Always set out off metre mark where applicable and when possible transfer for later reference (e.g inside inwall cistern)
0338eda7-fd3b-465c-bc90-0ee5a9dc779d | checkpoint | Review wall set out plans and ensure that bare pipe only is passing through fire rated walls to allow for fire rating
092525d9-60ec-5736-bbdb-3210e1aa7c55 | dropdown | Pressure Services | Suspended, Rough In, Risers
5bb0558e-104a-51c4-9446-f6ad1fa78bff | dropdown | Pipe Type | Sewer, Stormwater, Trade Waste, Rising Man
82974413-961e-4371-8a99-dd22908c22bf | section | Bracketing, fittings & Noggins
8a5cde2d-afe0-409a-80b8-8a343f18594b | checkpoint | Install Brackets as required, check alignment and spacing as per manufacturer's specification & applicable Australian Standard
08d72438-ead5-430f-bb2f-2ea1c4c09cf4 | checkpoint | Ensure correct brackets are used dependant on material selected
6961c9dd-bba6-4a4a-97a9-6fd9d31baab7 | checkpoint | See extract from AS 3500.1 for water services
d0ba4ec1-b799-430d-8467-5419e47005bc | checkpoint | Ensure correct fittings are used as per pipe weights, element exposure & project specification
996d2683-c33b-4c28-aeab-7588aa3fd024 | checkpoint | Ensure all Noggins are installed prior to sheeting of walls (e.g wall hung basin/shower rail/ fire hose reel)
0f653c2e-44d7-4c8a-aa16-2e4fd0d96846 | checkpoint | Ensure supports are installed min 600mm from penetrations through slabs or walls where insulation is required
bb1eb1f9-5df5-440e-9724-fba016bc19c3 | section | Install Pipework
40b3ae69-465b-4be2-80db-d2b11ca44cd5 | checkpoint | Accurately measure length of pipe & cut square. De-burr inside & outside of cut end
4474124b-91ae-49d1-81a7-8ef74e8ec98c | checkpoint | Ensure sockets are primed and clean and apply a sufficient amount of Type N solvent cement
3b426dfb-b123-4cbf-bc00-3567f2ec6712 | checkpoint | Gently insert the pipe and fitting to full depth with a quarter turn & hold until joint sets
6cb04cda-d76c-4975-b58f-e35c4ca96681 | checkpoint | Do not disturb joint for at least 5 minutes
6ee460db-4d79-4985-adfb-a741ac06f9bf | checkpoint | Wipe away any excess glue and inspect joint for soundness. Allow to cure for 24 hours before pressure testing
2cf71d78-0d4f-4f54-8037-f5bdcbd9c772 | checkpoint | Allow for expansion joints & inspection openings as per as per AS3500
ccffc657-1de2-43fd-88eb-8423dc4075ad | section | Test Pipework
58520b17-7c60-44ca-ac0b-947d3e165568 | checkpoint | Plug and fill stack with water at expansion and gate and ensure plug is unable to release into pipe system
fa66e1e9-53d6-4513-9229-327ffb00de6d | checkpoint | Gravity test of pipework for a minimum of 15 mins
d5660b19-e3e4-4490-8124-cc86146f80ab | checkpoint | Tape gate and expansion and initial cap with date, stating 'TESTED'
c1629504-bfc2-4cac-805e-dec8de2674b5 | checkpoint | Photograph of riser clearing showing testing info
4fad8e35-9eb1-43d2-b6a6-a92317b8d04e | section | Inspect Pipework
1685b98e-d755-4dee-a92b-b61533780205 | checkpoint | Complete all required inspections by third parties (client, authorities etc)
2be66617-5174-49d3-b0fe-4dca59c3ad20 | signoff | Work verified by Scentre Group
fec9acb9-1752-4fb6-ba59-d1f6a1eefa35 | section | Acoustic Installation & Pipe Identification
8fcadcf0-384c-4c9f-97f6-45296b6107a0 | checkpoint | Apply correct pipe identity stickers to indicate flow direction
e0ad104b-10a9-4967-ba91-18a100e36e15 | checkpoint | Apply thermal insulation to any hot water pipework. Thickness & type as per project specification
9787ada7-b6b3-4900-896b-60b68f47eef2 | section | Photos
ff898cf5-dc9f-47cb-8e0d-fa42a49d66f0 | checkpoint | Photographic record to be kept of process. Take photos of entire installation
86155b7f-b18f-4f22-9c7e-243816dfcd55 | checkpoint | Works verified as conforming (McPherson Plumbing Representative)
f08c9669-cadb-4bbc-a231-6a61cdb99456 | signoff | Work verified by Scentre Group
c1e70db2-08c5-4ced-bca2-43d61b64f9dc | checklist | ITP 5 - Drainage Services HDPE |  | ITP 5 - Drainage Services HDPE
a1f4ebc8-d813-457f-bac3-0dfa0d7ee003 | section | Setout & Location
08f9a679-bba2-4d19-84e0-56a6d9527cdb | checkpoint | Check dimensions on drawings and record any remarks / deviations on as built drawings & take photo of title block
6bb04d7a-00e9-4c50-951a-5bd84c588528 | checkpoint | Review wall set out plans and ensure pipe passes through wall square
386ae3f9-8bd3-4030-b3cd-c302c44a3fc4 | checkpoint | Review interfacing services and ensure no clashes
15ab51a3-f401-48f5-82f8-5b07ec842695 | checkpoint | Always set out off metre mark where applicable and when possible transfer for later reference (e.g inside inwall cistern)
022ce4d2-2b1d-4844-83eb-13e7f057e732 | checkpoint | Review wall set out plans and ensure that bare pipe only is passing through fire rated walls to allow for fire rating
c52acf8d-916b-5cff-805e-cadaafd7e31d | dropdown | Pressure Services | Suspended, Rough In, Risers
05ddc3ea-f0ef-558f-90df-92549148911e | dropdown | Type | Sewer, Stormwater, Trade Waste, Rising Man
e6db1b3b-a9f9-4155-aacb-1b5179fba5a7 | section | Bracketing, fittings & Noggins
8567a26d-7493-4058-8168-00b71a788877 | checkpoint | Install Brackets as required, check alignment and spacing as per manufacturer's specification & applicable Australian Standard
b5e35d3a-fcd5-4c33-b8f2-f909e466813c | checkpoint | Ensure correct brackets are used dependant on material selected
abbb418d-5fb2-4449-b3dd-86e0b8995be9 | checkpoint | See extract from AS 3500.1 for water services
61940dc7-6a4e-469f-9b2d-56ac80a7fe70 | checkpoint | Ensure correct fittings are used as per pipe weights, element exposure & project specification
59815c90-39a9-467c-b94d-62085755d465 | checkpoint | Ensure all Noggins are installed prior to sheeting of walls (e.g wall hung basin/shower rail/ fire hose reel)
3e901cfb-66ce-4694-bdb3-a19c0d2898d9 | checkpoint | Ensure supports are installed min 600mm from penetrations through slabs or walls where insulation is required
139cbe76-e685-4d56-941f-0fc5bff8204a | section | Install Pipework
4bf0cbfa-34da-4820-9e47-da2f30d3a540 | checkpoint | Accurately measure length of pipe & cut square. De-burr inside & outside of cut end and ensure pipes & fittings are dry
b6f2dfd5-4519-4ac7-bef6-840c1537e03c | checkpoint | Ensure constant power supply to the electrofusion welder as fittings can only be welded once
6e9e92a9-2b80-46cf-aaa7-7517d68889cd | checkpoint | Scrape the pipe section to the length of the insertion depth with emery cloth or manual scraper, removing oxidised layer
2a11f6de-fc64-4d53-aa50-bc5a61e810fb | checkpoint | Mark the insertion depth on the pipe and insert into the coupling. Ensure pipe is secured from movement
bae6a2a9-dec6-40e4-8a0c-54b5450da8fd | checkpoint | Weld the joint to the manufactures process and allow to cool before applying force or testing.
44e16c0a-db85-4483-a545-1396fba517f1 | checkpoint | When welding has been performed correctly the protruding yellow or black indicator should be raised
41483eaa-3632-4bb1-a385-18a740d076de | checkpoint | Allow for expansion joints & inspection openings as per as per AS3500
81570bb0-d6dc-4891-90e5-33b48b0ffb65 | section | Test Pipework
fb79fde4-160c-48bb-9f19-2e5cd7c1f3fd | checkpoint | Plug and fill stack with water at expansion and gate and ensure plug is unable to release into pipe system
80e79200-fcf2-4870-a428-4f3680a52999 | checkpoint | Gravity test of pipework for a minimum of 15 mins
ae7602f2-5045-4f70-9002-0756c0658f77 | checkpoint | Tape gate and expansion and initial cap with date, stating 'TESTED'
96f8bd5b-3fca-4b7f-824b-5a6d3ed3e83c | checkpoint | Photograph of riser clearing showing testing info
74f8f8dc-2d5d-481b-9db3-6c3ff94ccfd6 | section | Inspect Pipework
6e2e7b54-0df1-4f6b-936d-45be0d6b06ed | checkpoint | Complete all required inspections by third parties (client, authorities etc)
2881cb46-e399-4605-b6d2-4628cc628116 | signoff | Work verified by Scentre Group
7478367c-483f-4322-94c9-0526f0c1e485 | section | Acoustic Installation & Pipe Identification
887f70f5-275c-4077-9ed2-851342b55b41 | checkpoint | Apply correct pipe identity stickers to indicate flow direction
218f8d84-dd98-43e1-8045-1407895a5d8f | checkpoint | Apply thermal insulation to any hot water pipework. Thickness & type as per project specification
57abf629-9732-4e68-b9be-fa04574f2175 | section | Photos
697a6d3d-3fe5-494f-86b1-bd6dff128415 | checkpoint | Photographic record to be kept of process. Take photos of entire installation
72e8d548-bc23-403a-95cc-ecf61c99e341 | checkpoint | Works verified as conforming (McPherson Plumbing Representative)
ed941d6a-edc7-4221-a2a3-15cd98aa82bd | signoff | Work verified by Scentre Group
c3174891-48d7-4ae7-8e8f-83c594c2a074 | checklist | ITP 6 - Pressure Services - Brazed Copper |  | ITP 6 - Pressure Services - Brazed Copper
99fc122d-0cc0-4eec-b36e-5fc456ef3b87 | section | Setout & Location
a1b412f4-3b11-4660-aee2-f00362ff6d29 | checkpoint | Check dimensions on drawings and record any remarks / deviations on as built drawings & take photo of title block
4fbd1b3a-e91e-4da0-bbea-8b3528586f6e | checkpoint | Review wall set out plans and ensure pipe passes through wall square
08e7eef6-124e-4a72-93d9-c944e5780155 | checkpoint | Review interfacing services and ensure no clashes
4b88c1cd-2501-4c2c-a247-2117c7d83f86 | checkpoint | Always set out off metre mark where applicable and when possible transfer for later reference (e.g inside inwall cistern)
41182fd3-83cc-4600-9c3e-9ffab88f81b6 | checkpoint | Review wall set out plans and ensure that bare pipe only is passing through fire rated walls to allow for fire rating
9c27ebab-0d5e-5a20-968f-38662a75f1b0 | dropdown | Pressure Services | Suspended, Rough In, Risers
bd6217e5-e017-5618-a525-1830ffbefa83 | dropdown | Type | Potable Cold Water, Hot Water, Non-Potable Cold Water, Fire Services, Gas Services
728d3c5d-b573-4c6b-9ec5-95f0cdbe94f2 | section | Bracketing, fittings & Noggins
ec0c44cd-4834-45c8-9c79-dfa5765dc942 | checkpoint | Install Brackets as required, check alignment and spacing as per manufacturer's specification & applicable Australian Standard
03cf451f-ae06-4638-97a8-b78a654d80e9 | checkpoint | Ensure correct brackets are used dependant on material selected
e9894b03-deee-4d93-89cf-85004fdafe9f | checkpoint | See extract from AS3500.1 for water services
65ff3659-1c81-44de-b88f-9cfbedd16898 | checkpoint | Ensure correct fittings are used as per pipe weights, element exposure & project specification
04a42ff8-2c78-4bfd-abbf-dc43bb2a18de | checkpoint | Ensure all Noggins are installed prior to sheeting of walls (e.g wall hung basin/shower rail/ fire hose reel)
9050281d-596f-4f48-b111-8aa2f75358e3 | checkpoint | Ensure supports are installed min 600mm from penetrations through slabs or walls where insulation is required
1bbee35d-0280-4f43-9905-c7fb50a2eb99 | section | Install Pipework
07ade12a-5ed5-4891-bfa8-2c566a19d105 | checkpoint | Measure accurate length & use appropriate copper tube cutter to ensure a clean square cut.
f40fbfb8-0a54-4d1e-87fe-e8a02d396b0d | checkpoint | Ream inside & outside of cut with reaming tool or file & clean with abrasive cloth
b020969a-bd69-4c43-9257-1e9aa66a9c3c | checkpoint | Ensure pipe is pushed in to full insertion depth. For brass to copper joints ensure flux is applied prior to insertion
18223773-5152-4c5c-a97f-502d6522ab69 | checkpoint | Weld joint with correct amount of heat ensuring capillary action throughout & correct % silver solder is used. (min1.8)
23fd712b-2202-490c-8a4e-39e95fe65ce0 | checkpoint | Allow joint to cool naturally. Shock cooling may stress or crack the joint. Wipe off any left over flux residue
fd631187-6d89-48c6-a528-59d3be31724a | checkpoint | Inspect the joint for soundness and pin holes
f1b87114-deb8-4272-91f2-707caea4c021 | checkpoint | When installing non-potable services ensure pipework is not installed within 100mm of any parallel drinking service pipework
199c6be7-9ad8-4081-9481-0f782cacb787 | section | Test Pipework
c2ff792f-4b17-4b9a-95a4-e5db87dee525 | checkpoint | Photographic record to be kept of process. Take photos of gauges before and after
6ce12f1d-e89a-49a5-8c45-734710e09930 | checkpoint | Pump test pipework to required kpa and time period as per AS3500 & AS5601.1
d62ba63d-6e28-4d6d-ab02-2ae31e6b9a35 | checkpoint | For water test pipework to 1500kpa for a period of not less than 30 mins. Ensure no air left in pipelines
f168391f-3a65-4b32-a7d9-c8492526f637 | checkpoint | For reduced pressure water systems test pipework to manufacturer's specification kpa & time period
dbe0c2e8-b962-459d-9a22-4e3e1749d699 | checkpoint | For Gas Installations Test pipework to min 7Kpa or 1.5 times the working pressure whichever is greater for min 5min period
74dcb597-afc5-40d1-affc-242bcefae9ec | checkpoint | For Fire Service Installations Test pipework to min 1700Kpa for 30mins or specified time & pressure
b327c53a-902c-4601-8348-5fb083d238f8 | section | Inspect Pipework
991f5b2d-8715-4978-935c-b549fc244056 | checkpoint | Complete all required inspections by third parties (client, authorities etc)
4664849e-30d1-4325-b705-8082cae91e1d | signoff | Work verified by Scente Group
63907033-e77f-4fcf-99b6-29bc39d58b93 | section | Pipe Insulation & Identification
6dcfb845-02bb-43e4-ba6b-0a8d1396fb9e | checkpoint | Apply correct pipe identity stickers to indicate flow direction
6db9acc2-fa45-4ac2-91cb-02a067ba310a | checkpoint | Apply thermal insulation to any hot water pipework. Thickness & type as per project specification
bb38bb89-5a5c-4b98-8e93-318a3738bd8e | section | Photos
63c6630c-127c-4018-8219-0f02a30d46f8 | checkpoint | Photographic record to be kept of process. Take photos of entire installation
efbc7bd6-6bbb-40f8-a566-285d2b5694d6 | checkpoint | Works verified as conforming (McPherson Plumbing Representative)
64ad28f4-4e17-4eb1-9330-242ab2d8cdab | signoff | Work verified by Scente Group
abd2053e-ddf7-451f-b253-b108743f43a9 | checklist | ITP 6 - Pressure Services - PEX All |  | ITP 6 - Pressure Services - PEX All
c635b13d-1af1-42fe-8c9b-b1d3e4508306 | section | Setout & Location
b53285e1-5acb-46d4-ab81-624a56737539 | checkpoint | Check dimensions on drawings and record any remarks / deviations on as built drawings & take photo of title block
5f865034-a7d6-4eac-a672-bc1d5e234fad | checkpoint | Review wall set out plans and ensure pipe passes through wall square
5f3c4ff0-c961-4d39-a4bc-5f9408867fca | checkpoint | Review interfacing services and ensure no clashes
9644d1f3-a9a8-40e2-a257-a43519404fb2 | checkpoint | Always set out off metre mark where applicable and when possible transfer for later reference (e.g inside inwall cistern)
33454e1b-1e9e-4eec-a037-7d4f9149edda | checkpoint | Review wall set out plans and ensure that bare pipe only is passing through fire rated walls to allow for fire rating
b0e9a52c-ccc9-575a-b07f-c91cc46f4c48 | dropdown | Pressure Services | Suspended, Rough In, Risers
18b52f60-1435-5209-b1d2-ba0f7f9112d2 | dropdown | Type | Potable Cold Water, Hot Water, Non-Potable Cold Water, Fire Services, Gas Services
9deeed5a-e0d3-426b-a78c-b3ddae91631b | section | Bracketing, fittings & Noggins
f1958e57-3a8d-4dea-bb57-ea2da74f65a3 | checkpoint | Install Brackets as required, check alignment and spacing as per manufacturer's specification & applicable Australian Standard
16e8fd25-3cd2-4c74-b863-a366b149eac9 | checkpoint | Ensure correct brackets are used dependant on material selected
26d809c0-f226-4cd3-acb8-06bd51421eb4 | checkpoint | See extract from AS3500.1 for water services
507c40ea-6460-42a3-9118-ab5b1cee2d58 | checkpoint | Ensure correct fittings are used as per pipe weights, element exposure & project specification
a817afc6-d711-449c-b37e-c3258c0cf6dc | checkpoint | Ensure all Noggins are installed prior to sheeting of walls (e.g wall hung basin/shower rail/ fire hose reel)
2c2b561f-a8ff-4d4a-a361-c452fe145059 | checkpoint | Ensure supports are installed min 600mm from penetrations through slabs or walls where insulation is required
85300715-e140-4ad9-aeca-29c9d861fcf5 | section | Install Pipework
9acb809b-871a-4ea7-9aa2-eef9a7081a78 | checkpoint | Ensure appropriately coloured pipework is installed (Hot= Red, Cold= Black,Yellow=Gas)
93e5216d-d8fd-4920-ac1b-b76ba1edfb6f | checkpoint | Visually inspect the inside of the fitting to ensure it is free of any dirt or grit
60c14506-dfda-4e43-a2be-a9beb9d784c4 | checkpoint | Cut pipe cleanly and squarely using PE-X Pipe Cutters.
3d9275a2-608f-494f-ab21-e1b254ecb95e | checkpoint | Where required Deburr pipe end by inserting reaming tool fully into the pipe using a twisting action then rotate 2-3 full turns or until it moves freely within the pipe. Inspect to ensure sharp edges removed
9b72437e-7692-44f9-9cb2-44da6bddce37 | checkpoint | Push pipe into crimp fitting until the pipe is fully inserted and visible through the witness holes.
df62da33-653f-4585-8a19-51eab4f8b95d | checkpoint | Centralise Crimping Tool jaws over the sleeve and compress the jaws until they are fully enclosed around the fitting
6bfa910f-d2ad-4626-add3-e818cb5b8c02 | checkpoint | Inspect the joint for soundness and correct crimp operation. Ensure pipe is still visible in witness hole
ff48be59-a06d-47b3-ad3b-d01eeec7a1c1 | checkpoint | Ensure pipework is not installed in the path of future fittings (sheeting screws, bathroom accessory fittings etc.)
8280d71e-1a53-4150-8bb2-545be11ea22e | checkpoint | Use crimp gauge to check joint is crimped to correct torque. Tighten or loosen torque on crimp tool if necessary
1b3bd4fb-e5ff-4f54-8698-977f7f154062 | section | Test Pipework
e4a9eabf-44fc-4082-a27a-392699a3cba0 | checkpoint | Photographic record to be kept of process. Take photos of gauges before and after
210cb4fe-3eee-4af7-8e42-fdcd2b0036ab | checkpoint | Pump test pipework to required kpa and time period as per AS3500 & AS5601.1
3c3abac0-5027-45d4-8b18-db3fb3515224 | checkpoint | For water test pipework to 1500kpa for a period of not less than 30 mins. Ensure no air left in pipelines
52bb6c3e-66d8-4726-a756-63262887516d | checkpoint | For reduced pressure water systems test pipework to manufacturer's specification kpa & time period
cb4066b8-9bda-440a-bdfa-cdf0338dbb6a | checkpoint | For Gas Installations Test pipework to min 7Kpa or 1.5 times the working pressure whichever is greater for min 5min period
f5bf833c-13a1-4da7-a4bd-79a3e9c75f55 | checkpoint | For Fire Service Installations Test pipework to min 1700Kpa for 30mins or specified time & pressure
452aa58a-7704-46f7-89fb-98f3b0fa6388 | section | Inspect Pipework
c47869cc-3b76-44d5-8555-332712109d4d | checkpoint | Complete all required inspections by third parties (client, authorities etc)
78580e99-c466-407d-a0b4-7a3a75ebe482 | signoff | Work verified by Scente Group
92ebc1c1-43ca-487a-846b-eae3d279eaba | section | Pipe Insulation & Identification
c6b2651c-fb6c-47c5-a055-87199e18f662 | checkpoint | Apply correct pipe identity stickers to indicate flow direction
ebef2dd6-0519-4bd2-9d55-57da52832f17 | checkpoint | Apply thermal insulation to any hot water pipework. Thickness & type as per project specification
63b9b904-223c-4dee-95df-bd2303cb87cb | section | Photos
c3eddd20-9de6-4946-9ffc-6f8a2667e426 | checkpoint | Photographic record to be kept of process. Take photos of entire installation
d170acca-a2af-4eae-802e-3850443422de | checkpoint | Works verified as conforming (McPherson Plumbing Representative)
923fca7d-6873-4215-8052-cef735d4105c | signoff | Work verified by Scente Group
88ad3e39-48d6-4907-85d0-eb8e66ac0a62 | checklist | ITP 6 - Pressure Services - Polyethylene |  | ITP 6 - Pressure Services - Polyethylene
61424e7a-dc22-42e6-a7d6-6eb1f867298c | section | Setout & Location
2e0f3e29-edef-432f-91da-3b9873008935 | checkpoint | Check dimensions on drawings and record any remarks / deviations on as built drawings & take photo of title block
f721ac62-0344-41de-8198-dc84d15edfae | checkpoint | Review wall set out plans and ensure pipe passes through wall square
9f1cdd35-8d1a-44bd-b615-4e00f949eaae | checkpoint | Review interfacing services and ensure no clashes
4a605bc6-6043-4a5f-8a96-91b9875c3311 | checkpoint | Always set out off metre mark where applicable and when possible transfer for later reference (e.g inside inwall cistern)
450205ed-d66f-429c-87d1-8c7e2793b37e | checkpoint | Review wall set out plans and ensure that bare pipe only is passing through fire rated walls to allow for fire rating
a3cbd881-32c6-53d1-beb6-2bf1cec7ab31 | dropdown | Pressure Services | Suspended, Rough In, Risers
0b8211a9-16be-5044-91a1-2d736fba5eef | dropdown | Type | Potable Cold Water, Hot Water, Non-Potable Cold Water, Fire Services, Gas Services
27f0f75d-f7dd-4f10-bbe4-2d200c618bef | section | Bracketing, fittings & Noggins
376fd200-8e40-42f6-a639-a85515fc96cc | checkpoint | Install Brackets as required, check alignment and spacing as per manufacturer's specification & applicable Australian Standard
cf54df5d-1526-4391-900b-80f265c5032f | checkpoint | Ensure correct brackets are used dependant on material selected
c5c23cec-84be-4082-81ad-e0fa1da9b5b5 | checkpoint | See extract from AS3500.1 for water services
ad437ab1-f8ff-4883-80b8-3941e3db648e | checkpoint | Ensure correct fittings are used as per pipe weights, element exposure & project specification
6b155ef5-e845-4621-95f1-2c5b13491393 | checkpoint | Ensure all Noggins are installed prior to sheeting of walls (e.g wall hung basin/shower rail/ fire hose reel)
135bcec3-789e-4070-b6dd-d7a8695c1c07 | checkpoint | Ensure supports are installed min 600mm from penetrations through slabs or walls where insulation is required
437d9e63-faba-44ee-8f42-6fee38c82fd0 | section | Install Pipework
41760369-828f-4696-82a5-7c5a3810d0a5 | checkpoint | Accurately measure length of pipe & cut square. Deburr inside & outside of cut end
30d0b8c6-6c42-472b-8683-1a15b0593f84 | checkpoint | Ensure sockets are primed and clean and apply a sufficient amount of Type P solvent cement
21f33bdd-20a9-4a7e-99e1-075589bd15f8 | checkpoint | Gently insert the pipe and fitting to full depth with a quarter turn & hold for 30 seconds
f129b6fe-9d88-4389-9bb6-b51a39d65e7e | checkpoint | Do not disturb joint for at least 5 minutes
8d473f26-cb99-4ee1-afc7-0002bc569fe3 | checkpoint | Wipe away any excess glue and inspect joint for soundness. Allow to cure for 24 hours before pressure testing
0bfcda12-3059-44fd-bd04-2b562009d540 | checkpoint | When installing non-potable services ensure pipework is not installed within 100mm of any parallel drinking service pipework
16d4ad99-446a-4734-aeb9-e5557b9a617b | section | Test Pipework
a81dca50-bd44-4ce7-a872-f4ff615649a7 | checkpoint | Photographic record to be kept of process. Take photos of gauges before and after
bcaf906d-175c-443e-b089-349a26e2f9a7 | checkpoint | Pump test pipework to required kpa and time period as per AS3500 & AS5601.1
c8baba59-2a5e-4947-bb60-d167aee57506 | checkpoint | For water test pipework to 1500kpa for a period of not less than 30 mins. Ensure no air left in pipelines
ea78fb6e-92ba-44b8-b37d-36067ab82e8c | checkpoint | For reduced pressure water systems test pipework to manufacturer's specification kpa & time period
c9d692df-a3ee-4986-afd9-4ac028785d0b | checkpoint | For Gas Installations Test pipework to min 7Kpa or 1.5 times the working pressure whichever is greater for min 5min period
be2b2ae2-0a1e-41a7-8990-7a44fd106ee6 | checkpoint | For Fire Service Installations Test pipework to min 1700Kpa for 30mins or specified time & pressure
df46223a-d862-491e-8711-52792685c7c4 | section | Inspect Pipework
df7217ae-fd9a-437b-bb1a-b35c4cd3f591 | checkpoint | Complete all required inspections by third parties (client, authorities etc)
39fa4cbc-b243-474f-8fe5-1bc3486f1eab | signoff | Work verified by Scente Group
b8e837ab-25e7-45e9-92ca-c86e3eaa839c | section | Pipe Insulation & Identification
4707869a-92cc-4ad9-af05-c658ce9e2265 | checkpoint | Apply correct pipe identity stickers to indicate flow direction
1108285a-5ba6-47ee-99cd-8e6fdedf0fe7 | checkpoint | Apply thermal insulation to any hot water pipework. Thickness & type as per project specification
804a4bc7-eece-4bb3-b535-edee6ea30854 | section | Photos
a37dc4be-7c12-4e4a-b9d9-6127b094bd0d | checkpoint | Photographic record to be kept of process. Take photos of entire installation
d2ba7964-975b-4abd-844c-f7af1a1cc92d | checkpoint | Works verified as conforming (McPherson Plumbing Representative)
f91e15be-21bd-41ed-991b-fe1294a1e9b6 | signoff | Work verified by Scente Group
3324f354-c213-4041-bf61-2d0ebfba677a | checklist | ITP 6 - Pressure Services - Press Copper / Press Stainless Steel |  | ITP 6 - Pressure Services - Press Copper / Press Stainless Steel
2c1b014c-c382-4e81-8956-9c7c3555007b | section | Setout & Location
b4bb087b-7801-4138-bd47-0b5b2c2688e0 | checkpoint | Check dimensions on drawings and record any remarks / deviations on as built drawings & take photo of title block
aa01b738-4c73-4384-9066-397181f1b4e3 | checkpoint | Review wall set out plans and ensure pipe passes through wall square
696ab341-ad6a-41cf-bc96-f06f5ef35a5e | checkpoint | Review interfacing services and ensure no clashes
2345713c-33a8-4724-9430-f16604b01b40 | checkpoint | Always set out off metre mark where applicable and when possible transfer for later reference (e.g inside inwall cistern)
461f5a2d-5541-4a2c-aa81-8cf8451184ee | checkpoint | Review wall set out plans and ensure that bare pipe only is passing through fire rated walls to allow for fire rating
032481e5-aeb8-5e05-b854-bf0faeedf6c2 | dropdown | Type of pipe | Press Copper, Press Stainless Steel
e3fcc8b6-54cd-52ee-8461-d54d2aa09f20 | dropdown | Pressure Services | Suspended, Rough In, Risers
dff012b9-3bbd-52ac-9f11-563b34473f78 | dropdown | Type / Service | Potable Cold Water, Hot Water, Non-Potable Cold Water, Fire Services, Gas Services
02e4776f-06df-4b35-b3e6-d342d89b292f | section | Bracketing, fittings & Noggins
0e9a893b-af58-4a79-a9b1-722f89349325 | checkpoint | Install Brackets as required, check alignment and spacing as per manufacturer's specification & applicable Australian Standard
3f5084ba-4a88-4f6e-9e21-d03378366847 | checkpoint | Ensure correct brackets are used dependant on material selected
eb5a7466-453e-4df3-860e-4cb977de0c61 | checkpoint | See extract from AS3500.1 for water services
f8d2efc1-27a2-4683-be9a-865f4412d728 | checkpoint | Ensure correct fittings are used as per pipe weights, element exposure & project specification
5e9011b0-7bd1-4e48-ab29-b15677b81d18 | checkpoint | Ensure all Noggins are installed prior to sheeting of walls (e.g wall hung basin/shower rail/ fire hose reel)
4030c2f4-8bdb-4124-9b13-b2bc545c3a75 | checkpoint | Ensure supports are installed min 600mm from penetrations through slabs or walls where insulation is required
4ea16e4d-1e60-4c06-8d16-f0fd7411a268 | section | Install Pipework
cbe6002c-cae6-453d-91cd-775e947def61 | checkpoint | Select appropriate tool for brand being used. Only use batteries supplied with tool & with not less than 40% charge
691450be-567e-4e1d-9d84-68eb887b638f | checkpoint | Use appropriate copper tube cutter to ensure a clean square cut.
8b0da128-63cf-43ef-88aa-8a7f4712534d | checkpoint | Ensure cut end is clean and free from any scratches or damage such as dents or deformity.
b41397f3-8698-4b35-a823-34a99f8d8e18 | checkpoint | Ensure that the internal and external tube end is completely free from burrs or sharp edges by using a deburring tool
2cebfe5d-3ca7-4ae7-a217-1273dd3db804 | checkpoint | Before inserting the tube, check O-Rings for correct placement and that they are free of damage or debris.
665bee3e-158b-4b4e-b828-3e6a47b58c05 | checkpoint | Apply insertion depth mark with pen to the tube prior to insertion into the fitting.
6f666dd2-42a9-41bc-b6c0-221e6ecf37ef | checkpoint | Tube to be inserted Parallel into the fitting , ensuring the insertion mark is visible and in line with fitting end
6a3f3b5d-3380-4ec5-b1a0-0fb804a6e7b2 | checkpoint | Place jaw over the fitting, correctly aligned and positioned and activate tool to press the joint
7d486998-f58a-4945-873f-0ae5f3295a84 | checkpoint | Tool should complete the correct cycle and the jaw ends should fully close on completion.
c4dd6418-bd20-43c1-81e9-ea5540333766 | checkpoint | If the tool does not complete the required cycle during operation the fitting should be cut out, replaced then repressed.
c12aaaaa-f214-4d7e-a017-a97e6d85df2e | checkpoint | No fitting should be pressed more than once
c3564461-8144-4dc1-87d0-290cd3d7bc75 | checkpoint | When installing non-potable services ensure pipework is not installed within 100mm of any parallel drinking service pipework
b56560b2-a9fb-4ee8-ab14-78bbbeeac120 | section | Test Pipework
98cc7073-49cd-4b8a-a6e8-1fbd29d23e9b | checkpoint | Photographic record to be kept of process. Take photos of gauges before and after
374eae84-d130-431c-bfc6-ea42c3859031 | checkpoint | Pump test pipework to required kpa and time period as per AS3500 & AS5601.1
641070f3-d1a0-47d4-8445-71e5dbbef5a7 | checkpoint | For water test pipework to 1500kpa for a period of not less than 30 mins. Ensure no air left in pipelines
0e5c6157-8d6f-4cfc-aa54-839d88299471 | checkpoint | For reduced pressure water systems test pipework to manufacturer's specification kpa & time period
0862873a-b394-4ca3-a6e9-d749fe02eb3f | checkpoint | For Gas Installations Test pipework to min 7Kpa or 1.5 times the working pressure whichever is greater for min 5min period
dcd88c11-631c-473b-a385-56d5b754919e | checkpoint | For Fire Service Installations Test pipework to min 1700Kpa for 30mins or specified time & pressure
2cbf0882-6898-49b1-9263-e0aa104afcd6 | section | Inspect Pipework
cea8743a-ec20-41d0-90d3-a0d3efaae86d | checkpoint | Complete all required inspections by third parties (client, authorities etc)
6c58e4e1-d846-45c2-9e9a-7e6f58ed8d9e | signoff | Work verified by Scente Group
5524ed36-c1ae-452c-b022-b8595c3b4821 | section | Pipe Insulation & Identification
2416ef59-28b0-464d-9e77-b7c1481b9c4e | checkpoint | Apply correct pipe identity stickers to indicate flow direction
e7858665-d897-42fc-97b1-de927bf2dab0 | checkpoint | Apply thermal insulation to any hot water pipework. Thickness & type as per project specification
b19a1f90-4f56-4faa-812a-b65ae863e338 | section | Photos
f9427067-fef4-4d68-87a6-0d6b5396e3b1 | checkpoint | Photographic record to be kept of process. Take photos of entire installation
6c9db7b9-25e9-4755-886b-035c046cdc92 | checkpoint | Works verified as conforming (McPherson Plumbing Representative)
cac1d027-ea20-44a1-8dfd-5ee1314f30a4 | signoff | Work verified by Scente Group
badb99f8-6e57-424b-9447-71dbf4af62d3 | checklist | ITP 6 - Pressure Services - Roll Groove |  | ITP 6 - Pressure Services - Roll Groove
29513022-1a9d-4345-9c17-75ad3e10d1b9 | section | Setout & Location
b157faac-4440-4066-9bc9-6f03d2c1a895 | checkpoint | Check dimensions on drawings and record any remarks / deviations on as built drawings & take photo of title block
8cf1b2ab-951c-45d0-b16e-89c7b4123ff5 | checkpoint | Review wall set out plans and ensure pipe passes through wall square
181cfc87-66e7-40a5-b2bb-389e336f36ff | checkpoint | Review interfacing services and ensure no clashes
3920994d-d9af-4a61-bf71-5c3eafecfbb1 | checkpoint | Always set out off metre mark where applicable and when possible transfer for later reference (e.g inside inwall cistern)
bb0e31b6-ace9-4874-b081-e3c26e3b259c | checkpoint | Review wall set out plans and ensure that bare pipe only is passing through fire rated walls to allow for fire rating
d2c1c15d-6f28-5903-8843-17bbf1ad897b | dropdown | Pressure Services | Suspended, Rough In, Risers
3fe5d7ce-286b-5334-ac36-807217ea3aec | dropdown | Type | Potable Cold Water, Hot Water, Non-Potable Cold Water, Fire Services, Gas Services
c9caaaa1-023f-4f68-a730-d548e96212f4 | section | Bracketing, fittings & Noggins
f167bb9b-c6e7-49cc-8c49-0c4ddb7750bc | checkpoint | Install Brackets as required, check alignment and spacing as per manufacturer's specification & applicable Australian Standard
9b53c416-6d40-483a-89c2-e20361932e3a | checkpoint | Ensure correct brackets are used dependant on material selected
c87b5654-e5e7-42a0-82e4-2647b5ea0ae8 | checkpoint | See extract from AS3500.1 for water services
c83cc0cf-87e4-4b6b-9ea6-b9d4e6d014f2 | checkpoint | Ensure correct fittings are used as per pipe weights, element exposure & project specification
fde3c446-5630-446f-9417-850667c843ab | checkpoint | Ensure all Noggins are installed prior to sheeting of walls (e.g wall hung basin/shower rail/ fire hose reel)
a814b8b6-014e-4802-bfd2-c2ea0a7314f1 | checkpoint | Ensure supports are installed min 600mm from penetrations through slabs or walls where insulation is required
97bf63b7-7803-4892-8588-6d3914486d37 | section | Install Pipework
6107d5a5-623f-4b5b-8b64-788875cf6cb3 | checkpoint | Where practical, arrange for pipework to be pre-cut and grooved off site
46452c64-bd7f-48cb-aa91-c68d194fe220 | checkpoint | Ensure pipe is cut squarely with a fit for purpose tool
7ee7a8e8-d187-44b1-a7bc-7735bfc2e26e | checkpoint | Assure manufactured roll grooved ends of pipework are measured for appropriate circumference using approved tape measure
9dd84172-ef60-4fce-8864-cb022e021d24 | checkpoint | Ensure pipe cut on-site is grooved to required depth & check with approved tape measure
a687d7c7-280c-422d-99f9-5f4e154472a9 | checkpoint | Ensure pipe length is correct. Don't use coupling to pull incorrect pipe lengths together
5acfcbee-bc61-4547-ada4-918c3dab99f5 | checkpoint | Lubricate and install inner coupling for connection of pipe and fittings, ensuring it is lapped over each connection point
df9e8ebb-3f20-4b74-9ce5-f5c71aeb510e | checkpoint | tighten outer metal band gradually and evenly to a torque of the manufacturer's specification
baa6834f-c6d9-4e2a-a73f-23e50b9406e8 | checkpoint | Ensure a gap no more than 2mm is evident on joining portions of outer coupling
1f487644-42d8-4b1b-84ca-c311400b18c6 | checkpoint | Inspect fitting / pipe after roll groove collar tightening to ensure it is square and aligned
77aa2b72-79fc-4b30-8330-d934d75d08de | section | Test Pipework
893c90b4-24b5-4bd4-8f02-e0f638aa4937 | checkpoint | Photographic record to be kept of process. Take photos of gauges before and after
f97a67ee-1d30-4fee-af3b-84f2a6457a79 | checkpoint | Pump test pipework to required kpa and time period as per AS3500 & AS5601.1
3a1f3634-049e-46ef-b542-9451dae0988a | checkpoint | For water test pipework to 1500kpa for a period of not less than 30 mins. Ensure no air left in pipelines
c18f769c-5546-4635-bf05-c5e3799e37ba | checkpoint | For reduced pressure water systems test pipework to manufacturer's specification kpa & time period
53082e21-b972-4fbc-8171-c01dcbc92ad1 | checkpoint | For Gas Installations Test pipework to min 7Kpa or 1.5 times the working pressure whichever is greater for min 5min period
f992b13a-7765-4e71-8152-53aac35d65c9 | checkpoint | For Fire Service Installations Test pipework to min 1700Kpa for 30mins or specified time & pressure
08df816c-6692-4537-8e30-fd2fdc3a2c16 | section | Inspect Pipework
fbe6ae1f-e119-472e-ae0d-d95c3c96e8be | checkpoint | Complete all required inspections by third parties (client, authorities etc)
6978f7b4-8772-4e40-a572-229a990617fc | signoff | Work verified by Scente Group
585385df-311c-4126-8224-a36983f81a3f | section | Pipe Insulation & Identification
f9594ba2-ad17-40f5-998f-2a0cda2cbf0e | checkpoint | Apply correct pipe identity stickers to indicate flow direction
abd511ef-ef06-47f7-86a8-691600b64000 | checkpoint | Apply thermal insulation to any hot water pipework. Thickness & type as per project specification
97e2d8a5-6254-4846-9ed0-f3b5dacf2ddc | section | Photos
2790760a-5749-4f14-8d67-23ce72074611 | checkpoint | Photographic record to be kept of process. Take photos of entire installation
9cea9749-6579-4661-be57-f3ed109839f1 | checkpoint | Works verified as conforming (McPherson Plumbing Representative)
275e9d14-f84c-449e-9c53-383aad8a4ba3 | signoff | Work verified by Scente Group
f19d5dc0-c688-4f59-9d6e-f8b4e231087b | checklist | ITP 6 - Pressure Services - XLPE Sleeve Type |  | ITP 6 - Pressure Services - XLPE Sleeve Type
357eeb65-a038-4026-bee1-501e5464b4ac | section | Setout & Location
7ff0d961-ba1f-41d9-9682-5767fa9bfdca | checkpoint | Check dimensions on drawings and record any remarks / deviations on as built drawings & take photo of title block
d7fb1c23-bb63-4f10-af92-4f68e3e5098c | checkpoint | Review wall set out plans and ensure pipe passes through wall square
55b728df-7d38-41f8-9da2-d2a953d244b7 | checkpoint | Review interfacing services and ensure no clashes
38526b48-d307-4e57-8b0c-bef9e7515323 | checkpoint | Always set out off metre mark where applicable and when possible transfer for later reference (e.g inside inwall cistern)
86ce7226-d0f2-4729-ba38-0acf028ca683 | checkpoint | Review wall set out plans and ensure that bare pipe only is passing through fire rated walls to allow for fire rating
ea803bac-1d96-5b90-b42f-94728488780d | dropdown | Pressure Services | Suspended, Rough In, Risers
49c9c871-65bd-549d-aa7f-50190e3016e0 | dropdown | Type | Potable Cold Water, Hot Water, Non-Potable Cold Water, Fire Services, Gas Services
2e1aa0ce-2f72-4c0c-9b75-0fce8b72f0b9 | section | Bracketing, fittings & Noggins
0139c43c-5235-40e8-8d40-ef574af6f0bb | checkpoint | Install Brackets as required, check alignment and spacing as per manufacturer's specification & applicable Australian Standard
02a21a8f-901b-48f5-857e-216c3783d7a8 | checkpoint | Ensure correct brackets are used dependant on material selected
b1763ef6-5694-4b38-be1c-2dc53368b973 | checkpoint | See extract from AS3500.1 for water services
cf4a7d67-ffcf-4ea8-bfe2-72aa64fda250 | checkpoint | Ensure correct fittings are used as per pipe weights, element exposure & project specification
33c686c0-a78b-461d-be64-c0f53c8fc286 | checkpoint | Ensure all Noggins are installed prior to sheeting of walls (e.g wall hung basin/shower rail/ fire hose reel)
09b1ef00-510a-4e7b-a293-a0a76fc3869a | checkpoint | Ensure supports are installed min 600mm from penetrations through slabs or walls where insulation is required
2fd64ea2-11fb-4866-901b-057769d65c9c | section | Install Pipework
76d29043-56cb-4bff-b2bb-e49dcd9100b0 | checkpoint | Ensure appropriately coloured pipework is installed (Hot= Red, Cold= Black)
bac70c8d-edfe-41f7-8426-779e93e27cd9 | checkpoint | Cut pipe cleanly and squarely using PE-X Pipe Cutters. Place beveled end of the sleeve facing outwards toward joint
2419f91a-46c5-406e-800c-7a83a387b1b9 | checkpoint | Expand the pipe twice only using the approved Expanding Tool
e90db636-0ef0-4858-bda3-8edafc3ef203 | checkpoint | Insert the fitting into the expanded end of the pipe until the fitting reaches the pipe stop.
ff0012b7-ec3a-4db6-9585-e8e781bff66a | checkpoint | Slide the jointing sleeve towards the fitting. Position the jointing sleeve and the fitting squarely within the jaws of the Compression Tool.
a443f354-6edd-4b31-94a3-267253c0d4a7 | checkpoint | Draw the sleeve towards the fitting by closing the jaws of the Compression Tool until the sleeve reaches the shoulder of the fitting.
3bf59e17-7ccf-4b99-bdf9-645eb7c1d63d | checkpoint | Ensure pipework is not installed in the path of future fittings (sheeting screws, bathroom accessory fittings etc.)
ef63b534-056b-4d4e-9aee-4a7a4232597b | checkpoint | When installing non-potable services ensure pipework is not installed within 100mm of any parallel drinking service pipework
a1811756-cc06-4ede-877d-3d0d2cb99d46 | section | Test Pipework
15b31830-9a74-426b-a4ff-062c959b70ae | checkpoint | Photographic record to be kept of process. Take photos of gauges before and after
04cfa468-705e-417b-a338-f6748b0be925 | checkpoint | Pump test pipework to required kpa and time period as per AS3500 & AS5601.1
e5a57a6a-10ba-4b1b-8a19-c89a3bdb133c | checkpoint | For water test pipework to 1500kpa for a period of not less than 30 mins. Ensure no air left in pipelines
d2d751e2-edc8-4a6f-a955-33e15b9421d4 | checkpoint | For reduced pressure water systems test pipework to manufacturer's specification kpa & time period
14a00f1f-0819-424b-bf4a-e3565a0f3692 | checkpoint | For Gas Installations Test pipework to min 7Kpa or 1.5 times the working pressure whichever is greater for min 5min period
5ef83573-3ad2-42e3-b08f-88c307093690 | checkpoint | For Fire Service Installations Test pipework to min 1700Kpa for 30mins or specified time & pressure
b980dc40-9b8b-4026-930a-044c001dae23 | section | Inspect Pipework
01a70709-26b2-4aff-903c-8cf4b8b8124e | checkpoint | Complete all required inspections by third parties (client, authorities etc)
fbebe2d0-c1e4-416d-b285-0c5467f8adba | signoff | Work verified by Scente Group
e4186bdf-3596-4450-89c0-5c1270d7a0ea | section | Pipe Insulation & Identification
1e0d7d07-c73d-41e7-a797-515d6edb9ec9 | checkpoint | Apply correct pipe identity stickers to indicate flow direction
d5e59c7a-63d5-4d31-b02b-70619264a1f8 | checkpoint | Apply thermal insulation to any hot water pipework. Thickness & type as per project specification
c082a9b7-d5ae-486b-95eb-01da5022ee6c | section | Photos
2cd562a9-fec9-4598-a35d-8cdb7750eaf3 | checkpoint | Photographic record to be kept of process. Take photos of entire installation
bdb1b62a-f718-4205-b072-6c2c06305e70 | checkpoint | Works verified as conforming (McPherson Plumbing Representative)
62eb65f6-21fe-4653-9ae1-9ba64b2d28d7 | signoff | Work verified by Scente Group
e4b763d6-a34d-43fc-83ea-259cb767b84b | checklist | ITP 7 - Meters & Valves |  | ITP 7 - Meters & Valves
9a294edd-00dc-49c0-a668-4378dddf7bc7 | section | Setout & Location
562ea893-3a24-4e06-bde3-ffaca1dd7c32 | checkpoint | Check dimensions on drawings and record any remarks / deviations on as built drawings & take photo of title block
33cfdb75-95b7-4195-aaa5-6911fb14d87a | checkpoint | Setout of meter/valve installed as per authority & project requirements, Height & specials
1c4df7b9-c7b2-4236-b6a8-77a1fea93dc4 | checkpoint | Setout of meter/valve installed as per project requirements, Height & specials
55607eae-b06e-4454-a6f0-4e21176a61cb | checkpoint | Meter located as per Authority requirements
c58734c5-e695-54dd-9926-62148bfe0c15 | dropdown | Hydraulic Service Meter Valves | Metering, Temperature, Pressure, Testing, Control
53a5f68a-eaff-5185-8814-dc99545b5ff3 | dropdown | Service | Potable Cold Water, Hot Water, Non-Potable Cold Water, Fire Services, Gas Services
dcdb8fec-0f48-489a-8c16-fac5a2431f7a | section | Bracketing, fittings & Supports
681cc7f0-db4e-4bc2-af49-fc7811e1da6c | checkpoint | Install Brackets as required, check alignment and spacing as per manufacturer's specification & applicable Australian Standard
8e40d13e-f5d3-46a5-805f-983a339243c0 | checkpoint | Ensure correct brackets are used dependant on pump selected
d9c16f49-94a9-4c37-bc42-12ab0f01550d | checkpoint | Pipework supported independently of pump assembly
84941c04-560b-4c91-9ce1-ab4d8cdf0e44 | checkpoint | Ensure correct fittings are used as per pump/plant weights, element exposure & project specification
87d41c28-e2c5-4e59-8ef1-df64a951b38f | checkpoint | Ensure acoustic mounts/brackets are used as per acoustic spec
5e32f912-4088-4e15-afd8-a95a6e6292ac | section | Install of Valves / Meters
8d9c2f15-0f6f-4eda-9b20-88c2ae75aab4 | checkpoint | Flush all lines where possible prior to installation
fa6ab7ef-5913-494d-bd72-2c5d500509de | checkpoint | Install Valve/ Meter as per authority/manufacturer's requirements
2ed6fc62-d172-4f5a-aacb-7ead76b5ae53 | checkpoint | Mounting of valve/ meter at a serviceable height and location where required as well as vertical & plumb
badd674d-40c3-4ffb-b278-22350dd9e942 | checkpoint | Valve Installed as per standards (Height, proximity to other services/ walls etc)
8df83d76-e4c1-4557-adbe-769f3a32a12a | checkpoint | Unions, Isolation Valves, Strainers, Drains etc installed where required for servicing & as per manufacturer's specification
9b55090e-d44a-45d4-9ede-1710b20a8a4c | checkpoint | Teflon joints used over loxeal where servicing is required (loxeal used on male threads only)
f70bb878-d93e-49f5-a5a1-a389309b9b3f | checkpoint | Isolation valves installed as per meter/valve requirements
241793e4-2151-4f8b-89fe-ba78c794af50 | checkpoint | Petes Plug Valves installed as per Authority Requirements
ffc587f2-19d9-4ef4-a95f-f98d22a5ca3d | checkpoint | Valve/ Meter installed in the correct orientation (check for directional arrow)
12f7e424-887e-42f2-a337-a11034ae4466 | checkpoint | Install identification/service tags to authority/project specifications
366c0412-f449-4e28-8a62-0c055986a91a | section | Testing
d0166208-c6f2-4efa-a829-3914745df62f | checkpoint | Pressure Reduction valve tested for accuracy on outlet pipework as per manufacturer's specification
724ba688-4fe1-4f15-b2a8-328b8ab6eebc | checkpoint | Tempering valve outlet temperature checked for 50 degrees max or as per manufacturer/ project requirements
f90d73cb-acf8-46a0-a305-c99cfad3279c | checkpoint | Check that no leaks on unions or valve threads
a97b4df2-1cd8-40a7-bd0a-74f1a05b91d2 | checkpoint | Test valve and commision as per manufacturer's requirements
a098ae85-bb8d-488a-8a34-1bf99796d75a | checkpoint | Clean all strainers/dirt box from debris
f91d1f73-b34a-4fee-af7d-76b08a67aeeb | section | Inspect Pipework
c795931b-3314-4fd5-a453-3ae5837412da | checkpoint | Complete all required inspections by third parties (client, authorities etc)
0253c67f-5ea1-4085-a270-5d3ed536cd44 | signoff | Work verified by Scente Group
82759add-de78-4a70-b40c-a38093e5dfae | section | Photos
aa64a84f-f61c-4cf3-829d-e9c5f7b81a4b | checkpoint | Photographic record to be kept of process. Take photos of entire installation
c138c61e-08f9-4d6d-8c92-141b23b9a4bd | checkpoint | Works verified as conforming (McPherson Plumbing Representative)
973a1b11-976f-4206-934c-c93e19a9bbae | signoff | Work verified by Scente Group
fb74dfad-e599-494b-94d4-8fe72e83d585 | checklist | ITP 8 - PC Plant & Pump |  | ITP 8 - PC Plant & Pump
e9b0c4b3-4da8-4a77-bd2a-48f5a300551a | section | Setout & Location
6254be39-7515-4257-b2d4-012113899d8c | checkpoint | Check dimensions on drawings and record any remarks / deviations on as built drawings & take photo of title block
90447457-c776-4d90-a856-474548744a0e | checkpoint | Set Out of Pump/ Plant installed as per authority requirements, Height & specials
d7cb5cc5-6e55-555b-9a38-b9785945ab44 | dropdown | Service | Potable Cold Water, Hot Water, Non-Potable Cold Water, Fire Services, Gas Services, Sewer, Stormwater
d208955c-d104-4c7b-a170-3d81c123b03c | section | Bracketing, fittings & Supports
bbd54c01-4736-4c17-8d04-d83de6a2a4b7 | checkpoint | Install Brackets as required, check alignment and spacing as per manufacturer's specification & applicable Australian Standard
b3f3ddca-fe27-4da4-9bcc-faf96491f79f | checkpoint | Ensure correct brackets are used dependant on pump selected
2fd66ca9-c0d9-4053-8682-187f9c59d3be | checkpoint | Pipework supported independently of pump assembly
8f6a2245-9696-4827-a56c-cd9a59e106ce | checkpoint | Ensure correct fittings are used as per pump/plant weights, element exposure & project specification
91853561-b31e-4ee0-8ba1-53502748a8df | checkpoint | Ensure acoustic mounts/brackets are used as per acoustic spec
7c21e07e-536f-4653-9002-2baf55af2a49 | section | Install of Pumps / Plant
86239c99-25d0-4c68-9563-0a82f286babf | checkpoint | Installed as per manufacturer requirements & specifications
2e61894f-2861-4b57-ad08-5fa1857d7af0 | checkpoint | Installed as per Authority requirements & specifications
ae383c6b-d22a-4cf1-a432-ff130c3ce434 | checkpoint | Mounting of Pump/Plant/Valves at a serviceable height where required
2406f255-1a91-404b-86bc-e7f77ed5f76a | checkpoint | Installed in a tradesman like manner vertical & plumb
0ce8baf3-ece2-45bc-b71a-ef90ddc89c17 | checkpoint | Ventilation & Flooring installed as per authority/australian standards & manufacturer requirements
318ef65c-6c87-4f34-9280-550d668c90ac | checkpoint | Unions, Isolation Valves, Strainers, Drains etc installed where required for servicing & as per manufacturer's specification
e2e01614-ee3c-4df7-83bf-ccee528ef905 | checkpoint | Installed on membraned plinth as per manufacturer/project requirements
ee7427b6-60a4-4d5e-8b86-b2de628de822 | checkpoint | Isolation valves installed as per Manufacturer/Project requirements
c7018680-cfdd-4cf1-a7bf-60e335ea87e1 | checkpoint | Petes Plug Valves installed as per Authority Requirements
7f36be38-0727-4461-98f8-1e20771e49be | checkpoint | Temperature Gauges installed as per Project/Manufacturer Requirements
bebeac71-d59b-4c2a-85a2-3dbb957d5274 | checkpoint | Non-return valves installed as per Project/Manufacturer Requirements
e455cbe7-5bfb-4e6f-939b-32d3bddbb554 | checkpoint | Pressure Gauges installed as per Project/Manufacturer Requirements
d4f2d1dc-7465-4e8d-b9e4-c72b88dfb766 | checkpoint | Auto air release Valves installed as per Project/Manufacturer Requirements
a791096c-30a4-42be-aa72-ad10c2664775 | checkpoint | Pump installed in the correct orientation (check for directional arrow)
c9643e34-0489-4194-9fa6-3da171a54bef | checkpoint | Install identification tags to authority/project specifications
5f35d450-9955-4df1-b0f9-77e023ab5e96 | checkpoint | Install pipework identification as per AS1345
021f3fcb-185e-4830-9722-48431f112c72 | section | Testing & Commissioning
53a71c05-cfbf-4a87-9993-93cad94aff49 | checkpoint | Testing & Commissioning as per manufacturer's specification
0deb7963-8fe2-42dd-aa50-aa04fa3a74a6 | checkpoint | Testing & Commissioning by supplier Attached
06b1f742-2879-4f2b-94c5-b73b121296e7 | checkpoint | All air removed from system and strainers cleaned
63f57b2e-85f8-4c21-99ce-a707f19b8a75 | checkpoint | Permanent Power supplied to plant / pump
daf2bea5-10cf-45ed-91f1-c963c41255de | checkpoint | All safety shut off devices installed & commissioned
2c31da64-817a-480a-b03e-641c0bdb8732 | checkpoint | Clean all plant & equipment before handover
9f3be574-48e9-4782-a7f4-d90d063ad1c4 | checkpoint | All drains cleaned of construction debris in the case of plant failure
17f2d828-9fa3-4794-8624-3513e05e2307 | section | Inspect Pipework
e56af304-6dc1-4348-a579-3caaf43d0828 | checkpoint | Complete all required inspections by third parties (client, authorities etc)
9c8d34b1-45c0-4f28-b04f-6968cf041041 | signoff | Work verified by Scente Group
70c33f61-7e58-4981-adb3-b86ee7c71245 | section | Photos
4f232e55-c1f3-43b5-961d-3af4521828c4 | checkpoint | Photographic record to be kept of process. Take photos of entire installation
85d05e12-f607-46af-8600-854b2d540a29 | checkpoint | Works verified as conforming (McPherson Plumbing Representative)
bddd6a92-c372-4ebb-b09d-456a3e95dd38 | signoff | Work verified by Scente Group
1950c7e1-23a0-4e00-9609-976c1ddf9846 | checklist | ITP 9 - Amenities PC Installation & Commissioning |  | ITP 9 - Amenities PC Installation & Commissioning UPDATED
f7dbb908-9f7b-4698-a1fd-669baf8b51cb | checkpoint | Time taken to get hot water at most disadvantaged fixture
ba85a7ec-1659-5c3e-b5a6-da48765dd9e8 | textbox | Time:
64d5ba89-e2af-45f4-ac68-05bfa9ab90aa | checkpoint | Hot & Cold water isolation valve test for cross connection
e617640c-aa4a-4c48-958d-106378e7a3ee | checkpoint | Non-Potable water isolation valve test for cross connection
2ed05c94-0101-46ee-ac0e-db54f00740a5 | checkpoint | Tempering valve set to requirered temperature (50 degrees Celsius max for residential for TMV use TMV Commissioning Sheet)
a2ae0ea5-d478-5d05-a675-8612a86f5d66 | textbox | Set temp (C)
07f92d7b-946c-4eb0-a18f-c8afec4775bc | checkpoint | Remove all strainers & full flush all pipework to remove any foreign matter or dirty water
e4733463-7ce8-408a-a700-09afdc116557 | checkpoint | Sink Installed - Silicone
4ba269a7-9e7f-4545-ad42-089c651ff47f | checkpoint | Secure & damage free (photo)
064729dc-2968-44ea-afbb-10e4c75b70e0 | checkpoint | Sink Mixer or sensor Tap Installed - Tested/ secured/ cross connection check/ aerator clear/ damage free/Sensor operating
8ee798f1-f02f-44c7-a7ec-e260a3ba01e8 | checkpoint | Sink Plug & Waste Installed
fb8d0113-aed9-4e01-8f82-37bf8b261f9c | checkpoint | Sink Trap installed & tested
c2fd8ffd-68c7-4486-b592-b65319c1e449 | checkpoint | Sink Tundish Installed
98621750-3e7d-47ee-8d22-6d18a7cf25cd | checkpoint | Floor Wastes - Clear & Free from debris (photo)
ab25f8c0-130b-4902-9432-9afb5d10ca25 | checkpoint | WC's Installed - Silicone
e26a6c95-6efa-4d7d-b10b-2e06c42dc684 | checkpoint | WC's Installed - Seat
1f6d8fc9-3a56-4665-8651-903f13fd6434 | checkpoint | WC Secure & damage free (photo)
4277cc23-ebfb-4e59-9d0a-591af873f5e7 | checkpoint | WC Flush Plate installed Plumb and damage free (photo)
bd1b2689-990c-4171-acb1-7098a6334867 | checkpoint | WC Tested (minimum 10 flushes and inspect under pan for leaks)
c1b9eff3-6ad3-4622-8503-5df725039bd9 | checkpoint | Clear Out Grate Installed
96d30be1-e14d-4429-a85f-2b9d6af28647 | checkpoint | Basin Installed - Silicone
2ee48677-fd4e-4d22-af8a-b343cda4a3c1 | checkpoint | Basin Secure & damage free (photo)
5772ff8c-3701-45eb-af0f-10ea7481916c | checkpoint | Basin Mixer or sensor Tap Installed - Tested/ secured/ cross connection check/ aerator clear/ damage free/Sensor operating
adea43b9-d7f7-4511-afcc-eefa917ef791 | checkpoint | Basin Plug & Waste Installed
93507ea2-e5c6-4b37-8c4c-de3250fb8e6b | checkpoint | Basin Trap installed & tested
a49ba678-2a68-4402-834c-670505bd4fe9 | checkpoint | Basin Tundish Installed
3eb83479-c6e2-48ce-9480-34b16a93f7f7 | checkpoint | Shower Installed - Mixer Trim Kit & Rail
8854a706-aee9-43ea-9901-b1abfc777619 | checkpoint | Shower Installed - Floor Waste clear & free from debris
525dfc0e-990a-4ffb-84c6-d871675d7cf1 | checkpoint | Urinals Installed
6f836b67-1b9a-47d9-8571-8ffd18f40c30 | checkpoint | Urinal Photo secure & damage free
8daaab9b-33d1-4780-913c-af4494d17328 | checkpoint | Urinal Cistern or Sensor/ flushing device installed as per manufacturers instructions & working correctly
f42c593c-0380-4482-8a14-ea0948585190 | checkpoint | Hose Taps installed as per drawing and project specs
0b182044-e988-48f0-a3bd-7d5d636d62bf | checkpoint | McPherson Sign-Off
035df053-7fd4-40af-9f79-d5b4f10d239d | checkpoint | Scentre/ Third Party Sign-Off
5d3dbea9-545a-4427-a0db-13dcb9e9806a | checklist | ITP 9 - PC Installation & Commissioning |  | ITP 9 - PC Installation & Commissioning
08bf70b2-07ac-4cab-8272-20a5d5f3c579 | section | Water
d07b2dd2-398a-4612-ab5c-793d69a283ef | checkpoint | Water Meters Installed - Cold, Hot, Non - Potable, Gas - Take picture of meters
7e0e64b9-99fd-4fbb-b06e-e724ebbad04a | checkpoint | Time taken to get hot water at most disadvantaged fixture
83ccb79c-6d40-4c7e-b832-38676579deca | checkpoint | Hot & Cold water isolation valve test for cross connection
105e5031-9744-4b53-9c78-904be071bf3d | checkpoint | Non-Potable water isolation valve test for cross connection
41ffb2a1-c28b-48c4-8620-80d066b18625 | checkpoint | Tempering valve set to required temperature (50 max for residential for tmv use ITP #9) Set temp -
3eb77a7d-d600-471c-ab0e-a158e94eb92e | checkpoint | Pressure reduction valves set to required pressure (500kpa max for fixtures) Take picture of valves and comment (Cold Water PRV KPA, Hot Water PRV KPA, Non-Potable PRV KPA)
b2109586-8b63-4ff5-a800-eb460ee61eae | section | Kitchen
d764c30f-8829-421d-8fce-e90c9d83be31 | checkpoint | Sink Installed - Secure & damage free (photo)
3673a8fe-02ef-4ad5-aecd-7ec39793e21f | checkpoint | Mixer Installed - Tested/ secured/ cross connection check/ aerator clear/ damage free, ( photo )
98eb84b0-22d2-4320-a6c7-fc695b117356 | checkpoint | Trap installed & tested, Tundish Installed & test
20f4b9e5-a415-4b9e-8ae8-ba9e746c2d4e | checkpoint | AAV installed with allowance for servicing/replacement
e534dbd5-b367-4a86-ac8a-3c4a2d6e869c | checkpoint | Dishwasher Installed
64cb1dfb-ff20-4585-b29b-8889d6dab62f | checkpoint | DW QA - Cycle Run / Water Connection Ok/tight/secured / Waste Connection- Ok/tight/secured/drilled out
96afb6e7-7d5a-4000-a705-59af5c471497 | checkpoint | External Hose Tap Installed - Potable, Non-Potable - Installed plumb and damage free
26533256-0be9-4d2a-ba5e-54da58ad173a | checkpoint | Balcony Outlet - Clear & Free of debris (photo)
99d711a0-fd34-43c4-93a4-ad35889160b1 | checkpoint | Gas Cooktop Installed - Secured & damage free (photo)
ea2610c2-0dfa-4ee8-85b0-e8a5e8b56d4f | checkpoint | Gas Flexi / Isolation Valve / Regulator / Loxeal used on all parallel threads / Gas tape on reg thread (photo)
0cf25e21-2667-4827-ae86-dd38f20dc392 | checkpoint | Purge & Commision cook top as per manufacturer's specifications and AS5601
d4672959-8752-4d11-9f8c-569e03caf474 | checkpoint | Bayonet points installed - Internal / External / Installed plumb & damage free
f4adc776-45dd-4bec-a4d8-7ff7805fc2b9 | section | Laundry
24269489-502f-490b-bbe8-7e4affed1733 | checkpoint | Tub/Sink Installed - Secure & damage free (photo)
47e97e60-a99b-4402-ae24-39a53ad738fb | checkpoint | Mixer Installed - Tested/ secured/ cross connection check/ aerator clear/ damage free, ( photo )
a27512c5-0213-48f5-94f9-ea8869c94a3a | checkpoint | Trap installed & tested, Tundish Installed & test
d3d54aaa-8154-44ae-a3b8-ac79a7c65d0a | checkpoint | AAV installed with allowance for servicing/replacement
dd8e0077-ebcd-46ea-8090-44754704323d | checkpoint | Washing Machine Installed
6dceface-b903-41ac-b5d6-12c1c76772df | checkpoint | WM QA - Cycle Run / Water Connection Ok/tight/secured / Waste Connection- Ok/tight/secured/drilled out
5badf3b7-af39-4d3f-bd41-72cb3b48d27c | checkpoint | Floor Waste - Clear & Free from debris (photo)
08fd59af-294c-4cb7-8d25-bda25b937e29 | section | Bathroom & Ensuite
1a1fc514-7cd9-46c0-bb83-0c73d8811296 | checkpoint | Floor Waste - Clear & Free from debris (photo)
fb7df01f-7bf1-4a57-ab00-ddde19d4f97d | checkpoint | WC Installed - / Silicone / Seat - Secure & damage free (photo)
c478b45b-6755-4bc9-8935-498deb772f6b | checkpoint | Flush Plate installed Plumb and damage free (photo)
faf298fe-8969-428b-8a52-b1b63d386f4b | checkpoint | WC Tested (minimum 10 flushes and inspect under pan for leaks)
a0442378-caec-4a2b-bcb2-c4eecbc7e86b | checkpoint | Basin Installed / Silicone - Secure & damage free (photo)
b6b781ab-ef11-40aa-9e5f-a5c40723c318 | checkpoint | Basin Mixer Installed - Tested/ secured/ cross connection check / aerator clear/ damage free, ( photo )
8ed770f8-8cc7-4761-b441-b97ac7fbb95f | checkpoint | Plug & Waste Installed / Trap installed & tested / Tundish Installed
9bafec94-8d0a-44cc-bf79-fd624f95b78f | checkpoint | Shower Installed - Mixer Trim Kit / Rail / Hand Shower & Hose /Rose/Rain Head
da710ad8-1f4e-400a-a98c-67854596c37e | checkpoint | Shower Set Installed - Tested/ secured/ cross connection check / aerator clear/ damage free, ( photo )
51df1880-3d57-410c-8f40-8d2982c0899c | checkpoint | Shower Waste - Clear & Free from debris (photo)
31cf2782-1bd4-49e7-99ba-2ee0b35cb833 | checkpoint | Bath Installed - Inset / Free Standing / Silicone - Secure & damage free (photo)
3a0528fe-bf31-47c0-a6f8-a78b5b805834 | checkpoint | Bath Mixer Installed - Wall / Floor / Tested/ secured/ cross connection check / aerator clear/ damage free, ( photo )
701dcb5f-6959-4bff-b055-61bc1f70f499 | checkpoint | Plug & Waste Installed / Trap installed & tested / Bath Filled & Leak Checked
1c7ab59e-d008-4cdb-aa22-39e6a365b524 | checkpoint | Photos Uploaded or saved to appropriate location
2b5f710e-33aa-4e6f-b068-fb62fa0919e3 | checkpoint | Works verified as conforming (McPherson Plumbing Representative)
9788a6b4-3c37-4940-8239-7eb0733042c5 | signoff | Work verified by Scente Group
40d7efe7-b927-4619-97d3-e26f7ae8a0af | checklist | Subcontractor ITP |  | Subcontractor ITP
30050530-0f9f-45e5-962b-b0b543264f49 | checkpoint | Attach subcontractor ITP