## Project Structure
Folder Structure
Site QA
FOREMAN NOTES
DELIVERIES
PROJECT
TENANCIES
T1-AS02
ROUGH-IN
[5 empty] | MSSB-T1-AS02 | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | FCU-T1-L1-AS-02.1 | WC FCU Rough In checklist
[5 empty] | FCU-T1-L1-AS-02.2 | WC FCU Rough In checklist
[5 empty] | OAF-T1-B-LM-01 | EC FAN Rough-in Checklist
FIT-OFF
[5 empty] | MSSB-T1-AS02 | Switchboard Fit-off
[5 empty] | BMS CUBICLE | BMS Cubicle Fit-off
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Fit-off
[5 empty] | FCU-T1-L1-AS-02.1 | WC FCU Fit off checklist
[5 empty] | FCU-T1-L1-AS-02.2 | WC FCU Fit off checklist
[5 empty] | OAF-T1-B-LM-01 | EC FAN Fit off Checklist
ENERGISATION
[5 empty] | MSSB-T1-AS02 | Switchboard Energisation
[5 empty] | FCU-T1-L1-AS-02.1 | Circuit Energisation from switchboard checklist
[5 empty] | FCU-T1-L1-AS-02.2 | Circuit Energisation from switchboard checklist
[5 empty] | OAF-T1-B-LM-01 | Circuit Energisation from switchboard checklist
COMMISSIONING
[5 empty] | MSSB-T1-AS02 | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
[5 empty] | FCU-T1-L1-AS-02.1 | WC FCU Commissioning checklist
[5 empty] | FCU-T1-L1-AS-02.2 | WC FCU Commissioning checklist
[5 empty] | OAF-T1-B-LM-01 | EC FAN Commissioning Checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | FCU-T1-L1-AS-02.1 | WC FCU BMS checklist
[5 empty] | FCU-T1-L1-AS-02.2 | WC FCU BMS checklist
[5 empty] | OAF-T1-B-LM-01 | EC FAN BMS Checklist
T1-AS03
ROUGH-IN
[5 empty] | MSSB-T1-AS03 | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | FCU-T1-L1-AS-03.1 | WC FCU Rough In checklist
[5 empty] | FCU-T1-L1-AS-03.2 | WC FCU Rough In checklist
[5 empty] | FCU-T1-L1-AS-03.3 | WC FCU Rough In checklist
[5 empty] | OAF-T1-LM-05 | EC FAN Rough-in Checklist
FIT-OFF
[5 empty] | MSSB-T1-AS03 | Switchboard Fit-off
[5 empty] | BMS CUBICLE | BMS Cubicle Fit-off
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Fit-off
[5 empty] | FCU-T1-L1-AS-03.1 | WC FCU Fit off checklist
[5 empty] | FCU-T1-L1-AS-03.2 | WC FCU Fit off checklist
[5 empty] | FCU-T1-L1-AS-03.3 | WC FCU Fit off checklist
[5 empty] | OAF-T1-LM-05 | EC FAN Fit off Checklist
ENERGISATION
[5 empty] | MSSB-T1-AS03 | Switchboard Energisation
[5 empty] | FCU-T1-L1-AS-03.1 | Circuit Energisation from switchboard checklist
[5 empty] | FCU-T1-L1-AS-03.2 | Circuit Energisation from switchboard checklist
[5 empty] | FCU-T1-L1-AS-03.3 | Circuit Energisation from switchboard checklist
[5 empty] | OAF-T1-LM-05 | Circuit Energisation from switchboard checklist
COMMISSIONING
[5 empty] | MSSB-T1-AS03 | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
[5 empty] | FCU-T1-L1-AS-03.1 | WC FCU Commissioning checklist
[5 empty] | FCU-T1-L1-AS-03.2 | WC FCU Commissioning checklist
[5 empty] | FCU-T1-L1-AS-03.3 | WC FCU Commissioning checklist
[5 empty] | OAF-T1-LM-05 | EC FAN Commissioning Checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | FCU-T1-L1-AS-03.1 | WC FCU BMS checklist
[5 empty] | FCU-T1-L1-AS-03.2 | WC FCU BMS checklist
[5 empty] | FCU-T1-L1-AS-03.3 | WC FCU BMS checklist
[5 empty] | OAF-T1-LM-05 | EC FAN BMS Checklist
T1-AS04
ROUGH-IN
[5 empty] | MSSB-T1-AS04 | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | FCU-T1-L1-AS-04 | WC FCU Rough In checklist
FIT-OFF
[5 empty] | MSSB-T1-AS04 | Switchboard Fit-off
[5 empty] | BMS CUBICLE | BMS Cubicle Fit-off
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Fit-off
[5 empty] | FCU-T1-L1-AS-04 | WC FCU Fit off checklist
ENERGISATION
[5 empty] | MSSB-T1-AS04 | Switchboard Energisation
[5 empty] | FCU-T1-L1-AS-04 | Circuit Energisation from switchboard checklist
COMMISSIONING
[5 empty] | MSSB-T1-AS04 | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
[5 empty] | FCU-T1-L1-AS-04 | WC FCU Commissioning checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | FCU-T1-L1-AS-04 | WC FCU BMS checklist
T1-AS05
ROUGH-IN
[5 empty] | MSSB-T1-AS05 | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | FCU-T1-L1-AS-05 | WC FCU Rough In checklist
FIT-OFF
[5 empty] | MSSB-T1-AS05 | Switchboard Fit-off
[5 empty] | BMS CUBICLE | BMS Cubicle Fit-off
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Fit-off
[5 empty] | FCU-T1-L1-AS-05 | WC FCU Fit off checklist
ENERGISATION
[5 empty] | MSSB-T1-AS05 | Switchboard Energisation
[5 empty] | FCU-T1-L1-AS-05 | Circuit Energisation from switchboard checklist
COMMISSIONING
[5 empty] | MSSB-T1-AS05 | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
[5 empty] | FCU-T1-L1-AS-04 | WC FCU Commissioning checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | FCU-T1-L1-AS-05 | WC FCU BMS checklist
T1-AS06
ROUGH-IN
[5 empty] | MSSB-T1-AS06 | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | FCU-T1-L1-AS-06.1 | WC FCU Rough In checklist
[5 empty] | FCU-T1-L1-AS-06.2 | WC FCU Rough In checklist
FIT-OFF
[5 empty] | MSSB-T1-AS06 | Switchboard Fit-off
[5 empty] | BMS CUBICLE | BMS Cubicle Fit-off
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Fit-off
[5 empty] | FCU-T1-L1-AS-06.1 | WC FCU Fit off checklist
[5 empty] | FCU-T1-L1-AS-06.2 | WC FCU Fit off checklist
ENERGISATION
[5 empty] | MSSB-T1-AS06 | Switchboard Energisation
[5 empty] | FCU-T1-L1-AS-06.1 | Circuit Energisation from switchboard checklist
[5 empty] | FCU-T1-L1-AS-06.2 | Circuit Energisation from switchboard checklist
COMMISSIONING
[5 empty] | MSSB-T1-AS06 | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
[5 empty] | FCU-T1-L1-AS-06.1 | WC FCU Commissioning checklist
[5 empty] | FCU-T1-L1-AS-06.2 | WC FCU Commissioning checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | FCU-T1-L1-AS-06.1 | WC FCU BMS checklist
[5 empty] | FCU-T1-L1-AS-06.2 | WC FCU BMS checklist
T1-AS07
ROUGH-IN
[5 empty] | MSSB-T1-AS07 | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | FCU-T1-L1-AS-07.1 | WC FCU Rough In checklist
[5 empty] | FCU-T1-L1-AS-07.2 | WC FCU Rough In checklist
[5 empty] | MAF-T1-L1-03 | VSD Kitchen FAN Rough-in Checklist
[5 empty] | KEF-T1-L1-03 | VSD Kitchen FAN Rough-in Checklist
FIT-OFF
[5 empty] | MSSB-T1-AS07 | Switchboard Fit-off
[5 empty] | BMS CUBICLE | BMS Cubicle Fit-off
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Fit-off
[5 empty] | FCU-T1-L1-AS-07.1 | WC FCU Fit off checklist
[5 empty] | FCU-T1-L1-AS-07.2 | WC FCU Fit off checklist
[5 empty] | MAF-T1-L1-03 | VSD Kitchen FAN Fit-off Checklist
[5 empty] | KEF-T1-L1-03 | VSD Kitchen FAN Fit-off Checklist
ENERGISATION
[5 empty] | MSSB-T1-AS07 | Switchboard Energisation
[5 empty] | FCU-T1-L1-AS-07.1 | Circuit Energisation from switchboard checklist
[5 empty] | FCU-T1-L1-AS-07.2 | Circuit Energisation from switchboard checklist
[5 empty] | MAF-T1-L1-03 | Circuit Energisation from switchboard checklist
[5 empty] | KEF-T1-L1-03 | Circuit Energisation from switchboard checklist
COMMISSIONING
[5 empty] | MSSB-T1-AS07 | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
[5 empty] | FCU-T1-L1-AS-07.1 | WC FCU Commissioning checklist
[5 empty] | FCU-T1-L1-AS-07.2 | WC FCU Commissioning checklist
[5 empty] | MAF-T1-L1-03 | VSD Kitchen FAN Commissioning Checklist
[5 empty] | KEF-T1-L1-03 | VSD Kitchen FAN Commissioning Checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | FCU-T1-L1-AS-07.1 | WC FCU BMS checklist
[5 empty] | FCU-T1-L1-AS-07.2 | WC FCU BMS checklist
[5 empty] | MAF-T1-L1-03 | VSD Kitchen FAN BMS Checklist
[5 empty] | KEF-T1-L1-03 | VSD Kitchen FAN BMS Checklist
T1-AS09
ROUGH-IN
[5 empty] | MSSB-T1-AS09 | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | FCU-T1-L1-AS-09.1 | WC FCU Rough In checklist
[5 empty] | FCU-T1-L1-AS-09.2 | WC FCU Rough In checklist
[5 empty] | MAF-T1-L1-02 | VSD Kitchen FAN Rough-in Checklist
[5 empty] | KEF-T1-L1-02 | VSD Kitchen FAN Rough-in Checklist
FIT-OFF
[5 empty] | MSSB-T1-AS09 | Switchboard Fit-off
[5 empty] | BMS CUBICLE | BMS Cubicle Fit-off
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Fit-off
[5 empty] | FCU-T1-L1-AS-09.1 | WC FCU Fit off checklist
[5 empty] | FCU-T1-L1-AS-09.2 | WC FCU Fit off checklist
[5 empty] | MAF-T1-L1-02 | VSD Kitchen FAN Fit-off Checklist
[5 empty] | KEF-T1-L1-02 | VSD Kitchen FAN Fit-off Checklist
ENERGISATION
[5 empty] | MSSB-T1-AS09 | Switchboard Energisation
[5 empty] | FCU-T1-L1-AS-09.1 | Circuit Energisation from switchboard checklist
[5 empty] | FCU-T1-L1-AS-09.2 | Circuit Energisation from switchboard checklist
[5 empty] | MAF-T1-L1-02 | Circuit Energisation from switchboard checklist
[5 empty] | KEF-T1-L1-02 | Circuit Energisation from switchboard checklist
COMMISSIONING
[5 empty] | MSSB-T1-AS09 | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
[5 empty] | FCU-T1-L1-AS-09.1 | WC FCU Commissioning checklist
[5 empty] | FCU-T1-L1-AS-09.2 | WC FCU Commissioning checklist
[5 empty] | MAF-T1-L1-02 | VSD Kitchen FAN Commissioning Checklist
[5 empty] | KEF-T1-L1-02 | VSD Kitchen FAN Commissioning Checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | FCU-T1-L1-AS-09.1 | WC FCU BMS checklist
[5 empty] | FCU-T1-L1-AS-09.2 | WC FCU BMS checklist
[5 empty] | MAF-T1-L1-02 | VSD Kitchen FAN BMS Checklist
[5 empty] | KEF-T1-L1-02 | VSD Kitchen FAN BMS Checklist
T1-AS10
ROUGH-IN
[5 empty] | MSSB-T1-AS10 | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | FCU-T1-L1-AS-10.1 | WC FCU Rough In checklist
[5 empty] | FCU-T1-L1-AS-10.2 | WC FCU Rough In checklist
FIT-OFF
[5 empty] | MSSB-T1-AS10 | Switchboard Fit-off
[5 empty] | BMS CUBICLE | BMS Cubicle Fit-off
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Fit-off
[5 empty] | FCU-T1-L1-AS-10.1 | WC FCU Fit off checklist
[5 empty] | FCU-T1-L1-AS-10.2 | WC FCU Fit off checklist
ENERGISATION
[5 empty] | MSSB-T1-AS10 | Switchboard Energisation
[5 empty] | FCU-T1-L1-AS-10.1 | Circuit Energisation from switchboard checklist
[5 empty] | FCU-T1-L1-AS-10.2 | Circuit Energisation from switchboard checklist
COMMISSIONING
[5 empty] | MSSB-T1-AS10 | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
[5 empty] | FCU-T1-L1-AS-10.1 | WC FCU Commissioning checklist
[5 empty] | FCU-T1-L1-AS-10.2 | WC FCU Commissioning checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | FCU-T1-L1-AS-10.1 | WC FCU BMS checklist
[5 empty] | FCU-T1-L1-AS-10.2 | WC FCU BMS checklist
T1-AS11
ROUGH-IN
[5 empty] | MSSB-T1-AS11 | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | FCU-T1-L1-AS-11.1 | WC FCU Rough In checklist
[5 empty] | FCU-T1-L1-AS-11.2 | WC FCU Rough In checklist
FIT-OFF
[5 empty] | MSSB-T1-AS11 | Switchboard Fit-off
[5 empty] | BMS CUBICLE | BMS Cubicle Fit-off
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Fit-off
[5 empty] | FCU-T1-L1-AS-11.1 | WC FCU Fit off checklist
[5 empty] | FCU-T1-L1-AS-11.2 | WC FCU Fit off checklist
ENERGISATION
[5 empty] | MSSB-T1-AS11 | Switchboard Energisation
[5 empty] | FCU-T1-L1-AS-11.1 | Circuit Energisation from switchboard checklist
[5 empty] | FCU-T1-L1-AS-11.2 | Circuit Energisation from switchboard checklist
COMMISSIONING
[5 empty] | MSSB-T1-AS11 | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
[5 empty] | FCU-T1-L1-AS-11.1 | WC FCU Commissioning checklist
[5 empty] | FCU-T1-L1-AS-11.2 | WC FCU Commissioning checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | FCU-T1-L1-AS-11.1 | WC FCU BMS checklist
[5 empty] | FCU-T1-L1-AS-11.2 | WC FCU BMS checklist
T1-AS12
ROUGH-IN
[5 empty] | MSSB-T1-AS12 | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | FCU-T1-L1-AS-12 | WC FCU Rough In checklist
FIT-OFF
[5 empty] | MSSB-T1-AS12 | Switchboard Fit-off
[5 empty] | BMS CUBICLE | BMS Cubicle Fit-off
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Fit-off
[5 empty] | FCU-T1-L1-AS-12 | WC FCU Fit off checklist
ENERGISATION
[5 empty] | MSSB-T1-AS12 | Switchboard Energisation
[5 empty] | FCU-T1-L1-AS-12 | Circuit Energisation from switchboard checklist
COMMISSIONING
[5 empty] | MSSB-T1-AS12 | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
[5 empty] | FCU-T1-L1-AS-12 | WC FCU Commissioning checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | FCU-T1-L1-AS-12 | WC FCU BMS checklist
T1-AS13
ROUGH-IN
[5 empty] | MSSB-T1-AS13 | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | FCU-T1-L1-AS-13.1 | WC FCU Rough In checklist
[5 empty] | FCU-T1-L1-AS-13.2 | WC FCU Rough In checklist
FIT-OFF
[5 empty] | MSSB-T1-AS13 | Switchboard Fit-off
[5 empty] | BMS CUBICLE | BMS Cubicle Fit-off
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Fit-off
[5 empty] | FCU-T1-L1-AS-13.1 | WC FCU Fit off checklist
[5 empty] | FCU-T1-L1-AS-13.2 | WC FCU Fit off checklist
ENERGISATION
[5 empty] | MSSB-T1-AS13 | Switchboard Energisation
[5 empty] | FCU-T1-L1-AS-13.1 | Circuit Energisation from switchboard checklist
[5 empty] | FCU-T1-L1-AS-13.2 | Circuit Energisation from switchboard checklist
COMMISSIONING
[5 empty] | MSSB-T1-AS13 | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
[5 empty] | FCU-T1-L1-AS-13.1 | WC FCU Commissioning checklist
[5 empty] | FCU-T1-L1-AS-13.2 | WC FCU Commissioning checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | FCU-T1-L1-AS-13.1 | WC FCU BMS checklist
[5 empty] | FCU-T1-L1-AS-13.2 | WC FCU BMS checklist
T1-AS14
ROUGH-IN
[5 empty] | MSSB-T1-AS14 | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | FCU-T1-L1-AS-14 | WC FCU Rough In checklist
FIT-OFF
[5 empty] | MSSB-T1-AS14 | Switchboard Fit-off
[5 empty] | BMS CUBICLE | BMS Cubicle Fit-off
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Fit-off
[5 empty] | FCU-T1-L1-AS-14 | WC FCU Fit off checklist
ENERGISATION
[5 empty] | MSSB-T1-AS14 | Switchboard Energisation
[5 empty] | FCU-T1-L1-AS-14 | Circuit Energisation from switchboard checklist
COMMISSIONING
[5 empty] | MSSB-T1-AS14 | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
[5 empty] | FCU-T1-L1-AS-14 | WC FCU Commissioning checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | FCU-T1-L1-AS-14 | WC FCU BMS checklist
T1-AS15
ROUGH-IN
[5 empty] | MSSB-T1-AS15 | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | FCU-T1-L1-AS-15.1 | WC FCU Rough In checklist
[5 empty] | FCU-T1-L1-AS-15.2 | WC FCU Rough In checklist
[5 empty] | FCU-T1-L1-AS-15.3 | WC FCU Rough In checklist
[5 empty] | MAF-T1-L1-01 | VSD Kitchen FAN Rough-in Checklist
[5 empty] | KEF-T1-L1-01 | VSD Kitchen FAN Rough-in Checklist
FIT-OFF
MSSB-T1-AS15
BMS CUBICLE
FIRE CONTROL PANEL
[5 empty] | FCU-T1-L1-AS-15.1 | WC FCU Fit off checklist
[5 empty] | FCU-T1-L1-AS-15.2 | WC FCU Fit off checklist
[5 empty] | FCU-T1-L1-AS-15.3 | WC FCU Fit off checklist
[5 empty] | MAF-T1-L1-01 | VSD Kitchen FAN Fit-off Checklist
[5 empty] | KEF-T1-L1-01 | VSD Kitchen FAN Fit-off Checklist
ENERGISATION
[5 empty] | MSSB-T1-AS15 | Switchboard Energisation | add checklists
[5 empty] | FCU-T1-L1-AS-15.1 | Circuit Energisation from switchboard checklist | add checklists
[5 empty] | FCU-T1-L1-AS-15.2 | Circuit Energisation from switchboard checklist | add checklists
[5 empty] | FCU-T1-L1-AS-15.3 | Circuit Energisation from switchboard checklist | add checklists
[5 empty] | MAF-T1-L1-01 | Circuit Energisation from switchboard checklist | add checklists
[5 empty] | KEF-T1-L1-01 | Circuit Energisation from switchboard checklist | add checklists
COMMISSIONING
[5 empty] | MSSB-T1-AS15 | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
[5 empty] | FCU-T1-L1-AS-15.1 | WC FCU Commissioning checklist
[5 empty] | FCU-T1-L1-AS-15.2 | WC FCU Commissioning checklist
[5 empty] | FCU-T1-L1-AS-15.3 | WC FCU Commissioning checklist
[5 empty] | MAF-T1-L1-01 | VSD Kitchen FAN Commissioning Checklist
[5 empty] | KEF-T1-L1-01 | VSD Kitchen FAN Commissioning Checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | FCU-T1-L1-AS-15.1 | WC FCU BMS checklist
[5 empty] | FCU-T1-L1-AS-15.2 | WC FCU BMS checklist
[5 empty] | FCU-T1-L1-AS-15.3 | WC FCU BMS checklist
[5 empty] | MAF-T1-L1-01 | VSD Kitchen FAN BMS Checklist
[5 empty] | KEF-T1-L1-01 | VSD Kitchen FAN BMS Checklist
PUBLIC
T1 MSSB-NORTH
ROUGH-IN
[5 empty] | MSSB-T1-NORTH | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | OAF-T1-L1-03 | VSD FAN Rough-in Checklist
[5 empty] | EAF-T1-R-01 | VSD FAN Rough-in Checklist
[5 empty] | EAF-T1-LM-02 | EC FAN Rough-in Checklist
[5 empty] | EAF-T1-LM-03 | EC FAN Rough-in Checklist
[5 empty] | OAF-T1-LM-05 | EC FAN Rough-in Checklist
[5 empty] | EAF-T1-LM-05 | DOL FAN Rough-in Checklist
[5 empty] | ACU-T1-LM-01 | WC FCU Rough In checklist
[5 empty] | ACU-T1-LM-02 | SPLIT AC Rough-In Checklist
FIT-OFF
[5 empty] | MSSB-T1-NORTH | Switchboard Fit-off
[5 empty] | BMS CUBICLE | BMS Cubicle Fit-off
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Fit-off
[5 empty] | OAF-T1-L1-03 | VSD FAN Fit off Checklist
[5 empty] | EAF-T1-R-01 | VSD FAN Fit off Checklist
[5 empty] | EAF-T1-LM-02 | EC FAN Fit off Checklist
[5 empty] | EAF-T1-LM-03 | EC FAN Fit off Checklist
[5 empty] | OAF-T1-LM-05 | EC FAN Fit off Checklist
[5 empty] | EAF-T1-LM-05 | DOL FAN Fit-off Checklist
[5 empty] | ACU-T1-LM-01 | WC FCU Fit off checklist
[5 empty] | ACU-T1-LM-02 | SPLIT AC Fit-off Checklist
ENERGISATION
[5 empty] | MSSB-T1-NORTH | Switchboard Energisation
[5 empty] | OAF-T1-L1-03 | Circuit Energisation from switchboard checklist
[5 empty] | EAF-T1-R-01 | Circuit Energisation from switchboard checklist
[5 empty] | EAF-T1-LM-02 | Circuit Energisation from switchboard checklist
[5 empty] | EAF-T1-LM-03 | Circuit Energisation from switchboard checklist
[5 empty] | OAF-T1-LM-05 | Circuit Energisation from switchboard checklist
[5 empty] | EAF-T1-LM-05 | Circuit Energisation from switchboard checklist
[5 empty] | ACU-T1-LM-01 | Circuit Energisation from switchboard checklist
[5 empty] | ACU-T1-LM-02 | Circuit Energisation from switchboard checklist
COMMISSIONING
[5 empty] | MSSB-T1-AS03 | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
[5 empty] | OAF-T1-L1-03 | VSD FAN Commissioning Checklist
[5 empty] | EAF-T1-R-01 | VSD FAN Commissioning Checklist
[5 empty] | EAF-T1-LM-02 | EC FAN Commissioning Checklist
[5 empty] | EAF-T1-LM-03 | EC FAN Commissioning Checklist
[5 empty] | OAF-T1-LM-05 | EC FAN Commissioning Checklist
[5 empty] | EAF-T1-LM-05 | DOL FAN Commissioning Checklist
[5 empty] | ACU-T1-LM-01 | WC FCU Commissioning checklist
[5 empty] | ACU-T1-LM-02 | SPLIT AC BMS Checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | OAF-T1-L1-03 | FAN BMS Checklist
[5 empty] | EAF-T1-R-01 | FAN BMS Checklist
[5 empty] | EAF-T1-LM-02 | EC FAN BMS Checklist
[5 empty] | EAF-T1-LM-03 | EC FAN BMS Checklist
[5 empty] | OAF-T1-LM-05 | EC FAN BMS Checklist
[5 empty] | EAF-T1-LM-05 | FAN BMS Checklist
[5 empty] | ACU-T1-LM-01 | WC FCU BMS checklist
[5 empty] | ACU-T1-LM-02 | SPLIT AC BMS Checklist
T1 MSSB-SOUTH
ROUGH-IN
[5 empty] | MSSB-T1-SOUTH | Switchboard Installation
[5 empty] | BMS CUBICLE | BMS Cubicle Installation
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Installation
[5 empty] | OAF-T1-L1-01 | VSD FAN Rough-in Checklist
[5 empty] | OAF-T1-L1-02 | VSD FAN Rough-in Checklist
[5 empty] | EAF-T1-LM-01 | DOL FAN Rough-in Checklist
[5 empty] | EAF-T1-LM-04 | EC FAN Rough-in Checklist
FIT-OFF
[5 empty] | MSSB-T1-SOUTH | Switchboard Fit-off
[5 empty] | BMS CUBICLE | BMS Cubicle Fit-off
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Fit-off
[5 empty] | OAF-T1-L1-01 | VSD FAN Fit off Checklist
[5 empty] | OAF-T1-L1-02 | VSD FAN Fit off Checklist
[5 empty] | EAF-T1-LM-01 | DOL FAN Fit-off Checklist
[5 empty] | EAF-T1-LM-04 | EC FAN Fit off Checklist
ENERGISATION
[5 empty] | MSSB-T1-SOUTH | Switchboard Energisation
[5 empty] | OAF-T1-L1-01 | Circuit Energisation from switchboard checklist
[5 empty] | OAF-T1-L1-02 | Circuit Energisation from switchboard checklist
[5 empty] | EAF-T1-LM-01 | Circuit Energisation from switchboard checklist
[5 empty] | EAF-T1-LM-04 | Circuit Energisation from switchboard checklist
COMMISSIONING
[5 empty] | MSSB-SOUTH | Switchboard Commissioning
[5 empty] | BMS CUBICLE | BMS Cubicle Commissioning
[5 empty] | FIRE CONTROL PANEL | Fire Control Panel Commissioning
VSD FAN Commissioning Checklist
VSD FAN Commissioning Checklist
EC FAN Commissioning Checklist
DOL FAN Commissioning Checklist
BMS
[5 empty] | POWER METER | Power Meter BMS Checklist
[5 empty] | FIRE SIGNAL | Fire Signal BMS Checklist
[5 empty] | OAF-T1-L1-01 | FAN BMS Checklist
[5 empty] | OAF-T1-L1-02 | FAN BMS Checklist
[5 empty] | EAF-T1-LM-01 | EC FAN BMS Checklist
[5 empty] | EAF-T1-LM-04 | FAN BMS Checklist
T1-DB-NORTH
[5 empty] | INSTALLATION | Switchboard Installation
[5 empty] | FITOFF | Switchboard Fit-off
[5 empty] | ENERGISATION | Switchboard Energisation
[5 empty] | COMMISSIONING | Switchboard Commissioning
T1-DB-SOUTH
[5 empty] | INSTALLATION | Switchboard Installation
[5 empty] | FITOFF | Switchboard Fit-off
[5 empty] | ENERGISATION | Switchboard Energisation
[5 empty] | COMMISSIONING | Switchboard Commissioning

## Switchboard ITP
type | name | values | type | name | values
Checklist | Switchboard Installation |  | Checklist | Switchboard Fit-off
checkpoint | Wall Avaliable for Mounting Switchboard |  | checkpoint | All field cabling terminated
checkpoint | Switchboard Installed on Wall |  | checkpoint | Fire Signal supplied by others and terminated
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | Sub-mains supplied by others and terminated
|  |  | checkpoint | BMS cables installed and terminated
|  |  | checkpoint | All Field Tests completed
|  |  | checkpoint | Ready for Energisation
type | name | values
Checklist | Switchboard Energisation |  | type | name | values
checkpoint | All field cabling terminated |  | Checklist | Switchboard Commissioning
checkpoint | All field tests completed |  | checkpoint | All circuits operational
checkpoint | Power provided at Main Switch and tested |  | checkpoint | Power meter tested
|  |  | checkpoint | Fire Trip Tested
type | name | values
Checklist | BMS Cubicle Installation |  | type | name | values
checkpoint | Wall Avaliable for Mounting Switchboard |  | Checklist | BMS Cubicle Fit-off
checkpoint | Cubicle Installed on Wall |  | checkpoint | All BMS cabling terminated
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | Network cabling terminated
|  |  | checkpoint | Ready for power
type | name | values
Checklist | BMS Cubicle Commissioning
checkpoint | BMS Cubicle powered up
checkpoint | All Cards Online
checkpoint | All labels, drawings etc installed
checkpoint | BMS Cubicle cleaned out and ready for Handover
type | name | values
Checklist | Fire Control Panel Installation |  | type | name | values
checkpoint | Wall Avaliable for Mounting Switchboard |  | Checklist | Fire Control Panel Fit-off
checkpoint | Cubicle Installed on Wall |  | checkpoint | All interconnecting cabling to MSSB installed and terminated
checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | Fire cabling by others installed and terminated
type | name | values
Checklist | Fire Control Panel Commissioning
checkpoint | All fire relays and points test with fire contractor
checkpoint | All labels, drawings etc installed
checkpoint | Fire Control Panel cleaned out and ready for Handover

## Rough-in ITP
type | name | values
Checklist | VSD FAN Rough-in Checklist
checkpoint | Fan Installed
checkpoint | Power cabling roughed in
checkpoint | BMS cabling roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | SPLIT AC Rough-In Checklist
checkpoint | Outdoor unit installed
checkpoint | Indoor unit installed
checkpoint | Power supply to condensing unit roughed in
checkpoint | Power supply to indoor unit roughed in
checkpoint | Interconnecting cabling installed
checkpoint | Local thermostat roughed in
checkpoint | Transmission cabling rough-in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | DOL FAN Rough-in Checklist
checkpoint | Fan Installed
checkpoint | Power cabling roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | SEF VSD FAN Rough-in Checklist
checkpoint | Fan Installed
checkpoint | Fire Rated Supply roughed-in
checkpoint | Fire Rated Control cable roughed-in
checkpoint | Stainless Steel cable ties installed
checkpoint | Cables through roof
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | VSD Kitchen FAN Rough-in Checklist
checkpoint | Fan Installed
checkpoint | Power cabling roughed in
checkpoint | BMS cabling roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | Package Unit Rough-In Checklist
checkpoint | Area ready & accessible
checkpoint | Package Unit Installed
checkpoint | Power supply roughed in
checkpoint | LL Control cabling installed
checkpoint | Local thermostat roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | WC FCU Rough In checklist
checkpoint | Area ready & accessible
checkpoint | WC FCU installed
checkpoint | Power supply roughed-in
checkpoint | BMS cabling roughed-in
checkpoint | Thermostat roughed-in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | EC FAN Rough-in Checklist
checkpoint | Fan Installed
checkpoint | Power cabling roughed in
checkpoint | BMS cabling roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
DOL FAN Fit-off Checklist
checkpoint | Fan Installed
checkpoint | Power cabling roughed in
checkpoint | Ensure all rubbish and materials have been picked up and room is clean

## Fitoff ITP
type | name | values
Checklist | VSD FAN Fit off Checklist
checkpoint | VSD installed
checkpoint | Power supply terminated
checkpoint | EMC cable fit off
checkpoint | Control cable fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | SPLIT AC Fit-off Checklist
checkpoint | Outdoor unit installed
checkpoint | Power supply to condensing unit Fit off
checkpoint | Power supply to indoor unit Fit off
checkpoint | Interconnecting/transmission cabling Fit off
checkpoint | Local thermostat Fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | DOL FAN Fit-off Checklist
checkpoint | Power supply and isolator fit-off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | SEF VSD FAN Fitoff Checklist
checkpoint | VSD installed
checkpoint | Power supply terminated
checkpoint | EMC cable fit off
checkpoint | Control cable fit off
checkpoint | Ready for energisation
checkpoint | Conduit, decktites installed, penetration watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | VSD Kitchen FAN Fit-off Checklist
checkpoint | VSD installed
checkpoint | Power supply terminated
checkpoint | EMC cable fit off
checkpoint | BMS cable fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | Package Unit Fit-off Checklist
checkpoint | Power Supply Terminated
checkpoint | Low-level controls terminated
checkpoint | BMS points installed and fit-off
checkpoint | Ecomony Dampers wired and installed
checkpoint | Local thermostat fit-off
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | WC FCU Fit off checklist
checkpoint | Power supply and isoaltor fitoff
checkpoint | BMS points fit-off
checkpoint | Space temp fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | EC FAN Fit off Checklist
checkpoint | Power supply terminated
checkpoint | Control cable fit off
checkpoint | Ready for energisation
checkpoint | Ensure all rubbish and materials have been picked up and area is clean

## Energisation ITP
type | name | values
checklist | Circuit Energisation from switchboard checklist |  | Circuit Energisation from switchboard checklist
checkpoint | Power cable installed in switchboard |  | Circuit Energisation from Isolator checklist
checkpoint | Power cable tests completed
checkpoint | Circuit breaker installed
checkpoint | Power cable terminated at switchboard
checkpoint | Power cable terminated at Equipment
checkpoint | Circuit energised
checkpoint | Voltage Tested at equipment
type | name | values
checklist | Circuit Energisation from Isolator checklist
checkpoint | Isolator installed in correct position
checkpoint | Power cable terminated by others
checkpoint | Power cable terminated at Equipment
checkpoint | Circuit energised by others
checkpoint | Voltage Tested at equipment

## Commissioning ITP
type | name | values
Checklist | VSD FAN Commissioning Checklist
checkpoint | VSD parameters set
checkpoint | Rotation
checkpoint | AMP Draw
checkpoint | Correct operation
checkpoint | All Labels installed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | SPLIT AC Commissioning Checklist
checkpoint | Hard-wired controller working
checkpoint | Heating tested
checkpoint | Cooling tested
checkpoint | AMP draw
checkpoint | All Labels installed
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | DOL FAN Commissioning Checklist
checkpoint | Rotation
checkpoint | AMP Draw
checkpoint | Correct operation
checkpoint | All Labels installed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | SEF VSD FAN Commissioning Checklist
checkpoint | VSD parameters set
checkpoint | Rotation
checkpoint | AMP Draw
checkpoint | Correct operation from MSSB
checkpoint | Fire labels and Poadlock installed
checkpoint | FIRE TEST with fire contractor
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | VSD Kitchen FAN Commissioning Checklist
checkpoint | VSD parameters set
checkpoint | Rotation
checkpoint | AMP Draw
checkpoint | Correct operation
checkpoint | All Labels installed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | Package Unit Commissioning Checklist
checkpoint | SAF Running
checkpoint | Stage 1 tested
checkpoint | Stage 2 tested
checkpoint | Stage 3 tested
checkpoint | Rev valve tested
checkpoint | AMP draw
checkpoint | economy dampers tested
checkpoint | MSSB run/fault enable tested
checkpoint | All labels installed
checkpoint | Ensure all rubbish and materials have been picked up and room is clean
type | name | values
Checklist | WC FCU Commissioning checklist
checkpoint | Power supply and isoaltor fitoff
checkpoint | 0-10V tested up/down
checkpoint | Rotation
checkpoint | AMP Draw
checkpoint | Correct Operation
checkpoint | All labels installed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | EC FAN Commissioning Checklist
checkpoint | Rotation
checkpoint | AMP Draw
checkpoint | Correct operation
checkpoint | All Labels installed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean

## BMS ITP
type | name | values
Checklist | FAN BMS Checklist
checkpoint | Start/Stop
checkpoint | Fan Status
checkpoint | Fan Fault
type | name | values
Checklist | SPLIT AC BMS Checklist
checkpoint | AC unit on HLI
type | name | values
Checklist | SEF VSD FAN BMS Checklist
checkpoint | Fan Status
type | name | values
Checklist | Fire Signal BMS Checklist
checkpoint | ZFA Status
type | name | values
Checklist | Power Meter BMS Checklist
checkpoint | Power meter Online
type | name | values
Checklist | VSD Kitchen FAN BMS Checklist
checkpoint | Fan Start / Stop Enable
checkpoint | Fan Run Status (VSD)
checkpoint | Fan Status DP Switch
checkpoint | Filter Interlock
type | name | values
Checklist | Package Unit BMS Checklist
checkpoint | Supply fan start / stop
checkpoint | Fan status
checkpoint | Fault fault
checkpoint | Zone temperature
checkpoint | Heat / cool reversing valve
checkpoint | Stage 1 enable
checkpoint | Stage 2 enable
checkpoint | Supply air temperature
checkpoint | 0-10v fan speed
checkpoint | 0-10v compressor speed
type | name | values
Checklist | WC FCU BMS checklist
checkpoint | Zone Temperature Sensor(s)
checkpoint | Supply Air Temperature Sensor
checkpoint | Return Air Temperature Sensor
checkpoint | Mixed Air Temperature Sensor
checkpoint | Return Air CO2 Sensor
checkpoint | Filter Differential Pressure Sensor
checkpoint | CHW Valve
checkpoint | HHW Valve
checkpoint | Minimum Outside Air Damper
checkpoint | Fan Status DP Switch
checkpoint | Fan Fault Signal (VSD)
checkpoint | Fan Speed Control Signal (VSD)
checkpoint | Second Filter DP Switch
type | name | values
Checklist | EC FAN BMS Checklist
checkpoint | Start/Stop
checkpoint | Fan speed
checkpoint | Fan Status

## ITP Master
[6 empty] | type | name | values | type | name | values
type | name | values | type | name | values | checklist | Central Controller Fit off checklist |  | checklist | Circuit Energisation from switchboard checklist
Checklist | Switchboard Installation |  | checklist | Central Controller Rough In checklist |  | checkpoint | All transmission cabling and interfcae cards installed and fitoff |  | checkpoint | Power cable installed in switchboard
checkpoint | Wall Avaliable for Mounting Switchboard |  | checkpoint | All transmission cabling installed |  | checkpoint | Central controller controller Fit off to correct wall position |  | checkpoint | Power cable tests completed
checkpoint | Switchboard Installed on Wall |  | checkpoint | Central controller cable roughed in to correct wall position |  |  |  |  | checkpoint | Circuit breaker installed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean | [7 empty] | checkpoint | Power cable terminated at switchboard
|  |  | type | name | values | type | name | values | checkpoint | Power cable terminated at Equipment
|  |  | checklist | Cable Tray Install Checklist |  | Checklist | VSD FAN PBO Fit off Checklist |  | checkpoint | Circuit energised
|  |  | checkpoint | Cable Tray Installed |  | checkpoint | VSD installed |  | checkpoint | Voltage Tested at equipment
|  |  | checkpoint | Cable Lid Installed |  | checkpoint | Power supply terminated
[6 empty] | checkpoint | EMC cable fit off |  | type | name | values
|  |  | type | name | values | checkpoint | Control cable fit off |  | checklist | Circuit Energisation from Isolator checklist
|  |  | Checklist | VSD FAN PBO Rough-in Checklist |  | checkpoint | Ready for energisation |  | checkpoint | Isolator installed in correct position
|  |  | checkpoint | Fan Installed |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | Power cable terminated by others
|  |  | checkpoint | Isolator installed by others |  |  |  |  | checkpoint | Power cable terminated at Equipment
|  |  | checkpoint | BMS cabling roughed in |  | type | name | values | checkpoint | Circuit energised by others
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | Checklist | EC FAN Fit off Checklist |  | checkpoint | Voltage Tested at equipment
[6 empty] | checkpoint | Power supply terminated
|  |  | type | name | values | checkpoint | Control cable fit off
|  |  |  | VRF Condensing unit PBO Rough In Checklist |  | checkpoint | Ready for energisation
|  |  | checkpoint | Condensing unit installed |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
|  |  | checkpoint | Isolator installed by others
|  |  | checkpoint | Transmission cabling Roughed In |  |  | VRF Condensing unit PBO Fit off Checklist
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | Condensing unit installed
[6 empty] | checkpoint | Isolator and power supply installed by others
|  |  | type | name | values | checkpoint | Power supply fit off
|  |  | Checklist | VRF FCU PBO Rough-in Checklist |  | checkpoint | Transmission cabling Fit off
|  |  | checkpoint | VRF Indoor Installed |  | checkpoint | Ready for energisation
|  |  | checkpoint | Isolator installed by others |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
|  |  | checkpoint | Transmission cabling Roughed In
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean |  | type | name | values
[6 empty] | Checklist | VRF FCU PBO Fit off Checklist
|  |  | type | name | values | checkpoint | VRF Indoor unit installed
|  |  | Checklist | VSD FAN Rough-in Checklist |  | checkpoint | Isolator and power supply installed by others
|  |  | checkpoint | Fan Installed |  | checkpoint | Power supply fit off
|  |  | checkpoint | Power cabling roughed in |  | checkpoint | Transmission cabling Fit off
|  |  | checkpoint | BMS cabling roughed in |  | checkpoint | Interface card installed
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean |  | checkpoint | OA Damper installed and wired
[6 empty] | checkpoint | Ready for energisation
|  |  | type | name | values | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
|  |  | Checklist | EC FAN Rough-in Checklist
|  |  | checkpoint | Fan Installed |  | type | name | values
|  |  | checkpoint | Power cabling roughed in |  | Checklist | VSD FAN Fit off Checklist
|  |  | checkpoint | BMS cabling roughed in |  | checkpoint | VSD installed
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean |  | checkpoint | Power supply terminated
[6 empty] | checkpoint | EMC cable fit off
|  |  | type | name | values | checkpoint | Control cable fit off
|  |  | Checklist | WC FCU Rough In checklist |  | checkpoint | Ready for energisation
|  |  | checkpoint | Area ready & accessible |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
|  |  | checkpoint | WC FCU installed
|  |  | checkpoint | Power supply roughed in |  | type | name | values
|  |  | checkpoint | BMS cabling roughed in |  | Checklist | WC FCU Fit off checklist
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean |  | checkpoint | FCU Indoor unit installed
[6 empty] | checkpoint | Power supply fit off
[6 empty] | checkpoint | BMS cabling fit off
|  |  | type | name | values | checkpoint | Ready for energisation
|  |  | Checklist | Remote sensor Rough In checklist |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
|  |  | checkpoint | Wall installed
|  |  | checkpoint | Remote sensor cable roughed in
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean |  | type | name | values
[6 empty] | Checklist | Remote sensor Fit off checklist
|  |  | type | name | values | checkpoint | Wall plastered/painted
|  |  | Checklist | BMS Zone Sensor/AHPB Rough-in Checklist |  | checkpoint | Remote sensor cable Fit off on wall
|  |  | checkpoint | Wall installed |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
|  |  | checkpoint | 3 pair cable roughed in
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean |  | type | name | values
[6 empty] | Checklist | BMS Zone Sensor/AHPB Fit off Checklist
|  |  | type | name | values | checkpoint | Wall plastered/painted
|  |  | Checklist | Remote Sensor/AHPB Rough-in Checklist |  | checkpoint | Zone sensor/AHPB fit off on wall
|  |  | checkpoint | Wall installed |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
|  |  | checkpoint | Remote sensor and 2 pair cable roughed in
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean |  | type | name | values
[6 empty] | Checklist | Remote Sensor/AHPB Fit off Checklist
|  |  | type | name | values | checkpoint | Wall plastered/painted
|  |  | Checklist | BMS Zone Sensor Rough In checklist |  | checkpoint | Remote sensor/AHPB fit off on wall
|  |  | checkpoint | Wall installed |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
|  |  | checkpoint | 1 pair cable roughed in
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean |  | type | name | values
[6 empty] | Checklist | BMS Zone Sensor Fit off checklist
|  |  | type | name | values | checkpoint | Wall plastered/painted
|  |  | Checklist | SPLIT AC Rough-In Checklist |  | checkpoint | Zone sensor fit off on wall
|  |  | checkpoint | Area ready & accessible |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
|  |  | checkpoint | Outdoor unit installed
|  |  | checkpoint | Power supply to condensing unit roughed in |  | type | name | values
|  |  | checkpoint | Interconnecting cabling installed |  | Checklist | SPLIT AC Fit off Checklist
|  |  | checkpoint | Local thermostat roughed in |  | checkpoint | Outdoor unit installed
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean |  | checkpoint | Power supply to condensing unit Fit off
[6 empty] | checkpoint | Interconnecting cabling Fit off
|  |  | type | name | values | checkpoint | Local thermostat Fit off
|  |  | Checklist | AHPB Rough in Checklist |  | checkpoint | Ready for energisation
|  |  | checkpoint | Wall installed |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
|  |  | checkpoint | 2 pair cable roughed in
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean |  | type | name | values
[6 empty] | Checklist | AHPB Fit off Checklist
|  |  | type | name | values | checkpoint | Wall plastered/painted
|  |  | Checklist | DOL FAN PBO Rough-in Checklist |  | checkpoint | AHPBand Neon plate fit off on wall
|  |  | checkpoint | Fan Installed |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
|  |  | checkpoint | Isolator installed by others
|  |  | checkpoint | Local switch roughed in |  | Checklist | DOL FAN PBO Fit-off Checklist
|  |  | checkpoint | Cables through roof |  | checkpoint | Fan Fitoff
|  |  | checkpoint | Conduit, decktites installed, penetration watersealed |  | checkpoint | Local switch fitoff
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | Conduit, decktites installed, penetration watersealed
[6 empty] | checkpoint | Ready for energisation
|  |  | type | name | values | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
|  |  | Checklist | SEF VSD FAN Rough-in Checklist
|  |  | checkpoint | Fan Installed |  | type | name | values
|  |  | checkpoint | Fire Rated Supply rouged-in |  | Checklist | SEF VSD FAN Fitoff Checklist
|  |  | checkpoint | Fire Rated Control cable roughed-in |  | checkpoint | VSD installed
|  |  | checkpoint | Stainless Steel cable ties installed |  | checkpoint | Power supply terminated
|  |  | checkpoint | Cables through roof |  | checkpoint | EMC cable fit off
|  |  | checkpoint | Conduit, decktites installed, penetration watersealed |  | checkpoint | Control cable fit off
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean |  | checkpoint | Ready for energisation
[6 empty] | checkpoint | Conduit, decktites installed, penetration watersealed
|  |  | type | name | values | checkpoint | Ensure all rubbish and materials have been picked up and area is clean
|  |  | Checklist | Switchboard Installation
|  |  | checkpoint | Wall Avaliable for Mounting Switchboard
|  |  | checkpoint | Switchboard Installed on Wall
|  |  | checkpoint | Ensure all rubbish and materials have been picked up and area is clean