## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-017 - Basin Construction | itp |  |  |  |  | FHC-ITP-017 - Basin Construction
section | 1 - Preliminary Works
checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
note | FREQUENCY: Prior to commencing
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to Placement
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.4 Excavation Permit
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
note | • Plant and equipment shall be appropriate for the task.
note | • Excavation operations shall not disturb areas outside the limit of excavation
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Excavation permit
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Survey set-out
note | FREQUENCY: Prior to Commencing Excavation
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements.
note | • The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity.
note | • IFC and latest available revision used
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Site Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Survey records & pegs on the ground
note | – – – – – – – – –
note | SCP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Surveyor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.2 In situ Material
note | FREQUENCY: Initial
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: In situ material ripped and re-compacted to provide a smooth, stable working surface.
note | • Material to be free of debris, roots, sticks and sharp rocks/ boulders larger than 50mm
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-10-TNT-CRG-0013
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.3 Bentofix GCL Installation
note | FREQUENCY: Prior to placement of Type A
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Geotextile clay liner (GCL) shall be installed in accordancewith the manufacturer's requirements
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-10-TNT-CRG-0013 NSP4900
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.4 Type A Placement
note | FREQUENCY: Once GCL has been installed
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: A minimum 300mm thick Type A fill layer shall be placed over the Bentofix GCL that has been installed
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-10-TNT-CRG-0013
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.5 Base Construction
note | FREQUENCY: Once Type A fill layer has been installed
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Provide a compacted 400mm thick hard base.
note | • Approximately 50% 300mm size.
note | • The remaining 50% made up of 0-100mm graded rock, premixed with 300 dia rocks and spread and tracked so as to form a compated base.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Project Spec. MRP-708-C-AUR-DRG-10-TNT-CRG-0013
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: