## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 71528d6d-487b-4c3d-8c38-95e2f5354310 |  | checklist | QA - First Fix |  |  |  |  | Yes | QA - First Fix | 122895a3-77c4-44d5-9ff2-d8a08a5a3932
checkpoint-status | 529af275-4777-43eb-8ccc-c55aab28c1a4 |  | checkpoint | Area & substrate acceptable
checkpoint-status | 410eb875-7b55-4d9c-bf6d-825ce11d29ed |  | checkpoint | Pvc waste installed
checkpoint-status | ba34e552-57a9-42e3-a744-535f4169c4a5 |  | checkpoint | Pvc flood test
checkpoint-status | e44c5a76-5e25-4415-97d6-519c45c5be46 |  | checkpoint | Pvc sound lagged
checkpoint-status | f3a3eb9f-7c70-45ee-bbc0-749356b1759f |  | checkpoint | Shower installed
checkpoint-status | e5376e86-e882-43c0-9c51-d58b22a7ef53 |  | checkpoint | Heating system piping installed
checkpoint-status | 9ca91431-3176-4aed-8d85-aff1191e4d9d |  | checkpoint | Basin feeds in correct location
checkpoint-status | 7285814f-0bfe-47e3-819d-b002e4f9e149 |  | checkpoint | Inspection opening - plug removed and cap returned to place
checkpoint-status | 145f34f1-c441-4d6b-8c81-434c17452e95 |  | checkpoint | Toilet feed in correct location
checkpoint-status | c37e8b86-e609-47f2-bae0-9bd465e47c0e |  | checkpoint | Feeds tested to 1500 Kpa
checkpoint-status | 58046566-48b6-4fae-aa22-985d5fd3f5a4 |  | checkpoint | Fire wraps sealed at floor level
checkpoint-status | 23c978ed-67df-4d78-92f3-25f140a69df2 |  | checkpoint | Penetrations logged in register
checkpoint-status | 52ca2589-e047-41b2-afd7-378bcc43e620 |  | checkpoint | Rubbish removed
checkpoint-status | 13aeeb3c-4d35-43db-ab68-c72292a0c349 |  | checkpoint | Pipe securely clipped
checkpoint-status | 28629cc6-2011-447d-a667-69b91482a6ae |  | checkpoint | Shower tray protective box installed
checkpoint-status | 8831db16-f91a-4efb-a001-d17511b088f1 |  | checkpoint | Council inspection passed and attached
checkpoint-status | 680d7e87-2f1e-40f3-a547-53d0f0189065 |  | checkpoint | Area is left clean and tidy (attach photo)
checkpoint-status | 1cba5810-d1e8-4ad8-b444-d1c9c572399f |  | checkpoint | First Fix completed reviewed and approved
checklist-sectioned | 3179eefa-9802-4a95-afe0-2a8da41fa658 |  | checklist | Basement Underslab |  |  |  |  | Yes | QA - Basement Underslab | 32ea0ea8-e26a-4991-8c3b-d65265e0a614
checkpoint-group | f7de560d-518c-43b8-a873-788559153d57 |  | section | Area Prestart / Acceptance & Drawings
checkpoint-status | 4791534c-b414-4ef4-b5a7-ee5cb72c00b3 |  | checkpoint | Area ready for works (grids setout, area accessible and approval to start)
text | a0a4b47e-71b8-5661-a3d8-8cc9a83b2764 |  | textbox | Zone / Area
checkpoint-status | b8826527-babb-4785-b562-68b1e8f0712c |  | checkpoint | Current Dimensioned Slab Set Out Drawings numbers and revisions recorded
checkpoint-group | 0bc7423e-e1a8-431b-bf8b-26deb9217f17 |  | section | Under Slab Pipe install
checkpoint-status | a55b45fd-b90e-476f-aa9a-5418269fd95d |  | checkpoint | Correct pipe laid to specified level and grade (all joints sealed correctly as specified)
text | 4b444d90-e2a1-5ec2-bd5b-cb1ee66481a2 |  | textbox | Start Invert
text | 923d3447-d4c3-5c48-a778-9e23f757f8e1 |  | textbox | Finish Invert
text | b82a1c9e-96ba-5cb8-8acd-db7b499221c6 |  | textbox | Grade of Pre-Line %
text | 991dcb84-2e2d-5fbf-bb07-b0b24e2721b6 |  | textbox | Product Type
checkpoint-status | 7e1691f0-7ae1-4b1b-81f6-e57823215efa |  | checkpoint | Pipe supported
checkpoint-status | 04034572-a19f-4e70-b415-d51484134aca |  | checkpoint | Install Tests completed, reviewed & approved
text | 9e67ffd2-11a1-59af-a6f4-1fd5f7780af6 |  | textbox | Test method used
text | 98ce85c5-cb0f-540b-ae4b-b48c35523c27 |  | textbox | Duration
checkpoint-status | 88ee376b-f602-494e-93e6-80bb5d876c5e |  | checkpoint | Local Authority Inspection Passed
text | fa386568-cbba-5179-aa85-56010678a888 |  | textbox | Witnessed by
text | fd553973-4fdd-539d-92e7-896caca5fcd5 |  | textbox | Representing (Company)
text | e53bb4fd-dd76-5f3d-9c24-463e16779382 |  | textbox | Date
checkpoint-status | a4825606-c905-4c4e-b3b3-56e60714eb66 |  | checkpoint | All relevant test plugs removed where applicable
checkpoint-status | 175b8e8d-660d-4aaf-855a-09aa6a0e8af1 |  | checkpoint | Open ends sealed
checkpoint-status | ce974b23-3635-401b-a635-83159bfbb208 |  | checkpoint | General photos, comments and observations
checkpoint-status | b263d377-56ce-4138-955b-f4239c0d128d |  | checkpoint | Pipe Laying Completed
text | 543558a3-25b5-55db-8df7-620781346577 |  | textbox | Laid by
boolean | 5470c0ab-6f87-5b3e-b6ec-57b03f310600 |  | tickbox | Bedding Sound
boolean | 846a13a3-22f1-5ed3-8b13-7f85271f5ad7 |  | tickbox | Soil Removed
boolean | 38a32a0a-59f4-5057-9b55-d8dc6d4b6d94 |  | tickbox | Trench Compacted
boolean | 2de3b2fd-6d42-5fe5-b46c-506e4da898c5 |  | tickbox | Hard Filled
checkpoint-group | 13d158ea-33a1-4615-8457-73d1a7647569 |  | section | Area Completion/Signoff
checkpoint-status | 38e3778b-c47b-4bb8-a000-03c378beef91 |  | checkpoint | Specified Protection Around All feeds/pipes penetrating slab
checkpoint-status | 66743871-abd8-4a3f-a684-fb03461291fd |  | checkpoint | All Measurements Double Checked
checkpoint-status | 435c24f6-a5e2-4154-964c-98e1ad0a1df6 |  | checkpoint | As-Built Drawings recorded (drawing & revision number(s)
checkpoint-status | 5a1ec7ff-6735-452b-b537-86fde920c084 |  | checkpoint | All relevant under slab works completed, reviewed and approved
text | d0f41b6c-68b8-5c76-8c0c-e6b870c8097d |  | textbox | Completion Date
checklist-flat |  |  | checklist | Variation Contract - |  |  |  |  | Yes | Variation Contract | 40cbd6c8-bf31-476a-a6b3-1a65bc3509d6
checkpoint-no-status |  |  | checkpoint | Job Details
text | 51fefc9e-d0e5-419c-b6aa-3b31489bf21e |  | textbox | Details of Work (Inc. Location):
text | 736ff74e-eca9-4444-8673-73757bb18e82 |  | textbox | Client:
text | b9f6fbd1-e230-42a8-a652-f9c189290fd9 |  | textbox | Reason for Variation:
text | 369c090a-bd1d-49c2-b010-fe3c00fe171a |  | textbox | Project:
text | 1285206f-35b3-414c-89ee-5f2e6353ba0b |  | textbox | Job No:
text | b4b080dc-d867-4e2c-ac6f-033a4e9b170c |  | textbox | Hours:
text | ab8745e6-1157-4a3c-b0ee-552b7e3a968d |  | textbox | Site Instruction No:
text | 218305d5-9e67-4136-ba1b-632c37b8a96c |  | textbox | Materials Equipment:
text | 56d851bf-6135-48c5-aa68-3eb317865210 |  | textbox | Agreed Value:
checkpoint-no-status |  |  | checkpoint | Work Details:
text | 51fefc9e-d0e5-419c-b6aa-3b31489bf21e |  | textbox | Details of Work (Inc. Location):
text | c65d0a84-1d5d-4cd0-a8ba-5861a75214ea |  | textbox | Name:
text | b9f6fbd1-e230-42a8-a652-f9c189290fd9 |  | textbox | Reason for Variation:
text | b4b080dc-d867-4e2c-ac6f-033a4e9b170c |  | textbox | Hours:
text | 218305d5-9e67-4136-ba1b-632c37b8a96c |  | textbox | Materials Equipment:
text | 56d851bf-6135-48c5-aa68-3eb317865210 |  | textbox | Agreed Value:
checkpoint-status |  |  | checkpoint | Foreman Sign Off
text | 0e07a75b-cd35-4599-a063-de55afbb5ade |  | textbox | Name:
text | c65d0a84-1d5d-4cd0-a8ba-5861a75214ea |  | textbox | Name:
checkpoint-status |  |  | checkpoint | Project Manager Sign Off
text | 2cb2c7c5-ff73-4847-b7a0-9ec1caa52992 |  | textbox | Name:
text | 0e07a75b-cd35-4599-a063-de55afbb5ade |  | textbox | Name:
checkpoint-status |  |  | checkpoint | Signature of Authorising Officer
text | 2cb2c7c5-ff73-4847-b7a0-9ec1caa52992 |  | textbox | Name:
checklist-flat |  |  | checklist | Fit Off Checklist |  |  |  |  | Yes | Fit Off Checklist | 4a915d35-8ac6-49e7-bb49-a05d6734f44c
checkpoint-status |  |  | checkpoint | Fixtures installed at correct height/clearance
checkpoint-status |  |  | checkpoint | Appliances installed at correct location
checkpoint-status |  |  | checkpoint | Dishwasher installed & tested
checkpoint-status |  |  | checkpoint | Correct clearance between appliance & walls, fixtures/equipment
checkpoint-status |  |  | checkpoint | Correct clearance for connections & maintenance
checkpoint-status |  |  | checkpoint | Ensure bath is installed as per specifications
checkpoint-status |  |  | checkpoint | Final test completed & hot water tempered
checkpoint-status |  |  | checkpoint | Valves Installed/Completed (As Per Below) - Any issues comment below
checklist-sectioned |  |  | checklist | Plumbing Rough-In Water/Gas/Sewer Checklist |  |  |  |  | Yes | Plumbing Rough-In Water/Gas/Sewer Checklist | a617d2f0-adb1-41d5-bbd8-0912dae90d4d
checkpoint-group |  |  | section | Sewer Stacks/Water Supply
checkpoint-status |  |  | checkpoint | Pipe Work Secured in ceiling
checkpoint-status |  |  | checkpoint | Pipe Work Secured in wall
checkpoint-status |  |  | checkpoint | Pipe Work Siliconed
checkpoint-status |  |  | checkpoint | Check for Crossovers
checkpoint-status |  |  | checkpoint | Pressure Test 1500 KPA or product/job spec
checkpoint-status |  |  | checkpoint | Visual check & photos attached
checkpoint-status |  |  | checkpoint | Check all joints
checkpoint-status |  |  | checkpoint | Shower/bath outlet Crimp
boolean | 8857de63-da35-5f24-9af8-a2a699ed375a |  | tickbox | Photo uploaded
checkpoint-status |  |  | checkpoint | Final test completed
holdpoint |  |  | signoff | Request signoff from PM
checkpoint-group |  |  | section | Water & Gas Rough-In/Pre-line Inspection
checkpoint-status |  |  | checkpoint | Nogs in correct Location
checkpoint-status |  |  | checkpoint | Cylinder seismic nogs in place
checkpoint-status |  |  | checkpoint | Vanity, shower, toilet nogs
checkpoint-status |  |  | checkpoint | Shower mixer - Depths allowance for tiles, nogs square to wall
checkpoint-status |  |  | checkpoint | Mixers straight
checkpoint-status |  |  | checkpoint | Vanity Wingbacks
checkpoint-status |  |  | checkpoint | Outlets straight
checkpoint-status |  |  | checkpoint | Outlets correct length
checkpoint-status |  |  | checkpoint | HWC water feeds
checkpoint-status |  |  | checkpoint | Capped Off
checkpoint-status |  |  | checkpoint | Rubbish removed
checkpoint-status |  |  | checkpoint | Protective covers in place
label | 040e9b09-60fe-5845-bda7-288707476e86 |  | note | Attach photos of completed area
checkpoint-status |  |  | checkpoint | Final test completed
holdpoint |  |  | signoff | Request signoff from PM
checklist-flat |  |  | checklist | Commissioning/Handover & Testing Checklist |  |  |  |  | Yes | Commissioning/Handover & Testing Checklist | c84c68b1-a4fb-46c1-8ccc-a00c810a9248
checkpoint-status |  |  | checkpoint | Final completed for fire hydrant
checkpoint-status |  |  | checkpoint | Final sign off - Pass when happy to proceed (Any issues please comment & Add photos below)
checklist-flat |  |  | checklist | Date: |  |  |  |  | Yes | H&S - Daily Prestart | d1648d6c-9895-41f1-b7fd-2d1d5a73c6d4
checkpoint-status |  |  | checkpoint | Person/s in charge of site operations
checkpoint-status |  |  | checkpoint | Weather conditions
select | aa609aee-cc45-5bbd-8f79-7e21c1fb2b4d |  | dropdown | Conditions | Sunny, Overcast, Cloudy, Rainy
checkpoint-status |  |  | checkpoint | Wind Conditions
select | c62d18a3-5bdc-5566-aa28-6b2337f03812 |  | dropdown | Conditions | Strong, Medium, Low, None
checkpoint-status |  |  | checkpoint | Meeting minutes
checkpoint-status |  |  | checkpoint | Safety minutes
checkpoint-status |  |  | checkpoint | Main contractor supplied minutes
checkpoint-status |  |  | checkpoint | Signatures of all attendees
holdpoint |  |  | signoff | Send signoff to all attendees
checklist-sectioned |  |  | checklist | Toolbox Meeting - |  |  |  |  | Yes | H&S - Toolbox Meeting Minutes | fb04a980-8194-4f2c-aa4a-048ff1e32f02
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete (pass once all relevant details are inputted below)
text | d53229d0-5af1-539f-a027-6e308f09bb35 |  | textbox | Office location:
label | 8a42238e-e663-5b36-89a0-28a253d2a4b0 |  | note | Who is running this meeting
text | cf2af2af-84fc-5bb9-887c-f992f70d2ee5 |  | textbox | Name:
text | 3ead659d-0d7c-5eca-a73c-aa209c51df75 |  | textbox | Company:
text | 579b2761-860f-5a34-8fe5-72569618a936 |  | textbox | Agenda items:
text | 31b8b719-0ec6-586d-9a49-47951213016e |  | textbox | Theme of the week (topic for focus):
checkpoint-group |  |  | section | Health and safety issues
checkpoint-status |  |  | checkpoint | Relevant Issues recorded with appropriate actions and date
text | e23e9838-2435-55df-9221-92d48a9899e5 |  | textbox | Issue raised from site safety inspection:
text | 00266ad7-198e-5f50-9a0d-d88b3176db8a |  | textbox | Actions:
text | 83a2e6c8-2f2f-5b99-bf61-a7385018e545 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | Issues outstanding from previous briefings recorded with appropriate actions and date
text | 33a0ad1f-dcbb-55a1-a22d-1f1d97156aaa |  | textbox | Issues outstanding from previous briefings:
text | e1664cce-39ae-5c17-8af4-d23e01d3cef5 |  | textbox | Actions:
text | 28bfa81b-3880-59a8-821f-fd6dd0513136 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 3. Employee-raised issues recorded with appropriate actions and date
text | 691230f6-33a8-5ef5-bd76-de16c3dda469 |  | textbox | Employee-raised issues:
text | 6819295b-ab43-54c8-ad3c-c2c31ab7e87e |  | textbox | Actions:
text | 9b4efb57-5d97-5527-8eae-c16826e531da |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 4. Positive safe-action observations recorded with appropriate actions and date
text | 257539e0-9170-5a78-a888-a9529a8ca217 |  | textbox | Positive safe-action observations:
text | 2f72c5b8-6e3d-5c92-b044-f491dc33ab87 |  | textbox | Actions:
text | 9cd0cb28-e4ff-5e8a-a99b-78db00e666e4 |  | textbox | By who and when:
checkpoint-status |  |  | checkpoint | 5. Incidents or injuries recorded with appropriate actions and date
text | 2875bae6-7ed3-5a07-996f-53f9205724c0 |  | textbox | Incidents or injuries:
text | 278ae90e-d261-55df-af4e-bc7868cd2833 |  | textbox | Actions:
text | e9fe6b20-70a5-5be9-b54f-6965bc2da977 |  | textbox | By who and when:
checkpoint-group |  |  | section | Job plans reviewed
checkpoint-status |  |  | checkpoint | Job/Task plan(s) reviewed & Action(s) recorded below
text | d3d56c64-30d0-5140-8a1e-22e2c06c3540 |  | textbox | 1
text | 2b690165-119e-5cf9-af03-3047434783cb |  | textbox | 2
text | b7508aab-73d2-5cbc-9752-b3332cab14d1 |  | textbox | 3
text | be311b3c-0665-5299-b7f0-e31362bf9c54 |  | textbox | 4
text | 84c72f0d-9d91-5a53-a3c9-34f7128fbf20 |  | textbox | 5
text | 7464b7ff-e4c6-502d-bf12-bc2b02ad9ea9 |  | textbox | 6
checkpoint-group |  |  | section | Operational issues
checkpoint-status |  |  | checkpoint | Operational Item(s) & Action(s) recorded below
text | 56bb4fb4-f75b-5ee8-842d-3b83511e07ca |  | textbox | 1
text | 7688e72b-c9fc-5ddd-bd79-ff62dd8c487d |  | textbox | 2
text | 9ba99e61-199e-5718-bde5-167521d71ee5 |  | textbox | 3
text | d45e2bce-b582-5333-8976-efdd7a0e7f79 |  | textbox | 4
text | eefbda04-c338-502c-805b-b8ac6cf12b91 |  | textbox | 5
text | 82795158-71a4-5b6c-af6e-4777bd04facd |  | textbox | 6
checkpoint-group |  |  | section | Other business
checkpoint-status |  |  | checkpoint | Other Business Item(s) & Action(s) recorded below
text | f4042683-0bfc-54ca-bb69-7e62497ff89d |  | textbox | 1
text | 94219717-b8d8-5361-9c47-f50430da100d |  | textbox | 2
text | ddad65c2-7756-5f0c-aa5a-5bc5ad62f16a |  | textbox | 3
text | a8d544f9-d835-5222-919d-6a4c762c8630 |  | textbox | 4
checkpoint-group |  |  | section | Attendees
checkpoint-status |  |  | checkpoint | Add name and Photo of attendees (pass once all attendees are recorded)
holdpoint |  |  | signoff | Send signoff request to all attendees
checkpoint-group |  |  | section | Review by management
checkpoint-status |  |  | checkpoint | Send to management to review?
holdpoint |  |  | signoff | Reviewed and signed off by management