## ITP Cover Page
Landscaping Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - 117 - Rev E
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 117
Project Number: |  |  | DN1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Soft Landscaping |  |  |  |  | Revision: | 1000 |  | E
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | Landscape Drawings, Gully Enhancement Plan
Client: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification, Landscaping Specification
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Draft for Approval | 2024-06-16 |  | Zion Nordstrom | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for Approval | 2024-07-18 |  | Zion Nordstrom | [5 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
C | For Approval | 2024-08-08 |  | Zion Nordstrom | [5 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
D | For Approval | 2024-08-19 |  | Zion Nordstrom | [5 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
E | For Approval | 2024-09-06 |  | Zion Nordstrom | [5 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Landscaping Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - 117 - Rev E
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Construction Pack | Methodology and ITP to be submitted to the Engineer and approved prior to works beginning | Downer | Construction Pack | Submit 10 days prior to commencement of works | HP | ENG
3.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.03 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
3.01.04 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE
3.01.05 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE
3.01.06 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
3.01.07 | Previous Lots | Landscaping works to only be carried out in sections where surrounding work that will cause rework has already been completed. | Downer | IFC Drawings | Prior to works start | H | PE
3.01.08 | Subcontractors | Ensure that subcontract and supplier agreements have been completed. All subcontractors have been inducted. | Downer | IFC Drawings | Prior to works start | H | PE
3.01.09 | Site Preparation | Ensure the area has been sprayed with herbicide. The area has died off and is free of noxious weeds, plant pests, annual and perennial weeds and grasses. Ensure at least two weeks has passed prior to planting. | NZTA P39 Section D: Plant Pest and Animal Pest Control |  | Prior to works start | H | PE
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | Planting
4.01.01 | Mulch | 100% pallet mulch. Material will be stored in stockpiles nearby to work areas where possible. | NZTA P39 Section G: 3.9.1 | Dockets Record of Approval | Prior to use. | H | SE
4.01.02 | Weed Matting | Weed matting supplied is what is specified for the contract. Biodegradable mulching fabric minimum 450 gsm. | RITS Section 7.3.11 NZTA P39 Section G: 3.9.6.1 | Dockets | Prior to use. | H | SE
4.01.03 | Grassing | Specfied grass to be used unless alternative has been approved. Perennial rye-clover seed mix has been approved for use and will be used for all permanent grass application. | NZTA P39 Section C: Site Preparation | Dockets Checksheet | Prior to use. | H | SE
4.01.04 | Plants | All plants and alternatives have been approved for use. Plants to be as per the plant lists shown in landscaping drawings and schedules. | NZTA P39 Section C: Site Preparation | Dockets Checksheet | Prior to use. | H | SE
4.01.05 | Topsoil | Topsoil used is good quality material, clean and free of debris. Topsoil should not contain rubbish, contaminated material or pest plants. Material will be stored in stockpiles nearby to work areas where possible. Topsoil will be managed to prevent saturation and over-compaction. Avoid handling topsoil immediately following any heavy rainfall events. | NZTA P39 Section C and F | Photographs Inspection | Prior to use. | HP | ENG
4.01.06 | Root Barrier | Root barrier to be 1.0mm thick, 600mm high, recycled HDPE non-ribbed material. | RITS Section D7.4 | Dockets Checksheet | Prior to use. | H | SE
SECTION 5 – CONSTRUCTION ACTIVITY
5.01 | Planting
5.01.01 | Topsoil | Minimum topsoil thickness as follows: - Grassing 100mm - Mulching 300mm - Swales 150mm (TYP) - Swales 300mm (swales requiring 300mm to be advised by Landscape Architect) | Drawings | Inspections + Checklist + Photographs | Each Area | HP | ENG
5.01.02 | Planting (Dry) | Correct amount, size and type of plants have been delivered to relevant zone on site. Supply of plants - confirm order, inspect plants for health - Set up a test planting area for Landscape Architect inspection. This is to benchmark and agree typical set out (once for each planting mix/type). Ensure plant spacing and plant numbers are correct. Confirm application of slow release fertiliser tablets as per requirements - 3 per plant. (Photos) Ensure plants are correctly planted, upright and firmly heeled in. Small trees and large shrubs should be size 1.3L Delivery dockets to be provided for fertiliser tablets. Plants to be carried out during planting season unless approved by designer. | Designer | Dockets + Inspections + Checklist + Photographs + Record of Approval | Each Area | H | SE
5.01.03 | Wetland Planting | Wetland Planting to be done outside of summer months (Dec-Feb). | Designer | Checklist + Site Records | Each Area | H | SE
5.01.04 | Grassing | Grass seed has been applied and has full coverage in all required areas. | Designer | Checklist + Site Records | Each Area | H | SE
5.01.05 | Specimen Trees | Site meeting held with Landscape Architect to agree specimen tree locations prior to excavation of tree pits. Supply of trees - confirm order, inspect trees for health - landscape architect to check samples for compliance. Ensure tree pits have been dug out to the required dimensions (varies depending on location/slope). Check no standing water in tree pits .(Photos) Confirm application of three slow release fertiliser tablets per tree. Larger trees (160L) will be planted with a minimum of 8 tablets. Trees have been staked correctly.(Photos) | Drawings | Dockets + Inspections + Checklist + Photographs | Each Area | H | SE
5.01.06 | Mulching | Areas that are mulched and been laid 100mm thick and depths have been checked. HP (Inspection at Completion) | Drawings | Checklist + Site Records | Each Area | HP | ENG
5.01.07 | Herbicide | Avoid spraying any herbicide next to streams. Where required, only non-toxic herbicide may be applied near waterways and wetlands. | GEP | Checklist | Each Area | H | SE
5.01.08 | Tree Pits | Tree pits to be installed as per drawings. Individual pits should be 800mm wide and 850mm deep unless agreed otherwise. 150mm soil layer beneath tree pit should be scarified/loosened. Tree pits to be backfilled with topsoil and slow release fertiliser mixed with compost. Trees to be kept upright with 50mm stakes with horizontal straps no more than a third the height of the tree. Trees to be covered with 100mm mulch and pulled back from the tree trunk. | Drawings | Checklist + Site Records + Photos | Each Area | H | SE
5.01.09 | Root Barrier | Root barrier to be installed where tree pits are close to kerbs and footpaths. Root barrier to installed 2m wide and to be 600mm deep where required for tree pits. (Photos) | Drawings | Checklist + Site Records + Photos | Each Area | H | SE
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01 | Post-Construction
6.01.01 | Maintenance of Plants and Grassed Areas | The Contractor shall remedy all defects relating to the landscape treatment works, each year during the defects and maintenance period, at the first available opportunity. All planting defects shall be addressed duuring the correct planting season. | Landscaping Specification | Site Records | Each Area | H | SE
6.01.02 | Redline Markup | Redline markup of any design changes. |  | Redline Markup | Upon Completion | H | SE
6.01.03 | As Builts | Final tree locations to be provided. |  | As Built File | Upon Completion | H | SE
6.01.03 | QA Pack Compiled | Submitted for approval. |  |  | Upon Completion | HP | ENG
6.01.04 | Final Acceptance | Planting shall achieve an 80% canopy coverage of the ground by contract completion, | NZTA P39 Section A |  | Upon Completion | HP | ENG