## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Soft Landscaping - Rev E | itp |  |  |  |  | ITP - Soft Landscaping - Rev E
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Submit 10 days prior to commencement of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 3.01.03 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.04 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 3.01.05 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.06 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.07 - Previous Lots
label | Acceptance / Conformance Criteria - Landscaping works to only be carried out in sections where surrounding work that will cause rework has already been completed.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.08 - Subcontractors
label | Acceptance / Conformance Criteria - Ensure that subcontract and supplier agreements have been completed.
label | ○ All subcontractors have been inducted.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.09 - Site Preparation
label | Acceptance / Conformance Criteria - Ensure the area has been sprayed with herbicide. The area has died off and is free of noxious weeds, plant pests, annual and perennial weeds and grasses. Ensure at least two weeks has passed prior to planting.
label | Standard / Specification - NZTA P39 Section D: Plant Pest and Animal Pest Control
label | Verifying Document -
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Mulch
label | Acceptance / Conformance Criteria - 100% pallet mulch.
label | ○ Material will be stored in stockpiles nearby to work areas where possible.
label | Standard / Specification - NZTA P39 Section G: 3.9.1
label | Verifying Document - Dockets, Record of Approval
label | Frequency - Prior to use.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.02 - Weed Matting
label | Acceptance / Conformance Criteria - Weed matting supplied is what is specified for the contract.
label | ○ Biodegradable mulching fabric minimum 450 gsm.
label | Standard / Specification - RITS Section 7.3.11, NZTA P39 Section G: 3.9.6.1
label | Verifying Document - Dockets
label | Frequency - Prior to use.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.03 - Grassing
label | Acceptance / Conformance Criteria - Specfied grass to be used unless alternative has been approved.
label | ○ Perennial rye-clover seed mix has been approved for use and will be used for all permanent grass application.
label | Standard / Specification - NZTA P39 Section C: Site Preparation
label | Verifying Document - Dockets, Checksheet
label | Frequency - Prior to use.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.04 - Plants
label | Acceptance / Conformance Criteria - All plants and alternatives have been approved for use.
label | ○ Plants to be as per the plant lists shown in landscaping drawings and schedules.
label | Standard / Specification - NZTA P39 Section C: Site Preparation
label | Verifying Document - Dockets, Checksheet
label | Frequency - Prior to use.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 4.01.05 - Topsoil
label | Acceptance / Conformance Criteria - Topsoil used is good quality material, clean and free of debris.
label | Topsoil should not contain rubbish, contaminated material or pest plants.
label | Material will be stored in stockpiles nearby to work areas where possible.
label | Topsoil will be managed to prevent saturation and over-compaction.
label | Avoid handling topsoil immediately following any heavy rainfall events.
label | Standard / Specification - NZTA P39 Section C and F
label | Verifying Document - Photographs, Inspection
label | Frequency - Prior to use.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.01.06 - Root Barrier
label | Acceptance / Conformance Criteria - Root barrier to be 1.0mm thick, 600mm high, recycled HDPE non-ribbed material.
label | Standard / Specification - RITS Section D7.4
label | Verifying Document - Dockets, Checksheet
label | Frequency - Prior to use.
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint | 5.01.01 - Topsoil
label | Acceptance / Conformance Criteria - Minimum topsoil thickness as follows:
label | – Grassing 100mm
label | – Mulching 300mm
label | – Swales 150mm (TYP)
label | – Swales 300mm (swales requiring 300mm to be advised by Landscape Architect)
label | Standard / Specification - Drawings
label | Verifying Document - Inspections + Checklist + Photographs
label | Frequency - Each Area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.02 - Planting (Dry)
label | Acceptance / Conformance Criteria - Correct amount, size and type of plants have been delivered to relevant zone on site.
label | ○ Supply of plants - confirm order, inspect plants for health -
label | ○ Set up a test planting area for Landscape Architect inspection. This is to benchmark and agree typical set out (once for each planting mix/type).
label | ○ Ensure plant spacing and plant numbers are correct.
label | ○ Confirm application of slow release fertiliser tablets as per requirements - 3 per plant. (Photos)
label | ○ Ensure plants are correctly planted, upright and firmly heeled in.
label | ○ Small trees and large shrubs should be size 1.3L
label | ○ Delivery dockets to be provided for fertiliser tablets.
label | ○ Plants to be carried out during planting season unless approved by designer.
label | Standard / Specification - Designer
label | Verifying Document - Dockets + Inspections + Checklist + Photographs + Record of Approval
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.03 - Wetland Planting
label | Acceptance / Conformance Criteria - Wetland Planting to be done outside of summer months (Dec-Feb).
label | Standard / Specification - Designer
label | Verifying Document - Checklist + Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.04 - Grassing
label | Acceptance / Conformance Criteria - Grass seed has been applied and has full coverage in all required areas.
label | Standard / Specification - Designer
label | Verifying Document - Checklist + Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.05 - Specimen Trees
label | Acceptance / Conformance Criteria - Site meeting held with Landscape Architect to agree specimen tree locations prior to excavation of tree pits.
label | ○ Supply of trees - confirm order, inspect trees for health - landscape architect to check samples for compliance.
label | ○ Ensure tree pits have been dug out to the required dimensions (varies depending on location/slope). Check no standing water in tree pits .(Photos)
label | ○ Confirm application of three slow release fertiliser tablets per tree. Larger trees (160L) will be planted with a minimum of 8 tablets. Trees have been staked correctly.(Photos)
label | Standard / Specification - Drawings
label | Verifying Document - Dockets + Inspections + Checklist + Photographs
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.06 - Mulching
label | Acceptance / Conformance Criteria - Areas that are mulched and been laid 100mm thick and depths have been checked. HP (Inspection at Completion)
label | Standard / Specification - Drawings
label | Verifying Document - Checklist + Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.07 - Herbicide
label | Acceptance / Conformance Criteria - Avoid spraying any herbicide next to streams.
label | ○ Where required, only non-toxic herbicide may be applied near waterways and wetlands.
label | Standard / Specification - GEP
label | Verifying Document - Checklist
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.08 - Tree Pits
label | Acceptance / Conformance Criteria - Tree pits to be installed as per drawings. Individual pits should be 800mm wide and 850mm deep unless agreed otherwise. 150mm soil layer beneath tree pit should be scarified/loosened. Tree pits to be backfilled with topsoil and slow release fertiliser mixed with compost. Trees to be kept upright with 50mm stakes with horizontal straps no more than a third the height of the tree. Trees to be covered with 100mm mulch and pulled back from the tree trunk.
label | Standard / Specification - Drawings
label | Verifying Document - Checklist + Site Records + Photos
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 5.01.09 - Root Barrier
label | Acceptance / Conformance Criteria - Root barrier to be installed where tree pits are close to kerbs and footpaths.
label | ○ Root barrier to installed 2m wide and to be 600mm deep where required for tree pits. (Photos)
label | Standard / Specification - Drawings
label | Verifying Document - Checklist + Site Records + Photos
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - Maintenance of Plants and Grassed Areas
label | Acceptance / Conformance Criteria - The Contractor shall remedy all defects relating to the landscape treatment works, each year during the defects and maintenance period, at the first available opportunity. All planting defects shall be addressed duuring the correct planting season.
label | Standard / Specification - Landscaping Specification
label | Verifying Document - Site Records
label | Frequency - Each Area
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.01.02 - Redline Markup
label | Acceptance / Conformance Criteria - Redline markup of any design changes.
label | Standard / Specification -
label | Verifying Document - Redline Markup
label | Frequency - Upon Completion
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.01.03 - As Builts
label | Acceptance / Conformance Criteria - Final tree locations to be provided.
label | Standard / Specification -
label | Verifying Document - As Built File
label | Frequency - Upon Completion
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | 6.01.03 - QA Pack Compiled
label | Acceptance / Conformance Criteria - Submitted for approval.
label | Standard / Specification -
label | Verifying Document -
label | Frequency - Upon Completion
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.01.04 - Final Acceptance
label | Acceptance / Conformance Criteria - Planting shall achieve an 80% canopy coverage of the ground by contract completion,
label | Standard / Specification - NZTA P39 Section A
label | Verifying Document -
label | Frequency - Upon Completion
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT