## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | SWA-004 - Sprayed Bituminous Surfacing | itp |  |  |  |  | SWA-004 - Sprayed Bituminous Surfacing
section | Details
checkpoint | 1 - Preparation of sealing
label | SPECS REFERENCE: VR 408.02
label | DOCUMENTATION OR ACTION: Constructed to meet specified shape and level requirements Homogeneous and consistent with the material in the pavement base layer
label | ○ Uniform in texture
label | ○ Free of tearing and scabbing Free of lamination on or within 75 mm of the finished surface
label | ○ Level with adjacent sealed areas and edgings at the Joints
label | ○ A hard dense and tight surface capable of being swept with a rotary road broom or similar
label | ○ Free of looses and foreign materials
label | ○ Dried back to the moisture content and embedment requirements specified in Clause 310.03
label | RESPONSIBILITY: Subcontractor
date | Date:
checkpoint | 2 - Preparation Testing
label | SPECS REFERENCE: VR 408.03
label | DOCUMENTATION OR ACTION: Testing Scale B
label | ○ Maximum lot size 4000m2
label | RESPONSIBILITY: Subcontractor
date | Date:
checkpoint | 3 - Commencement of Work
label | SPECS REFERENCE: VR 408.03
label | DOCUMENTATION OR ACTION: HP - Work shall not commence until the contractor and the Superintendent have agreed that the road or pavement surface is fit and ready for surfacing no more than 24 prior to the work occurring.
label | RESPONSIBILITY: HP VR Rep. AP
label | ○ Site Eng
label | ○ Superintendent
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Limits of Work
label | SPECS REFERENCE: VR 408.04
label | DOCUMENTATION OR ACTION: Limits of works shall be marked out as per drawing and table 408.161
label | RESPONSIBILITY: Subcontractor
date | Date:
checkpoint | 5 - Materials
label | SPECS REFERENCE: VR 408.06 & 408.07
label | DOCUMENTATION OR ACTION: Materials to comply with specification, contractor to confirm materials to be used
label | RESPONSIBILITY: Subcontractor
date | Date:
checkpoint | 6 - Application
label | SPECS REFERENCE: VR 408.10
label | DOCUMENTATION OR ACTION: Supply Seal design to superintendent for review prior to application of seal and application rate not to be less than 0.1L/m2 for design
label | ○ Minimum air and pavement temperature to e not less than 15 degree C
label | RESPONSIBILITY: HP Subcontractor
label | ○ HP VR Rep. AP
label | ○ Site Eng
label | ○ Superintendent
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Removal of Loose Aggregate
label | SPECS REFERENCE: VR 408.11
label | DOCUMENTATION OR ACTION: Aggregate to be removed within 48 hours of application.
label | ○ Road to remain appropriately signed until aggregate is removed.
label | RESPONSIBILITY: Subcontractor
date | Date:
checkpoint | 8 - Acceptance of Loose Aggregate
label | SPECS REFERENCE: VR 408.12
label | DOCUMENTATION OR ACTION: ACCEPTANCE OF SEAL
label | ○ Accepted application rate shall not be 0.1L/m2 less than seal design rate
label | ○ Surface texture shall be based on visual assessment
label | ○ Aggregate retention shall be based on visual assessment
label | ○ The seal shall appear visually uniform.
label | RESPONSIBILITY: HP Subcontractor
label | ○ HP VR Rep. AP
label | ○ Site Eng
label | ○ Superintendent
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Maintenance of Seals (Repairs to Seal)
label | SPECS REFERENCE: VR 408.14
label | DOCUMENTATION OR ACTION: HP - Superintenden t to approve the proposed treatment to effect the above work before undertaking the work.
label | ○ HP - Where the treatment for protection or repair of a seal involves the application of a further seal coat the Superintenden t shall approve prior.
label | RESPONSIBILITY: HP Subcontractor
label | ○ HP VR Rep. AP
label | ○ Site Eng
label | ○ Superintendent
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP