## Breakdown Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Name of ITP/Checklist Template (If Required)
Site QA
| Zone 1 | General | Service location | PCP - Zone 1 Service Location and Pot Holing
|  | Bore Headworks | Headworks assembly
|  |  | Foundations | PCP Foundation Pads
|  | Drainage | Pipework | PCP Raw water pipeline & services CH 0-220
|  | WTP | Foundations | PCP Foundation Pads
|  | Access track | Earthworks
| Zone 2 | General | Service location | PCP - Service Location and Pot Holing Zone 2
|  | Drainage | Church Rd CH 90 - CH1350 | PCP - Drainage CHURCH RD CH 90 - 1350
|  |  | Church Rd CH 40 - 90 | Church Rd CH 40 - 90
|  |  | Church Rd CH 1350 -1450 | Church Rd CH 1350 - 1450
SH6 Thrusting
| Zone 3 | General | Service location | PCP - Service Location and Pot Holing Zone 3
|  | Drainage | Pipework
Directional drilling
| Zone 4 | Drainage | Pipework | PCP - Zone 4 Connections
| Zone 5 | General | Service location | PCP - Service Location and Pot Holing Zone 5
|  | Platform preparation | Earthworks
|  | Tank farm | Services installation
Thrusting
|  |  | Foundations | PCP Foundation Pads
|  | Earthworks bund | Earthworks
|  | Access Road | Earthworks
|  | Entranceway | TBC
Guide: The above lets our team know that you'd like to break your project down to three areas, and have two zones assigned in each. Clicking the last tier (i.e 'Zone 1' in Tier 3) in the app will open the assigned checklist/ITP.
NOTE: You are able to modify the structure to include more tiers, subfolders and checklist/ITPs as required.
ITPs: To assign an ITP to an area, simply type in the ITP name above instead. We take care of digitising your ITPs for you, and upload it directly to your account.