## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-312-CIV-HOP-ACO Drainage Installation
ITP Description: |  | HOP-ACO Drainage Installation
Document Number (in Teambinder): |  | 312
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2025-09-17
ITP created by: |  | Christopher Lodge
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Hopkins Road
Inspection & Test Plan - Precast Bridge Cross Head (Supply and Installation)
|  |  | Document No.: | 312 |  |  |  |  | Revision: | 0
[9 empty] | Date: | 2025-09-17
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | NIST-2659 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.2 | Non Dependent | VicRoads Section 610 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | VicRoads Section 611 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.4 | Non Dependent | VicRoads Section 612 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.5 | Non Dependent | NIST-012.2.1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.6 | Non Dependent | VicRoads Section 702 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.7 | Non Dependent | AS 1289 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries - Materials
2.1 | Concrete Mix (Min 32MPa) - No testing Req. | IFC Drawings 610.07 Table 610.071 | Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each mix design, 4 weeks prior to placement of concrete | HP* | Nominated Authority | ConQA Hold Point Release
2.2 | ACRS Certification (for Reinforcement) | 611.05 (a) | Current ACRS certification for materials and for bar processing. Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery) Enter: Teambinder Material Approval number [free text box] | Document Review | Once for each supplier, 14 days of award of contract | HP* | Nominated Authority | This ITP
2.3 | Bar Chairs/Aspros Certification | 610.26 (a) | Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads. Concrete aspros require annual compressive strength and soluble salt testing is required. Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority. Enter: Teambinder Material Approval number [free text box] | Document Review | Once for each supplier, 14 days prior to placement of reinforcement | WP | Nominated Authority | This ITP
2.4 | ACO Drain and Lid Supply | IFC Drawings | Aco Drain Type: KlassiDrain K300 - Linear/Nutral Grade Drain - Depth 300mm (300x325mm) Lid Type: Galvanised Steek Grated Lid Loading Class: - Class B for non trafficable areas - Class D for trafficable Areas Enter: Teambinder Material Approval number [free text box] | Document review | Once, for each product, prior to placement of product | HP* | Nominated Authority | ConQA Hold Point Release
2.5 | Pits and Pit Lids (Class D area's only) | IFC Drawings VicRoads SD1121 NIST-2659 NIST 012.2.1 Section 6.15-16 NIST 012.2.1 Section 6.9 NIST 012.2.1 Cl. 6.7 (c) | Pits: located within 1.5m of nearest rail, pit to be 300LA Railway loading Pits 900x900mm or greater, multipart pits lids to be used. Concrete Pits to be made as per AS 3600 Pit lids: Covers shall comply with AS3996-2006 Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class B Enter: Teambinder Material Approval number [free text box] | Document Review | Where applicable, once, install | HP* | Nominated Authority | ConQA Hold Point Release
2.6 | Bedding & Backfill Material | IFC Drawings NIST-2659 cl6.4.2 & cl6.4.3 VicRoads Spec Cl.701.10 VicRoads Spec Cl.701.05(b) AS 1289.5 Cl1.1 AS 1289.5 Cl3.1 AS 1289.5 Cl4.1 AS 1289.5 Cl5.1 AS 1289.5 Cl6.1 | Bedding & backfill material free of rocks that will not pass a 75mm sieve. The material shall be free or organic matter or anything that could damanage the conduits. Nominal agg size 20mm Swell => 2.5% 98% compaction | Document Review | Each Material Type, Each Delivery | IP | SE/PE | Attach Material Conformnace Certs, include TB Approval No. Attach delivery dockets
2.7 | Geotextile | IFC Drawings NIST-2659 cl7.4.2 Table 12 | For separation of subgrade and aggregate base a Class 2 geotextile is preferred. Either medium weight non-woven or a 155gsm woven. Minimum permittivity of 0.02 s -1 and maximum EOS of 600 µm. | Document Review | Each Material Type, Each Delivery | IP | SE/PE | Attach Material Conformnace Certs, include TB Approval No. Attach delivery dockets
2.8 | Joint Sealant | IFC Drawings 612.18 ASTM 0262 | 10x10mm Joint Sealant (eg Neoprene Compression Seal) Enter: Teambinder Material Approval number [free text box] | Document Review | Each Material Type, Each Delivery | IP | SE/PE | Attach Material Conformnace Certs, include TB Approval No. Attach delivery dockets
3 | Pre-installation Activities
3.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP
3.2 | Survey Set-out | IFC Drawings NIST-2659 cl6.4.1 | Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.473 (March/June 2019) as applicable to the element. | Measure Visual | Prior to Commencing | IP | Surveyor SE/PE/SPE | This ITP
3.3 | Temporary Drainage Provisions | VicRoads Spec. Cl.703.18 | Temporary diversion of drainage to be in place where required. Written approval of from V/Line (SAP) to be provided where diversions are to be installed. | Site Inspection | Where applicable, Prior to Commencing | IP | SE | This ITP
4 | Construction / Installation Activities
4.1 | Trench Excavation | NIST-2659 cl6.4.2 IFC Drawings Section 702.08 | Trench shall be excavated to allow for a min of 150mm between each side of the ACO drain The depth of the excavation shall be a min of 225mm below the base of the ACO drain in clay areas and 350mm in rock areas The bottom of the trench shall be compacted There shall be no departures from the grade of the base of the trench that would allow ponding of water. Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed. | Visual | Each Lot | HP | SE, NA (Nominated Authority) | This ITP
4.2 | Placement of bedding | 702.09 c) | Bedding of granular filter material of thickness between 75 mm and 200mm placed across bottom of trench and screeded & compactecd to level Place 150mm of bedding under pits | Visual inspection | Each lot | IP | SE/Site Supervisor | This ITP
4.3 | Placemnt of SL81 Mesh (75mm cover) - Trafficable areas only | IFC Drawings 611.06 611.09 611.10 611.11 611.12 | The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings. Splice lengths achieve the minimum length and are in contact for this length. The reinforcement surface condition is free from dirt, debris and damage. The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour. | Measure Visual | Each Lot | IP | SE/Site Supervisor | This ITP
4.4 | Formwork Design and Construction | IFC Drawings 614.04 614.05 614.06 | Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish. Formwork shall not be placed where steel & fixtures cannot be inspected. | Document Review Visual Measure | Each element | IP | Temporary Works Designer Proof Engineer SE/PE/SPE | This ITP
4.5 | Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m) | 614.08 | The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority Abutments, pile caps, footings, solid piers, pier columns and walls, with heights less than or equal to 2.0 metres Attach: Attachment C | Document Review Visual Measure | Each element (where 2m or less) | HP | PE/SPE | ConQA Hold Point Release
4.6 | Installatrion of Contraction Joints | IFC Drawings | Contraction joints shall be placed at a maximum spacing of 12m and shall comprice of the following: - 10x10 Blockout to be rfilled withapproved joint sealant - R10 x 500mn long gal dowels | Visual Measure | Each element | IP | SE | This ITP
4.7 | Pre-concrete check | VicRoads Spec Cl.703.09 Cl.610.17 (a)(b) (c)(d) | Concrete shall not be placed when the air temperature measured at the point of placement is >35 C or < 5 C. Temperature of concrete, measured immediately prior to placing, shall not be less than 10 C or greater than 32 C. Unless otherwise specified concrete shall be N32 standard strength. | Site Inspection Temp Varification | Each Lot | IP | SE | This ITP
4.8 | Concrete Placement | IFC Drawings VicRoads Spec. Cl.610.13(f) | Concrete Strength to be 32MPA as nominated on Drawings; Concrete placed within 60-90 minutes of the commencement of mixing; | Site Inspection | Each Lot | IP | SE | This ITP
4.9 | Concrete Finish | VicRoads Spec. Cl 703.25 | Egdings: Rendering shall be applied witihin 30 minutes of placing or extruding concrete. endered to a thickness not exceeding 3mm and steel trowel finished. Footpaths and Surfacing: Use a wooden float for a lightly textured non-skid finish. Concrete to have a neat appearance and uniform colour | Site Inspection | Each Lot | IP | SE | This ITP
5 | Post-installation Activities
5.1 | Backfilling | VicRoads Spec. Cl 703.29 | As soon as the concrete has cured sufficiently, but not earlier than 3 days after casting. Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging, unless otherwise specified. | Site Inspection | Each Lot | HP* | PE/SPE | This ITP
5.2 | Place ACO Drain | IFC Drawings | Place ACO as per IFC drawing in center of trench and fix in place at 1:300 grade ACO units to be placed flush with adjacent units with slope facing correctly as nominated on drawings. Joints between pits and ACO units to be grouted and watertight. | Site Inspection | Each Lot | IP | SE | This ITP
5.3 | Sealant | IFC Drawings | Remove 10x10mm blockout seal joint with 10x10mm or approved Sealant | Visual | Each element | IP | SE | This ITP
5.4 | Connection to Pits and Pit Cover Installation | IFC Drawings NIST-2659 | Gap between reinstated pit walls and Aco drain units shall be 20mm with nominated water stop seal as per drawings. | Site Inspection | Each Lot | IP | SE | This ITP
5.5 | As-built Survey | IFC Drawings 610.32 | Provide record of dimensional measurements to demonstrate Vertical and horizontal alignment between adjacent segments shall not exceed 5mm Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP
5.6 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /