## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-313-STR-HOP-Steel Structures Installation
ITP Description: |  | Steel Structures Installation
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 0
Revision Date: |  | 2025-08-12
ITP created by: |  | Manwel Kalyana
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Hopkins Road
Inspection & Test Plan - Steel Structures Installation (Anti-throw Screens)
[9 empty] | Revision: | 0
[9 empty] | Date: | 2025-08-12
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VR Section 610 Feburary 2020 VR Section 630 January 2022 VR Section 631 June 2017 IFC Drawings AS 1252.1, AS 1110.1 AS 1110.2 AS 1112.1 AS 4100 AS/NZS 5131 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Steel Material Compliance | Section 630.071 IFC Drawing | Steel should demonstrating compliance to the relevant steel product standards listed in Table 630.071, including all impact test values when appropriate. The test certificates shall be related to the steel by trademarks and heat number. Collate: Steel manufacturer’s Certificate of Product Compliance and all related test certificates and upload in a TeamBinder Lot Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, prior to placement of product | HP | Nominated Authority | Conqa HP Release
2.2 | Fasteners | Section 630.21 IFC Drawing AS 1252.1, AS 1110.1 AS 1110.2 AS 1112.1 | Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1252.1, AS 1110.1, AS 1110.2 and AS 1112.1 Collate: Bolt manufacturer's Certificate of Product Comliance and related documentation and upload in a TeamBinder Lot. Enter: Teambinder Material Approval number [free text box] | Document review | Each component | HP | Nominated Authority | Conqa HP Release
2.3 | Base Plate Structural Grout or Mortar | IFC Drawings Section 610.33 | Product to be selected based on the following criteria: i. Shall be self shrinkage compensating proprietary products with a consistancy appropriate for required use as per 610.33 ii. Must have a minimum of 28 days compressive strength, of not less than 50MPa as per IFC drawings. iii. Cementeous grouts shall be as a minimum Type C Class dual shrinkage compensating as per 610.33 iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, prior to placement of product | HP | Nominated Authority | Conqa HP Release
2.4 | Surface Finishes | IFC Drawings Section 631.05 | At least 14 days prior to commencing the protective treatment of steelwork, the Contractor shall submit to the Superintendent for review the information outline in section 631.05, for all proposed coating system (a)coating system, including hot-dip galvanizing if specified on the drawings. If hot-dip galvanizing is the only coating required, no further information is required to be submitted; (b) type of coatings; (c) name of paint manufacturer; (d) product names of paints; (e) technical data sheets and Material Safety Data Sheets (MSDS) for all paints; (f) documentary evidence from the manufacturer certifying compliance of paints with relevant specifications; (g) details of work to be carried out by shop treatment and those to be carried out by field treatment; (h) for field works, details of work methods, containment processes and environment controls; (i) details of solvent cleaning solution and soluble salt removal procedures; (j) abrasive to be used for abrasive blast cleaning; (k) analysis certificate for non-metallic abrasives; and (l) paint application conditions, including but not limited to - (i) the maximum and minimum ambient temperature, (ii) the maximum and minimum temperature of surfaces to be painted, (iii) maximum and minimum (if applicable) relative humidity, (iv) minimum difference between temperature of surface to be painted and the dew point, and (v) minimum and/or maximum time between application of successive coats. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, prior to placement of product | HP | Nominated Authority | Conqa HP Release
3 | Preliminaries - Procedures
3.1 | Fabrication and welding | Section 630.03 AS/NZS 5131 | The fabrication and welding procedures, and ITPs shall be submitted to the Superintendent one month prior to fabrication. Attach: Subcontractor Fabrication and welding ITP and Procedures Enter: Teambinder Approval number [free text box] | Document Review | 1 month prior to installation | HP | Nominated Authority | Conqa HP Release
3.2 | Weld Repairing of Steel | Section 630.07 | The use of any weld repaired steel, including welding to make up member length, shall not commence until approval to proceed is given by the Superintendent. | Verbal | Prior to welding | HP | Nominated Authority | Conqa HP Release
3.3 | Non-Destructive and Dimesion Inspections | Section 630.18 | The subcontractor shall submit test certificates for all non-destructive inspections and dimension inspections to the Superintendent for review at least two days prior to the steelwork being transported for protective treatment. Attach: Subcontractor test certificates for all non-destructive and dimesion inspection. Enter: Teambinder Approval number [free text box] | Document Review | 2 days prior to protective treatment | HP | Nominated Authority | Conqa HP Release
3.4 | Handling, Transport and Erection of Structural Steel Element | Section 630.09 AS/NZS 5131 | Methods of handling, transporting and erection of the steelwork shall be such that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations. An installation methodology and ITP in accordance with AS 5131 shall be submitted one (1) month prior to installation. As a minimum, the installation methodology shall include the following procedures below, when appropriate: (a) Lifting procedures for each component; transport to and handling on site (b) Bolt tightening procedures for snug tight bolting (c) Procedures for grouting of base plates (d) Procedures for ensuring that components are erected in the correct sequence and position. Attach: Subcontractor Installation ITP and Procedures Enter: Teambinder Approval number [free text box] | Document Review | 1 month prior to installation | HP | Nominated Authority | Conqa HP Release
4 | Preliminaries - Fabrication Documentation
4.1 | Steel Fabrication Certification | Section 630.03 AS/NZS 5131 | Details of the steel fabrication, including the appropriate certifications and any arrangements where the fabrication of steelwork is further subcontracted to a third party certified fabricator, must be submitted to the superintendant, at least 14 days prior to commencement of fabrication of steelwork. The Contractor shall submit evidence of certification of the steel fabricator to: (a) Construction Category CC2, CC3 or CC4 of AS/NZS 5131, as applicable to the works or to parts of the works, and (b) AS/NZS ISO 3834.2 for work requiring Construction Category CC3 or CC4; or to AS/NZS ISO 3834.3 for work requiring Construction Category CC2. Enter: Teambinder Approval number [free text box] | Document Review | 14 Days prior to fabrication | HP | Nominated Authority | Conqa HP Release
4.2 | Shop Drawing Verification | Section 630.04 | Prior to fabrication, the shop drawings shall be reviewed by a competent Structural Steel Designer to verify that the critical to quality requirements are complied with and that the design intent is achieved. Evidence of this review and the competency of the reviewer shall be submitted to the Superintendent prior to fabrication. Enter: Teambinder Approval number [free text box] | Document Review | Prior to fabrication | HP | Nominated Authority | Conqa HP Release
4.3 | Cambering, Straightening and Forms | Section 630.11 | The work instruction for cambering, straightening or forming, as appropriate shall be submitted to the Superintendent for review at least seven working days prior to commencement of these activities. Enter: Teambinder Approval number [free text box] | Document Review | 7 working days prior to activity | HP | Nominated Authority | Conqa HP Release
4.4 | Welding Procedure Qualification | Section 630.14 AS 2205.5.1 | Documentary evidence of the results of welding procedure testing, assessment against the acceptance criteria, and an approved Welding Procedure Specification (WPS and PQR) for each of the weld procedures to be used in the welding of the steelwork shall be submitted to the Superintendent for review at least five working days prior to commencement of welding. A photograph of the etched surface of all weld macro-tests, to AS 2205.5.1, at a magnification of x1, or greater, shall be submitted to the Superintendent with the test results. Enter: Teambinder Approval number [free text box] | Document Review | 5 days prior to welding | HP | Nominated Authority | Conqa HP Release
4.5 | Welding Operator Qualification | Section 630.15 | Documentary evidence of welding operator qualification through testing or assessment for each of the welding procedures to be used in the welding of the steelwork shall be submitted to the Superintendent for review at least five working days prior to commencement of welding. Enter: Teambinder Approval number [free text box] | Document Review | 5 days prior to welding | HP | Nominated Authority | Conqa HP Release
4.6 | Steel Fastening Procedure | Section 630.20 Section 630.21 AS/NZS 5131 | The Contractor shall submit to the Superintendent the bolt manufacturer’s Certificate of Product Compliance and all related test certificates demonstrating compliance of the supplied bolt assemblies to the relevant bolt product standards: AS/NZS 1252.1, AS 1110.1, AS 1110.2 and AS 1112.1, as appropriate , and including assembly testing to AS/NZS 1252.1 when appropriate. The test certificates shall be related to the bolts by manufacturer or supplier, batch and heat number, and manufacturing lot number. A documented work method statement (WMS) shall be prepared for each bolting operation. The bolting WMS shall include: i. The fastener requirements ii. The results of slip factor testing for high friction joints iii. A snug-tightening sequence iv. A high-friction tensioning sequence when appropriate v. Processes for assessment against the acceptance criteria vi. When appropriate, the specific requirements for use of direct tension. The bolting WMS for each of the procedures to be used in the bolting of the steelwork shall be submitted to the Superintendent for review at least five working days prior to commencement of bolting. Approval to use direct-tension indicator devices shall be obtained from the Superintendent at least 14 days prior to the use of such devices on bolting on the steelwork, and shall be used in accordance to manufacturer's instructions and AS/NZS5131 Enter: Teambinder Approval number [free text box] | Document Review | 14 days prior to fastening | HP | Nominated Authority | Conqa HP Release
5 | Pre-installation Activities
5.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP Signed Off
5.2 | Materials Inspection Checklist - Steel | IFC Drawings Section 630 | General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion. | Measure Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
5.3 | Materials Inspection Checklist - Fasteners | IFC Drawings Section 630 | Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings. Where bolted faces are sloping at 1:20 or greater, tapered washers must be used. | Measure Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
5.4 | Materials Inspection Checklist - Galvanising | IFC Drawings Section 631 | Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues. | Measure Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
5.5 | Materials Inspection Checklist - Surface Finish | IFC Drawings Section 631 | Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects. | Measure Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
5.6 | Servey Set-out | IFC Drawings | Survey activities undertaken to ensure and validate that all Works meet level and location requirements as per IFC drawings. | Measure Visual | Each component | IP | Surveyor, SE/PE | This ITP Signed Off
5 | Installation Activities
5.1 | Bearing / Mounting Surface Preparation | IFC Drawings Section 630.21c Product TDS | Ensure the bearing surface is clean and free from all oil, dirt, loose scale, loose rust, burrs, fins and any other defects on the surfaces of contact, that will prevent solid seating of the parts in the snug-tight condition. For a friction-type connection, the surfaces shall be clean as-rolled surfaces or equivalent and shall be free from plant, lacquer, glavanizing or other applied finish, unless the applied finish has been tested to establish the riction coefficient or slip factor. | Measure Visual | Where applicable, each installation location | IP | SE/PE/SPE | This ITP Signed Off
5.2 | Structural Steel Handling | Section 630.09 Section 631.14 AS/NZS 5131 | The method of handling, transporting and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations. All installation and erection of steel structures shall comply with the requirements of AS/NZS 5131. | Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
5.3 | Structural Steel Erection | AS4100 AS/NZS 5131 Section 630.12 | Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6. Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable). Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs. Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia | Measure Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
5.4 | Fastener Tightening - Snug Tight Condition | IFC Drawings Section 630.09 Section 630.21 AS/NZS 5131 | Place bolts, washers and nuts as detailed on the IFC Drawings. For posts base plates, the arrangement is to be (from the base plate): - Base Plate - Washer as specified - Lock Nut as specified - Nut - Bolt protrusion (1 clear tread) Washers shall cover the hole or slotted hole completely by 0.5 x holes diameter. Tapered washers shall be positioned as specified. Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm. | Measure Visual | Where applicable, each bolted connection | IP | SE/PE/SPE | This ITP Signed Off
5.5 | Survey Conformance | IFC Drawings AS4100 AS/NZS 5131 | Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below: Departure from RL = -15 mm, +5 mm Departure from plan position = ±6mm Departure from bolt group spacing = ±6mm Bolt group spacings <= 25mm in 30m Projection of bolt = +25mm, -5mm Location of column = ±7mm | Measure Visual | Each element | HP* | SE/PE/SPE Surveyor | This ITP Signed Off
5.6 | Base Plate Formwork Construction & Placement | IFC Drawings | Dimensions as per drawings to achieve the profile. Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks. | Measure Visual | Each post location | IP | SE/PE/SPE | This ITP Signed Off
5.7 | Pre-soaking Concrete Surface for Grout | Product TDS | Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS. Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower. | Visual | Each post location | IP | SE/PE/SPE | This ITP Signed Off
5.8 | Weather Conditions | Section 610.17 VR Table 610.171 | Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected. The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. Record: Required information on the Grout Pour Record. | Measure Visual | Each lot | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.9 | Mixing Product | Product TDS Section 610.28 | Size of mixer should match the application. Only whole bags to be mixed with potable water. Volume of water matches the required amount for flowable consistency and accurately measured. Product poured into the mixer slowly. Mixing time as per TDS so that a smooth, even consistency is obtained. Enter: Required information on the Grout Pour Record. | Measure Visual | Each lot | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.10 | Product Testing - Compressive Strength Cubes | Section 610.28 IFC Drawings | Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products. Testing is to be in accordance with the following frequencies: First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Enter: Required information on the Grout Pour Record. | Test | Each lot | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.11 | Placement & Compaction | Product TDS | All batches are traceable. Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water. Product should flow to all areas and self consolidate. Product that stiffens or is showing signs of stiffening shall not be used. Enter: Required information on the Grout Pour Record | Visual | Each post location | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.12 | Surface Finishes & Protection of Works | IFC Drawings Section 610.17 | If shaping of the unformed surface is required, shape prior to the product fully hardening. All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. | Visual | Where applicable, each post location | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.13 | Curing | Curing Methodology 610.23 Table 610.231 | Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231. Curing methodology to be in accordance with the approved procedure and manufacturer's TDS. | Visual | Where applicable, each post location | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.14 | Architectural Steel Erection | AS4100 Clause 15.2.3 AS/NZS 5131 Clause 11.5.7 630.12 | Place steel component into position, ensuring that it is plumb, level and square Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diamter of the bolts can pass through freely | Measure Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
5.15 | Architectural Steel Erection-Fasteners | IFC Drawings Section VR 630 | Place bolts, washers and nuts as detailed on the IFC Drawings. For architectural/Security screens, the arrangement is to be (from themounting post): - Post - Washer (s) as specified - insulating washer - insulating bush - Insulating washer - washer as specified - Lock nut - Nut - Bolt protrusion (1 clear tread) | Measure Visual | Where applicable, each bolted connection | IP | SE/PE/SPE | This ITP Signed Off
5.16 | Installation of Electrical Isolation Materials | IFC Drawings | Installation of Electrical Isolation Material in locations specified on the IFC drawings (where applicable). | Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
6 | Post-installation Activities
6.1 | Inspection of Coating | IFC Drawings Section 630 | After installation Works are complete, inspect the steel element for damage to the coatings. Where damage exists, it shall be repaired using an approved repair procedure. | Visual | Each component | IP | SE/PE/SPE | This ITP Signed Off
| Structural Steel Components | IFC Drawings MRPA Quality Management Plan Section 630.22 | Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component. Typically this consists of but not limited to: i. Certificate of Compliance ii. Completed Fabrication ITP iii. Weld Procedure Specifications iv. Weld Procedure Qualifications v. Welder Qualifications vi. Material Certificates and traceability vii. Quality Assurance check sheets viii. Welding Consumable batch certificates ix. Coating certificate(s) x. Non-destructive Testing (NDT) Reports xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot. Enter: Teambinder Material Approval number [free text box] | Document Review | Each component | HP | Nominated Authority | Conqa HP Release
6.2 | Compressive Strength Test Results | IFC Drawings Product TDS Section 610 | 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly. 28 day compressive strength per sample comply with the design strength. Attach: Compressive Strength Test Results | Document Review | Each Sample | IP | SE/PE/SPE | This ITP Signed Off
6.3 | As-built Survey | IFC Drawings AS/NZS 5131 | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below: Departure from RL = ±10mm Departure from plan position = ±6mm Departure from alignment = ±6mm Irregularities in alignment = 25mm in 30m Projection of bolt = +25mm, 5mm Location of beam = ±3mm Location of column = height/500, 10mm max. Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP Signed Off
6.4 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /