## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-312-CIV-HOP-ACO Drainage Installation | itp |  |  |  |  | ITP-312-CIV-HOP-ACO Drainage Installation Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-312-CIV-HOP-ACO Drainage Installation
label | ITP Description: HOP-ACO Drainage Installation
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 17/09/2025
label | ITP created by: Christopher Lodge
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - NIST-2659
label | 1.2 - Non Dependent
label | Reference - VicRoads Section 610
label | 1.3 - Non Dependent
label | Reference - VicRoads Section 611
label | 1.4 - Non Dependent
label | Reference - VicRoads Section 612
label | 1.5 - Non Dependent
label | Reference - NIST-012.2.1
label | 1.6 - Non Dependent
label | Reference - VicRoads Section 702
label | 1.7 - Non Dependent
label | Reference - AS 1289
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Concrete Mix (Min 32MPa) - No testing Req.
label | Reference - IFC Drawings 610.07 Table 610.071
label | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
label | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
label | Category - HP*
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
checkpoint | 2.2 - ACRS Certification (for Reinforcement)
label | Reference - 611.05 (a)
label | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
label | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once for each supplier, 14 days of award of contract
label | Category - HP*
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 2.3 - Bar Chairs/Aspros Certification
label | Reference - 610.26 (a)
label | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
label | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
label | Category - WP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 2.4 - ACO Drain and Lid Supply
label | Reference - IFC Drawings
label | Acceptance Criteria - Aco Drain Type: KlassiDrain K300
label | — Linear/Nutral Grade Drain
label | — Depth 300mm (300x325mm)
label | ○ Lid Type: Galvanised Steek Grated
label | ○ Lid Loading Class:
label | — Class B for non trafficable areas
label | — Class D for trafficable Areas
textbox | Enter: Teambinder Material Approval number
label | Method - Document review
label | Frequency - Once, for each product, prior to placement of product
label | Category - HP*
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
checkpoint | 2.5 - Pits and Pit Lids (Class D area's only)
label | Reference - IFC Drawings VicRoads SD1121
label | ○ NIST-2659
label | ○ NIST 012.2.1 Section 6.15-16
label | ○ NIST 012.2.1 Section 6.9
label | ○ NIST 012.2.1 Cl. 6.7 (c)
label | Acceptance Criteria - Pits: located within 1.5m of nearest rail, pit to be 300LA Railway loading
label | ○ Pits 900x900mm or greater, multipart pits lids to be used.
label | ○ Concrete Pits to be made as per AS 3600
label | ○ Pit lids: Covers shall comply with AS3996-2006
label | ○ Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class B
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Where applicable, once, install
label | Category - HP*
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
checkpoint | 2.6 - Bedding & Backfill Material
label | Reference - IFC Drawings NIST-2659 cl6.4.2 & cl6.4.3
label | ○ VicRoads Spec Cl.701.10
label | ○ VicRoads Spec Cl.701.05(b)
label | ○ AS 1289.5 Cl1.1
label | ○ AS 1289.5 Cl3.1
label | ○ AS 1289.5 Cl4.1
label | ○ AS 1289.5 Cl5.1
label | ○ AS 1289.5 Cl6.1
label | Acceptance Criteria - Bedding & backfill material free of rocks that will not pass a 75mm sieve. The material shall be free or organic matter or anything that could damanage the conduits.
label | ○ Nominal agg size 20mm
label | ○ Swell => 2.5%
label | ○ 98% compaction
label | Method - Document Review
label | Frequency - Each Material Type, Each Delivery
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - Attach Material Conformnace Certs, include TB Approval No.
label | ○ Attach delivery dockets
date | Date Completed:
checkpoint | 2.7 - Geotextile
label | Reference - IFC Drawings NIST-2659 cl7.4.2 Table 12
label | Acceptance Criteria - For separation of subgrade and aggregate base a Class 2 geotextile is preferred. Either medium weight non-woven or a 155gsm woven. Minimum permittivity of 0.02 s -1 and maximum EOS of 600 µm.
label | Method - Document Review
label | Frequency - Each Material Type, Each Delivery
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - Attach Material Conformnace Certs, include TB Approval No.
label | ○ Attach delivery dockets
date | Date Completed:
checkpoint | 2.8 - Joint Sealant
label | Reference - IFC Drawings 612.18 ASTM 0262
label | Acceptance Criteria - 10x10mm Joint Sealant (eg Neoprene Compression Seal)
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each Material Type, Each Delivery
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - Attach Material Conformnace Certs, include TB Approval No.
label | ○ Attach delivery dockets
date | Date Completed:
section | 3. Pre-installation Activities
checkpoint | 3.1 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - All
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.2 - Survey Set-out
label | Reference - IFC Drawings NIST-2659 cl6.4.1
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.473 (March/June 2019) as applicable to the element.
label | Method - Measure, Visual
label | Frequency - Prior to Commencing
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.3 - Temporary Drainage Provisions
label | Reference - VicRoads Spec. Cl.703.18
label | Acceptance Criteria - Temporary diversion of drainage to be in place where required.
label | ○ Written approval of from V/Line (SAP) to be provided where diversions are to be installed.
label | Method - Site Inspection
label | Frequency - Where applicable, Prior to Commencing
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Construction / Installation Activities
checkpoint | 4.1 - Trench Excavation
label | Reference - NIST-2659 cl6.4.2 IFC Drawings Section 702.08
label | Acceptance Criteria - Trench shall be excavated to allow for a min of 150mm between each side of the ACO drain
label | ○ The depth of the excavation shall be a min of 225mm below the base of the ACO drain in clay areas and 350mm in rock areas
label | ○ The bottom of the trench shall be compacted
label | ○ There shall be no departures from the grade of the base of the trench that would allow ponding of water.
label | ○ Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
label | Method - Visual
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - SE, NA (Nominated Authority)
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Placement of bedding
label | Reference - 702.09 c)
label | Acceptance Criteria - Bedding of granular filter material of thickness between 75 mm and 200mm placed across bottom of trench and screeded & compactecd to level
label | ○ Place 150mm of bedding under pits
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Placemnt of SL81 Mesh (75mm cover) - Trafficable areas only
label | Reference - IFC Drawings
label | ○ 611.06
label | ○ 611.09
label | ○ 611.10
label | ○ 611.11
label | ○ 611.12
label | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | ○ Splice lengths achieve the minimum length and are in contact for this length.
label | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | Method - Measure, Visual
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.4 - Formwork Design and Construction
label | Reference - IFC Drawings
label | ○ 614.04
label | ○ 614.05
label | ○ 614.06
label | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
label | Method - Document Review, Visual, Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.5 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | Reference - 614.08
label | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | ○ Abutments, pile caps, footings, solid piers, pier columns and walls, with heights less than or equal to 2.0 metres
label | ○ Attach: Attachment C
label | Method - Document Review, Visual, Measure
label | Frequency - Each element (where 2m or less)
label | Category - HP
label | Responsibility - PE/SPE
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6 - Installatrion of Contraction Joints
label | Reference - IFC Drawings
label | Acceptance Criteria - Contraction joints shall be placed at a maximum spacing of 12m and shall comprice of the following:
label | — 10x10 Blockout to be rfilled withapproved joint sealant
label | — R10 x 500mn long gal dowels
label | Method - Visual, Measure
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.7 - Pre-concrete check
label | Reference - VicRoads Spec Cl.703.09, Cl.610.17 (a)(b)(c)(d)
label | Acceptance Criteria - Concrete shall not be placed when the air temperature measured at the point of placement is >35 C or < 5 C.
label | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10 C or greater than 32 C.
label | ○ Unless otherwise specified concrete shall be N32 standard strength.
label | Method - Site Inspection, Temp Varification
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.8 - Concrete Placement
label | Reference - IFC Drawings VicRoads Spec. Cl.610.13(f)
label | Acceptance Criteria - Concrete Strength to be 32MPA as nominated on Drawings;
label | ○ Concrete placed within 60-90 minutes of the commencement of mixing;
label | Method - Site Inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.9 - Concrete Finish
label | Reference - VicRoads Spec. Cl 703.25
label | Acceptance Criteria - Egdings: Rendering shall be applied witihin 30 minutes of placing or extruding concrete. endered to a thickness not exceeding 3mm and steel trowel finished. Footpaths and Surfacing: Use a wooden float for a lightly textured non-skid finish. Concrete to have a neat appearance and uniform colour
label | Method - Site Inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Post-installation Activities
checkpoint | 5.1 - Backfilling
label | Reference - VicRoads Spec. Cl 703.29
label | Acceptance Criteria - As soon as the concrete has cured sufficiently, but not earlier than 3 days after casting. Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging, unless otherwise specified.
label | Method - Site Inspection
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Place ACO Drain
label | Reference - IFC Drawings
label | Acceptance Criteria - Place ACO as per IFC drawing in center of trench and fix in place at 1:300 grade
label | ○ ACO units to be placed flush with adjacent units with slope facing correctly as nominated on drawings.
label | ○ Joints between pits and ACO units to be grouted and watertight.
label | Method - Site Inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.3 - Sealant
label | Reference - IFC Drawings
label | Acceptance Criteria - Remove 10x10mm blockout seal joint with 10x10mm or approved Sealant
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.4 - Connection to Pits and Pit Cover Installation
label | Reference - IFC Drawings NIST-2659
label | Acceptance Criteria - Gap between reinstated pit walls and Aco drain units shall be 20mm with nominated water stop seal as per drawings.
label | Method - Site Inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.5 - As-built Survey
label | Reference - IFC Drawings 610.32
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate Vertical and horizontal alignment between adjacent segments shall not exceed 5mm
label | ○ Attach: Survey As-builts / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.6 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-313-STR-HOP-Steel Structures Installation | itp |  |  |  |  | ITP-313-STR-HOP-Steel Structures Installation Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-313-STR-HOP-Steel Structures Installation
label | ITP Description: Steel Structures Installation
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 12/08/2025
label | ITP created by: Manwel Kalyana
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VR Section 610 Feburary 2020
label | ○ VR Section 630 January 2022
label | ○ VR Section 631 June 2017
label | ○ IFC Drawings AS 1252.1, AS 1110.1, AS 1110.2, AS 1112.1, AS 4100, AS/NZS 5131
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Steel Material Compliance
label | Reference - Section 630.071 IFC Drawing
label | Acceptance Criteria - Steel should demonstrating compliance to the relevant steel product standards listed in Table 630.071, including all impact test values when appropriate.
label | ○ The test certificates shall be related to the steel by trademarks and heat number.
label | ○ Collate: Steel manufacturer’s Certificate of Product Compliance and all related test certificates and upload in a TeamBinder Lot
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product, prior to placement of product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Fasteners
label | Reference - Section 630.21 IFC Drawing
label | ○ AS 1252.1
label | ○ AS 1110.1
label | ○ AS 1110.2
label | ○ AS 1112.1
label | Acceptance Criteria - Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1252.1, AS 1110.1, AS 1110.2 and AS 1112.1
label | ○ Collate: Bolt manufacturer's Certificate of Product Comliance and related documentation and upload in a TeamBinder Lot.
textbox | Enter: Teambinder Material Approval number
label | Method - Document review
label | Frequency - Each component
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Base Plate Structural Grout or Mortar
label | Reference - IFC Drawings Section 610.33
label | Acceptance Criteria - Product to be selected based on the following criteria:
label | i. Shall be self shrinkage compensating proprietary products with a consistancy appropriate for required use as per 610.33
label | ii. Must have a minimum of 28 days compressive strength, of not less than 50MPa as per IFC drawings.
label | iii. Cementeous grouts shall be as a minimum Type C Class dual shrinkage compensating as per 610.33
label | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings
label | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product, prior to placement of product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Surface Finishes
label | Reference - IFC Drawings Section 631.05
label | Acceptance Criteria - At least 14 days prior to commencing the protective treatment of steelwork, the Contractor shall submit to the Superintendent for review the information outline in section 631.05, for all proposed coating system
label | (a) coating system, including hot-dip galvanizing if specified on the drawings. If hot-dip galvanizing is the only coating required, no further information is required to be submitted;
label | (b) type of coatings;
label | (c) name of paint manufacturer;
label | (d) product names of paints;
label | (e) technical data sheets and Material Safety Data Sheets (MSDS) for all paints;
label | (f) documentary evidence from the manufacturer certifying compliance of paints with relevant specifications;
label | (g) details of work to be carried out by shop treatment and those to be carried out by field treatment;
label | (h) for field works, details of work methods, containment processes and environment controls;
label | (i) details of solvent cleaning solution and soluble salt removal procedures;
label | (j) abrasive to be used for abrasive blast cleaning;
label | (k) analysis certificate for non-metallic abrasives; and
label | (l) paint application conditions, including but not limited to -
label | (i) the maximum and minimum ambient temperature,
label | (ii) the maximum and minimum temperature of surfaces to be painted,
label | (iii) maximum and minimum (if applicable) relative humidity,
label | (iv) minimum difference between temperature of surface to be painted and the dew point, and
label | (v) minimum and/or maximum time between application of successive coats.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product, prior to placement of product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures
checkpoint | 3.1 - Fabrication and welding
label | Reference - Section 630.03 AS/NZS 5131
label | Acceptance Criteria - The fabrication and welding procedures, and ITPs shall be submitted to the Superintendent one month prior to fabrication.
label | ○ Attach: Subcontractor Fabrication and welding ITP and Procedures
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 1 month prior to installation
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Weld Repairing of Steel
label | Reference - Section 630.07
label | Acceptance Criteria - The use of any weld repaired steel, including welding to make up member length, shall not commence until approval to proceed is given by the Superintendent.
label | Method - Verbal
label | Frequency - Prior to welding
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Non-Destructive and Dimesion Inspections
label | Reference - Section 630.18
label | Acceptance Criteria - The subcontractor shall submit test certificates for all non-destructive inspections and dimension inspections to the Superintendent for review at least two days prior to the steelwork being transported for protective treatment.
label | ○ Attach: Subcontractor test certificates for all non-destructive and dimesion inspection.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 2 days prior to protective treatment
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Handling, Transport and Erection of Structural Steel Element
label | Reference - Section 630.09 AS/NZS 5131
label | Acceptance Criteria - Methods of handling, transporting and erection of the steelwork shall be such that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | ○ An installation methodology and ITP in accordance with AS 5131 shall be submitted one (1) month prior to installation. As a minimum, the installation methodology shall include the following procedures below, when appropriate:
label | (a) Lifting procedures for each component; transport to and handling on site
label | (b) Bolt tightening procedures for snug tight bolting
label | (c) Procedures for grouting of base plates
label | (d) Procedures for ensuring that components are erected in the correct sequence and position.
label | ○ Attach: Subcontractor Installation ITP and Procedures
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 1 month prior to installation
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Preliminaries - Fabrication Documentation
checkpoint | 4.1 - Steel Fabrication Certification
label | Reference - Section 630.03 AS/NZS 5131
label | Acceptance Criteria - Details of the steel fabrication, including the appropriate certifications and any arrangements where the fabrication of steelwork is further subcontracted to a third party certified fabricator, must be submitted to the superintendant, at least 14 days prior to commencement of fabrication of steelwork.
label | ○ The Contractor shall submit evidence of certification of the steel fabricator to:
label | (a) Construction Category CC2, CC3 or CC4 of AS/NZS 5131, as applicable to the works or to parts of the works, and
label | (b) AS/NZS ISO 3834.2 for work requiring Construction Category CC3 or CC4; or to AS/NZS ISO 3834.3 for work requiring Construction Category CC2.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 14 Days prior to fabrication
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Shop Drawing Verification
label | Reference - Section 630.04
label | Acceptance Criteria - Prior to fabrication, the shop drawings shall be reviewed by a competent Structural Steel Designer to verify that the critical to quality requirements are complied with and that the design intent is achieved. Evidence of this review and the competency of the reviewer shall be submitted to the Superintendent prior to fabrication.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Prior to fabrication
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Cambering, Straightening and Forms
label | Reference - Section 630.11
label | Acceptance Criteria - The work instruction for cambering, straightening or forming, as appropriate shall be submitted to the Superintendent for review at least seven working days prior to commencement of these activities.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 7 working days prior to activity
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Welding Procedure Qualification
label | Reference - Section 630.14 AS 2205.5.1
label | Acceptance Criteria - Documentary evidence of the results of welding procedure testing, assessment against the acceptance criteria, and an approved Welding Procedure Specification (WPS and PQR) for each of the weld procedures to be used in the welding of the steelwork shall be submitted to the Superintendent for review at least five working days prior to commencement of welding.
label | ○ A photograph of the etched surface of all weld macro-tests, to AS 2205.5.1, at a magnification of x1, or greater, shall be submitted to the Superintendent with the test results.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 5 days prior to welding
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Welding Operator Qualification
label | Reference - Section 630.15
label | Acceptance Criteria - Documentary evidence of welding operator qualification through testing or assessment for each of the welding procedures to be used in the welding of the steelwork shall be submitted to the Superintendent for review at least five working days prior to commencement of welding.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 5 days prior to welding
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6 - Steel Fastening Procedure
label | Reference - Section 630.20, Section 630.21 AS/NZS 5131
label | Acceptance Criteria - The Contractor shall submit to the Superintendent the bolt manufacturer’s Certificate of Product Compliance and all related test certificates demonstrating compliance of the supplied bolt assemblies to the relevant bolt product standards: AS/NZS 1252.1, AS 1110.1, AS 1110.2 and AS 1112.1, as appropriate , and including assembly testing to AS/NZS 1252.1 when appropriate.
label | ○ The test certificates shall be related to the bolts by manufacturer or supplier, batch and heat number, and manufacturing lot number.
label | ○ A documented work method statement (WMS) shall be prepared for each bolting operation. The bolting WMS shall include:
label | i. The fastener requirements
label | ii. The results of slip factor testing for high friction joints
label | iii. A snug-tightening sequence
label | iv. A high-friction tensioning sequence when appropriate
label | v. Processes for assessment against the acceptance criteria
label | vi. When appropriate, the specific requirements for use of direct tension.
label | ○ The bolting WMS for each of the procedures to be used in the bolting of the steelwork shall be submitted to the Superintendent for review at least five working days prior to commencement of bolting.
label | ○ Approval to use direct-tension indicator devices shall be obtained from the Superintendent at least 14 days prior to the use of such devices on bolting on the steelwork, and shall be used in accordance to manufacturer's instructions and AS/NZS5131
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 14 days prior to fastening
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 5. Pre-installation Activities
checkpoint | 5.1 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - All
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.2 - Materials Inspection Checklist - Steel
label | Reference - IFC Drawings Section 630
label | Acceptance Criteria - General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.3 - Materials Inspection Checklist - Fasteners
label | Reference - IFC Drawings Section 630
label | Acceptance Criteria - Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | ○ Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.4 - Materials Inspection Checklist - Galvanising
label | Reference - IFC Drawings Section 631
label | Acceptance Criteria - Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.5 - Materials Inspection Checklist - Surface Finish
label | Reference - IFC Drawings Section 631
label | Acceptance Criteria - Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.6 - Servey Set-out
label | Reference - IFC Drawings
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements as per IFC drawings.
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
section | 5. Installation Activities
checkpoint | 5.1 - Bearing / Mounting Surface Preparation
label | Reference - IFC Drawings Section 630.21c Product TDS
label | Acceptance Criteria - Ensure the bearing surface is clean and free from all oil, dirt, loose scale, loose rust, burrs, fins and any other defects on the surfaces of contact, that will prevent solid seating of the parts in the snug-tight condition.
label | ○ For a friction-type connection, the surfaces shall be clean as-rolled surfaces or equivalent and shall be free from plant, lacquer, glavanizing or other applied finish, unless the applied finish has been tested to establish the riction coefficient or slip factor.
label | Method - Measure, Visual
label | Frequency - Where applicable, each installation location
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.2 - Structural Steel Handling
label | Reference - Section 630.09, Section 631.14 AS/NZS 5131
label | Acceptance Criteria - The method of handling, transporting and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | ○ All installation and erection of steel structures shall comply with the requirements of AS/NZS 5131.
label | Method - Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.3 - Structural Steel Erection
label | Reference - AS4100, AS/NZS 5131 Section 630.12
label | Acceptance Criteria - Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
label | ○ Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
label | ○ Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs.
label | ○ Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm
label | ○ Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.4 - Fastener Tightening - Snug Tight Condition
label | Reference - IFC Drawings Section 630.09, Section 630.21 AS/NZS 5131
label | Acceptance Criteria - Place bolts, washers and nuts as detailed on the IFC Drawings.
label | ○ For posts base plates, the arrangement is to be (from the base plate):
label | — Base Plate
label | — Washer as specified
label | — Lock Nut as specified
label | — Nut
label | — Bolt protrusion (1 clear tread)
label | ○ Washers shall cover the hole or slotted hole completely by 0.5 x holes diameter.
label | ○ Tapered washers shall be positioned as specified.
label | ○ Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | Method - Measure, Visual
label | Frequency - Where applicable, each bolted connection
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.5 - Survey Conformance
label | Reference - IFC Drawings AS4100 AS/NZS 5131
label | Acceptance Criteria - Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below:
label | ○ Departure from RL = -15 mm, +5 mm
label | ○ Departure from plan position = ±6mm
label | ○ Departure from bolt group spacing = ±6mm
label | ○ Bolt group spacings <= 25mm in 30m
label | ○ Projection of bolt = +25mm, -5mm
label | ○ Location of column = ±7mm
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - HP*
label | Responsibility - SE/PE/SPE, Surveyor
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.6 - Base Plate Formwork Construction & Placement
label | Reference - IFC Drawings
label | Acceptance Criteria - Dimensions as per drawings to achieve the profile. Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
label | Method - Measure, Visual
label | Frequency - Each post location
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.7 - Pre-soaking Concrete Surface for Grout
label | Reference - Product TDS
label | Acceptance Criteria - Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
label | ○ Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
label | Method - Visual
label | Frequency - Each post location
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.8 - Weather Conditions
label | Reference - Section 610.17, VR Table 610.171
label | Acceptance Criteria - Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
label | ○ The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ Record: Required information on the Grout Pour Record.
label | Method - Measure, Visual
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.9 - Mixing Product
label | Reference - Product TDS Section 610.28
label | Acceptance Criteria - Size of mixer should match the application.
label | ○ Only whole bags to be mixed with potable water.
label | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
label | ○ Product poured into the mixer slowly.
label | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
textbox | Enter: Required information on the Grout Pour Record.
label | Method - Measure, Visual
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.10 - Product Testing - Compressive Strength Cubes
label | Reference - Section 610.28 IFC Drawings
label | Acceptance Criteria - Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | ○ Testing is to be in accordance with the following frequencies:
label | — First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | — Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
textbox | Enter: Required information on the Grout Pour Record.
label | Method - Test
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.11 - Placement & Compaction
label | Reference - Product TDS
label | Acceptance Criteria - All batches are traceable.
label | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | ○ Product should flow to all areas and self consolidate.
label | ○ Product that stiffens or is showing signs of stiffening shall not be used.
textbox | Enter: Required information on the Grout Pour Record
label | Method - Visual
label | Frequency - Each post location
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.12 - Surface Finishes & Protection of Works
label | Reference - IFC Drawings Section 610.17
label | Acceptance Criteria - If shaping of the unformed surface is required, shape prior to the product fully hardening.
label | ○ All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | Method - Visual
label | Frequency - Where applicable, each post location
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.13 - Curing
label | Reference - Curing Methodology 610.23 Table 610.231
label | Acceptance Criteria - Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | Method - Visual
label | Frequency - Where applicable, each post location
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.14 - Architectural Steel Erection
label | Reference - AS4100 Clause 15.2.3, AS/NZS 5131 Clause 11.5.7 630.12
label | Acceptance Criteria - Place steel component into position, ensuring that it is plumb, level and square
label | ○ Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diamter of the bolts can pass through freely
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.15 - Architectural Steel Erection-Fasteners
label | Reference - IFC Drawings Section VR 630
label | Acceptance Criteria - Place bolts, washers and nuts as detailed on the IFC Drawings.
label | ○ For architectural/Security screens, the arrangement is to be (from themounting post):
label | — Post
label | — Washer (s) as specified
label | — insulating washer
label | — insulating bush
label | — Insulating washer
label | — washer as specified
label | — Lock nut
label | — Nut
label | — Bolt protrusion (1 clear tread)
label | Method - Measure, Visual
label | Frequency - Where applicable, each bolted connection
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.16 - Installation of Electrical Isolation Materials
label | Reference - IFC Drawings
label | Acceptance Criteria - Installation of Electrical Isolation Material in locations specified on the IFC drawings (where applicable).
label | Method - Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
section | 6. Post-installation Activities
checkpoint | 6.1 - Inspection of Coating
label | Reference - IFC Drawings Section 630
label | Acceptance Criteria - After installation Works are complete, inspect the steel element for damage to the coatings.
label | ○ Where damage exists, it shall be repaired using an approved repair procedure.
label | Method - Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | Structural Steel Components
label | Reference - IFC Drawings MRPA Quality Management Plan Section 630.22
label | Acceptance Criteria - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | ○ Typically this consists of but not limited to:
label | i. Certificate of Compliance
label | ii. Completed Fabrication ITP
label | iii. Weld Procedure Specifications
label | iv. Weld Procedure Qualifications
label | v. Welder Qualifications
label | vi. Material Certificates and traceability
label | vii. Quality Assurance check sheets
label | viii. Welding Consumable batch certificates
label | ix. Coating certificate(s)
label | x. Non-destructive Testing (NDT) Reports
label | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | ○ Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each component
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - Compressive Strength Test Results
label | Reference - IFC Drawings Product TDS Section 610
label | Acceptance Criteria - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength per sample comply with the design strength.
label | ○ Attach: Compressive Strength Test Results
label | Method - Document Review
label | Frequency - Each Sample
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 6.3 - As-built Survey
label | Reference - IFC Drawings AS/NZS 5131
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | ○ Departure from RL = ±10mm
label | ○ Departure from plan position = ±6mm
label | ○ Departure from alignment = ±6mm
label | ○ Irregularities in alignment = 25mm in 30m
label | ○ Projection of bolt = +25mm, 5mm
label | ○ Location of beam = ±3mm
label | ○ Location of column = height/500, 10mm max.
label | ○ Attach: Survey As-builts / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-314-STR-HOP-Concrete Coating (Protective and or Decorative) | itp |  |  |  |  | ITP-314-STR-HOP-Concrete Coating (Protective and or Decorative) Rev 1
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-314-STR-HOP-Concrete Coating (Protective and or Decorative) Rev 1
label | ITP Description: Concrete Coating (Protective and or Decorative) Rev 1
label | Discipline (e.g. CIV/STR/RAIL): 314-STR-HOP
label | Revision Number: 1
label | Revision Date: 3/09/2025
label | ITP created by: Manwel KALYANA
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Standard Section 685
label | 1.2 - Non Dependent
label | Reference - VicRoads Standard Section 686
label | 1.3 - Non Dependent
label | Reference - IFC Drawings
section | 2. Preliminaries
checkpoint | 2.1 - Anti-graffiti System Selection
label | Reference - IFC Drawings, Coating System TDS
label | ○ VicRoads:
label | — Section 685.04
label | — Section 685.06 (a)(b)
label | — Section 686.04
label | — Section 686.05 (a)(e)
label | Acceptance Criteria - The system shall be selected based on the following criteria:
label | i. be either a film-forming or a penetrant system
label | ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification)
label | iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible
label | iv. be non-yellowing, colour-fast and not subject to fading
label | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | vi. application thicknesses (film-forming): WFT total = 175µm min. DFT total = 100µm min. when anti-graffiti coating is also used as anti-carbonation, then DFT total = 150µm min.
label | vii. adhesion to substrate (film-forming): 0.75MPa min.
label | viii. application rate (penetrants) as per the minimum thickness on the manufacturer's TDS
textbox | Enter: TeamBinder Material approval No.
label | Method - Document Review
label | Frequency - Once, for each coating system, 14 days prior to application
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Decorative & Anti-carbonation System Selection
label | Reference - IFC Drawings, Coating System TDS
label | ○ VicRoads:
label | — Section 686.04
label | — Section 686.05 (a)(b)
label | — Table 686.051
label | Acceptance Criteria - The system shall be selected based on the following criteria:
label | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
label | ii. be water or acrylic based, solvent-free with all coats compatible with each other
label | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
label | iv. be non-yellowing, colour-fast and not subject to fading
label | v. be guaranteed to last for 10 years of outdoor exposure
label | vi. application thicknesses: WFT per coat = enough to achieve the total DFT = 150µm min.
label | vii. adhesion to substrate: 0.75MPa min.
label | viii. able to bridge cracks up to 0.3mm wide
label | ix. able to be re-coated within 24 hours
label | x. have a minimum pot life of 1 hour
label | xi. compatibility to an alkaline surface
label | xii. equivalent air thickness >150m, equivalent concrete thickness >450mm, CO2 diffusion coefficient <2 x 10^-7 cm2/s, Water vapour equivalent air layer <4m
textbox | Enter: TeamBinder Material approval No.
label | Method - Document Review
label | Frequency - Once, for each coating system, 21 days prior to application
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Quality Documentation
label | Reference - IFC Drawings, Coating System TDS, Cleaning System TDS
label | ○ VicRoads:
label | — Section 685
label | — Section 686
label | Acceptance Criteria - The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
textbox | Enter: TeamBinder Hold Point Approval No.
label | Method - Document Review
label | Frequency - Once for each coating system
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Personnel & Equipment
label | Reference - IFC Drawings
label | ○ VicRoads:
label | — Section 685.16
label | — Section 686.19
label | Acceptance Criteria - Application personnel and sub-contractors shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques for anti-graffiti coating. For all other coating, Application personnel shall have a minimum of 2 years experience. The supervisor shall have a minimum of 5 years experience and must remain present at all times. Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
label | Method - Document Review
label | Frequency - Once, prior to application
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 2.5 - Protection of Adjacent Works & property
label | Reference - VicRoads:
label | — Section 685.17
label | — Section 686.10
label | Acceptance Criteria - Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes. No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place. Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
label | Method - Visual and Document Review
label | Frequency - Where applicable, 2 days prior to application
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Minimum Concrete Curing Period
label | Reference - VicRoads:
label | — Section 685.08
label | — Section 686.16
label | Acceptance Criteria - Concrete shall not be coated until the minimum concrete curing times have elapsed: Standard cured concrete = 28 days, Accelerated cured concrete = 14 days, Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
label | ○ Note: All durations may be reduced by 50% if the moisture content is less than 10% when measured with a calibrated moisture meter.
label | Method - Visual and Document Review
label | Frequency - Once, prior to application
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Trial Application Inspection
label | Reference - VicRoads:
label | — Section 685.11
label | — Section 686.13
label | Acceptance Criteria - A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate, 14 days prior to the commencement of coating work. Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
textbox | Enter: TeamBinder Hold Point Approval No.
label | Method - Visual and Document Review
label | Frequency - Once for each coating system, 14 days prior to full coating application
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Pre-Application Activities
checkpoint | 3.1 - Material Records
label | Reference - Coating System TDS, Surface Cleaner TDS
label | ○ VicRoads:
label | — Section 685.10
label | — Section 686.12
label | Acceptance Criteria - Materials shall be brought to site in unopened, sealed containers, clearly marked with: the manufacturer's name & address product reference batch number quantity manufactured in the batch date of manufacture
label | ○ Product beyond the manufacturer's shelf life shall not be used. Each product shall be traceable to final location.
label | Method - Visual
label | Frequency - Prior to application
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.2 - Weather Conditions
label | Reference - Coating System TDS, Surface Cleaner TDS
label | ○ VicRoads:
label | — Section 685.09
label | — Section 685.12 (a)
label | — Section 686.11
label | — Section 686.14 (a)(iii)
label | Acceptance Criteria - Coating systems shall not be applied under any of the following conditions:
label | i. windy conditions where spray/splatter may be generated
label | ii. when wind-borne debris is likely to contaminate the uncured surface
label | iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise
label | iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C
label | v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating
label | vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate
label | vii. when the substrate surface is wet or damp (unless it is required for the coating system)
label | ○ Weather conditions are to be recorded.
label | Method - Visual and Measure
label | Frequency - Prior to application and every 4 hours each shift
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.3 - Surface Preparation
label | Reference - Coating System TDS, Surface Cleaner TDS
label | ○ VicRoads:
label | — Section 685.05
label | — Section 686.06
label | Acceptance Criteria - The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means. The surface shall then be flushed with water. Any concrete defects exposed during the surface preparation shall be repaired accordingly.
label | Method - Visual
label | Frequency - Once, prior to application
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.4 - Surface Moisture Testing
label | Reference - VicRoads:
label | — Section 685.12 (a)
label | — Section 686.14 (a)(iii)
label | Acceptance Criteria - The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS. Surface moisture conditions are to be recorded.
label | Method - Test
label | Frequency - Prior to application, test 1m2
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Application Activities
checkpoint | 4.1 - Method of Application
label | Reference - Coating System TDS, Surface Cleaner TDS
label | ○ VicRoads:
label | — Section 685.07
label | — Section 686.07
label | — Section 686.09
label | Acceptance Criteria - Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved. Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified. For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application. Times of coating(s), material names, locations coated and volumes used shall be recorded.
label | Method - Visual and Measure
label | Frequency - Each coat
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Inspection & Defect Identification
label | Reference - VicRoads:
label | — Section 685.07
label | — Section 685.13 (d)
label | — Section 686.07
label | — Section 686.15
label | Acceptance Criteria - The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats. Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
label | Method - Visual
label | Frequency - After each coat
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Drying & Curing
label | Reference - Coating System TDS
label | ○ VicRoads:
label | — Section 685.17
label | — Section 686.09
label | Acceptance Criteria - Coatings shall be protected from adverse conditions, dust and debris during the curing period.
label | Method - Visual
label | Frequency - After each coat
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Post-application Activities
checkpoint | 5.1 - Clean-up & Waste Disposal
label | Reference - VicRoads:
label | — Section 685.07 (c)
label | — Section 686.10
label | Acceptance Criteria - All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated. All rubbish and remaining coating products shall be removed from site.
label | Method - Visual
label | Frequency - At completion of works
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Wet Film Thickness Testing
label | Reference - Coating System TDS
label | ○ VicRoads:
label | — Section 685.12 (b)(ii)
label | — Section 686.14 (b)(ii)
label | Acceptance Criteria - Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
label | ○ Attach: WFT Test Results
label | Method - Test
label | Frequency - Where applicable, 3 no. tests every 50m2 or part thereof
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.3 - Dry-Film Thickness Testing
label | Reference - VicRoads:
label | — Section 685.12 (b)(iii)
label | — Section 686.14 (b)(iii)
label | Acceptance Criteria - At least three tests for each of bond strength, WFT and DFT and amount of penetration of anti-graffiti penetrant shall be carried out after the application of materials to demonstrate compliance
label | ○ The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses: i. Anti-graffiti system = 100µm Ii. Decorative & anti-carbonation = 150µm iii. Decorative, anti-carbonation & anti-graffiti = 150µm iv. Atmospheric & splash zone (dual protective) = 200µm
label | ○ No more than 15% of the readings shall be less than 90% of the required thickness.
label | ○ Attach: DFT Test Results
label | Method - Test
label | Frequency - Where applicable, 3 no. tests every 50m2 or part thereof
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.4 - Adhesion Bond Strength Testing
label | Reference - VicRoads:
label | — Section 685.12 (b)(i)
label | — Section 686.14 (b)(i)
label | Acceptance Criteria - At least three tests for each of bond strength, WFT and DFT and amount of penetration of anti-graffiti penetrant shall be carried out after the application of materials to demonstrate compliance
label | ○ A minimum of 14 days after application, the bond-strengths between: i. the coating system to the substrate, and ii. Separate coating layers shall be tested using 50mmØ aluminium dollies. The subsequent results shall be greater than 0.75MPa.
label | ○ Attach: Adhesive Bond Strength Testing Results
label | Method - Test
label | Frequency - Where applicable, 3 no. tests every 50m2 or part thereof
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.5 - Penetration Depth Testing
label | Reference - VicRoads:
label | — Section 685.12 (b)(v)
label | — Section 686.14 (b)(v)
label | Acceptance Criteria - At least three tests for each of bond strength, WFT and DFT and amount of penetration of anti-graffiti penetrant shall be carried out after the application of materials to demonstrate compliance
label | ○ Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration. The subsequent results shall be: i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible) ii. Silane, Solid Silane or Silane Cream = 5mm min. iii. Silane-Siloxane or Siloxane = 3mm min.
label | ○ Attach: Penetration Depth Testing Results
label | Method - Test
label | Frequency - Where applicable, 3 no. tests every 50m2 or part thereof
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.6 - Non-conforming Coatings
label | Reference - VicRoads:
label | — Section 685.14
label | — Section 686.17
label | Acceptance Criteria - Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired. Such Work may include removal of the coating, surface preparation and re-application. Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
label | Method - Visual
label | Frequency - Where required
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.7 - Coating Application Guarantee
label | Reference - VicRoads:
label | — Section 685.06 (b)
label | — Section 686.05 (a)
label | Acceptance Criteria - Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
label | ○ Attach: Coating Application Guarantee
label | Method - Document Review
label | Frequency - At completion of works
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.8 - Repair to Damaged Coating
label | Reference - VicRoads:
label | — Section 686.17
label | Acceptance Criteria - Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
label | Method - Visual
label | Frequency - Where required
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.9 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP