## Sheet1
Geometric Design | Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual | Principal Approval | Contractor and Principal peer review | per design revision | — | — | C or S | — | C | E | Y | — | Geometric Design | Controlling Documents - Austroads Guide to Road Design Part 3: Geometric Design, TNZ State Highway Geometric Design Manual | Acceptance Criteria - Principal Approval | Inspection or Test: Method - Contractor and Principal peer review | Inspection or Test: Frequency - per design revision | Inspection or Test: Responsible Person - — | Verifying Document - — | Inspection / Test Authority: Conduct - C or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - E | Hold Point - Y | Witness Point - — | Source Property -Coarse Aggregate - Crushing Resistance
Pavement Treatment Design | Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2) | Principal Approval | Contractor and Principal peer review | per design | — | Pavement Rehabilitation Design Report | C or S | — | C | E | Y | — | Pavement Treatment Design | Controlling Documents - Austroads Guide to Pavement Technology, New Zealand Guide to Pavement Evaluation and Treatment Design:2018 (Version 1.2) | Acceptance Criteria - Principal Approval | Inspection or Test: Method - Contractor and Principal peer review | Inspection or Test: Frequency - per design | Inspection or Test: Responsible Person - — | Verifying Document - Pavement Rehabilitation Design Report | Inspection / Test Authority: Conduct - C or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - E | Hold Point - Y | Witness Point - — | Controlling Documents - TNZ M6, RNZ 9805:2009
Aggregate Sampling | NZS 4407:2015, WSP Rotorua Sampling Guide | — | — | — | — | Sampling Worksheet | C or S | — | — | S | Y | — | Aggregate Sampling | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide | Acceptance Criteria - — | Inspection or Test: Method - — | Inspection or Test: Frequency - — | Inspection or Test: Responsible Person - — | Verifying Document - Sampling Worksheet | Inspection / Test Authority: Conduct - C or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - — | Inspection / Test Authority: Approval - S | Hold Point - Y | Witness Point - — | Acceptance Criteria - CHAR(LESS)10% fines under 230kN minimum
Source Property Test | CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Soaked CBR ≥ 40 | Soaked CBR test (NZS:4407:2015:3.15) | — | Supervisor | Test Report | Sp or C or S | — | Sp or S | E | Y | — | Source Property Test | Controlling Documents - CBR - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Acceptance Criteria - Soaked CBR ≥ 40 | Inspection or Test: Method - Soaked CBR test (NZS:4407:2015:3.15) | Inspection or Test: Frequency - — | Inspection or Test: Responsible Person - Supervisor | Verifying Document - Test Report | Inspection / Test Authority: Conduct - Sp or C or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - Sp or S | Inspection / Test Authority: Approval - E | Hold Point - Y | Witness Point - — | Inspection or Test: Method - Sample Test - Crushing Resistance NZS 4407 Test 3.10
Production Property Test | Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Sand Equivalent >35, OR CHAR(LESS)35 but well graded with no more than 10% by mass passing through a 0.425mm sieve | Sand Equivalent Test (NZS:4407:2015, 3.6) | — | Supervisor | Test Report | Sp or C or S | — | Sp or S | E | Y | — | Production Property Test | Controlling Documents - Sand Equivalent - BOPE NOC Contract Documents Maintenance Specification Section 2.5.3 | Acceptance Criteria - Sand Equivalent >35, OR CHAR(LESS)35 but well graded with no more than 10% by mass passing through a 0.425mm sieve | Inspection or Test: Method - Sand Equivalent Test (NZS:4407:2015, 3.6) | Inspection or Test: Frequency - — | Inspection or Test: Responsible Person - Supervisor | Verifying Document - Test Report | Inspection / Test Authority: Conduct - Sp or C or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - Sp or S | Inspection / Test Authority: Approval - E | Hold Point - Y | Witness Point - — | Inspection or Test: Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
Aggregate Sampling | NZS 4407:2015, WSP Rotorua Sampling Guide | — | — | — | — | Sampling Worksheet | — | — | — | — | — | — | Aggregate Sampling | Controlling Documents - NZS 4407:2015, WSP Rotorua Sampling Guide | Acceptance Criteria - — | Inspection or Test: Method - — | Inspection or Test: Frequency - — | Inspection or Test: Responsible Person - — | Verifying Document - Sampling Worksheet | Inspection / Test Authority: Conduct - — | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - — | Inspection / Test Authority: Approval - — | Hold Point - — | Witness Point - — | Inspection or Test: Responsible Person - Surfacing Project Manager
Source Property Test (1) | Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test) | less than 10% fines passing 2.36mm sieve size under a load of 130kN | Curshing Resistance Test (NZS 4407:1991, Test 3.10) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S | — | Sp or S | E | Y | — | Source Property Test (1) | Controlling Documents - Crushing Resistance (3.3.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.10 (The Crushing Resistance Test) | Acceptance Criteria - less than 10% fines passing 2.36mm sieve size under a load of 130kN | Inspection or Test: Method - Curshing Resistance Test (NZS 4407:1991, Test 3.10) | Inspection or Test: Frequency - One test for every 10,000m³ of source material | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Test Report | Inspection / Test Authority: Conduct - Sp or C or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - Sp or S | Inspection / Test Authority: Approval - E | Hold Point - Y | Witness Point - — | Verifying Document - IANZ Report's
Source Property Test (2) | Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test) | AA, AB, AC, BA, BB or CA | Weathering Quality Index Test (NZS 4407: 1991, Test 3.11) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S | — | Sp or S | E | Y | — | Source Property Test (2) | Controlling Documents - Weathering Quality Index (3.3.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.11 (Weathering Quality Index Test) | Acceptance Criteria - AA, AB, AC, BA, BB or CA | Inspection or Test: Method - Weathering Quality Index Test (NZS 4407: 1991, Test 3.11) | Inspection or Test: Frequency - One test for every 10,000m³ of source material | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Test Report | Inspection / Test Authority: Conduct - Sp or C or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - Sp or S | Inspection / Test Authority: Approval - E | Hold Point - Y | Witness Point - — | Inspection / Test Authority: Conduct - C
Source Property Test (3) | California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test) | Soaked CBR ≥ 80% | California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | One test for every 10,000m³ of source material | Quality Controller | Test Report | Sp or C or S | — | Sp or S | E | Y | — | Source Property Test (3) | Controlling Documents - California Bearing Ratio (3.3.3) - TNZ M/4: 2006, NZS 4402: 1986 Test 4.1.3, NZS 4407: 1991 Test 3.15 (California Bearing Ratio Test) | Acceptance Criteria - Soaked CBR ≥ 80% | Inspection or Test: Method - California Bearing Ratio Test (NZS 4407: 1991, Test 3.15) after being compacted according to Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | Inspection or Test: Frequency - One test for every 10,000m³ of source material | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Test Report | Inspection / Test Authority: Conduct - Sp or C or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - Sp or S | Inspection / Test Authority: Approval - E | Hold Point - Y | Witness Point - — | Inspection / Test Authority: Witness - —
Production Property Test (1) | Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4 | Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5 | Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S | — | Sp or S | E | Y | — | Production Property Test (1) | Controlling Documents - Sand Equivalent (4.2.1.1) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.6 or Clay Index (4.2.1.2) - TNZ M/4: 2006, NZS 4407: 1991, Test 3.5 or Plasticity Index (4.2.1.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.4 | Acceptance Criteria - Sand Equivalent ≥40; or Clay Index ≤3; or Plasticity Index ≤5 | Inspection or Test: Method - Sand Equivalent Test (NZS:4407:2015, 3.6); or Clay Index Test (NZS:4407: 1991, 3.5); or Plasticity Index Test (NZS 4407:1991, 3.4) | Inspection or Test: Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Test Report | Inspection / Test Authority: Conduct - Sp or C or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - Sp or S | Inspection / Test Authority: Approval - E | Hold Point - Y | Witness Point - — | Inspection / Test Authority: Produce Record - C
Production Property Test (2) | Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14 | Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces | Broken Face Test (NZS:4407: 1991, Test 3.4) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S | — | Sp or S | E | Y | — | Production Property Test (2) | Controlling Documents - Broken Face Content (4.2.2) - TNZ M/4: 2006, NZS:4407: 1991 Test 3.14 | Acceptance Criteria - Broken Face Content ≥70% between 37.5mm and 4.75mm sieve and ≥2 broken faces | Inspection or Test: Method - Broken Face Test (NZS:4407: 1991, Test 3.4) | Inspection or Test: Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Test Report | Inspection / Test Authority: Conduct - Sp or C or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - Sp or S | Inspection / Test Authority: Approval - E | Hold Point - Y | Witness Point - — | Inspection / Test Authority: Approval - N
Production Property Test (3) | Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test) | Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution | Wet Sieving Test (NZS 4407: 1991, Test 3.8.1) | 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Quality Controller | Test Report | Sp or C or S | — | Sp or S | E | Y | — | Production Property Test (3) | Controlling Documents - Particle Size Distribution (4.2.3) - TNZ M/4: 2006, NZS 4407: 1991 Test 3.8.1 (Wet Sieving Test) | Acceptance Criteria - Particle size distribution as per Table 2 and Table 3, 4.2.3 Particle Size Distribution | Inspection or Test: Method - Wet Sieving Test (NZS 4407: 1991, Test 3.8.1) | Inspection or Test: Frequency - 2 Samples required as per Table 1, Production Property Test Sampling (4.1) - TNZ M/4: 2006 | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Test Report | Inspection / Test Authority: Conduct - Sp or C or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - Sp or S | Inspection / Test Authority: Approval - E | Hold Point - Y | Witness Point - — | Hold Point - Y
Stabilising Agent Selection | Cement (4.1.2) - TNZ B/5: 2008 | GP | Visual inspection of supplier docket | per truck load | Quality Controller | Supplier Docket Supplier Cert | Sp or S | — | Sp or S | C | Y | — | Stabilising Agent Selection | Controlling Documents - Cement (4.1.2) - TNZ B/5: 2008 | Acceptance Criteria - GP | Inspection or Test: Method - Visual inspection of supplier docket | Inspection or Test: Frequency - per truck load | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Supplier Docket Supplier Cert | Inspection / Test Authority: Conduct - Sp or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - Sp or S | Inspection / Test Authority: Approval - C | Hold Point - Y | Witness Point - — | Witness Point - Y
Water draw for stabilising | Water (5.0.0) - TNZ B/5: 2008 | Free from impurities justified by use of municipal water supply | Visual inspection | per truck load | Quality Controller | Hydrant use form | Sp or S | — | Sp or S | C | Y | — | Water draw for stabilising | Controlling Documents - Water (5.0.0) - TNZ B/5: 2008 | Acceptance Criteria - Free from impurities justified by use of municipal water supply | Inspection or Test: Method - Visual inspection | Inspection or Test: Frequency - per truck load | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Hydrant use form | Inspection / Test Authority: Conduct - Sp or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - Sp or S | Inspection / Test Authority: Approval - C | Hold Point - Y | Witness Point - — | Source Property -Coarse Aggregate - Weathering Resistance
Geotextile (Strength Class C) A29 or greater | TNZ F7 Specification | Details on Docket | Visual inspection | Per Delivery | Quality Controller | MDS | Sp or S | — | Sp or S | C | Y | — | Geotextile (Strength Class C) A29 or greater | Controlling Documents - TNZ F7 Specification | Acceptance Criteria - Details on Docket | Inspection or Test: Method - Visual inspection | Inspection or Test: Frequency - Per Delivery | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - MDS | Inspection / Test Authority: Conduct - Sp or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - Sp or S | Inspection / Test Authority: Approval - C | Hold Point - Y | Witness Point - — | Controlling Documents - TNZ M6, RNZ 9805:2009
Production Testing of stabilised material - OMC/MDD | TNZ B/5 section 7.5 CHAR(AMP) 7.7.1 | To obtain OMC CHAR(AMP) MDD | NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test. | Once on commencement and then each stablilised layer at one test per 5000m2 | Quality Controller | Test report | C | C | C | — | — | Y | Production Testing of stabilised material - OMC/MDD | Controlling Documents - TNZ B/5 section 7.5 CHAR(AMP) 7.7.1 | Acceptance Criteria - To obtain OMC CHAR(AMP) MDD | Inspection or Test: Method - NZS 4402, test 4.1.3, New Zealand vibrating hammer compaction test. | Inspection or Test: Frequency - Once on commencement and then each stablilised layer at one test per 5000m2 | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Test report | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - C | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - — | Hold Point - — | Witness Point - Y | Acceptance Criteria - AA or BA
Production Testing of stabilised material - Solid Density | TNZ B/5 section 7.7 | For info. and use in MDD calculation | NZS 4407; test 3.7.1 | Once on commencement and if any materials change | Quality Controller | Test report | C | C | C | — | — | Y | Production Testing of stabilised material - Solid Density | Controlling Documents - TNZ B/5 section 7.7 | Acceptance Criteria - For info. and use in MDD calculation | Inspection or Test: Method - NZS 4407; test 3.7.1 | Inspection or Test: Frequency - Once on commencement and if any materials change | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Test report | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - C | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - — | Hold Point - — | Witness Point - Y | Inspection or Test: Method - Weathering Quality Index NZS 4407 Test 3.10
Project survey setting out | Reference from Project Drawings | — | Survey/Mobile Roads, Marks with Dazzle | Chainages for every different pavement sections | Subcontractor/ Engineer | Construction drawings | C | — | C | — | — | Y | Project survey setting out | Controlling Documents - Reference from Project Drawings | Acceptance Criteria - — | Inspection or Test: Method - Survey/Mobile Roads, Marks with Dazzle | Inspection or Test: Frequency - Chainages for every different pavement sections | Inspection or Test: Responsible Person - Subcontractor/ Engineer | Verifying Document - Construction drawings | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - — | Hold Point - — | Witness Point - Y | Inspection or Test: Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum
Pre-treatment Repair Method Selection | Site specifics to be confirmed | Confirm scala acceptance criteria based on treatment type | Scala Penetrometer on Excavation Floor | As required | Quality Controller | Agreed treatment plan | S | C | S | E | — | Y | Pre-treatment Repair Method Selection | Controlling Documents - Site specifics to be confirmed | Acceptance Criteria - Confirm scala acceptance criteria based on treatment type | Inspection or Test: Method - Scala Penetrometer on Excavation Floor | Inspection or Test: Frequency - As required | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Agreed treatment plan | Inspection / Test Authority: Conduct - S | Inspection / Test Authority: Witness - C | Inspection / Test Authority: Produce Record - S | Inspection / Test Authority: Approval - E | Hold Point - — | Witness Point - Y | Inspection or Test: Responsible Person - Surfacing Project Manager
Digout of Patches to repair | Higgins SOP 0128 - Digout Repair | 250mm deep unless specified | Visual inspection | As required | Quality Controller | Dig out site records/ Asbuilt | S | C | S | C | — | Y | Digout of Patches to repair | Controlling Documents - Higgins SOP 0128 - Digout Repair | Acceptance Criteria - 250mm deep unless specified | Inspection or Test: Method - Visual inspection | Inspection or Test: Frequency - As required | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Dig out site records/ Asbuilt | Inspection / Test Authority: Conduct - S | Inspection / Test Authority: Witness - C | Inspection / Test Authority: Produce Record - S | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Verifying Document - IANZ Report's
Subgrade material hardness Check base of excavation | Higgins SOP 0128 - Digout Repair | Scala > 3 blows per 100mm | Scala Penetrometer test on base of digout | As required depending on size of digout | Quality Controller | Test report | S/C | C | S/C | E | — | Y | Subgrade material hardness Check base of excavation | Controlling Documents - Higgins SOP 0128 - Digout Repair | Acceptance Criteria - Scala > 3 blows per 100mm | Inspection or Test: Method - Scala Penetrometer test on base of digout | Inspection or Test: Frequency - As required depending on size of digout | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Test report | Inspection / Test Authority: Conduct - S/C | Inspection / Test Authority: Witness - C | Inspection / Test Authority: Produce Record - S/C | Inspection / Test Authority: Approval - E | Hold Point - — | Witness Point - Y | Inspection / Test Authority: Conduct - C
Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd) | TNZ F7 Specification | Meet TNZ F7 Spec. | Visual inspection | Per Delivery | Quality Controller | Certificate of conformance | Sp or S | — | C | C | — | Y | Geotextile (Strength Class C = A29) Layer beneath treatment layer (if rqd) | Controlling Documents - TNZ F7 Specification | Acceptance Criteria - Meet TNZ F7 Spec. | Inspection or Test: Method - Visual inspection | Inspection or Test: Frequency - Per Delivery | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Certificate of conformance | Inspection / Test Authority: Conduct - Sp or S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Inspection / Test Authority: Witness - —
Place and compact GAP65 in digout area | Higgins SOP 0128 - Digout Repair | Clegg value > 45 | Clegg Test | Min. 2 per digout | Quality Controller | Test report | S/C | C | S/C | E | — | Y | Place and compact GAP65 in digout area | Controlling Documents - Higgins SOP 0128 - Digout Repair | Acceptance Criteria - Clegg value > 45 | Inspection or Test: Method - Clegg Test | Inspection or Test: Frequency - Min. 2 per digout | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Test report | Inspection / Test Authority: Conduct - S/C | Inspection / Test Authority: Witness - C | Inspection / Test Authority: Produce Record - S/C | Inspection / Test Authority: Approval - E | Hold Point - — | Witness Point - Y | Inspection / Test Authority: Produce Record - C
Place M/4 AP40 Basecourse Material | TNZ B/5 (section 7) | Evenly spread, no segregation, placed near optimium moisture content | Visual Inspection | On completion of placement | Quality Controller | Photographs and Daily Site Record | S or C | — | S or C | C | — | Y | Place M/4 AP40 Basecourse Material | Controlling Documents - TNZ B/5 (section 7) | Acceptance Criteria - Evenly spread, no segregation, placed near optimium moisture content | Inspection or Test: Method - Visual Inspection | Inspection or Test: Frequency - On completion of placement | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Photographs and Daily Site Record | Inspection / Test Authority: Conduct - S or C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - S or C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Inspection / Test Authority: Approval - N
Spreading of Cement | Spreading of Cement (7.3) - TNZ B/5: 2008 | Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate | Mat test (1m² canvas) and Average Usage Test | per 400m² and upon emptying the spreader | Quality Controller | Mat Test Form and truck dockets | S or Sp | C | S | E | — | Y | Spreading of Cement | Controlling Documents - Spreading of Cement (7.3) - TNZ B/5: 2008 | Acceptance Criteria - Within ± 0.5 kg/m² of the specified rate and within ± 2.5% of the specified rate | Inspection or Test: Method - Mat test (1m² canvas) and Average Usage Test | Inspection or Test: Frequency - per 400m² and upon emptying the spreader | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Mat Test Form and truck dockets | Inspection / Test Authority: Conduct - S or Sp | Inspection / Test Authority: Witness - C | Inspection / Test Authority: Produce Record - S | Inspection / Test Authority: Approval - E | Hold Point - — | Witness Point - Y | Hold Point - Y
Addition of Water | Addition of Water (7.5) - TNZ B/5: 2008 | 90-100% OWC | Nuclear Densometer Testing prior to Stabilisation | ≥1 per 1000m² lot | Quality Controller | NDM Record | S | — | S | C | — | Y | Addition of Water | Controlling Documents - Addition of Water (7.5) - TNZ B/5: 2008 | Acceptance Criteria - 90-100% OWC | Inspection or Test: Method - Nuclear Densometer Testing prior to Stabilisation | Inspection or Test: Frequency - ≥1 per 1000m² lot | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - NDM Record | Inspection / Test Authority: Conduct - S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - S | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Witness Point - Y
Cut Depth | Control of cut depth (7.6.1) - TNZ B/5: 2008 | -5mm and +15mm of design stab depth | Physical Measure and Visual Record | ≥1 per 200m of cut length | Quality Controller | Photographs and Daily Site Record | S | — | S | C | — | Y | Cut Depth | Controlling Documents - Control of cut depth (7.6.1) - TNZ B/5: 2008 | Acceptance Criteria - -5mm and +15mm of design stab depth | Inspection or Test: Method - Physical Measure and Visual Record | Inspection or Test: Frequency - ≥1 per 200m of cut length | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Photographs and Daily Site Record | Inspection / Test Authority: Conduct - S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - S | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Source Property - Skid Resistance
Longitudinal Joints | Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008 | The minimum of 100mm or half the layer thickness | Visual Record | per sucessive cut | Quality Controller | Photographs, Daily Site Record and Stabilising Plan | S | — | S | C | — | Y | Longitudinal Joints | Controlling Documents - Overlap on longitudinal joints (7.6.2) - TNZ B/5: 2008 | Acceptance Criteria - The minimum of 100mm or half the layer thickness | Inspection or Test: Method - Visual Record | Inspection or Test: Frequency - per sucessive cut | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Photographs, Daily Site Record and Stabilising Plan | Inspection / Test Authority: Conduct - S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - S | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Controlling Documents - NZTA T/10
Continuity of Layer | Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008 | Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents | Visual Record | per sucessive cut | Quality Controller | Photographs, Daily Site Record and Stabilising Plan | S | — | S | C | — | Y | Continuity of Layer | Controlling Documents - Continuity of stabilised layer (7.6.3) - TNZ B/5: 2008 | Acceptance Criteria - Longitudinal overlap 1m for cement, 5m for bituminous stabilising agents | Inspection or Test: Method - Visual Record | Inspection or Test: Frequency - per sucessive cut | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Photographs, Daily Site Record and Stabilising Plan | Inspection / Test Authority: Conduct - S | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - S | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Acceptance Criteria - Meet Skid performance Requirement
Stabilised Material Particle Size | Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008 | No excessive breakdown of stabilised material | Visual Record | within 20m of each section and then regularly based on material variability | Quality Controller | Photographs | S or C | — | S or C | C | — | Y | Stabilised Material Particle Size | Controlling Documents - Particle size distribution of stabilised material (7.6.4) - TNZ B/5: 2008 | Acceptance Criteria - No excessive breakdown of stabilised material | Inspection or Test: Method - Visual Record | Inspection or Test: Frequency - within 20m of each section and then regularly based on material variability | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Photographs | Inspection / Test Authority: Conduct - S or C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - S or C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Inspection or Test: Method - Aggregate Perfomance Method TNZ T/10 section 12.3
Establish Compaction Methodology - type of plant, number and speed of passes | Compaction (7.7) - TNZ B/5: 2008 | To establish type of plant, number and speed of passes to achieve MDD | Plateau Density Testing | 1 time, or additional tests when material changes visually | Supervisor | Test record | S or C | — | S or C | C | — | Y | Establish Compaction Methodology - type of plant, number and speed of passes | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008 | Acceptance Criteria - To establish type of plant, number and speed of passes to achieve MDD | Inspection or Test: Method - Plateau Density Testing | Inspection or Test: Frequency - 1 time, or additional tests when material changes visually | Inspection or Test: Responsible Person - Supervisor | Verifying Document - Test record | Inspection / Test Authority: Conduct - S or C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - S or C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Inspection or Test: Frequency - Each Site
Establish Compaction Target | Compaction (7.7) - TNZ B/5: 2008 | To provide MDD for NDM testing | Plateau Density Testing | Minimum once per Lot. A lot shall not exceed 1000 m2. | Quality Controller | Test Record | S or C | — | S or C | E | — | Y | Establish Compaction Target | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008 | Acceptance Criteria - To provide MDD for NDM testing | Inspection or Test: Method - Plateau Density Testing | Inspection or Test: Frequency - Minimum once per Lot. A lot shall not exceed 1000 m2. | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Test Record | Inspection / Test Authority: Conduct - S or C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - S or C | Inspection / Test Authority: Approval - E | Hold Point - — | Witness Point - Y | Inspection or Test: Responsible Person - Surfacing Project Manager
Degree of Compaction MDD to obtain target for NDM testing (1) | Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008 | To provide MDD for NDM testing | Laboratory MDD at OMC NZS 4402 test 4.1.3. | Minimum once per Lot. A lot shall not exceed 5000 m2. | Quality Controller | Test Record | S or C | — | S or C | C | — | Y | Degree of Compaction MDD to obtain target for NDM testing (1) | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008 | Acceptance Criteria - To provide MDD for NDM testing | Inspection or Test: Method - Laboratory MDD at OMC NZS 4402 test 4.1.3. | Inspection or Test: Frequency - Minimum once per Lot. A lot shall not exceed 5000 m2. | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Test Record | Inspection / Test Authority: Conduct - S or C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - S or C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Verifying Document - IANZ Report's
Degree of Compaction MDD to obtain target for NDM testing (2) | Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008 | Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test | Plateau Density Testing Lab. MDD | At commencement of construction and whenever materials change | Quality Controller Engineer | Notice to Contractor/ Notice to Engineer | S or C | — | S or C | E | — | Y | Degree of Compaction MDD to obtain target for NDM testing (2) | Controlling Documents - Compaction (7.7) - TNZ B/5: 2008, Acceptance criteria for stabilised pavement layer compaction (7.7.1) - TNZ B/5: 2008 | Acceptance Criteria - Formally agree with the Engineer the MDD target, based on review of the lab. MDD and the site plateau test | Inspection or Test: Method - Plateau Density Testing Lab. MDD | Inspection or Test: Frequency - At commencement of construction and whenever materials change | Inspection or Test: Responsible Person - Quality Controller Engineer | Verifying Document - Notice to Contractor/ Notice to Engineer | Inspection / Test Authority: Conduct - S or C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - S or C | Inspection / Test Authority: Approval - E | Hold Point - — | Witness Point - Y | Inspection / Test Authority: Conduct - C
Compaction Acceptance | Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, | Mean value ≥ 98% and Minimum Value ≥ 95% | Nuclear Densometer Testing | ≥ 5 tests per 1000m² lot | Quality Controller | NDM Record | S or C | — | S or C | E | Y | — | Compaction Acceptance | Controlling Documents - Acceptance criteria for stabilised pavement layer compaction (7.7.1) and Table 5 - TNZ B/5: 2008, | Acceptance Criteria - Mean value ≥ 98% and Minimum Value ≥ 95% | Inspection or Test: Method - Nuclear Densometer Testing | Inspection or Test: Frequency - ≥ 5 tests per 1000m² lot | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - NDM Record | Inspection / Test Authority: Conduct - S or C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - S or C | Inspection / Test Authority: Approval - E | Hold Point - Y | Witness Point - — | Inspection / Test Authority: Witness - —
Control Testing (if required) | Control testing during and after construction (7.7.2) - TNZ B/5: 2008 | Nil | Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | when agreed with the Engineer | Quality Controller | Test Report | S or C | — | S or C | E | — | Y | Control Testing (if required) | Controlling Documents - Control testing during and after construction (7.7.2) - TNZ B/5: 2008 | Acceptance Criteria - Nil | Inspection or Test: Method - Vibrating Hammer Compaction Test at OWC (NZS 4402: 1986, Test 4.1.3) | Inspection or Test: Frequency - when agreed with the Engineer | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Test Report | Inspection / Test Authority: Conduct - S or C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - S or C | Inspection / Test Authority: Approval - E | Hold Point - — | Witness Point - Y | Inspection / Test Authority: Produce Record - C
Surface Smoothness | Surface shape (7.8) - TNZ B/5: 2008 | ± 10mm deviation along a 3m straight edge, No water ponding | 3m Straight Edge | during construction and prior to seal | Supervisor | Photographs | S or C | C and E | S or C | E | — | Y | Surface Smoothness | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008 | Acceptance Criteria - ± 10mm deviation along a 3m straight edge, No water ponding | Inspection or Test: Method - 3m Straight Edge | Inspection or Test: Frequency - during construction and prior to seal | Inspection or Test: Responsible Person - Supervisor | Verifying Document - Photographs | Inspection / Test Authority: Conduct - S or C | Inspection / Test Authority: Witness - C and E | Inspection / Test Authority: Produce Record - S or C | Inspection / Test Authority: Approval - E | Hold Point - — | Witness Point - Y | Inspection / Test Authority: Approval - N
Surface Shape | Surface shape (7.8) - TNZ B/5: 2008 | Between -5mm and +15mm | String lines or Survey Asbuilt | during construction and prior to seal | Supervisor | String Sheet/Survey Asbuilts | S or C | C and E | S or C | E | — | Y | Surface Shape | Controlling Documents - Surface shape (7.8) - TNZ B/5: 2008 | Acceptance Criteria - Between -5mm and +15mm | Inspection or Test: Method - String lines or Survey Asbuilt | Inspection or Test: Frequency - during construction and prior to seal | Inspection or Test: Responsible Person - Supervisor | Verifying Document - String Sheet/Survey Asbuilts | Inspection / Test Authority: Conduct - S or C | Inspection / Test Authority: Witness - C and E | Inspection / Test Authority: Produce Record - S or C | Inspection / Test Authority: Approval - E | Hold Point - — | Witness Point - Y | Hold Point - Y
Cross Fall | Crossfall (7.9) - TNZ B/5: 2008 | 0.5% ≤ X ≤ -0.5% | 3m straight edge or Survey Asbuilt | during construction and prior to seal | Supervisor | Cross Fall Records/Survey Asbuilts | S or C | C and E | S or C | E | — | Y | Cross Fall | Controlling Documents - Crossfall (7.9) - TNZ B/5: 2008 | Acceptance Criteria - 0.5% ≤ X ≤ -0.5% | Inspection or Test: Method - 3m straight edge or Survey Asbuilt | Inspection or Test: Frequency - during construction and prior to seal | Inspection or Test: Responsible Person - Supervisor | Verifying Document - Cross Fall Records/Survey Asbuilts | Inspection / Test Authority: Conduct - S or C | Inspection / Test Authority: Witness - C and E | Inspection / Test Authority: Produce Record - S or C | Inspection / Test Authority: Approval - E | Hold Point - — | Witness Point - Y | Witness Point - Y
Surface Finish | Surface finish (7.10) - TNZ B/5: 2008 | Tightly bound matrix post sweep | Visual inpsection | prior to seal | Supervisor | Pre-seal inspection sheet | S or C | C and E | S or C | E | — | Y | Surface Finish | Controlling Documents - Surface finish (7.10) - TNZ B/5: 2008 | Acceptance Criteria - Tightly bound matrix post sweep | Inspection or Test: Method - Visual inpsection | Inspection or Test: Frequency - prior to seal | Inspection or Test: Responsible Person - Supervisor | Verifying Document - Pre-seal inspection sheet | Inspection / Test Authority: Conduct - S or C | Inspection / Test Authority: Witness - C and E | Inspection / Test Authority: Produce Record - S or C | Inspection / Test Authority: Approval - E | Hold Point - — | Witness Point - Y | Production Property - Cleaness Value
Degree of Saturation, DOS | Pre-sealing requirements (7.12) - TNZ B/5: 2008, | ≤80%, however 65% is ideal | Nuclear Densometer Testing | ≥5 tests per 1000m² lot | Quality Controller | NDM Record | S or C | C and E | S or C | E | — | Y | Degree of Saturation, DOS | Controlling Documents - Pre-sealing requirements (7.12) - TNZ B/5: 2008, | Acceptance Criteria - ≤80%, however 65% is ideal | Inspection or Test: Method - Nuclear Densometer Testing | Inspection or Test: Frequency - ≥5 tests per 1000m² lot | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - NDM Record | Inspection / Test Authority: Conduct - S or C | Inspection / Test Authority: Witness - C and E | Inspection / Test Authority: Produce Record - S or C | Inspection / Test Authority: Approval - E | Hold Point - — | Witness Point - Y | Controlling Documents - NZTA P/17, M/6
Roughness (NAASRA) | NZTA Maintainence specification section 6.1.2 | For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km | NZTA Maintainence specification section 6.1.2 | Average of three replica runs for each lane reported at 20m intervals. | Quality Controller | Test Records | S or C | C and E | S or C | E | Y | — | Roughness (NAASRA) | Controlling Documents - NZTA Maintainence specification section 6.1.2 | Acceptance Criteria - For chipseal or non structural AC surfacing; No 100m moving average shall exceed 2.9 lane IRI.qc m/km 75 NAASRA counts/km | Inspection or Test: Method - NZTA Maintainence specification section 6.1.2 | Inspection or Test: Frequency - Average of three replica runs for each lane reported at 20m intervals. | Inspection or Test: Responsible Person - Quality Controller | Verifying Document - Test Records | Inspection / Test Authority: Conduct - S or C | Inspection / Test Authority: Witness - C and E | Inspection / Test Authority: Produce Record - S or C | Inspection / Test Authority: Approval - E | Hold Point - Y | Witness Point - — | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
Binder - Penetration Grade | TNZ M/1 | Table 1 | Property Test | Annual | Bitumen Supplier/ Surfacing Project Manager | IANZ Report's | C | — | C | N | — | Y | Binder - Penetration Grade | Controlling Documents - TNZ M/1 | Acceptance Criteria - Table 1 | Inspection or Test: Method - Property Test | Inspection or Test: Frequency - Annual | Inspection or Test: Responsible Person - Bitumen Supplier/ Surfacing Project Manager | Verifying Document - IANZ Report's | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - N | Hold Point - — | Witness Point - Y | Inspection or Test: Method - Sample Test - Cleaness Value NZS 4407 Test 3.9
Binder - Polymer Modified Emulsion | Higgins Internal Specification | % PMB Required, PH, Residue by Evaporation, Viscosity | Property Test | 1/100,000 litres supplied | Bitumen Supplier/ Surfacing Project Manager | IANZ Report's | C | — | C | N | — | Y | Binder - Polymer Modified Emulsion | Controlling Documents - Higgins Internal Specification | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity | Inspection or Test: Method - Property Test | Inspection or Test: Frequency - 1/100,000 litres supplied | Inspection or Test: Responsible Person - Bitumen Supplier/ Surfacing Project Manager | Verifying Document - IANZ Report's | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - N | Hold Point - — | Witness Point - Y | Inspection or Test: Frequency - Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples
Source Property -Coarse Aggregate - Crushing Resistance | TNZ M6, RNZ 9805:2009 | CHAR(LESS)10% fines under 230kN minimum | Sample Test - Crushing Resistance NZS 4407 Test 3.10 | 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum | Surfacing Project Manager | IANZ Report's | C | — | C | N | Y | Y | Source Property -Coarse Aggregate - Crushing Resistance | Controlling Documents - TNZ M6, RNZ 9805:2009 | Acceptance Criteria - CHAR(LESS)10% fines under 230kN minimum | Inspection or Test: Method - Sample Test - Crushing Resistance NZS 4407 Test 3.10 | Inspection or Test: Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum | Inspection or Test: Responsible Person - Surfacing Project Manager | Verifying Document - IANZ Report's | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - N | Hold Point - Y | Witness Point - Y | Inspection or Test: Responsible Person - Surfacing Project Manager
Source Property -Coarse Aggregate - Weathering Resistance | TNZ M6, RNZ 9805:2009 | AA or BA | Weathering Quality Index NZS 4407 Test 3.10 | 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum | Surfacing Project Manager | IANZ Report's | C | — | C | N | Y | Y | Source Property -Coarse Aggregate - Weathering Resistance | Controlling Documents - TNZ M6, RNZ 9805:2009 | Acceptance Criteria - AA or BA | Inspection or Test: Method - Weathering Quality Index NZS 4407 Test 3.10 | Inspection or Test: Frequency - 1 test per 10,000m³ or 1 test per annum if less than 10,000m³ produced per annum | Inspection or Test: Responsible Person - Surfacing Project Manager | Verifying Document - IANZ Report's | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - N | Hold Point - Y | Witness Point - Y | Verifying Document - IANZ Report's
Source Property - Skid Resistance | NZTA T/10 | Meet Skid performance Requirement | Aggregate Perfomance Method TNZ T/10 section 12.3 | Each Site | Surfacing Project Manager | IANZ Report's | C | — | C | N | Y | Y | Source Property - Skid Resistance | Controlling Documents - NZTA T/10 | Acceptance Criteria - Meet Skid performance Requirement | Inspection or Test: Method - Aggregate Perfomance Method TNZ T/10 section 12.3 | Inspection or Test: Frequency - Each Site | Inspection or Test: Responsible Person - Surfacing Project Manager | Verifying Document - IANZ Report's | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - N | Hold Point - Y | Witness Point - Y | Inspection / Test Authority: Conduct - C
Production Property - Cleaness Value | NZTA P/17, M/6 | G2 - 89 min, G3 - 87 min, G4 - 85 min | Sample Test - Cleaness Value NZS 4407 Test 3.9 | Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples | Surfacing Project Manager | IANZ Report's | C | — | C | N | Y | Y | Production Property - Cleaness Value | Controlling Documents - NZTA P/17, M/6 | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min | Inspection or Test: Method - Sample Test - Cleaness Value NZS 4407 Test 3.9 | Inspection or Test: Frequency - Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples | Inspection or Test: Responsible Person - Surfacing Project Manager | Verifying Document - IANZ Report's | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - N | Hold Point - Y | Witness Point - Y | Inspection / Test Authority: Witness - —
Production Property - Particle Size/Shape | NZTA P/17, M/6 | As per Table 3 NZTA M/6 | Sample Test - Particle Size/Shape NZS 4407 Test 3.13 | Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples | Surfacing Project Manager | IANZ Report's | C | — | C | N | Y | Y | Production Property - Particle Size/Shape | Controlling Documents - NZTA P/17, M/6 | Acceptance Criteria - As per Table 3 NZTA M/6 | Inspection or Test: Method - Sample Test - Particle Size/Shape NZS 4407 Test 3.13 | Inspection or Test: Frequency - Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples | Inspection or Test: Responsible Person - Surfacing Project Manager | Verifying Document - IANZ Report's | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - N | Hold Point - Y | Witness Point - Y | Inspection / Test Authority: Produce Record - C
Production Property - Broken Faces | NZTA P/17, M/6 | Min. 98% | Sample Test - Broken Faces NZS 4407 Test 3.14 | Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples | Surfacing Project Manager | IANZ Report's | C | — | C | N | Y | Y | Production Property - Broken Faces | Controlling Documents - NZTA P/17, M/6 | Acceptance Criteria - Min. 98% | Inspection or Test: Method - Sample Test - Broken Faces NZS 4407 Test 3.14 | Inspection or Test: Frequency - Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples | Inspection or Test: Responsible Person - Surfacing Project Manager | Verifying Document - IANZ Report's | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - N | Hold Point - Y | Witness Point - Y | Inspection / Test Authority: Approval - N
Chipseal Designs | EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17 | Client Approval | Review | Annual | Surfacing Project Manager | EBOP NOC Design Report Acceptance | C | — | C | N | Y | Y | Chipseal Designs | Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17 | Acceptance Criteria - Client Approval | Inspection or Test: Method - Review | Inspection or Test: Frequency - Annual | Inspection or Test: Responsible Person - Surfacing Project Manager | Verifying Document - EBOP NOC Design Report Acceptance | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - N | Hold Point - Y | Witness Point - Y | Hold Point - Y
Ensure limits of site are marked | EBOP NOC Design Report | Visual Inspection | Visual | Prior to start sealing each site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C | — | C | C | — | Y | Ensure limits of site are marked | Controlling Documents - EBOP NOC Design Report | Acceptance Criteria - Visual Inspection | Inspection or Test: Method - Visual | Inspection or Test: Frequency - Prior to start sealing each site | Inspection or Test: Responsible Person - Surfacing Supervisor | Verifying Document - Chip Sealing Quality and Site Record | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Witness Point - Y
Sweep surface clean of deleterious material | P/17 | Visual Inspection | Visual | Each site, prior to start of sealing | Surfacing Supervisor | Chip Sealing Quality and Site Record | C | — | C | C | — | Y | Sweep surface clean of deleterious material | Controlling Documents - P/17 | Acceptance Criteria - Visual Inspection | Inspection or Test: Method - Visual | Inspection or Test: Frequency - Each site, prior to start of sealing | Inspection or Test: Responsible Person - Surfacing Supervisor | Verifying Document - Chip Sealing Quality and Site Record | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Production Property - Particle Size/Shape
Record ATP's on site | N/A | Visual Inspection | Visual | Each site, prior to start of sealing | Surfacing Supervisor | Chip Sealing Quality and Site Record | C | — | C | C | — | Y | Record ATP's on site | Controlling Documents - N/A | Acceptance Criteria - Visual Inspection | Inspection or Test: Method - Visual | Inspection or Test: Frequency - Each site, prior to start of sealing | Inspection or Test: Responsible Person - Surfacing Supervisor | Verifying Document - Chip Sealing Quality and Site Record | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Controlling Documents - NZTA P/17, M/6
Confirm correct treatment(s) and chip | EBOP NOC Design Report | Details/chip correct | Visual | Each Site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C | — | C | C | Y | — | Confirm correct treatment(s) and chip | Controlling Documents - EBOP NOC Design Report | Acceptance Criteria - Details/chip correct | Inspection or Test: Method - Visual | Inspection or Test: Frequency - Each Site | Inspection or Test: Responsible Person - Surfacing Supervisor | Verifying Document - Chip Sealing Quality and Site Record | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - C | Hold Point - Y | Witness Point - — | Acceptance Criteria - As per Table 3 NZTA M/6
Cutback Bitumen Blend | RNZ 9803_0513 | +/- 2PPH Cutter, +ve for Adhesion agent presence | Sample and test | 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed | Surfacing Project Manager, Surfacing Supervisor | IANZ Report's | C | — | C | C | — | Y | Cutback Bitumen Blend | Controlling Documents - RNZ 9803_0513 | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence | Inspection or Test: Method - Sample and test | Inspection or Test: Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed | Inspection or Test: Responsible Person - Surfacing Project Manager, Surfacing Supervisor | Verifying Document - IANZ Report's | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Inspection or Test: Method - Sample Test - Particle Size/Shape NZS 4407 Test 3.13
Bitumen Application Rate | E/2 Certificate, Seal Design / Spray Instruction | Current E/2 Certificate +/- 4% per Spray Run | Test, Review | Per Sprayer, Per Site | Surfacing Supervisor | E/2 Certificate. Spray Sheets | C | — | C | C | — | Y | Bitumen Application Rate | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction | Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run | Inspection or Test: Method - Test, Review | Inspection or Test: Frequency - Per Sprayer, Per Site | Inspection or Test: Responsible Person - Surfacing Supervisor | Verifying Document - E/2 Certificate. Spray Sheets | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Inspection or Test: Frequency - Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples
Chip Application Rates | Chipsealing in NewZealand | As per Chipping Guide | Visual | Each Site | Surfacing Supervisor | Chip application check sheet. Chip Sealing Quality and Site Record | C | — | C | C | — | Y | Chip Application Rates | Controlling Documents - Chipsealing in NewZealand | Acceptance Criteria - As per Chipping Guide | Inspection or Test: Method - Visual | Inspection or Test: Frequency - Each Site | Inspection or Test: Responsible Person - Surfacing Supervisor | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Inspection or Test: Responsible Person - Surfacing Project Manager
Rolling | Chipsealing in NewZealand | Mimimum as per CS in NZ - Bit volume / 3600 | Visual | Each Site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C | — | C | C | — | Y | Rolling | Controlling Documents - Chipsealing in NewZealand | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600 | Inspection or Test: Method - Visual | Inspection or Test: Frequency - Each Site | Inspection or Test: Responsible Person - Surfacing Supervisor | Verifying Document - Chip Sealing Quality and Site Record | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Verifying Document - IANZ Report's
Cleanup | Chipsealing in NewZealand | Site including adjacent surfaces free of loose chip | Visual | Each Site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C | — | C | C | — | Y | Cleanup | Controlling Documents - Chipsealing in NewZealand | Acceptance Criteria - Site including adjacent surfaces free of loose chip | Inspection or Test: Method - Visual | Inspection or Test: Frequency - Each Site | Inspection or Test: Responsible Person - Surfacing Supervisor | Verifying Document - Chip Sealing Quality and Site Record | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Inspection / Test Authority: Conduct - C
Post Sweeping | Chipsealing in NewZealand | Site including adjacent surfaces free of loose chip | Visual | Each Site | Surfacing Supervisor | Site Record | C | — | C | C | — | Y | Post Sweeping | Controlling Documents - Chipsealing in NewZealand | Acceptance Criteria - Site including adjacent surfaces free of loose chip | Inspection or Test: Method - Visual | Inspection or Test: Frequency - Each Site | Inspection or Test: Responsible Person - Surfacing Supervisor | Verifying Document - Site Record | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Inspection / Test Authority: Witness - —
Linemarking and RRPM Reinstated | MOTSAM | Matches previous linemarking - within 48hours of sealing | Visual | Each Site | Surfacing Supervisor | Site Record | C | — | C | C | — | Y | Linemarking and RRPM Reinstated | Controlling Documents - MOTSAM | Acceptance Criteria - Matches previous linemarking - within 48hours of sealing | Inspection or Test: Method - Visual | Inspection or Test: Frequency - Each Site | Inspection or Test: Responsible Person - Surfacing Supervisor | Verifying Document - Site Record | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - C | Hold Point - — | Witness Point - Y | Inspection / Test Authority: Produce Record - C
Post Construction Walkover | — | Formal Agreement | Visual Inspection | Post seal sweep | Quality Controller, Supervisor and Engineer | Meeting Minutes | C | C, S and E | C | E | Y | — | Post Construction Walkover | Controlling Documents - — | Acceptance Criteria - Formal Agreement | Inspection or Test: Method - Visual Inspection | Inspection or Test: Frequency - Post seal sweep | Inspection or Test: Responsible Person - Quality Controller, Supervisor and Engineer | Verifying Document - Meeting Minutes | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - C, S and E | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - E | Hold Point - Y | Witness Point - — | Inspection / Test Authority: Approval - N
Resurfacing Construction Completion report | NOC; MS 6.1.3 | Comply with Requirement of NOC MS 6.1.3 | Record | Within 2 months of completing the annual resurfacing programme | Surfacing Manager | Construction Completion Report | C | — | C | C | Y | — | Resurfacing Construction Completion report | Controlling Documents - NOC; MS 6.1.3 | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3 | Inspection or Test: Method - Record | Inspection or Test: Frequency - Within 2 months of completing the annual resurfacing programme | Inspection or Test: Responsible Person - Surfacing Manager | Verifying Document - Construction Completion Report | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - — | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - C | Hold Point - Y | Witness Point - — | Hold Point - Y
Pavement Rehabilitation Construction Completion Report | Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification | Engineer Approval | Visual Inspection | ≤2 months of 1st Coat Seal | Quality Controller/ Contract Manager | Signed Report | C | C, S and E | C | E | Y | — | Pavement Rehabilitation Construction Completion Report | Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification | Acceptance Criteria - Engineer Approval | Inspection or Test: Method - Visual Inspection | Inspection or Test: Frequency - ≤2 months of 1st Coat Seal | Inspection or Test: Responsible Person - Quality Controller/ Contract Manager | Verifying Document - Signed Report | Inspection / Test Authority: Conduct - C | Inspection / Test Authority: Witness - C, S and E | Inspection / Test Authority: Produce Record - C | Inspection / Test Authority: Approval - E | Hold Point - Y | Witness Point - — | Witness Point - Y
Production Property - Broken Faces
Controlling Documents - NZTA P/17, M/6
Acceptance Criteria - Min. 98%
Inspection or Test: Method - Sample Test - Broken Faces NZS 4407 Test 3.14
Inspection or Test: Frequency - Per Stockpile CHAR(LESS)100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 - 3 Samples
Inspection or Test: Responsible Person - Surfacing Project Manager
Verifying Document - IANZ Report's
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - —
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - N
Hold Point - Y
Witness Point - Y
Chipseal Designs
Controlling Documents - EBOP NOC Design Report, Chipsealing in NZ, NZTA P/17
Acceptance Criteria - Client Approval
Inspection or Test: Method - Review
Inspection or Test: Frequency - Annual
Inspection or Test: Responsible Person - Surfacing Project Manager
Verifying Document - EBOP NOC Design Report Acceptance
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - —
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - N
Hold Point - Y
Witness Point - Y
Ensure limits of site are marked
Controlling Documents - EBOP NOC Design Report
Acceptance Criteria - Visual Inspection
Inspection or Test: Method - Visual
Inspection or Test: Frequency - Prior to start sealing each site
Inspection or Test: Responsible Person - Surfacing Supervisor
Verifying Document - Chip Sealing Quality and Site Record
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - —
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - C
Hold Point - —
Witness Point - Y
Sweep surface clean of deleterious material
Controlling Documents - P/17
Acceptance Criteria - Visual Inspection
Inspection or Test: Method - Visual
Inspection or Test: Frequency - Each site, prior to start of sealing
Inspection or Test: Responsible Person - Surfacing Supervisor
Verifying Document - Chip Sealing Quality and Site Record
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - —
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - C
Hold Point - —
Witness Point - Y
Record ATP's on site
Controlling Documents - N/A
Acceptance Criteria - Visual Inspection
Inspection or Test: Method - Visual
Inspection or Test: Frequency - Each site, prior to start of sealing
Inspection or Test: Responsible Person - Surfacing Supervisor
Verifying Document - Chip Sealing Quality and Site Record
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - —
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - C
Hold Point - —
Witness Point - Y
Confirm correct treatment(s) and chip
Controlling Documents - EBOP NOC Design Report
Acceptance Criteria - Details/chip correct
Inspection or Test: Method - Visual
Inspection or Test: Frequency - Each Site
Inspection or Test: Responsible Person - Surfacing Supervisor
Verifying Document - Chip Sealing Quality and Site Record
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - —
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - C
Hold Point - Y
Witness Point - —
Cutback Bitumen Blend
Controlling Documents - RNZ 9803_0513
Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
Inspection or Test: Method - Sample and test
Inspection or Test: Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
Inspection or Test: Responsible Person - Surfacing Project Manager, Surfacing Supervisor
Verifying Document - IANZ Report's
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - —
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - C
Hold Point - —
Witness Point - Y
Bitumen Application Rate
Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
Acceptance Criteria - Current E/2 Certificate +/- 4% per Spray Run
Inspection or Test: Method - Test, Review
Inspection or Test: Frequency - Per Sprayer, Per Site
Inspection or Test: Responsible Person - Surfacing Supervisor
Verifying Document - E/2 Certificate. Spray Sheets
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - —
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - C
Hold Point - —
Witness Point - Y
Chip Application Rates
Controlling Documents - Chipsealing in NewZealand
Acceptance Criteria - As per Chipping Guide
Inspection or Test: Method - Visual
Inspection or Test: Frequency - Each Site
Inspection or Test: Responsible Person - Surfacing Supervisor
Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - —
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - C
Hold Point - —
Witness Point - Y
Rolling
Controlling Documents - Chipsealing in NewZealand
Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
Inspection or Test: Method - Visual
Inspection or Test: Frequency - Each Site
Inspection or Test: Responsible Person - Surfacing Supervisor
Verifying Document - Chip Sealing Quality and Site Record
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - —
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - C
Hold Point - —
Witness Point - Y
Cleanup
Controlling Documents - Chipsealing in NewZealand
Acceptance Criteria - Site including adjacent surfaces free of loose chip
Inspection or Test: Method - Visual
Inspection or Test: Frequency - Each Site
Inspection or Test: Responsible Person - Surfacing Supervisor
Verifying Document - Chip Sealing Quality and Site Record
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - —
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - C
Hold Point - —
Witness Point - Y
Post Sweeping
Controlling Documents - Chipsealing in NewZealand
Acceptance Criteria - Site including adjacent surfaces free of loose chip
Inspection or Test: Method - Visual
Inspection or Test: Frequency - Each Site
Inspection or Test: Responsible Person - Surfacing Supervisor
Verifying Document - Site Record
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - —
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - C
Hold Point - —
Witness Point - Y
Linemarking and RRPM Reinstated
Controlling Documents - MOTSAM
Acceptance Criteria - Matches previous linemarking - within 48hours of sealing
Inspection or Test: Method - Visual
Inspection or Test: Frequency - Each Site
Inspection or Test: Responsible Person - Surfacing Supervisor
Verifying Document - Site Record
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - —
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - C
Hold Point - —
Witness Point - Y
Post Construction Walkover
Controlling Documents - —
Acceptance Criteria - Formal Agreement
Inspection or Test: Method - Visual Inspection
Inspection or Test: Frequency - Post seal sweep
Inspection or Test: Responsible Person - Quality Controller, Supervisor and Engineer
Verifying Document - Meeting Minutes
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - C, S and E
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - E
Hold Point - Y
Witness Point - —
Resurfacing Construction Completion report
Controlling Documents - NOC; MS 6.1.3
Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
Inspection or Test: Method - Record
Inspection or Test: Frequency - Within 2 months of completing the annual resurfacing programme
Inspection or Test: Responsible Person - Surfacing Manager
Verifying Document - Construction Completion Report
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - —
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - C
Hold Point - Y
Witness Point - —
Pavement Rehabilitation Construction Completion Report
Controlling Documents - Pavement Rehabilitation Construction Completion Report (6.1.2) - BOPE 2_14-001_601 Maintenance Specification
Acceptance Criteria - Engineer Approval
Inspection or Test: Method - Visual Inspection
Inspection or Test: Frequency - ≤2 months of 1st Coat Seal
Inspection or Test: Responsible Person - Quality Controller/ Contract Manager
Verifying Document - Signed Report
Inspection / Test Authority: Conduct - C
Inspection / Test Authority: Witness - C, S and E
Inspection / Test Authority: Produce Record - C
Inspection / Test Authority: Approval - E
Hold Point - Y
Witness Point - —