## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-007
[11 empty] | Revision : 1 | Date : 17/05/23
Client: |  | VicRoads |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Tarneit Bus Interchange |  | General Demolition |  | Name: | Samuel Johnson | Name: | Patrick Fagan |  | Name: | Shaun Kent
Contract No: |  | 7268500 |  | Specifications: CoM Sawn Bluestone Paving, Kerbing and Gutterstone Materials - Tech Spec. VR Spec Section 201 & 204
|  |  |  | Structure / Component: Earthworks/Civil |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: 680 Leakes Road Tarneit |  | Date : | 2023-05-17 | Date : | 2023-05-17 |  | Date : | 2023-05-17
Lot No: | 1 |  | Lot Details: | Demolition of the Existing Tarneit South Carpark |  |  |  |  | Lot Size/ Quantity: |  | 600m^2
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Site Engineer/ Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed | HP* | Site Engineer/ Site Foreman | N/A |  | N/A
1.3 | Service Identification |  | Prior to start | Services within vicinity of area to be demolished should be identified and marked, and all services to be retained shall be protected | ITP sign off | Verify | This ITP signed | HP* | Site Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Saw cutting |  | Where required | Extent and location of cuts to be clearly set out and checked prior to saw cutting | ITP sign off | Visual Inspection | This ITP signed | WP | Site Engineer | N/A |  | N/A
2.2 | Excavation Permit |  | During excavation | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task Excavation operations shall not disturb areas outside the limit of excavation | VicRoads 204.06 | Visual Inspection | This ITP signed | HP* | Site Engineer | N/A |  | N/A
2.3 | Redundant Pits |  | After clearing | Any redundant pits , are to be removed to a depth no less than 0.3m below the stripped surface or no less than 0.6m below finished subgrade (wichever is lesser) Seal any pipe openings with concrete and backfill pit area with material and compact to a density ratio of 95% (standard compactive effort) | 201.05 | Visual Inspection | This ITP Signed off | IP | Site Engineer | N/A |  | N/A
2.4 | Disposal of Material |  | All times | Surplus material, debris and demolished material are to be sorted and transported off site. Material to be kept in condition for re-use where possible. | ITP sign off | Visual Inspection | This ITP signed | WP | Site Engineer/ Site Foreman | N/A |  | N/A
2.5 | Maintaining cleanliness of site |  | All times | Site and surrounding environment are to be maintained at a good standard of cleanliness | ITP sign off | Visual Inspection | This ITP signed | WP | Site Engineer/ Site Foreman | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.